## Tdoc cover sheet
3GPP TSG-CT WG4 Meeting #121 Athens, Greece; 26th February–1st March 2024 |  | C4-240614
Source: | Huawei
Title: | 5MBS_Ph2 CT4 Work Plan
Agenda item: | 6.1.11
Document for: | Information

## CT4
CT4 Work Plan - CT4#121 - 2024-02 - 5MBS_Ph2 WI (CP-232031)
Impact | Specification | Targeted date | History | Status
Definition of Associated Session ID. | 23.003 | TSG#103 (2024-03) |  | Completed (Clause 30.5 of TS 23.003)
Provisioning of MBS Assistance Information using Nudm_ParameterProvision service operations. | 29.503 | TSG#103 (2024-03) |  | Completed (Clauses: 6.5.6.2.2, 6.5.6.2.27)
Retrieval of MBS Assistance Information from UDM by SMF. |  |  |  | Completed (Clause 6.1.3.31.3)
Possibly impacted, e.g. provisioning of MBS Assistance Information. | 29.505 | TSG#103 (2024-03)
Impacts to the Namf_MBSBroadcast API to support the transport change for resource sharing across broadcast MBS Sessions in MOCN procedure. | 29.518 | TSG#103 (2024-03) | CT4#118: C4-234325 (29518, CR 0978) Addition of Associated Session ID to the Namf_MBSBroadcast_ContextCreate as per stage 2 and RAN3 requirements CT4#119: C4-235525 (29.518, CR 0993): - NGAP message name and IE type aligned with 3GPP TS 38.413; - introduce "200 OK" as Acknowledge to ContextStatusNotify request CT4#121: C4-235808 (29.532, CR 0086): - MOCN feature defined. | Completed
Impacts to Nmbsmf_MBSSession_Create service operation to indicate the Associated Session ID. | 29.532 | TSG#103 (2024-03) |  | Completed (Clause 5.3.2.2.1)
Impacted, e.g. to define Associated Session ID and MBS Assistance Information. | 29.571 | TSG#103 (2024-03) |  | Completed (Clause 5.9.4.21.1)
Support for RedCap UEs in MBS broadcast | 29.532 29.571 | TSG#103 (2024-03) | CT4#121: Requirements added in SA2#160-Ad Hoc e-meeting (23.247 CR0341). Subject to SA plenary approval. C4-240612 (29.571 CR 0516): - data types to support NR RedCap UEs in MBS Broadcast defined. C4-240807 (29.532, CR 0085): - Support for RedCap UEs in MBS broadcast added, - New feature defined. | Completed