## General
Latest update: 31/05/2021
Rel-17 - WI: Enhancement for the 5G Control Plane Steering of Roaming for UE in CONNECTED mode (eCPSOR_CON)
Latest WID: CP-210148
Completion Status: CT#89: CT1-5% CT#90: CT1->10% and CT4->5% CT#91: CT1->35% and CT4->5%, CT6 0% CT#92: CT1->50% and CT4->10%, CT6 0%
>> CT#92e: CT1 stage2= 90% and stage3 =10%

## CT1 stage 2 issues
Latest update: 27/07/2021
CT1 Issues
Issue number | Description | Contributor to the next meeting? | DP /CR- Spec | Status | Notes
Generic issues also related to the procedure description
1 | Do we need to provide the SOR-CMCI info to the UE at initial registration, as no PDU session exists at that point when SOR is performed (SOR info received by the Reg. Accept message)? |  |  | closed | Contribution to CT1#126e, see C1-205951.
2 | The SOR-CMCI is dynamically generated similar to SOR info. Or is there some information that can be statically configured in the UE? |  |  | closed | Contribution to CT1#126e, see C1-206529
3 | What are the Static and dynamic info to be configured in the UE? |  |  | closed | related to issue-2.
4 | Should SOR info and SOR-CMCI arrive at the UE at the same time? The procedure where SOR is checked should also check the SOR-CMCI. How to handle the UE behaviour when receiving the information (SOR info+SOR-CMCI) at the same time or with a delay (received in different messages). |  |  | closed | Contribution to CT1#126e, See C1-206065, C1-205950. SOR-CMCI shall be received in the same container with other SOR related info. It was agreed in C1-211504 (CT1#128e) that the SOR-CMCI does not need to be sent to the UE during initial/emr Reg procedures. second part is moved to 4a.
4a | The procedure where SOR is checked should also check the SOR-CMCI. How to handle the UE behaviour when receiving the information (SOR info+SOR-CMCI) at the same time or with a delay (received in different messages). |  |  | closed | stage 2 describes how to handle received SOR-CMCI with the SOR info or seperately (configured or via NAS). stage 3 is still open.
5 | Editor's note: it is FFS whether the SOR-CMCI is (a) configured in the UE using the UE parameters update via UDM control plane procedure, (b) included in a SOR transparent container, (c) transported in a new transparent container, or (d) other means. |  |  | closed | It is clear that the SOR is included in the SOR transparent container as part of the SOR information. See issues 4, 6. based on offline comment from Ivo, I let this open and updated the EN. C1-210416 in CT1#127bise removed the EN
6 | Editor's Note: The exact structure and detailed parameters of SOR-CMCI is FFS. |  |  | closed | Contribution to CT1#126e, see C1-205954. stage 2 defining the required information is agreed in CT1#127e in C1-207567. Stage 3 is still open.
7 | SOR-CMCI, do we need another definition for secured new SOR info? |  |  | ignore | SOR-CMCI is part of the SOR information.
8 | Editor's note: it is FFS whether the UE performs local NAS signalling connection release or de-registration procedure when the SOR-CMCI requires that the UE shall move to the idle mode. |  |  | closed | Contribution to CT1#126e, see C1-206329. agreed in CT1#127e in C1-207567. using deregistration procedure is agreed. C1-210343 in CT1#127bise removes the EN C1-210343 is revised and agreed in C1-211225.
9 | Identify when to provide the new SOR information to the UE, while the UE is in the HPLMN, or only when in the VPLMN? This is mainly to update the USIM. |  |  | ignore | replaced by issue13
10 | If UPU is used; solve the issue of reserved values for UPU to allow indicating a new code point for SOR-CMCI. |  |  | closed | Contribution to CT1#126e, see C1-206065 the intention is that UPU will not be used for transporting SOR-CMCI.
11 | it is FFS whether the UDM can provide the SOR-CMCI to a UE not supporting SOR-CMCI. |  |  | closed | DP in (C1-207038) and CR (C1-207568), CT1#127e. C1-211504 in CT1#128e.
12 | it is FFS how the SOR-AF knows that it should provide the SOR-CMCI for the UE. |  |  | closed | resolved in C1-211504- CT1#128e
12a | it is FFS whether the SOR-AF can provide the SOR-CMCI to a UE not supporting SOR-CMCI. |  |  | closed | resolved in C1-211504- CT1#128e. C1-212486 in CT1#129e
13 | How would the home operator configure the SOR-CMCI in the UE? It is FFS whether subclause C.3 is to describe configuring the UE with SOR-CMCI or whether a new subclause will be specified to describe configuring the UE with SOR-CMCI. |  |  | closed | C1-210416 in CT1#127bise removed the EN
14 | It is FFS on how the UE convey his support for SOR-CMCI from the UE to the HPLMN. How does the UE provide its support for SOR-CMCI to the UDM, which messages, service operation,..etc? |  |  | closed | DP in (C1-207038) and CRs (C1-207568) and (C1-207562), CT1#127e. C1-210106 in CT1#127bise. resolved in C1-211504- CT1#128e.
15 | Editor's Note: aligning the text related to the "list of available and allowable PLMNs in the area" mentioned in the paragraph above is to be aligned to what will be agreed in C.2. |  |  | closed | align with the text in C.2 is needed. EN resolved in C1-210343 -CT1#127bise. C1-210343 is revised and agreed in C1-211225.
16 | It is FFS if an indication that the "UE supports SOR-CMCI" can be provided from the UE to the UDM together with the UE ACK. |  |  | closed | DP in (C1-207038) and CR (C1-207568), CT1#127e. resolved in C1-211504- CT1#128e.
16a | Tsor-cm timer handling in case of IRAT transitions |  |  | ongoing | New issue raised in CT1#129e
Related to PDU sessions handling
17 | Define the UE behaviour upon receiving the new SOR information while in connected mode. This includes consideration towards the newly requested sessions or re-established sessions. |  |  | ignore | covered by issue 20
18 | Editor's note: How the UE determines that the SOR-CMCI requires that the UE shall move to the idle mode is FFS. |  |  | closed | Stage 2 is agreed in CT1#127e. See C1-207567. EN is removed in C1-210343 in CT1#127bise
19 | Editor's note: If the UE has an established emergency PDU session, it is FFS whether the UE shall attempt to perform the PLMN selection immediately after the emergency PDU session is released or after some time to enable PSAP callback. |  |  | closed | C1-210386 in CT1#127bise. C1-211451- CT1#128e. C1-212387 CT1#129e
20 | how to handle PDU sessions requested while SOR/SOR-CMCI is under process in the UE? i.e will the PDU session requested after the SOR-CMCI is evaluated be allowed/rejected/handled according to SOR-CMCI (taking the exisiting sessions/timers into consideration)? |  |  | closed | for the registration procedure, it is agreed in C1-206754, CT1#126e. C1-210341 - CT1#127bise (introduces EN in 20b) C1-210341 is revised and agreed in C1-211296 (CT1#128e).
20a | Also we need to consider how to handle the Uplink data status in case of SOR during initial registration. |  |  | closed | resolved in 5Gprotoc17 CR agreed in C1-211224.
20b | Editor's Note: In the condition above, it is FFS how to set Tsor-cm if the matching criteria in the SOR-CMCI for the newly requested or modified PDU session or service indicates Tsor-cm=infinity. |  |  | closed | introduced by C1-210341 in CT1#127bise. Resolved in C1-211296 and C1-211252 (CT1#128e).
21 | Editor's Note: It is FFS on how to handle the case where there are more than one criterion applicable for multiple PDU sessions and services, resulting in multiple values applicable to timer Tsor-cm. |  |  | closed | DP in (C1-207038) and CR (C1-207568), CT1#127e. covered in the CR in C1-210339, CT1#127bise.
UE storage and handling of the SOR-CMCI
22 | Possible solutions for considering SOR-CMCI over Rel-15 onwards NW and what are the impacts. |  |  | closed | Contribution to CT1#126e, see C1-206065. Also see C1-210275 in CT1#127bise C1-211504 CT1#128e Note:see issue 14 as well.
23 | Editor's note: Whether to store the SOR-CMCI in the UE's ME or USIM is FFS. Also Are the SOR-CMCIs stored on the USIM and ME the same or have different values (one is generic and one specific per PLMN)? |  |  | closed | Discussion paper (C1-206380), CT1#126e DP in (C1-207038) and CR (C1-207039), CT1#127e. C1-210275 in CT1#127bise (new EN in 23a) second part is moved to 23b.
23a | Editor's Note: It is FFS whether the USIM or ME always needs to store the SOR-CMCI or the HPLMN needs to indicate to the UE to store the SOR-CMCI in the USIM or ME. |  |  | closed | introduced by C1-210275 in CT1#127bise DP in C1-211021 (CT1#128e). C1-21239 and C1-212596 CT1#129e
23b | are the SOR-CMCIs stored on the USIM and ME the same or have different values (one is generic and one specific per PLMN)? |  |  | closed | C1-21239 and C1-212596 CT1#129e
24 | When receiving SOR info without SOR-CMCI, but having SOR-CMCI preconfigured, should the UE use the preconfigured values? It would mean it would not behave as Rel-16, but still 17. Or asking differently: Does it mean that the UE can only use the SOR-CMCI if received with SOR-Info? If this is the case, does it make sense to consider where the UE stores the received SOR-CMCI, if it kind of cannot use it after in fact? |  |  | closed | DP in (C1-207038) and CR (C1-207568), CT1#127e. DP in C1-210164 and CR in C1-210275, CT1#127bise
25 | How to specify if the SOR-CMCI is part of the secured packet is FFS. Editor's Note: How the SOR-CMCI is provided to the UE in a REFRESH command needs to be specified by CT6. |  |  | closed | stage 2 is agreed in CT1#127e. See C1-207567. CT6 work is still open, however already started the discussions.
26 | Whether the UDM needs to instruct the UE to use or not use the SOR-CMCI stored in the UE, and the options available for the UDM to do so, are FFS. |  |  | closed | DP in (C1-207038) and CR (C1-207568), CT1#127e. C1-21239 and C1-212596 CT1#129e.
SOR-CMCI criteria and exempted services
27 | Define the services that are exempted from eCPSOR-CON New clause in Annex-c. - use of DNN, S-NSSAI or 5QI to identify the services - 5GMM/5GSM procedures (exempted or not) |  |  | closed | Contribution to CT1#126e, see C1-205954. further contribution in CT1#127e, see C1-207567. further ENs are added as individual issues
28 | Editor's Note: It is FFS whether 5QI is considered as part of the PDU session attribute type criteria. |  |  | closed | This EN is removed in CT1#130e
29 | High priority service exempt from release due to SOR. Editor's Note: It is FFS whether other services are exempted from being forced to release the related established PDU session to enter idle mode. |  |  | closed | SA1 response is in S1-204376. C1-210333 - CT1#127bise
30 | Editor's Note: It is FFS whether other service criterion types or parameters are to be added. |  |  | closed | available criteria is agreed in CT1#127e (C1-207567) C1-210333 and LS in C1-210040 - CT1#127bise (introducing EN in 32)
31 | It is FFS if the user preference will be part of the UDM evaluation of SOR-CMCI. |  |  | ongoing | DP in (C1-207038) and CR (C1-207568), CT1#127e. related to SA1 response in S1-204376. In CT1#127bise - introducing EN in 32.
32 | Editor's Note: It is FFS how to ensure that the HPLMN can control if the UE can have a configured "user controlled list of services exempted from release due to SOR" and/or is aware that the UE has a configured "user controlled list of services exempted from release due to SOR", and/or the user is having a service that matches one of the services included in the "user controlled list of services exempted from release due to SOR" during SOR. |  |  | ongoing | introduced by C1-207568.

## CT1 stage2 contributions & LSes
Latest update: 12/08/2021
CT1 stage-2 Contributions and Liaison statements
meeting /Item No | Item | Contributor | Spec-CR/DP/LS | Tdoc Number | Notes
CT1#125e /1 | Kick-off – Stage-2 required work and project planning for the WI eCPSOR_CON | NTT DOCOMO /Ban | DP | C1-204618 | Noted
CT1#125e /2 | Rel-17 SOR enhancement – Identifying the session type | NTT DOCOMO /Ban | DP | C1-204619 | Qualcomm/Lena: do not use OSid + APP id, use of DNN, S-NSSAI or 5QI is fine. Ericsson/Ivo: benefit in interrupting ongoing NAS (5GMM or 5GSM) procedures is not clear. Those procedures are very quick.
CT1#125e /3 | Discussion to providing the SOR connected mode information | Ericsson /Ivo | DP | C1-204780 | DOCOMO/Ban: not clear what are the configurations in the UE. The information should be dynamically provided to the UE. Apple/Robert: Backward compatibility issue with configuring the SOR connected mode information in the UE using the UE parameters update via UDM control plane procedure. As the UDM initiating UE parameters update procedure it currently is not aware of the release of the UE.TS 24.501, in figure 9.11.3.53A code points are defined as “reserved" in UPU. Orange/Marius: sees some information change dynamically and others are can be static and configured in the UE.
CT1#125e /4 | Enhancement for CP-SOR for UE in connected mode | Ericsson /Ivo | Spec: 23.122 CR 0566 | Provided in C1-204781 Agreed in C1-205289 | Editor's note: it is FFS whether the SOR-CMCI is (a) configured in the UE using the UE parameters update via UDM control plane procedure, (b) included in a SOR transparent container, (c) transported in a new transparent container, or (d) other means. Editor's note: Exact structure of the SOR-CMCI is FFS. Editor's note: If the UE has an established emergency PDU session, it is FFS whether the UE shall attempt to perform the PLMN selection immediately after the emergency PDU session is released or after some time to enable PSAP callback. Editor's note: it is FFS whether the UE performs local NAS signalling connection release or de-registration procedure when the SOR-CMCI requires that the UE shall move to the idle mode.Editor's note: How the UE determines that the SOR-CMCI requires that the UE shall move to the idle mode is FFS.
CT1#125e /5 | Introducing the definition "Steering of roaming connected mode control information" | NTT DOCOMO /Ban | Spec: 23.122 CR 0572 | Provided in C1-204805 Agreed in C1-205244 | Editor's Note: The detailed parameters of SOR-CMCI is FFS.
CT1#125e /6 | LS on providing the SOR connected mode information | Ericsson /Ivo | LS to SA2 | C1-204782 | Postponed
CT1#125e /7 | LS on high priority service exempt from release due to SOR | Nokia /Sung | LS to SA1 | C1-204941 | Agreed
CT1#125e /8 | LS on VPLMN release version for Rel-17 enhancement for CP-SOR in connected mode | NTT DOCOMO /Ban | LS to SA1 | Provided in C1-205055 Revised to C1-205224 | Postponed
CT1#126e /1 | Discussion – main requirements for achieving CP-SOR in connected mode | NTT DOCOMO /Ban | DP | C1-205950 | Ivo provided some comments. some of the requirements are implemented in C1-205952.
CT1#126e /2 | Enhanced CP-SOR in connected mode- UE behaviour during initial registration | NTT DOCOMO /Ban | DP | C1-205951 | Lena and Ivo disagree with the conclusions. Ban: The only one condition that is not covered in 24.501 subclause 4.2 and is required for SOR is the handling of the Uplink data status that indicates to the network the preserved PDU sessions which have uplink data pending. The NW then may re-establish the PDU sessions. then we solved the issue partially by agreeing to C1-206753/C1-206754 (Rel-16/17 respectively).
CT1#126e /3 | Introducing new requirements for CP-SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0591 | Provided in C1-205952 agreed in C1-206529 | Requirements for using SOR-CMCI
CT1#126e /4 | Updating the requirements for CP-SOR in 5GS | NTT DOCOMO /Ban | Spec: 23.122 CR0592 | Provided in C1-205953 agreed in C1-206542 | adding reference to 22.261
CT1#126e /5 | SOR-CMCI configuration and session handling for enhanced control plane SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0593 | C1-205954 | Postponed. Reason: Nokia does not see defining a criteria for the SOR-CMCI is required, and sending only one timer to the UE is sufficient. This timer is used to release any PDU session, independent of the communication type. Latest with Nokia's comments: https://www.3gpp.org/ftp/tsg_ct/WG1_mm-cc-sm_ex-CN1/TSGC1_126e/Inbox/Drafts/C1-20xxxx-%20revision%20of%20C1-205954-draft-v6.docx
CT1#126e /6 | Delivery mechanism for Connected-Mode SoR Information | Samsung | DP | C1-206065 | Good proposal for including the SOR-CMCI as part of the SOR information. Also requires the UE to indicate its support for such IE. Requires CT4 confirmation.
CT1#126e /7 | Editor's note on de-registration or NAS signalling connection release | Ericsson /Ivo | Spec: 23.122 CR0612 | C1-206329 | Postponed. Reason: Ban indicated that releasing the PDU sessions, by UE deregistration, will help having clear charging records among operators.
CT1#126e /8 | No need to release NAS signalling connection when the selected VPLMN is the highest priority PLMN | Ericsson /Ivo | Spec: 23.122 CR0613 | Provided in C1-206332 revised to C1-206737 | postponed. Different companies had different views on usage of the "list of available and allowable PLMNs in the area" in 23.122 annex C. NTT Docomo and Apple wanted to remove usage of the list where Qualcomm wanted to preserve using the list. Note: this was then provided and agreed in CT1#127e ( C1-207729) for 5Gprotoc WI.
CT1#126e /9 | No need to release NAS signalling connection when the selected VPLMN is the highest priority PLMN | Ericsson /Ivo | Spec: 23.122 CR0614 | C1-206333 | withdrawn - double reserved number
CT1#126e /10 | Obtaining SOR-CMCI | Ericsson /Ivo | Spec: 23.122 CR0615 | Provided in C1-206336 Agreed in C1-206735 | describing how the UDM obtains the SOR-CMCI (from the UDR or the SOR-AF).
CT1#126e /11 | SOR-CMCI configuration data | Thales /Ly Thanh | DP | C1-206380 | Identifying new open issues related to configuration of SOR-CMCI in the ME/USIM
CT1#127e /1 | SOR-CMCI configuration and session handling for enhanced control plane SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0593 | Provided in C1-207036 agreed in C1-207567 | revision of C1-205954 The CR is agreed with ENs for the requirements/solutions that were no agreement on among the companies.
CT1#127e /2 | LS – Providing the UE support for SOR-CMCI to the HPLMN UDM | NTT DOCOMO /Ban | LS out | C1-207040 | Postponed, as it relates to C1-207039 and C1-207469
CT1#127e /3 | Provisioning and handling of SOR-CMCI | NTT DOCOMO /Ban | DP | C1-207038 | This discussion paper discuss the method on how to provide the UE support for SOR-CMCI to the HPLMN to allow the HPLMN to use this information for further actions. Also storing the SOR-CMCI in the UE (ME /USIM) is discussed. Comments were received on the various proposals.
CT1#127e /4 | Support of SOR-CMCI in UE and CN | NTT DOCOMO /Ban | Spec: 23.122 CR0622 | Provided in C1-207039 revised into C1-207568 | Postponed several ENs were added as no agreements on the proposed requirements/solutions. Ericsson objected the first EN as it does not implicitly mention the use of transparent container for passing the UE support for SOR-CMCI between the UE and the UDM.
CT1#127e /5 | UE indication of SOR-CMCI capability 24.501 | Orange / Mariusz | Spec: 24.501 CR2943 | Provided in C1-207469 revised into C1-207562 | Postponed Ericsson objected the solution. See C1-207568. moved to CT1 stage 3 contributions tab
CT1#127e /6 | LS on Changes to SoR Delivery Mechanism (C4-205696; to SA3; cc: CT1; contact: Samsung) | CT4 | LS in | C1-207507 | LS with attached CR#500 to 3GPP TS 29.503, and CR#108 to 3GPP TS 29.509, related to the changes to SOR Delivery Mechanism.
CT1#127bise /0 | Reply LS on high priority service exempt from release due to SOR (S1-204376) | SA1 | LS in | C1-210040 | LS with attached CR#488 for TS 22.261, reply to LS in (S1-204274/C1-204941).
CT1#127bise /1 | Handling of multiple Tsor-cm timers and multiple PDU sessions | NTT DOCOMO /Ban | DP | Provided in C1-210059 | Discussion paper related to C1-210060 and C1-210061
CT1#127bise /2 | Handling and coordination of multiple Tsor-cm timers | NTT DOCOMO /Ban | Spec: 23.122 CR 0644 | Provided in C1-210060 agreed in C1-210339 | describes the coordination of multiple Tsor-cm timers set for multiple PDU sessions.
CT1#127bise /3 | Setting Tsor-cm timer for new or modified PDU sessions | NTT DOCOMO /Ban | Spec: 23.122 CR 0645 | Provided in C1-210061 agreed in C1-210341 | Revised in CT1#128e describes how to set Tsor-cm timer for newly requested PDU sessions/serivces or modified PDU sessions while SOR procedure with SOR-CMCI is ongoing.
CT1#127bise /4 | Removing resolved Editor's Notes and general corrections | NTT DOCOMO /Ban | Spec: 23.122 CR 0646 | Provided in C1-210062 agreed in C1-210343 | Revised in CT1#128e several corrections.
CT1#127bise /5 | No de-registration when Tsor-cm stops due to going to idle mode | OPPO / Rae | Spec: 23.122 CR 0647 | Provided in C1-210063 agreed in C1-210330 | When Tsor-cm stops due UE entring idle mode, the UE perfrom local release.
CT1#127bise /6 | UE behavior upon receiving higher priority PLMN ID in the SOR transparent container | SHARP | Spec: 23.122 CR 0648 | Provided in C1-210085 revised into C1-210313 | Postponed Tsor-cm timer handling while the PLMN the UE is registring on is the highest in the PLMN/AT list received in the SOR information.
CT1#127bise /7 | UE behavior while timer Tsor-cm is running | SHARP | Spec: 23.122 CR 0649 | Provided in C1-210086 | withdrawn
CT1#127bise /8 | Preventing sending of SOR-CMCI when the UE does not support SOR-CMCI | Ericsson / Ivo | Spec: 23.122 CR 0650 | Provided in C1-210106 | Postponed Trying to solve how the UE informs the HPLMN about its support for SOR-CMCI. Nokia indicated that they have an alternative solution to be proposed to the next meeting.
CT1#127bise /9 | Configuring UE with SOR-CMCI | Ericsson / Ivo | Spec: 23.122 CR 0651 | Provided in C1-210107 agreed in C1-210416 | describing a procedure on how to configure the UE with SOR-CMCI while SOR is not requested.
CT1#127bise /10 | Configuration of services exempted from release due to SOR at the UE | Qualcomm Incorporated / Lena | Spec: 23.122 CR 0652 | Provided in C1-210114 agreed in C1-210333 | Related to LS in C1-210040. Introducing the requirement allowing the UE to be configured by the user with a list of services that are exempted from a release due to SOR.
CT1#127bise /11 | Analysis on the storage of SOR-CMCI in the UE | NTT DOCOMO /Maoki | DP | Provided in C1-210164 | related to C1-210165
CT1#127bise /12 | Storage of SOR-CMCI in the UE | NTT DOCOMO /Maoki | Spec: 23.122 CR 0653 | Provided in C1-210165 agreed in C1-210275 | partially resolved by C1-210275. Describing the storage of SOR-CMCI in the UE (USIM and ME)
CT1#127bise /13 | Definition of CP-SOR | vivo | Spec: 23.122 CR 0654 | Provided in C1-210186 agreed in C1-210383 | editorial
CT1#127bise /14 | UDM obtaining SOR-CMCI from the SOR-AF | vivo | Spec: 23.122 CR 0655 | Provided in C1-210187 agreed in C1-210384 | of editorial nature - CR title is changed to"Providing SOR-CMCI in figures"
CT1#127bise /15 | UDM obtaining SOR-CMCI using the Nsoraf_SoR_Get service operation | vivo | Spec: 23.122 CR 0656 | Provided in C1-210188 agreed in C1-210385 | correcting a requirement
CT1#127bise /16 | UE behavior upon receiving new timer valuer for Tsor-cm timer | SHARP | Spec: 23.122 CR 0657 | Provided in C1-210195 agreed in C1-210387 | Revised in CT1#128e Describing the UE behavior when the UE receives new SOR-CMCI while one or more Tsor-cm timers are running.
CT1#127bise /17 | Handling of timer Tsor-cm when changing the network selection mode to manual mode | SHARP | Spec: 23.122 CR 0658 | Provided in C1-210196 agreed in C1-210292 | describing that when the UE changes to manual mode of operation, while Tsor-cm is running, the UE stops the timer and do not move to Idle mode.
CT1#127bise /18 | Handling of timer Tsor-cm when SOR-CMCI has more than one criterion applicable for multiple PDU sessions and services | SHARP | Spec: 23.122 CR 0659 | Provided in C1-210197 | merged into C1-210060
CT1#127bise /19 | PLMN selection when the emergency PDU session is released | vivo | Spec: 23.122 CR 0660 | Provided in C1-210217 agreed in C1-210386 | The UE shall attempt to perform the PLMN selection after the emergency PDU session or the high priority service is released and after the UE enters idle mode or 5GMM-CONNECTED mode with RRC inactive indication
CT1#128e /1 | Setting Tsor-cm timer for new or modified PDU sessions | NTT DOCOMO, ZTE, Apple | Spec: 23.122 CR 0645 | C1-210590 agreed in C1-211296 | Revision of C1-210341 In this revision, the criteria for new PDU session and new service has not change, however instead of checking for updated PDU session we check the service start/stop aginst the SOR-CMCI.
CT1#128e /2 | Removing resolved Editor's Notes and general corrections | NTT DOCOMO /Ban | Spec: 23.122 CR 0646 | C1-210591 agreed in C1-211225 | Revision of C1-210343 In this revision, it is mainly to remove changes in C.3.
CT1#128e /3 | Preventing sending of SOR-CMCI when the UE does not support SOR-CMCI | Ericsson, BlackBerry UK Ltd. / Ivo | Spec: 23.122 CR 0650 | C1-210669 merged into C1-211168 | Merged into C1-211168 Revision of C1-210106 alternative to sending UE support of SOR-CMCI from the UE to the HPLMN over a transparent container.
CT1#128e /4 | Counter-proposal to CR0650: Preventing sending of SOR-CMCI when the UE does not support SOR-CMCI | Nokia, Nokia Shanghai Bell /Sung | Spec: 23.122 CR 0664 | C1-210785 not pursued | Not persued Alternative to C1-210669 alternative to allowing the HPLMN to have the knowledge of the UE support of SOR-CMCI based on the PEI of the UE.
CT1#128e /5 | Counter-proposal to CR0651: Configuring UE with SOR-CMCI | Nokia, Nokia Shanghai Bell /Sung | Spec: 23.122 CR 0665 | C1-210787 Not persued | Not persued Overlaps with C1-210416 related to C1-210785
CT1#128e /6 | Knowledge in network on the support of SOR-CMCI by UE | Nokia, Nokia Shanghai Bell | discussion | C1-210788 | Noted summarises the 3 alternatives in C1-210669, C1-210785 and C1-211504
CT1#128e /7 | Discussion on expiration of Tsor-cm timer | ZTE | discussion | C1-210838 | Noted Noted Related with CRs in C1-210841 and C1-210842.
CT1#128e /8 | Clarification on the UE behaviour upon expiration of Tsor-cm timer associated with a PDU session type criterion | ZTE | Spec: 23.122 CR 0666 | C1-210841 not agreed | Not agreed
CT1#128e /9 | Clarification on the UE behaviour upon expiration of Tsor-cm timer associated with service type criterion | ZTE | Spec: 23.122 CR 0667 | C1-210842 not agreed | Not agreed
CT1#128e /10 | Clarification on the network-requested PDU session modification procedure during Tsor-cm timer running | ZTE | Spec: 23.122 CR 0668 | C1-210843 Merged into C1-210590 | Merged into C1-210590
CT1#128e /11 | UE behavior upon receiving new timer valuer for Tsor-cm timer | SHARP, vivo, NTT DOCOMO /Yudai | Spec: 23.122 CR 0657 | C1-210866 agreed in C1-211252 | Revision of C1-210387 updates to clarify the conditions.
CT1#128e /12 | Including the SOR-CMCI in the steering of roaming information | vivo, Ericsson | Spec: 23.122 CR 0670 | C1-210916 agreed in C1-211344 | Agreed adding the SOR-CMCI to the definition of SOR-information.
CT1#128e /13 | The condition when the UE starts the Tsor-cm timer | SHARP | Spec: 23.122 CR 0671 | C1-210920 postponed | Postponed
CT1#128e /14 | Resolve Editor’s Note on storage of SOR-CMCI | NTT DOCOMO /Maoki | discussion | C1-211021 | Noted
CT1#128e /15 | Clarification on SOR with SOR-CMCI and emergency PDU session | Orange / Mariusz | Spec: 23.122 CR 0675 | C1-211116 agreed in C1-211451 | Agreed adding clarification to the emergency procedures while SOR-CMCI is received.
CT1#128e /16 | Preventing sending of SOR-CMCI when the UE does not support SOR-CMCI | Nokia, Ericsson, NTT DOCOMO | Spec: 23.122 CR 0676 | C1-211168 agreed in C1-211504 | New CR as alternative to C1-210669, C1-210785 providing a solution where the UE sends its support for SOR-CMCI over the ACK transparent container.
CT1#129e /1 | PLMN selection with SOR-CMCI and emergency PDU session | vivo / Yanchao | Spec: 23.122 CR 0677 | C1-212027 | Postponed
CT1#129e /2 | "ME support of SOR-CMCI" indicator | vivo / Yanchao | Spec: 23.122 CR 0678 | C1-212028 | Postponed
CT1#129e /3 | General corrections and alignments for SOR | DOCOMO, Ericsson /Ban | Spec: 23.122 CR 0679 | C1-212051 Agreed in C1-212486 | Agreed
CT1#129e /4 | Solving EN related to HPLMN control on the "user controlled list of services exempted from release due to SOR" | DOCOMO /Ban | Spec: 23.122 CR 0680 | C1-212052 Postponed | Postponed Solving the EN as in the title of the CR.
CT1#129e /5 | Solving EN related to the HPLMN control on the "user controlled list of services exempted from release due to SOR" | DOCOMO /Ban | discussion | C1-212053 | Noted. Related CR in C1-212052 and LS out in C1-212399
CT1#129e /6 | Support of SOR-CMCI | Huawei, HiSilicon / Cristina | Spec: 24.501 CR 3105 | C1-212117 agreed in C1-212494 | Agreed adding abbrev. Needs revision in CT1#130-e to fix overlap with C1-212525 moved to CT1 stage 3 contributions tab
CT1#129e /7 | Clarify the UE behaviour when the emergency PDU session is released | ZTE/Shuang | Spec: 23.122 CR 0684 | C1-212130 Agreed in C1-212387 | Agreed removing the EN related to call-Back
CT1#129e /8 | Clarify the UE behaviour when the the last running Tsor-cm timer expires | ZTE/Shuang | Spec: 23.122 CR 0685 | C1-212131 Agreed in C1-212388 | Agreed clarificationfor condition to stop Tsor-cm
CT1#129e /9 | A "user controlled list of services exempted from release due to SOR" synchronization | SHARP/ Yudai | Spec: 23.122 CR 0686 | C1-212134 Merged into C1-212052 | Merged into C1-212052.
CT1#129e /10 | UE behavior upon updating "user controlled list of services exempted from release due to SOR" | SHARP/ Yudai | Spec: 23.122 CR 0687 | C1-212135 Agreed in C1-212452 | Agreed UE behaviour when the user controlled services is recnfigured by the user while SOR is ongoing and Tsor-cm is running.
CT1#129e /11 | SOR-CMCI provision with legacy AMF | Huawei, HiSilicon/Lin | Spec: 23.122 CR 0688 | C1-212147 Agreed in C1-212519 | Agreed. Clarification on how the UDM knows the AMF in the VPLMN supports the new feature (SOR-CMCI).
CT1#129e /12 | Availability of SOR-CMCI in ME | Samsung R&D Institute India /Danish | Spec: 23.122 CR 0677 | C1-212188 revised into C1-212403 Postponed | Postponed C1-212403-not provided
CT1#129e /13 | SOR-CMCI handling in lower layer failure | Samsung R&D Institute India /Danish | Spec: 23.122 CR 0690 | C1-212199 Revised into C1-212521 postponed | postponed. Revised into C1-212521
CT1#129e /14 | Resolve EN on the SOR-CMCI storage in the UE | NTT DOCOMO INC./ Maoki | Spec: 23.122 CR 0691 | C1-212200 Agreed in C1-212392 | Agreed HPLMN indicating to the UE to store the SOR-CMCI sent over NAS.
CT1#129e /15 | ME Support of SOR-CMCI indication by UE | Samsung R&D Institute India /Danish | discussion | C1-212201 | Noted. Related CR in C1-212204 and LS out in C1-212203
CT1#129e /16 | Clarification on handling the storage of the SOR-CMCI in the ME | NTT DOCOMO INC. /Maoki | Spec: 23.122 CR 0692 | C1-212202 Agreed in C1-212596 | Agreed The UE replaces the old SOR-CMCI stored in the non-volatile memory of the UE by the new one received over NAS.
CT1#129e /17 | Support of SOR-CMCI indication by UE | Samsung R&D Institute India /Danish | Spec: 23.122 CR 0693 | C1-212204 | Postponed.
CT1#129e /18 | UE indicating support of SOR-CMCI | Ericsson / Ivo | discussion | C1-212215 | Noted. Related LS out in C1-212216.
CT1#129e /19 | "ME support of SOR-CMCI" indicator | Ericsson, NTT DOCOMO, Nokia, Nokia Shanghai Bell / Ivo | Spec: 25.501 CR 3131 | C1-212217 Agreed in C1-212525 | Agreed. Introducing the procedure and coding for the ME support of SOR-CMCI. Needs revision in CT1#130-e to fix overlap with C1-212494 moved to CT1 stage 3 contributions tab
CT1#129e /20 | Preventing configuring SOR-CMCI when the UE does not support SOR-CMCI | Ericsson, NTT DOCOMO / Ivo | Spec: 23.122 CR 0696 | C1-212224 Agreed in C1-212573 | Agreed. Clarifying the missing conditions of ME support of SOR-CMCI when sent stand alone.
CT1#129e /21 | UE behaviour in case of configured SOR-CMCI information | Apple France / Roland | Spec: 23.122 CR 0697 | C1-212248 Agreed in C1-212409 | Agreed UE conditions for applying configured SOR-CMCI while processing USAT REFRESH with type “Steering of Roaming”. Some restructuring.
CT1#129e /22 | Maintaining the user controlled list of services exempted from release due to SOR | Vivo / LuFeng | Spec: 23.122 CR 0699 | C1-212254 Agreed in C1-212490 | Agreed deleting the user controlled services from the ME if the USIM is changed.
CT1#129e /23 | Setting the timer value of Tsor-cm | Vivo / LuFeng | Spec: 23.122 CR 0700 | C1-212255 Agreed in C1-212491 | Agreed clarifying UE behaviour when having services that has matching criteria in the SOR-CMCI and the user controlled service.
CT1#129e /24 | Tsor-cm timer handling in case of IDLE and IRAT transitions | Apple France /Roland | Spec: 23.122 CR 0701 | C1-212258 | Postponed.
CT1#129e /25 | Missing Formats of SOR-CMCI sent from the HPLMN to the UE | DOCOMO /Ban | discussion | C1-212260 | Noted. No objecion to the content and conclusion.
CT1#129e /26 | Reply LS on AMF transparency for SOR (C4- 211701) | CT4 | LS in | C1-212032 | Postponed
CT1#129e /27 | LS on Support of SOR-CMCI indication by UE | Samsung | LS out SA3 | C1-212203 | Not Pursue
CT1#129e /28 | LS on integrity protection between the UE and the HPLMN of additional fields in SOR transparent container carrying SOR acknowledgement | CT1 /Ericsson | LS out SA3 | C1-212216 Approved in C1-212523 | Approved. To SA3, asking them to consider IP while adding parameters to the ACK (from UE to HPLMN).
CT1#129e /29 | LS on user controlled services during SOR | DOCOMO | LS out GSMA/SA1 | C1-212399 | Postponed
CT1#130e /1 | Reply LS on AMF transparency for SOR (C4- 211701) | CT4 | LS in | C1-212813 | Noted
CT1#130e /2 | Correction of setting the SOR-CMCI criteria | NTT DOCOMO/ Ban | Spec: 23.122 CR0704 | C1-212895 agreed in C1-213654 | Agreed alignment on how to use the criteria.
CT1#130e /3 | Correcting the SOR-CMCI format sent to the UE | NTT DOCOMO/ Ban | Spec: 23.122 CR0705 | C1-212896 agreed in C1-213655 | Agreed In Annex C-clause C.4.3, intoduced the possibiltiy to send the SOR-CMCI as stand alone in the secured packet to the UE.
CT1#130e /4 | Resolution of Editor’s note on HPLMN control of the "user controlled list of services exempted from release due to SOR" | Qualcomm Incorporated, vivo, Apple / Lena | Spec: 23.122 CR706 | C1-212926 | Postponed. Removing the EN.
CT1#130e /5 | Tsor-cm timer handling in case of IDLE and IRAT transitions | Apple France | Spec: 23.122 CR0701 | C1-213123 | Postponed. Discusses the IRAT mobility impacts on the use of the Tsor-cm timers
CT1#130e /6 | Removal of ENs related to SOR-CMCI criteria | Orange / Mariusz | Spec: 23.122 CR0717 | C1-213212 Agreed in C1-213871 | Agreed Two ENs related to SOR-CMCI criteria for PDU session attribute type and service type are removed.
CT1#130e /7 | Performing PLMN selection after the emergency PDU session is released | vivo | Spec: 23.122 CR0720 | C1-213267 agreed in C1-213833 | Agreed. Related to EMR PDU session handling.
CT1#130e /8 | Radio link failure during Tsor timer is running | Samsung, NTT DOCOMO | Spec: 23.122 CR0721 | C1-213306 Agreed in C1-213961 | Agreed. UE shall not stop Tsor-cm timer(s) on entering idle mode due to lower layer failure
CT1#130e /9 | SOR-CMCI configuration for SOR security check failure | Samsung | Spec: 23.122 CR0722 | C1-213307 | Postponed Introduce new Tsor timer configuration for the case of SOR security check failure
CT1#130e /10 | InterSystem handling of Tsor-CM timers | Samsung | Spec: 23.122 CR0723 | C1-213310 | Postponed. Proposal for Tsor-CM timer behavior for intersystem change.
CT1#130e /11 | Remove unnecessary requirement on handling on receipt of SOR-CMCI | NTT DOCOMO / Maoki | Spec: 23.122 CR0726 | C1-213411 agreed in C1-213650 | Agreed. UE receiving SOR-CMCI in a secured packet with EF update command, not with SoR refresh command.
CT1#130e /12 | Storage of user controlled list of services exempted from release due to SOR | NTT DOCOMO / Maoki | Spec: 23.122 CR0727 | C1-213422 agreed in C1-213649 | Agreed. user controlled list storage is specified
CT1#130e /13 | LS on user controlled services during SOR | DOCOMO/ Ban | LS out GSMA/SA1 | C1-212894 Agreed in C1-213652 | Postponed. Asking GSMA's opinion on user controlled list.
CT1#131e /1 | Reply-LS on integrity protection between the UE and the HPLMN of additional fields in SOR transparent container carrying SOR acknowledgement | SA3 | LS in | C1-214037
CT1#131e /2 | Reply LS on Changes to SoR Delivery Mechanism | SA3 | LS in | C1-214041
CT1#131e /3 | Steering of Roaming regarding handling of SOR-CMCI | GSMA | LS in | C1-214058
CT1#131e /4 | Tsor-cm timer handling in case of IRAT transitions | Apple France | Spec: 23.122 CR | C1-214078
CT1#131e /5 | Corrections to the procedure in C.4.3 and other editorial corrections | DOCOMO Communications Lab. | Spec: 23.122 CR | C1-214113
CT1#131e /6 | Removing resolved Editor's Notes in Annex C | DOCOMO Communications Lab. | Spec: 23.122 CR | C1-214114
CT1#131e /7 | Correction to the "match all" criterion | DOCOMO Communications Lab. | Spec: 23.122 CR | C1-214115
CT1#131e /8 | LS on new parameters for SOR | DOCOMO Communications Lab. | LS out | C1-214118
CT1#131e /9 | Correction to SOR-CMCI attribute type criterion | Huawei, HiSilicon / Vishnu | Spec: 23.122 CR | C1-214418
CT1#131e /10 | Correction of SOR-CMCI structure definition | Orange / Mariusz | Spec: 23.122 CR | C1-214419
CT1#131e /11 | VPLMN being part of User Controlled PLMN Selector with Access Technology list | vivo | Spec: 23.122 CR | C1-214529
CT1#131e /12 | Tsor-cm not related with PDU sessions | vivo | Spec: 23.122 CR | C1-214530
CT1#131e /13 | The timer value for Tsor-cm being zero | vivo | Spec: 23.122 CR | C1-214531
CT1#131e /14 | DP-the usage of the match all type criterion | vivo | Spec: 23.122 CR | C1-214532
CT1#131e /15 | The match all type criterion in SOR-CMCI | vivo | Spec: 23.122 CR | C1-214533
CT1#131e /16 | Inter RAT handling of Tsor-CM timers | Samsung R&D Institute India | Spec: 23.122 CR | C1-214609
CT1#131e /17 | Tsor-CM timer handling in Manual to Auto mode change | Samsung R&D Institute India | Spec: 23.122 CR | C1-214610
CT1#131e /18 | SOR- CMCI handling for the security check failure | Samsung R&D Institute India | Spec: 23.122 CR | C1-214611
CT1#131e /19 | Correction on parameters description of SOR-CMCI | Huawei, HiSilicon / Cristina | Spec: 23.122 CR | C1-214655
CT1#131e /20 | S-NSSAI SST of SOR-CMCI rule | Huawei, HiSilicon / Cristina | Spec: 23.122 CR | C1-214656
CT1#131e /21 | Removal of editor's notes on SOR-CMCI | Huawei, HiSilicon / Cristina | Spec: 23.122 CR | C1-214657

## CT1 stage3 Contributins
Latest update: 12/08/2021
CT1 stage-3 Contributions
Meeting | Description | Contributor | DP, CR - Spec | Tdoc number | Status | Notes
CT1#127e | UE indication of SOR-CMCI capability 24.501 | Orange / Mariusz | Spec: 24.501 CR2943 | Provided in C1-207469 revised into C1-207562 | Postponed | Ericsson objected the solution. See C1-207568.
CT1#129e | "ME support of SOR-CMCI" indicator | Ericsson, NTT DOCOMO, Nokia, Nokia Shanghai Bell / Ivo | Spec: 25.501 CR3131 | C1-212217 Agreed in C1-212525 | Agreed. | Introducing the procedure and coding for the ME support of SOR-CMCI. Needs revision in CT1#130-e to fix overlap with C1-212494.
CT1#129e | Support of SOR-CMCI | Huawei, HiSilicon / Cristina | Spec: 24.501 CR3105 | C1-212117 agreed in C1-212494 | Agreed | adding abbrev. Needs revision in CT1#130-e to fix overlap with C1-212525
CT1#130e | SOR-CMCI transport and usage | Ericsson, NTT DOCOMO / Ivo | Spec: 24.501 CR3207 | C1-213028 agreed in C1-213912 | Agreed | Structure of the SOR-CMCI / NAS IEs.
CT1#131e | Alignments for the introduction of SOR-CMCI | NTT DOCOMO | Spec: 24.501 CR | C1-214116
CT1#131e | Correction to SOR-CMCI attribute type criterion | Huawei, HiSilicon / Vishnu | Spec: 24.501 CR | C1-214414
CT1#131e | Editorial correction for S-NSSAI SST criterion type | Huawei, HiSilicon / Vishnu | Spec: 24.501 CR | C1-214613

## CT4 Contributions & LSes
Latest update: 10/08/2021
CT4 Contributions and Liaison statements
Meeting | Description | Contributor | DP, LS, CR - Spec | Tdoc number | Status | Notes
General
UDM - UDR
UDM - SOR-AF
CT4#101 | Evolution of SoR delivery mechanism – SoR-AF API Changes | Samsung | Spec: 29.550 CR0014 | C4-205114 | not pursued | not pursued
UDM - AUSF
CT4#101 | Evolution of SoR delivery mechanism – AUSF API Changes | Samsung | Spec: 29.509 CR0108 | Provided in C4-205113 agreed in C4-205611 | Agreed | As detailed in Discussion Paper C4-205111, this CR proposes to modify the encoding of SorInfo attribute so that AUSF need not bother aboout contents of the SoR Information while protecting the same using Nausf_SoRProtection Service.
UDM - AMF
CT4#101 | Evolution of SoR delivery mechanism | Samsung | DP | C4-205111 | Noted | This discussion paper is an extension of C4-204094 (Evolution of UE Parameter Update mechanism) presented in CT4 #99e. The SoR delivery mechanism, as described by CT1 (stage-2) in 23.122, assumes that there is a "transparent container" sent by the UDM towards the UE, via the AMF (after being integrity-protected by the AUSF).
CT4#101 | Evolution of SoR delivery mechanism – UDM API Changes | Samsung | Spec: 29.503 CR0500 | Provided in C4-205112 agreed in C4-205610 | Agreed | As detailed in Discussion Paper C4-205111, this CR proposes to modify the encoding of SorInfo attribute so that SoR information can be transparently passed to UE without requiring any software changes to AMF (which may be in VPLMN) in case SoR information is extended to include new information.
CT4#102 | SoR Transparent Container in Uplink | Samsung, NTT DOCOMO | Spec: 29.503 CR0559 | C4-211008 agreed in C4-211533 | Agreed | As requested in LS C4-210044 from CT1, this CR modifies the encoding of AcknowledgeInfo attribute so that SoR Acknowledge information can be transparently passed to UDM without requiring any software changes to AMF (which is in the VPLMN) in case SoR Acknowledgement information is extended to include new information.
CT4#104 | Negotiation of Feature sorTransparentSupport | Huawei | Spec: 29.503 CR0655 | C4-213318 agreed in C4-213459 | Agreed | Describes the Negotiation of Feature for sorTransparentSupport in Steering Of Roaming information service operation of SDM service in uplink direction.
Liaison statements
CT4#101 | LS on Changes to SoR Delivery Mechanism | CT4 | LS Out | C4-205696 | Approved | Sentt to SA3 and CT1.
CT4#102 | AMF transparency for SOR | CT1 | LS in | C4-211147 | Noted | reply in C4-211832.
CT4#102 | AMF transparency for SOR | CT4 | LS out | C4-211832 | Approved | Reply to the LS from CT1, and providing the CR in C4-211533.
| Reply LS on Changes to SoR Delivery Mechanism | SA3 | LS in | C4-214155 |  | Reply LS from SA3, to ensure that in Rel-17 AMF does not need to understand the contents of the transparent container received from UDM or from UE. Including the CR S3-212339.

## CT6 contributions & LSes
Latest update: 21/08/2021
Issue No. | Identified issues
1 | Editor's Note in TS23.221-AnnexC: How the SOR-CMCI is provided to the UE in a REFRESH command needs to be specified by CT6.
2 | Storage of SOR-CMCI in the USIM
3 | In case the SOR-CMCI is present, the length of SOR-CMCI contents field equal to zero, and the USIM needs to store the SOR-CMCI, then the USIM uses this information to clear the stored SOR-CMCI in the USIM, if any. (Similar action is proposed for the ME in C1-214116 - CT1#131e -- to follow up on the outcome and align the behaviour in the USIM.)
4 | For other possible requirements please check 23.122-Annex C.
CT6 Contributions and Liaison statements
Meeting | Description | Contributor | DP, LS, CR - Spec | Tdoc number | Status | Notes
CT#106e | REFRESH SOR-CMCI introduction | THALES / Hervé | Spec: 31.111 CR0751 | C6-210132 revised to C6-210168 | Postponed | Introducing new SOR-CMCI paremeters on REFRESH “Steering of Roaming” to be aligned with CT1 Steering Of Roaming Connected Mode Control Information procedure as specified in 3GPP TS 23.122
CT#106e | SOR-CMCI USIM storage | THALES / Hervé | Spec: 31.102 CR0917 | C6-210148 revised to C6-210167 | Postponed | Introducing new SOR-CMCI paremeters storage on USIM as specified in TS 23.122 Annex C.1
CT#107e | SOR-CMCI USIM storage | THALES | Spec: 31.102 CR0917 | C6-210248
CT#107e | REFRESH SOR-CMCI introduction | THALES | Spec: 31.111 CR0751 | C6-210249