# NewToN – Workplan

# Introduction

A new work item on New Training Sequences for GERAN, acronym NewToN, was approved at GERAN#60, see [1].

The work consists of defining new training sequences for both CS and PS services in GERAN with the aim to reduce the cross correlation between TSCs to primarily allow for a more spectral efficient implementation of synchronized GSM networks.

This document captures the workplan of NewToN.

Outcome of the 3GPP GERAN#63 meeting and NewToN telco#5 has been captured in red.

# Workplan

| Milestone | Plan | Outcome |
| --- | --- | --- |
| NewToN telco#1 16th Jan, 2014 | Discussion and agreement on: - Performance evaluation framework - Design framework - Workplan | - Discusison papers on performane evaluation framework and design framework submitted as well as a proposed workplan. - Discussion on whether or not design framework is needed, and if so, how to capture it. - Discussion on performance evaluation framework - WA proposed but only discussed (not agreed). |
| NewToN telco#2 12th Feb, 2014 | Discussion and agreement on: - Performance evaluation framework - Design framework - Workplan | - Continued discussion on performance evaluation framework agreeing 18/24 proposed WAs (on telco level) - Initial discussion on NewToN related to VAMOS implementation - Initial discussion on resource segregation on USF / PAN for PS channels. |
| GERAN#61 24-28 Feb, 2014 | Formal agreement on: - Performance evaluation framework - Design framework - Workplan Draft CRs for discussion: - 24.008, 44.060, 44.018, 45.001, 45.002, 45.008, 45.009 | - Discussion and agreement on 27/27 working assumptions. The performance evaluation framework is considered complete. - No discussion on design aspects. - Initial discussion on CRs - Discussion on how NewToN relates to VAMOS. More specifically, what TSC sets should be supported depending on MS capability, what TSC pairing that is allowed for NewToN MSs supporting VAMOS. |
| NewToN telco#3 8th of May, 2014 | CR discussion | - A TSC proposal submitted together with the methodology used to derive the set. - Request to move final date for TSC proposal and TSC evaluation one meeting cycle due to move of 3GPP Rel-12 freeze date. - No CRs submitted for discussion |
| GERAN#62 26-30 May, 2014 | CRs for discussion and agreement: - 24.008, 44.060, 44.018, 45.001, 45.002, 45.008, 45.009 | - Excel sheet for collecting performance was noted. - Further discussion on all related CRs to the NewToN work except to TR 45.050. - Discussion on that if there will be only one company proposing a TSC set, that set need to be compared to the legacy sets available. |
| NewToN telco#4 14th of August, 2014 | Remaining CRs for discussion and agreement: - 24.008, 44.060, 44.018, 45.001, 45.002, 45.008, 45.009 Draft CR to TR45.050 Final date for TSC proposal It should be noted that TSC sets can be proposed earlier than this date, and also changed, but after this date it is the latest proposal from each company that will be used for evaluation. | - Submission of TSC set proposal from one company. - Initial discussion on CR to 45.050. |
| GERAN#63 25-29 Aug, 2014 | Remaining CRs for conditional agreement: - 24.008, 44.060, 44.018, 45.001, 45.008, 45.009 Agreement on CR apart from the inclusion of TSC sets:: - 45.002 Draft CR to 45.050 capturing the design and evaluation framework of the TSC proposal agreed. | - Conditional agreement of CRs to 24.008, 44.060 and 44.018 by WG2 - Agreement of WG1 specifications pending evaluation of NewToN with VAMOS on system level, as captured in the exception sheet of the work, see [2]. - TSC set included in 45.002, but CR postponed. - CR to 45.050 reviewed. Performance evaluation to be included. |
| NewToN telco#5 5th of November, 2014 | Further discussion and agreement on CRs. CR to 45.050 with performance evaluation included. Final date for TSC evaluation It should be noted that TSC sets can be evaluated using a sub-set of the complete evaluation framework, or using not all proposed TSC set, earlier than this date. At this date a full evaluation (according to the framework) of all TSC sets are required. | - Discussion on NewToN with VAMOS on system level, as agreed to be provided in the exception sheet, see [2]. - CR to 45.050 reviewed with performance evaluation included |
| GERAN#64 17-21 Nov, 2014 | Formal agreement on TSC and CR set LS to CT1 on MS capability signaling (endorsed draft CR to 24.008 attached) Completion of work item |  |

# References

GP-131139, “New Training Sequence Codes for GERAN”, source Telefon AB LM Ericsson, Telecom Italia S.p.A., China Mobile Com. Corporation, NOKIA Corporation, Alcatel-Lucent, Vodafone Group, Com-Research GmbH. GERAN#60.

GP-140542, “NewToN Work Item Exception”, source WI Rapporteur. GERAN#63.