MIMO for Downlink Workplan

# Introduction

At GERAN#57 the MIMO for Downlink study item [1] for Release 12 was agreed with the objective to investigate the feasibility of single user MIMO in the downlink for PS data services including EGPRS and EGPRS2-A.

This document presents the work plan for the study item. This is an update of [2]. The updated text is provided with blue fonts.

# Work plan

| Milestone | Meeting | Date | Expected outcome | Status |
| --- | --- | --- | --- | --- |
| M1 | TSG GERAN#58 | 13th -17th May, 2013 | - Agreement on work plan - Agreement on TR structure - Offline discussion on mixed modulations and blind modulation detection | Work plan and TR structure in V0.0.1 agreed. Discussion on mixed modulation inconclusive. |
| M2 | MIMO for Downlink Telco #1 | 31st July, 2013 | - Discussion on draft TR structure - Further discussion on mixed modulations and blind modulation detection - Dicussion on link and mode adaptation - Discussion on multiplexing with legacy MS - Definition of respective simulation assumptions | Several modifications were suggested and agreed on the TR structure. It was deemed necessary to investigate further on mixed modulation before GERAN#59 No discussion on link and mode adaptation No discussion on multiplexing A number of common simulation assumptions were agreed. |
| M3 | TSG GERAN#59 | 26th – 30th Aug, 2013 | - Dicussion on link and mode adaptation - Discussion on spatial channel models - Agreement on respective simulation assumptions - Updated TR based on the telco discussion | Impact of time variation of channel on link adaptation discussed. No discussion on mode adaptation. MIMO Channel Model with Variable Spatial Correlation taken from TS 36.101 presented. Simulation assumptions partially agreed. Rest is left open for case by case study. |
| M4 | MIMO for Downlink Telco#2 | 17th October, 2013 | - Discussion on other RLC/MAC protocols aspects. - Dicussion on mode adaptation signalling - Discussion on MS Capability signalling - Definition of remaining simulation assumptions | Discussion on other RLC/MAC protocols and capability signalling. No discussion on mode and link adaptation and signalling of these. Simulation assumptions: SCPIR assumptions modified. |
| M6 | TSG GERAN#60 | 18th – 22nd Nov, 2013 | - Version 0.0.3 of TR submitted with conclusion on modulation aspects and other RLC/MAC protocol aspects | Texts in the pCR approved for a new TR version 0.2.0, to be submitted in GERAN#61. |
| M7 | TSG GERAN#61 | 24th – 28th Feb, 2014 | - Version 0.2.0 TR submitted with TR number - pCR on channel model agreed | - pCR on channel model agreed - Version 0.3.0 of TR 45.871 submitted and agreed |
| M8 | TSG GERAN#62 | 26th-30th May, 2014 | - pCR on remaining sections agreed - Final simulation results presented - Version 1 of TR submitted - Agreement on final simulation assumption | Agreement on final simulation assumption reached. |
| M9 | MIMO for Downlink Telco#3 | 30th July, 2014 | - Discussion on Mode and Link Adaptation | Discussion on Mode adaptation initiated with simulation results. Further work was deemed needed. |
| M10 | TSG GERAN#63 | 25th – 29th Aug, 2014 | - Discussion on Mode and Link Adaptation | Discussion on Mode adaptation initiated with simulation results. Further work was deemed needed. |
| M11 | MIMO for Downlink Telco#4 | 30th Oct, 2014, 9 am – 12 pm CET | - Discussion on Mode and Link Adaptation - Discussion on other aspects - Final simulation results presented | Final simulation results presented partially |
| M12 | TSG GERAN#64 | 17th – 21st Nov, 2014 | - pCR on Final Simulation results section agreed - Version 0.4.0 of TR submitted | Section 8 on Performance Evaluation included in TR 0.4.0 (agreed in GP-140991). Additional subsection for Performance Summary created. |
| M13 | MIMO for Downlink Telco#5 | 12th Feb, 2015, 9 am - 11 am CET | - | Telco was not held. |
| M14 | TSG GERAN#65 | 9th – 13th Mar, 2015 | - Performance Summary - Aspects on Mode and Link Adaptation - Remaining aspects for investigation | Workplan updated. |
| M15 | MIMO for Downlink Telco#5 | 12th May, 2015 | - | Telco was not held. |
| M16 | TSG GERAN#66 | 25th – 29th May, 2015 | - Performance Summary - Aspects on Mode and Link Adaptation - Remaining aspects for investigation | Workplan updated extending study to GERAN#68. |
| M17 | TSG GERAN#67 | 10th – 14th August, 2015 | - Performance Summary - Aspects on Mode and Link Adaptation - Draft Conclusion - Version 1 of the TR presented | Workplan updated extending study to GERAN#69. |
| M18 | TSG GERAN#68 | 16th – 20th November, 2015 | - Performance Summary - Aspects on Mode and Link Adaptation - Draft Conclusion - Version 1 of the TR presented | Workplan updated extending study to GERAN#70. |
| M19 | MIMO for Downlink Telco#5 | 15th Dec, 2015, 9 - 11 am CET | - Performance Summary - Aspects on Mode and Link Adaptation - Draft Conclusion | Telco was held, but there was no discussion due to lack of participants. |
| M20 | TSG GERAN#69 | 15th–19th February, 2016 | - Performance Summary - Aspects on Mode and Link Adaptation - Draft Conclusion - Version 1 of the TR presented | Performance Summary agreed to be included in TR. Aspects on Mode and Link Adaptation discussed. |
| M21 | TSG GERAN#70 | 23rd–27th May, 2016 | - Aspects on Mode and Link Adaptation - Draft Conclusion - Version 1 of the TR presented |  |
| M21 | RANWG6#1 | 22nd–26th August, 2016 | - Aspects on Mode and Link Adaptation - Conclusion - Version 2 of the TR presented - Approval of TR and conclusion of SI |  |

# References

- GP-130288 New Study Item on Downlink MIMO (update of GP-130282), Nokia Siemens Networks et al., GERAN#57

- GP-151132 MIMO for Downlink Workplan, SI Rapporteur, GERAN#68