## Band combination table
Are there any change marks? (More explaination can be found in coversheet) | Band combination configuration | UpLink configuration | BCS | Subclass | Contact Name | Contact Company | Contact Email | Other supporting companies (min.3) | RAN Plenary in which the conbination was requested | Related WI (acronym) | Supported next level fallback modes including status (in DL and UL) | Status (New,Ongoing,Completed,Stopped) | TR# | TPs provided as input for TR | CRs provided to RAN | Core part Done? yes/no | Perf. part Done? yes/no | Open issues/Comments | Note
Unchange | CA_n66(2A) | CA_n66(2A) | 2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#89 | NR_CA_R17_intra-Core | (new) DL_n66(2A)_BCS2 | Ongoing |  |  |  | No | No
Unchange | CA_n66(3A) | CA_n66(2A) | 0 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#89 | NR_CA_R17_intra-Core | (new) DL_n66(3A)_BCS0 (new) DL_n66(2A)_UL_n66(2A)_BCS2 | Ongoing |  |  |  | No | No
Unchange | CA_n66(A-B) | CA_n66A CA_n66B | 0 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#89 | NR_CA_R18_Intra-Core | (Complete) DL_n66(2A)_UL_n66A (Complete) DL_n66(2A)_UL_n66A | Ongoing |  |  |  | No | No
Unchange | CA_n46(2A) | - | 0 | Only FR1 | Marc Grant | AT&T | marc.grant@att.com | Ericsson, Qualcomm, Nokia | RAN#90 | NR_CA_R18_intra-Core | None | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217057 endorsed
Modified | CA_n78D | CA_n78C | N/A | Only FR1 | Bo Liu | China Telecom | liubo1@chinatelecom.cn | Huawei, HiSilicon, CATT, ZTE, sanechips, Ericsson, Qualcomm, Nokia, Nokia Shanghai Bell | RAN#91 | NR_CA_R17_intra-Core | (completed) DL_n78D_BCS0 | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Unchange | CA_n78(A-C) | - | 0 | Only FR1 | Donghyeon Kim | SK Telecom | dhthomas.kim@sk.com | Ericsson, Murata, Samsung, LGE, | RAN#96 | NR_CA_R18_intra-Core | (Completed) DL_n78(2A)_BCS2 (Completed) DL_n78C_BCS1 | Completed | 38.718-01-01 | R4-2218520 | R4-2218945 | Yes | Yes
Unchange | CA_n46(2A) | CA_n46(2A) | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n46(2A)_UL_n46A_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n46C | CA_n46C | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n46C_UL_n46A_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n102(2A) | CA_n102(2A) | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102(2A)_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102(3A) | - | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102(2A)_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102(4A) | - | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102(3A)_UL_n102A_BCS0 (new) DL_n102(2A)_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102B | CA_n102B | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102B_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102C | CA_n102C | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102C_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102D | - | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102C_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n102E | - | 0 | Only FR1 | Stephen Truelove | BT plc | stephen.truelove@bt.com | Ericsson, Huawei, Nokia | RAN#97 | NR_CA_R18_Intra | (new) DL_n102D_UL_n102A_BCS0 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2217058 endorsed
Unchange | CA_n41(A-C) | CA_n41C | 4 and 5 | Only FR1 | Bill Shvodian | T-Mobile USA | bill.shvodian@t-mobile.com | Deutsche Telekom, Ericsson, Nokia, Nokia Shainghai Bell | RAN#97 | NR_CA_R18_intra-Core | (Completed) DL_n41(A-C)_BCS4 (Completed) DL_n41C_UL_n41C_BCS4 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2220783 endorsed
Unchange | CA_n41(2A-C) | CA_n41C | 4 and 5 | Only FR1 | Bill Shvodian | T-Mobile USA | bill.shvodian@t-mobile.com | Deutsche Telekom, Ericsson, Nokia, Nokia Shainghai Bell | RAN#97 | NR_CA_R18_intra-Core | (Completed) DL_n41(2A-C)_BCS4 (New) DL_n41(A-C)_UL_n41C_BCS4 | Completed |  |  | R4-2218945 | Yes | Yes | draft CR R4-2220783 endorsed
Unchange | CA_n257(A-G) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n257(2A)_BCS0 (Completed) DL_n257G_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(A-G) | CA_n257G | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n257(2A)_BCS0 (Completed) DL_n257G_UL_n257G_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(2G) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n257(A-G)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(2G) | CA_n257G | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n257(A-G)_UL_n257G_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(A-D) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n257(2A)_BCS0 (Completed) DL_n257D_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n258(A-D) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n258(2A)_BCS0 (Completed) DL_n258D_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216056 endorsed
Unchange | CA_n257(A-H) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n257H_BCS0 (New) DL_n257(A-G)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(G-H) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n257(2G)_BCS0 (New) DL_n257(A-H)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(A-I) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n257I_BCS0 (New) DL_n257(A-H)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n257(G-I) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n257(G-H)_BCS0 (New) DL_n257(A-I)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216055 endorsed
Unchange | CA_n258(A-H) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n258H_BCS0 (New) DL_n258(A-G)_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n258(G-H) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n258(2G)_BCS0 (New) DL_n258(A-H)_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n258(A-I) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (Completed) DL_n258I_BCS0 (New) DL_n258(A-H)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216056 endorsed
Unchange | CA_n258(G-I) | - | 0 | non-contiguous | Zhang Peng | Huawei | zhangpeng169@huawei.com | HiSilicon, Vodafone, Samsung | RAN#97 | NR_CA_R18_intra | (New) DL_n258(G-H)_BCS0 (New) DL_n258(A-I)_BCS0 | Completed |  |  | R4-2218946 | Yes | Yes | draft CR R4-2216056 endorsed
Unchange | CA_n66B | CA_n66B | 0 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#97 | NR_CA_R18_Intra | (Complete) DL_n66B_BCS0 | Ongoing |  |  |  | No | No
Modified | CA_n41B | CA_n41B | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n77C | CA_n77C | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n77D | - | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | (New) CA_n77C | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n78C | CA_n78C | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n78D | - | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | (New) CA_n78C | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n79C | - | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n79D | CA_n79D | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | (New) CA_n79C | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n77(3A) | - | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | (Complete) CA_n77(2A) | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n78(2A) | CA_n78(2A) | BCS4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#98 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n26(2A) | - | BCS4 and 5 | Only FR1 | Laura White | Telstra | laura.white@team.telstra.com | Ericsson, Mediatek, Nokia | RAN#98 | NR_CA_R18_intra | None | Completed |  | R4-2303574 | R4-2301057 | Yes | Yes
Modified | CA_n77(3A) | n77 CA_n77(2A) | 1 | Only FR1 | Per Lindell | Ericsson | per.lindell@ericsson.com | Bell Mobility, TELUS, Nokia, Samsung | RAN#99 | NR_CA_R18_intra | (Completed) DL_n77(2A)_BCS4/5 | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n78(2A) | n78 | 2 | Only FR1 | Per Lindell | Ericsson | per.lindell@ericsson.com | Bell Mobility, TELUS, Nokia, Samsung | RAN#99 | NR_CA_R18_intra | (Completed) DL_n78A | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n77B | - | 4 and 5 | Only FR1 | Sebastian Thalanany | UScellular | sebastian.thalanany@uscellular.com | Ericsson, Nokia, Samsung | RAN#99 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2306474 endorsed
Modified | CA_n77C | - | 4 and 5 | Only FR1 | Sebastian Thalanany | UScellular | sebastian.thalanany@uscellular.com | Ericsson, Nokia, Samsung | RAN#99 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2305371 endorsed
Modified | CA_n2(2A) | - | 4 and 5 | Only FR1 | Sebastian Thalanany | UScellular | sebastian.thalanany@uscellular.com | Ericsson, Nokia, Samsung | RAN#99 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2306474 endorsed
Modified | CA_n48(2A) | - | 4 and 5 | Only FR1 | Bill Shvodian | T-Mobile USA | bill.shvodian@t-mobile.com | Deutsche Telekom, Ericsson, Nokia, Nokia Shainghai Bell | RAN#99 | NR_CA_R18_intra | - | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2304860 endorsed
Modified | CA_n48B | - | 4 and 5 | Only FR1 | Bill Shvodian | T-Mobile USA | bill.shvodian@t-mobile.com | Deutsche Telekom, Ericsson, Nokia, Nokia Shainghai Bell | RAN#99 | NR_CA_R18_intra | (New) DL_n48B_BCS4 | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2304860 endorsed
Modified | CA_n48C | - | 4 and 5 | Only FR1 | Bill Shvodian | T-Mobile USA | bill.shvodian@t-mobile.com | Deutsche Telekom, Ericsson, Nokia, Nokia Shainghai Bell | RAN#99 | NR_CA_R18_intra | - | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2304860 endorsed
Modified | CA_n48(2A) | - | 4 and 5 | Only FR1 | Tricia Li | Huawei Technologies Limited | tricia.li@huawei.com | CBN, CATT, CTC, HiSilicon | RAN#99 | NR_CA_R18_intra | None | Completed |  |  | R4-2309383 | Yes | Yes | draft CR R4-2304860 endorsed
Unchange | CA_n5B | CA_n5B | 1, 2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | AT&T, Ericsson, Nokia, Samsung, Qualcomm | RAN#99 | NR_CA_R18_Intra | (Complete) DL_n5B_BCS0 | Ongoing |  |  |  | No | No
Unchange | CA_n96B | CA_n96B | 0 | Only FR1 | Frank Azcuy | Charter Communications Inc. | Fank.Azcuy@charter.com | Qorvo, Cable Labs, Comcast | RAN#99 | NR_CA_R18_Intra | none | Ongoing |  |  |  | No | No
Unchange | CA_n96C | CA_n96C | 0 | Only FR1 | Frank Azcuy | Charter Communications Inc. | Fank.Azcuy@charter.com | Qorvo, Cable Labs, Comcast | RAN#99 | NR_CA_R18_Intra | none | Ongoing |  |  |  | No | No