3GPP TSG RAN meeting #100										RP-231143

Taipei, June 12-14, 2023

Status Report to TSG

Agenda item:			9.3.4.12

| WI / SI Name | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_MIMO_OTA_enh |  |  |  |  |
| Unique ID | 970081 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-223509 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: | Core part: Dec/2023 | Performance part: Jun/2024 | Testing part: |  |
| Overall Completion level | Study Item: | Core part: 60% | Performance Part: 20% | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN WG4 |
| --- | --- | --- |
| Rapporteur | Name | Zhu, Siting |
|  | Company | CAICT |
|  | Email | zhusiting@caict.ac.cn |

1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

2.4	RAN4

2.4.1	Agreements

RAN4 #106-bis-e (Electronic Meeting, 17 April –26 April, 2023)

- General

  - Email summary for NR_MIMO_OTA_enh WI is in R4-2305999 [21].

  - WF on Rel-18 MIMO OTA in R4-2305910 is approved [19].

  - Framework and time plan for FR1 MIMO OTA is approved in R4-2305911 [20].

Sub-topic 1-1 Framework and time plan for FR1 MIMO OTA

<Agreement>:

- Measurement results from labs other than Rel-17/18 aligned labs to analysis UE performance or other MIMO antenna issues are not precluded.

Issue 1-2-3: PAD delivery scheme

<Agreement>:

- Discuss and conclude the PAD delivery scheme together with the confirmation of volunteer labs and PADs at the next meeting. Consider volunteer labs outside Asia to receive FR1 MIMO OTA PADs for last, e.g.: Apple (Cupertino/California/USA) as a last lab to test PADs.

Issue 1-2-4: Noise impact issue at low bands

<Agreement>:

- System Integrators are encouraged to do the noise impact experiments to eliminate the noise impact at low bands and provide guidance to labs, and should be compatible with the time plan in R4-2305911.

- Labs and/or system integrators should do the noise impact experiments to determine suitable values of attenuators for their own systems (The value might be 0~30 dB depends on different MIMO OTA system configurations).

- Power validation defined in TS 38.151 Annex C.3.6 should be done for Low bands, the target power should be set within a reasonable power level, e.g., -77 dBm/30kHz ~ -94.8 dBm/30kHz, to ensure the well power control of wanted signal and noise.

Issue 1-3-1: Feasibility of FR1 MIMO OTA test with hand phantom

Proposals:

- Proposal 1: Adjust positioning guidelines to ensure that the DUT and hand phantom can be encompassed in the 20 cm QZ in DMP.

- Proposal 2: Further discuss the MU assessment and CM impact with hand phantom based on the conclusion of the QZ size issue.

<Agreement>:

- FFS the feasibility and the proposals.

Issue 1-3-2: Necessity of FR1 MIMO OTA test with hand phantom

<Agreement>:

- FFS the necessity of FR1 MIMO OTA test with hand phantom at next meetings.

- Focus more on the necessity than the feasibility of FR1 MIMO OTA test with hand phantom at the next meeting.

Issue 2-1-1: FR2 lab alignment activity

<Agreement>:

- Use measured MASC values as pass/fail criteria to decide the lab alignment outcome.

- RAN4 needs to finalize the preliminary MU budget for FR2 3D-MPAC system firstly and then make the decision on pass/fail limit based on the MU budget and measurement results conducted in lab alignment activity. Adopt [0.5-1]*preliminary MU as starting point and further check after the FR2 MU is decided and some PAD measurement results are available.

- Each lab should finalize PAD measurement within 10 workdays, and deliver to the next lab in the same country ASAP with PAD In/Out information shared via email-reflector; otherwise, labs in the same country should equally share the period for testing the PADs.

Issue 2-1-2: Simulation platform validation activity

<Agreement>:

- Proposal: Keep the previous agreements in the FR2 MIMO OTA framework (R4-2302927) as below.

  - The lab alignment is required for the validation activity, i.e., the measurement results used for the validation activity should come from the aligned lab(s).

  - To align the assumptions in the simulation with the measurement, use prototypes and commercial devices (1st priority).

Issue 2-1-3: Minimum number of measurement data for requirements development

<Agreement>:

- Keep the previous agreement [8-15], FFS after receiving some feedback from volunteer labs on the estimated amount of measurement data can be provided. More measurement data is preferred.

Issue 2-1-4: Approaches to increase the measurement data for requirements development

<Agreement>:

- Include the PAD measurement results from aligned labs into the data pool for specifying FR2 MIMO OTA performance requirements, if allowed by PAD providers. FFS how to process the PAD measurement results from aligned labs.

Issue 2-2-1: PADs for FR2 lab alignment activity

<Agreement>:

- Confirm the following four PADs for the FR2 lab alignment activity.

| Provider | How many PADs can be provided | NSA (preferred) /SA | Current location | When will the PAD(s) be ready | Supported bands | Note |
| --- | --- | --- | --- | --- | --- | --- |
| Huawei | One commercial device for lab alignment activity but not for simulation validation activity | NSA | Beijing, China | Ready now | n257 | Not to disclose any UE information except supported bands |
| Keysight | Two commercial devices | EN-DC | USA | Can be hand carried to May RAN4 meeting | PAD_1: n257, n258, n260, n261 PAD_2: n260, n261 | Not to disclose the manufacturers and models |
| Samsung | One commercial device | EN-DC | Korea | Can be hand carried to May RAN4 meeting | n260, n261 | Not to disclose the manufacturers and models |

Issue 2-2-2: Volunteer labs for FR2 lab alignment activity

<Agreement>:

- Confirm the following five volunteer labs for FR2 lab alignment activity.

| Volunteer lab | City | Contact |
| --- | --- | --- |
| Apple | Cupertino, California, USA | Istvan Szini Istvan@apple.com |
| CAICT | Beijing, China | Xuan Yi, yixuan@caict.ac.cn |
| CMCC | Beijing, China | Yichen Zhao: zhaoyichen@cmdc.chinamobile.com Xiaohang Yang: yangxiaohang@caict.ac.cn |
| ETS-Lindgren | Cedar Park, Texas, USA | Edwin Mendivil Edwin.Mendivil@ets-lindgren.com |
| Huawei | Beijing, China | Lingyu Kong: konglingyu4@hisilicon.com Jizheng wang: wangjizheng@hisilicon.com |

Issue 2-2-3: FR2 PAD delivery scheme

<Agreement>:

- Adopt the following PAD delivery scheme for FR2 MIMO OTA lab alignment activity as baseline.

  - Keysight’s two PADs and Samsung’s one PAD: Huawei -> CMCC -> CAICT -> (transfer the PADs at Oct RAN4) -> Apple -> ETS-Lindgren -> Return to Keysight and Samsung

    - Note: The PADs can be tested in different labs located in the same country in parallel during the same period.

  - Huawei’s one PAD: Huawei -> CMCC -> [CAICT (if possible)] -> (transfer the PAD at Aug RAN4) -> Apple -> ETS-Lindgren -> (transfer the PAD at Oct RAN4) -> [CAICT (if cannot measure the PAD before Aug)] -> Return to Huawei

Issue 2-3-1: Work plan and general views

<Agreement>:

- To ensure the lab alignment activity can be concluded on time, companies are encouraged to contribute on FR2 preliminary MU assessment in recent RAN4 meetings. RAN4 should complete FR2 preliminary MU assessment before the end of lab alignment activity, i.e., no later than RAN4#109 (Nov 2023).

Issue 2-3-2: MU budget for FR2 MIMO OTA test system

<Agreement>:

- Further discuss preliminary MU budget for FR2 MIMO OTA test system at the next meeting. Inputs from CE vendors are encouraged.

Issues 2-4-1 and 2-4-2: Example LTE anchor band selection and Decision tree

<Agreement>:

- To make sure a consistent test condition for a particular UE across different labs, an example LTE anchor band along with a decision tree shall be defined.

- LTE B66 is selected as the example LTE anchor band for n261 FR2 MIMO OTA test. For UEs that don’t support B66, use a decision tree to select the LTE anchor band.

- Further discuss details of the decision tree at next meetings.

- Note: UEs that support n261 with any LTE anchor are allowed for the FR2 band n261 MIMO OTA Measurement Campaign.

Issue 3-1: FR2 MIMO OTA channel model validation

<Agreement>:

- FFS the following proposals with details brought by the proponent company at the next meeting.

  - Consider to add on TS 38.151 a PDP target definition for an additional cluster at 0ns.

  - Consider the to add an option to measure the EPRE Power Validation using a test equipment capable to decode the NR signal.

- Keep the FR2 temporal correlation validation pass/fail limits as agreed for consistency with FR1. FFS whether FR2 temporal correlation validation pass/fail limits can be tightened when more measurement results are available in future meetings.

Topic #4: CR work split for TS 38.151

<Agreement>:

- It is recommended to provide CRs to TS 38.151 based on the following work split:

| Clause in TS 38.151 | Clause name/Related Rel-18 Topics | Company |
| --- | --- | --- |
| 1, 2, 3, 4, 5 | Scope, References, Definitions, General, Frequency bands (if any) | CAICT |
| 6 | FR1 MIMO OTA requirements | Vivo, Xiaomi, CAICT, Apple, OPPO |
| 7 | FR2 MIMO OTA requirements | Qualcomm, Huawei, CAICT, Apple, Samsung, OPPO |
| Annex A | FR1 Test methodology (e.g., Enhancement for tablet type, hand phantom, if applicable) | Vivo, Xiaomi, CAICT, Apple, OPPO |
| Annex B | FR2 Test methodology (e.g., Preliminary MU) | Qualcomm, Huawei, Apple |
| Annex C | FR1 Channel models and Validation procedure | Huawei, CAICT, Spirent, Keysight |
| Annex D | FR2 Channel models and Validation procedure | Huawei, Spirent, Keysight |
| Annex E | gNB configurations (e.g., test time reduction, if applicable) | CAICT, Samsung |
| Annex F | Environmental requirements (if any) | Apple, Huawei |
| Note: 1. Please distinguish Rel-17 and Rel-18 CRs. New MIMO OTA requirements and new test methods/features defined in Rel-18 should be Rel-18 CRs. Test methodology complement/maintenance should be Rel-17 CRs. 2. For clauses with multiple interested companies, alignment discussions before each RAN4 meeting are encouraged. |  |  |

RAN4 #107 (Incheon, KR, May 22nd – May 26th, 2023)

- General

  - Topic summary for NR_MIMO_OTA_enh WI is in R4-2310470 [39].

  - Ad-hoc minutes for R18 MIMO OTA in R4-2309751 is approved [40].

  - WF for Rel-18 MIMO OTA in R4-2309821 is approved [41].

  - Updated Framework for FR2 MIMO OTA performance requirements development in R4-2309816 is approved [28].

  - Template for FR2 MIMO OTA lab alignment activity in R4-2308740 is approved [27].

Issue 1-1-1: Necessity of FR1 MIMO OTA test with hand phantom

<Agreement>:

- Further study the necessity based on operators’ demand and measurement results.

  - RAN4 will make decision on the necessity at August meeting.

Issue 1-2-1: Volunteer labs for FR1 lab alignment activity

<Agreement>:

- Confirm the following volunteer labs for Rel-18 FR1 MIMO OTA lab alignment.

| Volunteer lab | City | Contact |
| --- | --- | --- |
| Apple | Cupertino, California, USA | Istvan Szini, Istvan@apple.com |
| CAICT | Beijing, China | Xuan Yi, yixuan@caict.ac.cn |
| CMCC&BUPT joint lab | Beijing, China | Yichen Zhao, zhaoyichen@cmdc.chinamobile.com Xiaohang Yang, yangxiaohang@caict.ac.cn |
| MediaTek | Beijing, China | Shuang Zhang, Allen.zhang@mediatek.com |
| Xiaomi | Beijing, China | Shengxiang Guo, guoshengxiang@xiaomi.com |
| Huawei | Shanghai, China | Li Jinxing, lijinxing3@huawei.com; Hai Zhou, hai.zhou1@huawei.com |

Issue 1-2-2: PADs for FR1 lab alignment activity

<Agreement>:

- Tentatively confirm the following PADs for Rel-18 FR1 MIMO OTA lab alignment.

| Provider | How many PADs | Supported FR1 bands | PAD current location | When will the PAD(s) be ready |
| --- | --- | --- | --- | --- |
| [vivo] | [1] | TBA | TBA | TBA |
| [Xiaomi] | [1] | TBA | TBA | TBA |
| TBA |  |  |  |  |

Issue 1-2-3: Implementation of FR1 MIMO OTA lab alignment

<Agreements>:

- Adopt the following PAD delivery scheme for Rel-18 FR1 MIMO OTA lab alignment activity.

  - Labs in Beijing -> Labs in Shanghai -> (transfer the PADs at Oct RAN4) -> Labs outside Asia

    - Note: The PADs can be tested in different labs located in the same country in parallel during the same period.

- FR1 Lab Alignment Activity can start with the labs that completed channel model validation at band n28, after RAN4#107 immediately, once PADs are ready.

Issue 2-1-1: Whether to consider a certain number of UE panels

<Agreements>:

- Not to require a minimum number of single-panel UEs in Measurement Campaign.

- The previous agreements on Clause 2.2.7 in the framework (R4-2302927) are kept.

- OEM are encouraged to provide UEs with different numbers of antenna panels for the Measurement Campaign.

Issue 2-1-2: Working procedures for Measurement campaign

<Agreement>:

- The following working procedures for Measurement campaign are agreed.

- Test cases for FR2 MIMO OTA Measurement Campaign:

  - Test band: n261 (first stage)

  - Operation mode: NR Non-Standalone (NSA) (first stage)

  - Powe class: PC3 (first stage)

- Commercial Device (Smartphone) selection criteria:

  - DUT capability: at least support n261 (for the first stage)

  - The following selection criteria can also be considered:

    - Year of production: 2019-2023

    - Brand variety

    - Popularity

    - Number of bands supported

  - Power Class: PC3

- Commercial devices preparation:

  - Test labs can collect commercial devices by themselves based on the above selection criteria

  - Other companies are also encouraged to provide commercial devices based on the above selection criteria

- Measurement results submission:

  - Use the same worksheet template to submit the measurement results (a template will be submitted to RAN4 meetings for approval)

  - The measurement results should be submitted to RAN4 by anonymous approach (the UE model should not be disclosed). The following information should be provided:

    - All FR2 bands supported by each UE

    - Production year of each UE

    - Other information that should be disclosed is FFS

  - The plan and progress of each lab are encouraged to be shared via the RAN4 reflector (e.g., how many devices are planned to be/ have been measured)

Issue 2-2-1: Collect PADs’ information on supported LTE bands

<Agreement>:

- The supported LTE bands information can be collected and shared publicly.

- The tested EN-DC band combination should be shared among the volunteer labs to ensure a same test condition for same device across different labs, but should not be disclosed publicly to avoid any PADs being identified.

Issue 2-3-1: EN-DC band combination selection for FR2 MIMO OTA

<Agreement>:

- To make sure a consistent test condition for a particular UE across different labs, an example LTE anchor band along with a decision tree shall be defined. LTE B66 is selected as the example LTE anchor band for n261 FR2 MIMO OTA test. For UEs that don’t support B66, use a decision tree to select the LTE anchor band.

- Reuse the same selection logic of FR1 TRP TRS for FR2 MIMO OTA to select EN-DC band combination.

Issue 2-3-2: Applicability rules for MIMO OTA testing of FR2 SA and NSA UEs

<Agreement>:

- RAN4 further discuss how to handle the applicability rules for both SA and NSA capable FR2 UEs.

Issue 2-4: FR2 channel emulator MU element

<Agreement>:

- Re-use the FR1 Channel Emulator definition and MU values for FR2.

Issue 3-1: FR2 Channel Model Power Validation

<Agreement>:

- Implement on TS 38.151 an option to measure FR1 and FR2 EPRE Power Validation adopting a test equipment capable to decode the NR signal.

- The proponent companies are encouraged to submit a corresponding CR containing detailed measurement procedures at the next meeting.

2.4.2	Remaining Open issues

Core part WI:

- FR2 MIMO OTA test methodology enhancement

- Further refinement on Test parameters for FR2 MIMO OTA is not precluded

- Power validation pass/fail limit for FR2 channel model

- FR1 MIMO OTA test methodology enhancement

- Further study the necessity and feasibility of FR1 MIMO OTA test with hand phantom

- Test time reduction methodology for FR1 MIMO OTA is not precluded

- Preliminary Measurement Uncertainty (MU) assessment corresponding to newly defined test methodologies and test configurations, if any

Perf. part WI:

- FoM and criteria for FR2 MIMO OTA

- Refine the additional criteria of FR2 MIMO OTA for PC3 UE, if necessary

- Study the FoM and additional criteria of FR2 MIMO OTA for UE with other power classes

- Specify FR2 MIMO OTA performance requirements based on the approved framework and time plan

- Down-selection between the Pure measurement approach and the Hybrid approach

- Specify FR1 MIMO OTA performance requirements

- Specify FR1 MIMO OTA performance requirements based on the approved framework and time plan

- Specify recommended test tolerance (TT) for FR1 and FR2 MIMO OTA performance requirements

3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

None

4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

RAN4#106-bis-e contributions

- R4-2304026	on MIMO OTA test with hand phantom	Huawei Tech.(UK) Co.. Ltd

- R4-2304073	Research on FR1 MIMO OTA noise impact at low band	MediaTek Beijing Inc.

- R4-2304215	Noise impact of FR1 low frequency for CMCC&BUPT joint lab	CMCC

- R4-2304346	On FR1 MIMO OTA lab alignment PADs roaming	Apple

- R4-2304347	On FR2 MIMO OTA lab alignment PADs roaming	Apple, ETS-Lindgren

- R4-2304677	Views on FR2 MIMO OTA requirements	Qualcomm Incorporated

- R4-2304829	On EN-DC band combination selection for FR2 MIMO OTA	Samsung

- R4-2304830	Discussion on single panel UE in FR2 MIMO OTA campaign	Samsung

- R4-2305122	Further views on FR1 MIMO OTA test for smartphone with hand phantom	CAICT, SAICT

- R4-2305124	Views on FR2 MIMO OTA lab alignment	CAICT

- R4-2305363	Alternative method to accommodate single-panel UEs in FR2 MIMO OTA requirement	Apple

- R4-2305498	Discussion on FR2 MIMO OTA test methodology enhancement	Huawei,HiSilicon

- R4-2305525	on the FR1 MIMO OTA	Xiaomi

- R4-2305526	on the FR2 MIMO OTA	Xiaomi

- R4-2305608	MU budget for FR2 MIMO OTA test system	Qualcomm Incorporated

- R4-2305613	On FR1 MIMO OTA in browsing mode	OPPO

- R4-2305614	On hybrid approach for FR2 MIMO OTA	OPPO

- R4-2305784	On Phantom Testing and QZ Sizes	Keysight Technologies UK Ltd

- R4-2305910	WF on Rel-18 MIMO OTA	CAICT

- R4-2305911	Framework and time plan for FR1 MIMO OTA performance requirements development	CAICT

- R4-2305999	Email summary for [106bis-e][330] NR_MIMO_OTA_enh	Moderator (CAICT)

RAN4#107 contributions

- R4-2307241	CR to TS38.151 on FR1 power validation pass fail limit	Huawei, HiSilicon, CAICT, MVG

- R4-2307242	MU associated with hand phantom	Huawei, HiSilicon

- R4-2307244	On the necessity of testing with hand phantom	Huawei, HiSilicon

- R4-2307506	Channel validation results at low bands	MediaTek (Hefei) Inc.

- R4-2307938	On applicability decision tree for FR2 MIMO OTA	Samsung

- R4-2308740	3GPP FR2 MIMO OTA Lab Alignment Activity Template	CAICT

- R4-2309816	Updated Framework for FR2 MIMO OTA performance requirements development (May 2023)	CAICT

- R4-2308742	On FR1 MIMO OTA test with hand phantom	CAICT

- R4-2308743	On FR1 MIMO OTA lab alignment	CAICT

- R4-2308979	On positioning guidelines with hand phantom	OPPO

- R4-2309014	On the FR1 MIMO OTA	Xiaomi

- R4-2309242	Views on FR2 MIMO OTA requirements	Qualcomm Incorporated

- R4-2309301	Discussion on FR2 MIMO OTA test methodology enhancement	Huawei,HiSilicon

- R4-2309467	On Phantom Testing and QZ Sizes	Keysight Technologies UK Ltd

- R4-2309468	On FR2 CE MU	Keysight Technologies UK Ltd, Spirent Communications

- R4-2309473	On FR2 MIMO OTA channel model validation	Apple, Keysight Technologies

- R4-2309304	Discussion on FR2 MIMO OTA channel validation	Huawei,HiSilicon

- R4-2310470	Topic summary for [107][333] NR_MIMO_OTA_enh	Moderator (CAICT)

- R4-2309751	Ad-hoc minutes for R18 MIMO OTA		Moderator (CAICT)

- R4-2309821	WF on Rel-18 MIMO OTA 	CAICT

26.04.2023		minor adaptations for RAN #100

01.02.2023		minor adaptations for RAN #99

27.10.2022		minor adaptations for RAN #98e

01.08.2022		minor adaptations for RAN #97e

21.05.2022		minor adaptations for RAN #96

10.01.2022		minor adaptations for RAN #95e

04.10.2021		minor adaptations for RAN #94e

08.08.2021		minor adaptations for RAN #93e

17.05.2021		minor adaptations for RAN #92e

28.01.2021		minor adaptations for RAN #91e

09.11.2020		minor adaptations for RAN #90e

31.08.2020		minor adaptations for RAN #89e

20.04.2020		minor adaptations for RAN #88e

18.02.2020		minor adaptations for RAN #87e

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template