## Cover sheet
3GPP TSG RAN Meeting #102 | [8 empty] | RP-233566
Edinburgh, Scotland, December 11-15, 2023
Agenda Item: | 13.3.35
Source: | China Telecom, ZTE
Title: | WP for LTE_CA_R17-UEConTest
Work item code: | LTE_CA_R17-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the present work item is to develop RF, RRM and protocol test cases for Rel-17 LTE CA configurations. The scope of this work item is conformance testing of all Rel-17 LTE CA configurations specified by 3GPP TSG RAN WG4. The introduction of the CA configurations into the 3GPP TSG RAN WG5 test specification is dependent on the progress of the associated core and performance work items in 3GPP TSG RAN WG4.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases / configurations (Note 1) | Number of new test cases / configurations | Comments
Overall completion |  | 5% (+5%)
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 5%
FR1 |  | 5%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NEW TEST CASES
5 References
[1] RP-232260 | New WID on UE Conformance - Rel-17 LTE CA Configurations
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for LTE_CA_R17-UEConTest | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_CA_R17-UEConTest | [13 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The objective of this work item is to define the UE conformance test cases correspond to the defined test requirements in WI ‘LTE_CA_R17_2BDL_1BUL’, ‘LTE_CA_R17_3BDL_1BUL’, 'LTE_CA_R17_xBDL_1BUL', 'LTE_CA_R17_2BDL_2BUL' and 'LTE_CA_R17_xBDL_2BUL'. The scope of this work item is conformance testing of all Rel-17 LTE CA configurations specified by 3GPP TSG RAN WG4. The introduction of the CA configurations into the 3GPP TSG RAN WG5 test specification is dependent on the progress of the associated core and performance work items in 3GPP TSG RAN WG4. | [13 empty] | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common Clause | 38.521-x: Tx test cases / 38.522: Test case applicability | 38.521-x: Rx test cases / 38.522 Test case applicability | 38.521-4: RF perfromance test cases / 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Lei GAO |  | gaol8@chinatelecom.cn | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  | N/A
WP Item ID | Is new configuration or test case? | DL Configuration | UL configuration(s) | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
19
0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [14 empty] | CALCULATED CELLS | TS STATUS INPUT
NEW HPUE CONFIGURATIONS
LTE_CA_R17_2BDL_1BUL(880087)
|  | CA_38A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_38C-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_26A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_26A-38C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-8A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_46A_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_46C_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_46D_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_46E_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_48A_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_48C_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_48D_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_30A-48A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#101(Nov-23) |  |  | 1
|  | CA_2C-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-3A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-3A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_40A-40A-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_40A-40A-42C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_40A-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_40C-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_40A-40A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-46E | CA_2A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
LTE_CA_R17_3BDL_1BUL(880088)
|  | CA_2A-13A-66A-66B | CA_66B | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-48A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-48C |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-48D |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-13A-48C | CA_48C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-48E-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-48C-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-48D-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_13A-48C-66A | CA_48C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_13A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_13A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-38A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-38C-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-12A-66A-66A | CA_66A-66A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_12A-30A-66A-66A | CA_66A-66A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-12A-30A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-12A-66A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-5A-30A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-12A-66A-66A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8A-41A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-20A-38A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-40A-41A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-28-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-7A-8A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-8A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-8A-20A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-8A-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-20A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-12A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-5A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7A-7A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7C-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-7A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-7A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-7A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-7A-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-29A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#101(Nov-23) |  |  | 1
|  | CA_2A-29A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-29A-66A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#101(Nov-23) |  |  | 1
|  | CA_2A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7C-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_5A-7A-7A-28A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-3A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-3C-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-28A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-28A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
LTE_CA_R17_xBDL_1BUL(880089)
|  | CA_1A-3A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-7A-8A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-8A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-8A-40C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7C-20A | CA_7C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7C-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-28A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-7A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-3C-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-1A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-20A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-3A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-8A-40C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-8A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-5A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-7A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-7A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-5A-7C-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7A-12A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7C-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7A-7A-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7A-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-7C-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_2A-2A-29A-30A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#101(Nov-23) |  |  | 1
|  | CA_3A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
LTE_CA_R17_2BDL_2BUL(880090)
|  | CA_30A-48A | CA_30A-48A | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#101(Nov-23) |  |  | 1
|  | CA_8A-20A | CA_8A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_8A-28A | CA_8A-28A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-38A | CA_3A-38A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40A | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40A-40A | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40C | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-40D | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-40A-40A | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-40D | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-40C | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40D | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_28A-40C | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-26A | CA_3C CA_3A-26A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_7C-26A | CA_7C CA_7A-26A | New LTE CA Config |  |  | Pending |  |  |  | 1
LTE_CA_R17_xBDL_2BUL(880091)
|  | CA_3C-7A-8A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-8A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3C-8A-20A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-20A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8A-20A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-7A-8A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-8A-20A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-8A-20A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-20A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3C-20A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-8A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-8A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-8A-20A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-8A-20A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A_3A_7A_8A_38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A_3A_8A_20A_38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-20A-38A | CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-20A-38A | CA_1A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-7A-20A-38A | CA_1A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-7A-20A-38A | CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-7A-20A-38A | CA_1A-3A CA_1A-20A CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40A | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-28A-40A | CA_3A-40A CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40A-40A | CA_1A-3A CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_3A-28A-40A-40A | CA_3A-28A CA_3A-40A CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40D | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
|  | CA_1A-3A-40C | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on S1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).