## Slide 1: Initial View on 6G Timeline and IMT-2030 Submission Planning

## Slide 2: ITU-R Timeline
Major milestone in ITU-R timeline for IMT-2030 (within red dotted box)
  6G spectrum will be decided in WRC-27
  Technical proposal submission window (’27.2~’29.2)
  Final IMT-2030 specification approval in ’30.06

## Slide 3: 3GPP 6G Timeline [1/2]
3GPP timeline should support early 6G commercialization around early ‘29 & beyond, ensuring IMT-2030 schedule at the same time
Proposals
2022
2023
2024
2025
2026
2027
2028
2029
2030
Vision
Technical requirements
Evaluation
Decision & Rec
Trends
Vision
Req.
IMT-2030
Recommendation
WRC26
WRC27
R19 6G
channel model SI1)
R20 Stage1 Req. SI
R22 6G phase 2 WI
6G Technical
Study Item
Earliest
Possible
6G start time
(‘25.6)
2nd possible
6G start time
(‘25.9)
RAN level requirements
R21 6G phase 1 WI
6G
R21 5G-Adv.
R20 5G-Adv.
R19 5G-Adv.
RAN1
freezing
Core part
freezing
ASN.1
freezing
1) upper mid-band, ISAC channel model, etc
R18 5G Adv.
Initial 6G submission
with R21 normative work
Second 6G submission
with R22 normative work
Stage 1
Requirements

## Slide 4: 3GPP 6G Timeline [2/2]
Assuming 18-month release duration, important milestone for 6G in 3GPP can be summarized as follows
  6G channel model study in Rel-19 (will be approved during RAN #102)
  Study item for RAN-level requirement and deployment scenarios for 6G
    ’24.09 or ‘24.12, which is 9 months before approval of SI for 6G Radio Access Technology
    6G workshop in 3GPP can be considered 3 months after approval of RAN level requirement study item (‘24.12 or ’25.03) in order to allow companies to consider technical enablers based on input on RAN-level requirements during first 3 months
  Study item for 6G Radio Access Technology
    Can be proceeded as Rel-20 study item which expands towards Rel-21
    The potential start time is ‘25.06 (RAN1 functional freezing for Rel-19) or ‘25.09 (core part freezing for Rel-19)
    A set of basic features selected for initial 6G will be proceeded in Rel-21, while other enhancing features can be studied together, targeting for 2nd version of 6G
  Initial 6G normative work is expected in Rel-21 (with a set of basic features)
    This version can be submitted to ITU-R
  2nd 6G normative work is expected in Rel-22 (with a set of enhancing features)
    This is business as usual
No multiple drops within one release (early/major/late)
  This is lesson learned from 5G standardization and commercialization