## Slide 1
3GPP Work Plan
Review at Plenary #102
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#102 (subject to removal if not TSG-approved)
Does not include: - the company-proposed WIDs approved at TSG#102
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2023
SP-231807/ RP-234079 (rev of SP-231794, SP-231698/RP-233992, rev of RP-232718 / CP-233012 / SP-231618) - 3GPP TSG#101, 11 -15 December 2023, Edinburgh, Scotland, UK

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing Releases
Ongoing Releases
  Rel-18 Timeline and Progress
  Rel-19 Timeline and Progress
  Rel-20 initial talks
  Rel-21 initial talks
Background information

## Slide 3
Ongoing Releases timelines
#96
Release 19
Release 18
Note: All starting dates are indicative
#98e
#100
#102
#104
#106
#108
#110
#112
#114
2022
2023
2025
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
SA1 Stage 1
Stage 3 (CT & SA)
Stage 2 Normative
RAN Content def.*
RAN Completion**
Maint.*
ASN.1 & Open APIs
ASN.1
1st review
#99
#101
#103
#107
#109
#111
#113
2024
2026
SA1 Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1 & Open APIs
Stage 2 Normative
#105
#97-e
RAN Content Def*
SA St.2 Content Def
2021
#92-e
#94-e
#95-e
#93-e
Mar.
#91-e
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Rel-21 initial talks
Background information

## Slide 5
Release 18 timeline
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)

## Slide 6: Release 18 Progress: Stages 1 & 2
Stage 1 and TSG content definition:
  Completed since TSG#94
  SA1 has 25 normative items plus 14 studies.
Stage 2 at SA2 and SA6:
  Studies :
    Completed since TSG#99
    SA2 and SA6 have 43 studies
  Normative :
    Completed since TSG#100, except for EDGEAPP_EXT (UID 960011, SA6, from 65% to 95%)
    SA2 and SA6 have 57 normative items

## Slide 7: Release 18 Progress: Stage 3 (SA/CT)
Stage 3 (CT WGs) and SA3, SA4 and SA5*: In progress.
  Studies:
    75 studies for all these WGs
    OCI (St.3 Studies) = 92% - against 84% at previous TSG
  Normative:
    239 items for all these WGs
    OCI (St.3 Norm) = 78% - against 65% at previous TSG
    Still 31 items below 50%, including:
      SA5 and CT6 aspects of 5GSATB
      CT1&3 aspects of ADAES
    Reminder: deadline is next March meeting
OCI = Overall Completion Index =sum of all % completion divided by the number of items
*Note: For tools limitation reasons, SA3, SA4 and SA5 are reported in this slide, even if they may cover several Stages

## Slide 8: Release 18 Progress: Stage 3 (RAN)
Stage 3 in RAN: (reminder: new WIDs/SIDs approved at RAN#102 not considered here)
  RAN studies (17 items): OCI: 95% - against 85% at previous RAN
  RAN Core aspects: OCI: 88% - against 73% at previous RAN
    RAN1 Core (after “maintenance”): 8 items 100% complete, one at 99%
    RAN2 Core: 9 items 100% complete, two at 95%
    RAN 3 Core: 6 items 100% complete, one at 80%
    RAN4 Core: OCI: 84% (67 items)
  RAN Perf aspects: OCI: 55% - against 35% at previous RAN
    RAN1 Perf (after “maintenance”): 31 % (7 items)
    RAN2 Perf: 10 % (4 items)
    RAN3 Perf: 20% (1 item)
    RAN4 Perf: OCI: 61 % (60 items)
  RAN5 testing: OCI: 31% (10 items)
OCI = Overall Completion Index =sum of all % completion divided by the number of items
  RAN#102: RP-231776 (RAN chair) : As planned, Release 18 in RAN2/3/4 is functionally frozen
  actual completion: RAN “nearing achievement”, now starting the
  “maintenance phase” for RAN2/3/4Core, until March 2024

## Slide 9: Release 18 recap – text version
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze (before maintenance)
    Freeze for SA3 (stages 2 & 3) – maintenance to continue
  Dec 2023 (TSG#102):
    RAN1 freeze (after maintenance)
    RAN2, RAN3, RAN4Core freeze (before maintenance)
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Now

## Slide 10: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress – and content
Rel-20 initial talks
Rel-21 initial talks
Background information

## Slide 11
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 12: Release 19 progress overview
Stage 1 (SA1):
  Studies :
    14 studies – stable for long
    All studies completed (against 94% at previous TSG)
      Except for FS_ISN, exception request submitted
  Normative :
    24 tasks, including “miniWIDs” - one new miniWID at SA#102
    All normative completed (against 92 %) except for:
      Stage 1 of Ambient power-enabled Internet of Things: 95%
      Stage 1 of DualSteer: 95%
    See next slide on Rel-19 content
Stage 2, Stage 3, RAN:
  Overall
    SA & RAN Content Definition taking place during TSG#101 & 102, deciding for RAN content (Studies and normative) and for SA2 Studies (rocess 2nd batch)
  Studies :
    30 studies (not counting SA2 studies approved at SA#102) – against 4 at TSG#101
  Normative :
    20 normative – against 8 at TSG#101
  OCI not really relevant (neither for studies nor for normative) since items are being introduced

## Slide 13: Release 19 timeline recap - text version
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now

## Slide 14: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Rel-21 initial talks
Background information

## Slide 15: Release 20
Rel-20 will cover 5GA (normative & studies) and 6G studies
Rel-20 Studies (5GA and 6G) & 6G workshop:
  May 2024: Workshop on IMT-2030 use cases (SA1 ad-hoc , see SP-231619)
  Sept 2024 (TSG#105): Approval of SA1 SIDs. The SA1 SIDs are exceptionally divided in two Parts (about 50% of SA1 time to be dedicated to each Part):
      Part 1 (“5GA-centric”): the Rel-20 SIDs for which corresponding normative work is anticipated to also belong to Rel-20
      Part 2 (“6G-centric”): the Rel-20 SIDs for which corresponding normative work is anticipated to be after Rel-20.
  TBD (decision to be taken by TSG#103): RAN plenary SID (e.g., radio requirements and KPIs)
  March 2025 (TSG#107): First TSG-wide 6G workshop
  June 2025 (TSG#108):
    Approval of SA2 SID
    Approval of RAN-WG SIDs
Rel-20 Normative work (5GA):
    No decision yet about Rel-20 normative work timeline. More dates to be decided at TSG#103

## Slide 16: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Rel-21 initial talks
Background information

## Slide 17: Release 21 initial talks
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP Rel-21 (normative) work will be submitted to ITU before 2030
All Release 21 Freezing dates and other milestones TBD
Note that, as usual in 3GPP, previous Generations will also continue to be maintained & enhanced
* source: TSG#102-endorsed RP-233985

## Slide 18: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Rel-21 initial talks
Background information

## Slide 19: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 19; Master version in MS Project; Working versions in Excel
NEW: Tutorials on content, maintenance, etc. in subfolder \info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
Started – skeleton in RP-233919 / CP-233305 / SP-231617, call for contribution in RP-233777 / CP-233299 / SP-231516

## Slide 20: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 5 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date. However, the deadlines for SA5’s Stage 1 and Stage 2 are SA5-internal since there is no dependency (i.e. SA5 is not expecting work from any other WGs).
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2