## Cover sheet
3GPP TSG RAN WG5#103 | [10 empty] | R5-243276
<Fukuoka, Japan, 20th May – 24th May, 2024>
Agenda Item: | 7.5.2
Source: | China Unicom
Title: | UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects
Work item code: | NR_redcap_enh_plus_CT1-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects work item is to define the UE conformance requirements corresponding to WID on NR_redcap_enh_plus_CT1-UEConTests, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the RedCap UE work item in Rel-18. At the RAN#103 meeting the Rel-18 RAN5 work item for UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects(NR_redcap_enh_plus_CT1-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+0%) | 0 | 17 (-94)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+0%) | 0 | 17 (-94)
FR1 |  | 5% | 0 | 17 (-94)
FR2 |  | 5% | 0 | 14 (+2)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx | 0% |  |  | 0%
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
RF Demod/QSI test cases | 38.521-4 | 0% | 0 | 3 (-20) | 0% | 0 | 3 (-20)
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 14 (+2) | 0% | 0 | 14 (+2) | 0% | 0 | 14 (+2)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Protocol Test suites (TTCN) | 38.523-3
5 References
[1] RP-240054 | New WID on UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspect | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_redcap_enh_plus_CT1-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance – Enhanced support of reduced capability NR devices plus CT1 aspect comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID | [12 empty] | vs Area
WP Resp: |  | Yu Shi(China Unicom),Yang, Zhaobing (Huawei) ,Calle Hagenfeldt (Ericsson),Yogesh Tugnawat (Qualcomm) |  |  | shiyu19@chinaunicom.cn;yangzhaobing@hisilicon.com;calle.hagenfeldt@ericsson.com;yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 5% | 5%
[14 empty] | 80 (-167) | 66 (-16)
[14 empty] | 98.5 (-103.2) | 70.5 (-17)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | common test environment for eRedCap | Definition of common test environment for eRedCap |  |  |  |  | 3 | 0% | 0% |  | 0% | 0%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments |  |  |  |  | 3 | 0% | 0% |  | 0% | 0%
3 |  | 38.508-1 | 6 | Test environments for Signalling test | Necessary changes to Signalling test environments |  |  |  |  | 3 | 0% | 0% |  | 0% | 0%
4 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  |  |  |  | 3 | 0% | 0% |  | 0% | 0%
5 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
6 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for eRedCap |  |  |  |  | 3 | 0% | 0% |  | 0% | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
7 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | [5 empty] | 2 | 0% | 0% |  | 0%
8 |  | 38.521-1 | 4 | General | [5 empty] | 2 | 0% | 0% |  | 0%
9 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | [5 empty] | 2 | 0% | 0% |  | 0%
10 |  | 38.521-1 | Annex |  | Check if necesarry to update Annex |  |  |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
Transmitter characteristics (Clause 6)
11 |  | 38.521-1 Tx | 6 | Tx TC for eRedCap | Check if necesarry to update Tx TCs for eRedCap |  |  |  |  | 5 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
Receiver characteristics(Clause 7)
12 |  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
13 |  | 38.521-1 Rx | 7.3I.3 | Reference sensitivity power level for eRedCap | Update of diveristy characteristics intrdocution for eRedCap |  |  |  |  | 5 | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
36 |  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 1 | 0% | 0% |  | 0%
74 | Y | 38.521-4 | [7 empty] | 1 | 0% | 0% |  | 0%
75 | Y | 38.521-4 | [7 empty] | 1 | 0% | 0% |  | 0%
76 | Y | 38.521-4 | [7 empty] | 1 | 0% | 0% |  | 0%
82 |  | 38.521-4 | Annex A | Measurement channels | [5 empty] | 1 | 0% | 0% |  | 0%
83 |  | 38.521-4 | Annex B | Propagation conditions | [5 empty] | 1 | 0% | 0% |  | 0%
84 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances for FR1 | [5 empty] | 1 | 0% | 0% |  | 0%
85 |  | 38.521-4 | Annex G | Minimum test time | [5 empty] | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
86 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. |  |  |  |  | 1 | 0% | 0% |  | 0%
87 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. |  |  |  |  | 1 | 0% | 0% |  | 0%
88 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-2. |  |  |  |  | 0 | 0% | 0% |  |  | 0%
89 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
90 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
395 |  | 38.903 | 8 and attachment | Grouping and TT analysis of test cases defined in TS 38.533 | TT analysis grouping for RRM test cases |  |  |  |  | 0 | 0% | 0% |  |  | 0%
395 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | MU analysis for Power class 7 |  |  |  |  | 0 | 0% | 0% |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
396 |  | 38.905 | 4 | Test coverage analysis | Add header, general text and table to list test point analysis for RedCap |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
397 | Y | 38.523-1 | 6.1.2.X | Cell Selection / eRedCap | TP1:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except that the UE supported Rx is barred by cellBarred-eRedCap1Rx or/and cellBarred-eRedCap2Rx in the SIB1. THEN: the UE considers the cell as barred and no camping on this cell can take place. TP2:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except intraFreqReselection-eRedCap in SIB1 is absent. THEN: the UE considers the cell as barred and no camping on this cell can take place. TP3:[TS 38.331 clause 5.2.2.4.2, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN:a cell fulfils the requirements for a suitable cell. THEN: the UE considers the cell suitable and camps on it. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
397 | Y | 38.523-1 | 6.1.2.X | Cell Selection / eRedCap / emergency calls | TP1: WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except that the UE supported Rx is barred by cellBarred-eRedCap1Rx or/and cellBarred-eRedCap2Rx in the SIB1, barringExempt-eRedCap is set to “true” in SIB1, and user initiates an Emergency call. THEN: the UE considers the cell as not barred and successfully completes the Emergency call. |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
397 | Y | 38.523-1 | 6.1.2.X | Cell Selection / eRedCap / halfDuplexRedCapAllowed / MFBI | TP1:[TS 38.331 clause 5.2.2.4.2 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a cell fulfils the requirements for a suitable cell except halfDuplexRedCapAllowed is not present in SIB1 , and frequencyBandList only includes one band in SIB1. THEN: the UE, supporting only half-duplex FDD operation on this band, considers the cell as barred and no camping on this cell can take place. TP1:[TS 38.331 clause 5.2.2.4.2 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a MFBI cell fulfils the requirements for a suitable cell except halfDuplexRedCapAllowed is not present in SIB1 , and frequencyBandList includes two bands in SIB1. THEN:the UE, supporting only half-duplex FDD operation on two bands, considers the cell as barred and no camping on this cell can take place. TP1:[TS ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: a MFBI cell fulfils the requirements for a suitable cell except halfDuplexRedCapAllowed is not present in SIB1 , and frequencyBandList includes two bands in SIB1. THEN:the UE, supporting only half-duplex FDD operation on the first band in the frequencyBandList and supporting full-duplex FDD operation on the second band in the frequencyBandList , considers the cell as not barred and camps on it. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
398 | Y | 38.523-1 | 6.1.2.X | Cell reselection / inter-frequency / eRedCap | TP1:[TS 38.331 clause 5.2.2.4.5, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with interFreqCarrierFreqList-v1800 is absent, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE reselects the inter-frequency neighbour cell. TP1:[TS 38.331 clause 5.2.2.4.5, 5.2.2.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with eRedCapAccessAllowed is present in interFreqCarrierFreqList-v1800, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE reselects the inter-frequency neighbour cell. TP1:[TS ] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: serving cell broadcasts SIB4 with eRedCapAccessAllowed is not present in interFreqCarrierFreqList-v1800, and inter-frequency neighbour cell fulfils reselection criteria. THEN: UE does not reselect the inter-frequency neighbour cell. |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
Layer 2
399 | Y | 38.523-1 | 7.1.1.1.X | Random access procedure / eRedCap UE identification / Msg3-based / CCCH1 | TP1:[TS 38.321 clause 6.2.1] WITH: UE supporting eRedCap and in NR RRC_Inactive state and useFullResumeID is signalled in SIB1. WHEN: UE starts Random Access procedure. THEN: the UE uses the eRedCap specific LCID in Msg3. |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
400 | Y | 38.523-1 | 7.1.1.1.X | Random access procedure / eRedCap UE identification / Msg1-based / Contention based / Msg3-based / CCCH | TP1:[TS 38.321 clause 5.1.1b,5.1.1c ] WITH: UE supporting eRedCap and in NR RRC_IDLE state . WHEN: UE starts Random Access procedure and there is a set of configured RA resources with eRedCap indication. THEN: the UE uses the eRedCap specific random access resource in Msg1. TP2:[TS 38.321 clause 5.1.1b,5.1.1c; TS 38.331 clause 6.3.2] WITH: UE supporting eRedCap and in NR RRC_IDLE state. WHEN: UE starts Random Access procedure and there is no set of configured RA resources with eRedCap indication and there is a set of configured RA resources with RedCap indication. THEN: the UE uses the RedCap specific random access resource in Msg1. TP3:[TS 38.321 clause 5.1.1b,5.1.1c ] WITH: UE supporting eRedCap and in NR RRC_IDLE state . WHEN: UE starts Random Access procedure and there is no set of configured RA resources with eRedCap indication and there is no set of configured RA resources with RedCap indication. THEN: the UE uses the legacy random access resource in Msg1. TP4:[TS 38.321 clause 5.1.1b,5.1.1c ] WITH: UE supporting eRedCap and in NR RRC_IDLE state . WHEN: UE starts Random Access procedure. THEN: the UE uses the eRedCap specific LCID in Msg3 regardless whether (e)RedCap specific Random Access configuration is configured. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
401 | Y | 38.523-1 | 7.1.1.1.X | Random access procedure / eRedCap UE identification / Msg1-based / Contention free | TP1:[TS 38.321 clause 5.1.1b ] WITH: UE supporting eRedCap and in NR RRC_CONNECTED state. WHEN: UE performs handover to the target cell and starts random Access procedure, and contention-free Random Access Resources have been provided for this Random Access procedure and eRedCap is applicable for the current Random Access procedure and there is one set of Random Access resources available that is only configured with eRedCap indication. THEN: the UE selects the set of Random Access resources configured with eRedCap indication for this Random Access procedure. TP2:[TS 38.321 clause 5.1.1b ] WITH: UE supporting eRedCap and in NR RRC_CONNECTED state. WHEN: UE performs handover to the target cell and starts random Access procedure, and contention-free Random Access Resources have been provided for this Random Access procedure and eRedCap is applicable for the current Random Access procedure and there is no set of Random Access resources available that is only configured with eRedCap indication and there is one set of Random Access resources available that is only configured with RedCap indication. THEN: the UE selects the set of Random Access resources configured with RedCap indication for this Random Access procedure. |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
402 | Y | 38.523-1 | 7.1.1.1.X | Random access procedure / eRedCap / Correct handling of contention Resolution with large bandwidth | TP1:[TS 38.321 clause 5.1.5 ] WITH: UE supporting eRedCap and in NR RRC_IDLE state and UE has send Msg3 including CCCH SDU. WHEN: UE detects that PDSCH transmission scheduled by PDCCH has a larger bandwidth than UE can receive or process per slot, and the PDCCH is addressed by TEMPORARY_C-RNTI. THEN: the UE stops ra-ContentionResolutionTimer and considers this Contention Resolution not successful. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
403 | Y | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
RRC
404 |  | 38.523-1 | [7 empty] | 0
405 | Y | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
NAS
406 | Y | 38.523-1 | 11.7.X | Enhanced eDRX / Inactive / CN-initiated paging / RAN-initiated paging | TP1:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In an overlapped PH, during the overlapped part of CN configured PTW and RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP2:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In an overlapped PH, during CN configured PTW and outside RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP3:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: In a non-overlapped PH, during CN configured PTW and outside RAN configured PTW , the network sends a CN-initiated Paging message within a paging occasion. THEN: UE goes to RRC_IDLE state and establishes an RRC connection. TP4:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN). WHEN: In an overlapped PH, outside CN configured PTW and during RAN configured PTW , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP5:[TS 38.304 clause 7.1] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN). WHEN: In a non-overlapped PH, outside CN configured PTW and during RAN configured PTW , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP6:[TS 38.331 clause 6.2.2] WITH: UE in NR RRC_INACTIVE state and configured eDRX (TeDRX, RAN > 10.24s and TeDRX, CN > TeDRX, RAN) . WHEN: the network changes SIB1 to exclude eDRX-AllowedInactive-r18. THEN: UE applies the new system information and stops using extended DRX for RAN-initiated paging in RRC_INACTIVE state. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
407 |  | 38.523-1 | 11.7.X | Enhanced eDRX / Inactive / RAN-initiated paging / Correct using ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17 | TP1:[TS 38.304 clause 7.4; TS 38.331 clause 6.2.2 ] WITH: UE in NR RRC_INACTIVE state and configured different eDRX in ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17. WHEN: UE camps on the NR Cell with eDRX-AllowedInactive-r18 signalling in SIB1 , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. TP2:[TS 38.304 clause 7.4; TS 38.331 clause 6.2.2 ] WITH: UE in NR RRC_INACTIVE state and configured different eDRX in ran-ExtendedPagingCycleConfig-r18 and ran-ExtendedPagingCycle-r17. WHEN: UE moves to a NR Cell with only eDRX-AllowedInactive-r17 signalling in SIB1 , the network sends a RAN-initiated Paging message within a paging occasion. THEN: UE resumes RRC connection. | Huawei,Hisilicon | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
408 | Y | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
409 | Y | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
410 | Y | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
Legacy testcases adjustment
|  | 38.523-1 | [7 empty] | 0
411 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
412 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
413 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
414 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
415 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
416 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
417 |  | 38.523-1 | [7 empty] | 0.5 | 0% | 0% |  | 0% | 0%
418 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
419 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
420 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
421 |  | 38.523-1 | [7 empty] | 0.5 | 0% | 0% |  | 0% | 0%
422 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
423 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
424 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
425 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
426 |  | 38.523-1 | [7 empty] | 0.5 | 0% | 0% |  | 0% | 0%
427 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
428 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
429 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
430 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
431 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
432 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
433 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
434 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
435 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
436 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
437 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
438 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
439 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
440 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
441 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
442 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
443 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
444 |  | 38.523-1 | [7 empty] | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
445 |  | 38.523-2 | <Clause> | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
446 |  | 38.523-2 | <Clause> | <Title of task> | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
448 |  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0% | 0%
TS 34.229-2: ICS for IMS test cases
447 |  | 34.229-2 | <Clause> | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
449 |  | 34.229-2 | <Clause> | <Title of task> | <Describe task> |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.