## Cover sheet
3GPP TSG RAN Meeting #104 | [10 empty] | RP-241191
Shanghai, China, June 17-20, 2024
Agenda Item: | 13.2.4
Source: | Apple
Title: | WP - UE Conformance Aspects - NR RRM enhancements
Work item code: | NR_RRM_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this RAN5 WI is to enable UE conformance testing for the Release 16 RRM enhancements related requirements. RAN5 conformance test procedures will be created to verify test requirements as per the scope being covered in RAN4.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 70% (+5%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR)
FR1
FR2
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance Aspects - NR RRM enhancements | [13 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RRM_enh-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for new Release 16 RRM Enhancements | [15 empty] | vs Area
WP Resp: |  | Xinrong Wang |  |  | xinrong_wang@apple.com | [6 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | WP - UE Conformance Aspects - NR RRM enhancements | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | TT | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
Overall
[15 empty] | Number of WP items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Sum weight of WP items |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
|  | 36.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | 1
TS 36.521-1: RF test cases - Tx
|  | 36.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.521-1 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.521-1 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.521-1 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.521-1: RF test cases - Rx
|  | 36.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.521-1 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.521-1 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.521-1 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.521-1: Demod/CSI reporting test cases
|  | 36.521-1 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.521-1 Demod | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.521-1 Demod | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.521-1 Demod | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 36.521-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 36.521-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 36.521-1 and 38.521-3. |  | TBD |  |  |  | 0.1
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.521-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.521-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TR 36.904: Test Tolerances analysis receiver test cases
|  | 36.904 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.904 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.904 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TR 36.905: Test Point analysis receiver and transmitter test cases
|  | 36.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
Idle Mode
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
Layer 2
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
RRC
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
NAS
TBD |  | 36.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD |  | 36.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD | Y | 36.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 36.523-1 |  | TBD |  |  |  | 0.1
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  |  | TBD
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-1 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-1 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-1 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-1 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-1 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-1 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-2 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-2 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-2 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-2 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-2 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-2 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-2 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-3 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-3 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-3 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-3 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-3 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-3 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  |  | 0.1
TS 38.533: RRM test cases
EN_DC with all NR cells in FR1
|  | 38.533 | 4.3.2.2 | Random Access | [6 empty] | 0.1
1 | Y | 38.533 | 4.3.2.2.3 | 2-step RA type contention based random access test in FR1 for PSCell in EN-DC | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.3.2.2.3 (new in 38.133 Rel-16) | 1
2 | Y | 38.533 | 4.3.2.2.4 | 2-step RA type non-contention based random access test in FR1 for PSCell in EN-DC | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.3.2.2.4 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.5.2 | Interruption | [6 empty] | 0.1
3 | Y | 38.533 | 4.5.2.8 | E-UTRAN - NR FR1 interruptions at NR SRS carrier based switching in asynchronous EN-DC | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227188, R5-227189 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.2.8 (verified) | 1
4 | Y | 38.533 | 4.5.2.9 | E-UTRAN – NR interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227190 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.2.9 (verified) | 1
|  | 38.533 | 4.5.3 | SCell activation and deactivation delay | [6 empty] | 0.1
5 | Y | 38.533 | 4.5.3.4 | SCell Activation and deactivation of multiple unknown SCells in FR1 with single activation/deactivation command | Rel16 test requirements for Multiple Scell activation | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.3.4 (verified) | 1
6 | Y | 38.533 | 4.5.3.5 | Direct SCell activation at SCell addition of known SCell in FR1 | Rel16 test requirements for Direct Scell activation |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.5.3.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 4.5.5 | Beam Failure Detection and Link recovery procedures | [6 empty] | 0.1
7 | Y | 38.533 | 4.5.5.5 | EN-DC Beam Failure Detection and Link Recovery Test for FR1 SCell configured with CSI-RS-based BFD and SSB-based LR in non-DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.5.5.5 (New in 38.133 Rel-16) | 1
8 | Y | 38.533 | 4.5.5.6 | EN-DC Beam Failure Detection and Link Recovery Test for FR1 SCell configured with CSI-RS-based BFD and SSB-based LR in DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.5.5.6 (New in 38.133 Rel-16) | 1
|  | 38.533 | 4.5.6 | Active BWP switch | [6 empty] | 0.1
|  | 38.533 | 4.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
9 | Y | 38.533 | 4.5.6.3.1 | Simultaneous E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in EN-DC on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon | RAN5#98 (Feb-23) | R5-227188, R5-227189 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.6.3.1 (verified) | 1
|  | 38.533 | 4.5.6.4 | SCell dormancy switch | [6 empty] | 0.1
10 | Y | 38.533 | 4.5.6.4.1 | E-UTRAN – NR FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Rel16 test requirements for SCell dormancy switch | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.6.4.1 (new in 38.133 Rel-16) | 1
11 | Y | 38.533 | 4.5.6.4.2 | E-UTRAN – NR FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Rel16 test requirements for SCell dormancy switch | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.6.4.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
12 | Y | 38.533 | 4.5.6.5.1 | E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in synchronous EN-DC on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon | RAN5#98 (Feb-23) | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.4.5.6.5.1 (verified) | 1
|  | 38.533 | 4.5.8 | UL switching | [6 empty] | 0.1
13 | Y | 38.533 | 4.5.8.1 | EN-DC FR1 interruptions at switching between two uplink carriers | Rel16 test requirements for UL switching |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.5.8.1 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.5.9 | UE specific CBW change | [6 empty] | 0.1
14 | Y | 38.533 | 4.5.9.1 | UE specific CBW change on FR1 NR PSCell with non-DRX in synchronous EN-DC | Rel16 test requirements for UE specific CBW change | Apple | RAN5#101 (Nov-23) | R5-237183 R5-237184 | R5-241337 done | Aligned with TS 38.133 Clause A.4.5.9.1 (verified) | 1
|  | 38.533 | 4.6.1 | Intra-frequency Measurements | [6 empty] | 0.1
15 | Y | 38.533 | 4.6.1.7 | EN-DC event triggered reporting tests under DRX for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for Intra-frequency Measurements |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.1.7 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.6.4 | L1-RSRP measurement for beam reporting | [6 empty] | 0.1
16 | Y | 38.533 | 4.6.4.5 | SSB based L1-RSRP measurement when DRX is used for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for L1-RSRP measurement for beam reporting |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.4.6.4.5 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.6.5 | CLI measurements | [6 empty] | 0.1
17 | Y | 38.533 | 4.6.5.1 | SRS-RSRP measurement with non-DRX | Rel16 test requirements for CLI measurements |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.5.1 (new in 38.133 Rel-16) | 1
18 | Y | 38.533 | 4.6.5.2 | CLI-RSSI measurement with non-DRX | Rel16 test requirements for CLI measurements |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.5.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.6.6 | Measurements with Autonomous Gaps | [6 empty] | 0.1
19 | Y | 38.533 | 4.6.6.1 | EN-DC intra-frequency CGI identification of NR FR1 cell with autonomous gaps in synchronous EN-DC | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237185 R5-237715 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.6.6.1 (verified) | 1
|  | 38.533 | 4.6.7 | L1-SINR measurement for beam reportin | [6 empty] | 0.1
20 | Y | 38.533 | 4.6.7.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reportin |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.7.1 (new in 38.133 Rel-16) | 1
21 | Y | 38.533 | 4.6.7.2 | L1-SINR measurement with SSB based CMR and dedicated IMR when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reportin |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.7.2 (new in 38.133 Rel-16) | 1
22 | Y | 38.533 | 4.6.7.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR configured when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.6.7.3 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.6.8 | CSI-RS based intra-frequency Measurement | [6 empty] | 0.1
23 | Y | 38.533 | 4.6.8.1 | EN-DC event triggered reporting tests without gap under DRX | Rel16 test requirements for CSI-RS based intra-frequency Measurement | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.6.8.1 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.6.9 | CSI-RS based inter-frequency Measurement | [6 empty] | 0.1
24 | Y | 38.533 | 4.6.9.1 | EN-DC event triggered reporting tests for FR1 cell when non-DRX is used | Rel16 test requirements for CSI-RS based inter-frequency Measurement | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.6.9.1 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.6 | CLI measurements | [6 empty] | 0.1
25 | Y | 38.533 | 4.7.6.1 | EN-DC SRS-RSRP measurement accuracy with FR1 serving cell | Rel16 test requirements for CLI measurements |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.7.6.1 (new in 38.133 Rel-16) | 1
26 | Y | 38.533 | 4.7.6.2 | EN-DC CLI-RSSI measurement accuracy with FR1 serving cell | Rel16 test requirements for CLI measurements |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.6.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.7 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
|  | 38.533 | 4.7.7.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement | [6 empty] | 0.1
27 | Y | 38.533 | 4.7.7.1.1 | EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR absolute measurement accuracy | Rel16 test requirements for EN-DC FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Rel-16 Clause A.4.7.7.1 (new in 38.133 Rel-16) | 1
28 | Y | 38.533 | 4.7.7.2 | L1-SINR measurement with SSB based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.4.7.7.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.7.3 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement | [6 empty] | 0.1
29 | Y | 38.533 | 4.7.7.3.1 | EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR absolute measurement accuracy | Rel16 test requirements for EN-DC FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Rel-16 Clause A.4.7.7.3 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.8 | CSI-RSRP | [6 empty] | 0.1
30 | Y | 38.533 | 4.7.8.1 | EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRP | Sporton | RAN5#103 (May-24) | R5-241830 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.8.1 (new in 38.133 Rel-16) | 1
31 | Y | 38.533 | 4.7.8.2 | EN-DC inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRP | Sporton | RAN5#103 (May-24) | R5-241198 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.8.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.9 | CSI-RSRQ | [6 empty] | 0.1
32 | Y | 38.533 | 4.7.9.1 | EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241311 R5-241312 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.9.1 (new in 38.133 Rel-16) | 1
33 | Y | 38.533 | 4.7.9.2 | EN-DC Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241313 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.9.2 (new in 38.133 Rel-16) | 1
|  | 38.533 | 4.7.10 | CSI-SINR | [6 empty] | 0.1
34 | Y | 38.533 | 4.7.10.1 | EN-DC Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241314 R5-241315 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.10.1 (new in 38.133 Rel-16) | 1
35 | Y | 38.533 | 4.7.10.2 | EN-DC Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241316 | need to do TT analysis | Aligned with TS 38.133 Clause A.4.7.10.2 (new in 38.133 Rel-16) | 1
EN_DC with one or more NR cells in FR2
|  | 38.533 | 5.3.2.2 | Random Access | [6 empty] | 0.1
36 | Y | 38.533 | 5.3.2.2.3 | 2-step RA type contention based random access test in FR2 for PSCell/SCell in EN-DC | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.5.3.2.2.3 (new in 38.133 Rel-16) | 1
37 | Y | 38.533 | 5.3.2.2.4 | 2-step RA type non-contention based random access test in FR2 for PSCell/SCell in EN-DC | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.5.3.2.2.4 (new in 38.133 Rel-16) | 1
|  | 38.533 | 5.5.2 | Interruption | [6 empty] | 0.1
38 | Y | 38.533 | 5.5.2.7 | E-UTRAN – NR FR2 interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227192 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.2.7 (verified) | 1
39 | Y | 38.533 | 5.5.2.8 | E-UTRAN – NR FR2 interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227193 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.2.8 (verified) | 1
|  | 38.533 | 5.5.3 | SCell Activation and Deactivation Delay | [6 empty] | 0.1
40 | Y | 38.533 | 5.5.3.2 | SCell Activation and deactivation of known SCell in FR1 for 160ms SCell measurement cycle | Rel15 test requirements for SCell Activation and Deactivation Delay | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.3.2 (In 38.133 Rel-15 already, not new in 38.133 Rel-16) | 1
41 | Y | 38.533 | 5.5.3.5 | SCell Activation and deactivation of SCell in FR2 | Rel15 test requirements for SCell Activation and Deactivation Delay | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.3.5 (In 38.133 Rel-15 already, New in 38.133 Rel-16) | 1
42 | Y | 38.533 | 5.5.3.6 | Multiple SCell Activation and deactivation of one unknown SCell and one known SCell in FR2 | Rel16 test requirements for Multiple Scell activation and deactivation | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.3.6 (New in 38.133 Rel-16) | 1
43 | Y | 38.533 | 5.5.3.7 | Direct SCell activation at SCell addition of known SCell in FR2 | Rel16 test requirements for Direct Scell activation |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.5.3.7 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.5.5 | Beam Failure Detection and Link recovery procedures | [6 empty] | 0.1
44 | Y | 38.533 | 5.5.5.6 | EN-DC Beam Failure Detection and Link Recovery Test for FR2 SCell configured with CSI-RS-based BFD and LR in non-DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.5.5.6 (New in 38.133 Rel-16) | 1
45 | Y | 38.533 | 5.5.5.7 | EN-DC Beam Failure Detection and Link Recovery Test for FR2 SCell configured with CSI-RS-based BFD and LR in DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.5.5.7 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.5.6 | Active BWP switch | [6 empty] | 0.1
|  | 38.533 | 5.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
46 | Y | 38.533 | 5.5.6.3.1 | E-UTRAN – NR PSCell FR2 and NR SCell FR2 DL active BWP switch on multiple CCs in synchronous EN-DC | Rel16 test requirements forActive BwP Switch | Apple | RAN5#101 (Nov-23) | R5-237187 R5-237716 | R5-241894 done | Aligned with TS 38.133 Clause A.5.5.6.3.1 (verified) | 1
|  | 38.533 | 5.5.6.4 | Scell dormancy switch | [6 empty] | 0.1
47 | Y | 38.533 | 5.5.6.4.1 | E-UTRAN – NR FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Rel16 test requirements for Scell Dormancy Switch | Apple | RAN5#101 (Nov-23) | R5-237189 R5-237717 | R5-241895 done | Aligned with TS 38.133 Clause A.5.5.6.4.1 (verified) | 1
48 | Y | 38.533 | 5.5.6.4.2 | E-UTRAN – NR FR1 PSCell SCell dormancy switch of two FR2 SCells outside active time | Rel16 test requirements for Scell Dormancy Switch | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.6.4.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CC | [6 empty] | 0.1
49 | Y | 38.533 | 5.5.6.5.1 | E-UTRAN – NR PSCell FR2 and NR SCell FR2 DL active BWP switch on multiple CCs with non-DRX in synchronous EN-DC | Rel16 test requirements for active BWP Switch | Apple | RAN5#103 (May-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.6.5.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.5.7 | PSCell addition and release delay | [6 empty] | 0.1
50 | Y | 38.533 | 5.5.7.1 | Addition and Release Delay of NR PSCell | Rel15 test requirements for PSCell addition and release delay |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.7.1 (In 38.133 Rel-15 already, also in R16, but it is void in 38.533) | 1
|  | 38.533 | 5.5.9 | Uplink Spatial Relation Switch | [6 empty] | 0.1
|  | 38.533 | 5.5.9.1 | MAC-CE based Uplink Spatial Relation Switch | [6 empty] | 0.1
51 | Y | 38.533 | 5.5.9.1.1 | E-UTRAN – NR PSCell FR2 uplink spatial relation switch for a known spatial relation | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#99 (May-23) | finished in RAN5#100. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.5.9.1.1 (verified) | 1
|  | 38.533 | 5.5.9.2 | RRC based Uplink Spatial Relation Switch | [6 empty] | 0.1
52 | Y | 38.533 | 5.5.9.2.1 | E-UTRAN – NR PSCell FR2 spatial relation switch associated with a known DL-RS | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#99 (May-23) | finished in RAN5#100. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.5.9.2.1 (verified) | 1
|  | 38.533 | 5.5.10 | UE specific CBW change | [6 empty] | 0.1
53 | Y | 38.533 | 5.5.10.1 | UE specific CBW change on FR2 NR PSCell | Rel16 test requirements for UE specific CBW change | Apple | RAN5#101 (Nov-23) | R5-237191 R5-237192 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.5.10.1 (verified) | 1
|  | 38.533 | 5.6.4 | CLI measurements | [6 empty] | 0.1
54 | Y | 38.533 | 5.6.4.1 | SRS-RSRP measurement with DRX | Rel16 test requirements for CLI measurements |  |  | finished in RAN5#100? Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.6.4.1 (New in 38.133 Rel-16) | 1
55 | Y | 38.533 | 5.6.4.2 | CLI-RSSI measurement with DRX | Rel16 test requirements for CLI measurements |  |  | finished in RAN5#100? Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.5.6.4.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.6.5 | Measurements with Autonomous Gaps | [6 empty] | 0.1
56 | Y | 38.533 | 5.6.5.1 | EN-DC inter-frequency CGI identification of NR neighbor cell in FR2 | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237193 R5-237718 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.6.5.1 (verified) | 1
|  | 38.533 | 5.6.6 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
57 | Y | 38.533 | 5.6.6.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.6.6.1 (New in 38.133 Rel-16) | 1
58 | Y | 38.533 | 5.6.6.2 | L1-SINR measurement with SSB based CMR and dedicated IMR when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.6.6.2 (New in 38.133 Rel-16) | 1
59 | Y | 38.533 | 5.6.6.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR configured when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.6.6.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.6.7 | CSI-RS based Intra-frequency Measurements | [6 empty] | 0.1
60 | Y | 38.533 | 5.6.7.1 | EN-DC event triggered reporting test without gap under non-DRX | Rel16 test requirements for CSI-RS based Intra-frequency Measurements | Sporton | RAN5#103 (May-24) | R5-243707 | done | Aligned with TS 38.133 Clause A.5.6.7.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.6.8 | CSI-RS based Inter-frequency Measurements | [6 empty] | 0.1
61 | Y | 38.533 | 5.6.8.1 | EN-DC event triggered reporting tests for NR FR2 cell when DRX is used | Rel16 test requirements for CSI-RS based Inter-frequency Measurements | Sporton | RAN5#103 (May-24) | R5-243708 | done | Aligned with TS 38.133 Clause A.5.6.8.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.7.5 | CLI measurements | [6 empty] | 0.1
62 | Y | 38.533 | 5.7.5.1 | EN-DC SRS-RSRP measurement accuracy with FR2 serving cell | Rel16 test requirements for CLI measurements |  |  | finished in RAN5#100? Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.7.5.1 (New in 38.133 Rel-16) | 1
63 | Y | 38.533 | 5.7.5.2 | EN-DC CLI-RSSI measurement accuracy with FR2 serving cell | Rel16 test requirements for CLI measurements |  |  | finished in RAN5#100? Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.5.7.5.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.7.6 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
64 | Y | 38.533 | 5.7.6.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in RAN5#100? Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.7.6.1 (New in 38.133 Rel-16) | 1
65 | Y | 38.533 | 5.7.6.2 | L1-SINR measurement with SSB based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in RAN5#100? Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.7.6.2 (New in 38.133 Rel-16) | 1
66 | Y | 38.533 | 5.7.6.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in RAN5#100? Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.5.7.6.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.7.7 | CSI-RSRP | [6 empty] | 0.1
67 | Y | 38.533 | 5.7.7.1 | EN-DC intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRP | Sporton | RAN5#103 (May-24) | R5-243709 | done | Aligned with TS 38.133 Clause A.5.7.7.1 (New in 38.133 Rel-16) | 1
68 | Y | 38.533 | 5.7.7.2 | EN-DC inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRP | Sporton | RAN5#103 (May-24) | R5-243710 | done | Aligned with TS 38.133 Clause A.5.7.7.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.7.8 | CSI-RSRQ | [6 empty] | 0.1
69 | Y | 38.533 | 5.7.8.1 | EN-DC intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241317 R5-241318 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.7.8.1 (New in 38.133 Rel-16) | 1
70 | Y | 38.533 | 5.7.8.2 | EN-DC inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241319 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.7.8.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 5.7.9 | CSI-SINR | [6 empty] | 0.1
71 | Y | 38.533 | 5.7.9.1 | EN-DC intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241320 R5-241321 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.7.9.1 (New in 38.133 Rel-16) | 1
72 | Y | 38.533 | 5.7.9.2 | EN-DC inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241322 | need to do TT analysis | Aligned with TS 38.133 Clause A.5.7.9.2 (New in 38.133 Rel-16) | 1
NR Standalone in FR1
|  | 38.533 | 6.1.1 | Cell re-selection to NR | [6 empty] | 0.1
73 | Y | 38.533 | 6.1.1.3 | Cell reselection to FR1 intra-frequency NR case for UE fulfilling low mobility relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.1.3 (New in 38.133 Rel-16) | 1
74 | Y | 38.533 | 6.1.1.4 | Cell reselection to FR1 intra-frequency NR case for UE fulfilling not-at-cell edge relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.1.4 (New in 38.133 Rel-16) | 1
75 | Y | 38.533 | 6.1.1.5 | Cell reselection to FR1 inter-frequency NR case for UE fulfilling low mobility relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.1.5 (New in 38.133 Rel-16) | 1
76 | Y | 38.533 | 6.1.1.6 | Cell reselection to FR1 inter-frequency NR case for UE fulfilling not-at-cell edge relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.1.6 (New in 38.133 Rel-16) | 1
77 | Y | 38.533 | 6.1.1.7 | Cell reselection to FR1 intra-frequency NR case for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.1.7 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.1.2 | Inter-RAT E-UTRAN cell re-selection | [6 empty] | 0.1
78 | Y | 38.533 | 6.1.2.3 | Cell reselection to lower priority E-UTRAN for UE fulfilling low mobility relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.2.3 (New in 38.133 Rel-16) | 1
79 | Y | 38.533 | 6.1.2.4 | Cell reselection to lower priority E-UTRAN for UE fulfilling not-at-cell edge relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.2.4 (New in 38.133 Rel-16) | 1
80 | Y | 38.533 | 6.1.2.5 | Cell reselection to lower priority E-UTRAN cell for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.1.2.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.3.1 | Handover | [6 empty] | 0.1
81 | Y | 38.533 | 6.3.1.6 | SA NR - UTRAN FDD handover | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.6 (New in 38.133 Rel-16) | 1
82 | Y | 38.533 | 6.3.1.7 | Intra-frequency synchronous DAPS handover in FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.7 (New in 38.133 Rel-16) | 1
83 | Y | 38.533 | 6.3.1.8 | Intra-frequency asynchronous DAPS handover in FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.8 (New in 38.133 Rel-16) | 1
84 | Y | 38.533 | 6.3.1.9 | Intra-band inter-frequency synchronous DAPS handover test in SA for FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.9 (New in 38.133 Rel-16) | 1
85 | Y | 38.533 | 6.3.1.10 | Intra-band inter-frequency asynchronous DAPS handover test in SA for FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.10 (New in 38.133 Rel-16) | 1
86 | Y | 38.533 | 6.3.1.11 | Inter-band inter-frequency synchronous DAPS handover from FR1 to FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.11 (New in 38.133 Rel-16) | 1
87 | Y | 38.533 | 6.3.1.12 | Inter-band inter-frequency asynchronous DAPS handover from FR1 to FR1 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.1.12 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.3.3 | Conditional handover | [6 empty] | 0.1
88 | Y | 38.533 | 6.3.3.1 | Intra-frequency conditional handover from FR1 to FR1 | Rel16 test requirements for Conditional handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.3.1 (New in 38.133 Rel-16) | 1
89 | Y | 38.533 | 6.3.3.2 | Inter-frequency conditional handover from FR1 to FR1 | Rel16 test requirements for Conditional handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.3.3.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.5.2 | Interruption | [6 empty] | 0.1
90 | Y | 38.533 | 6.5.2.2 | SA interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227830, R5-227194 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.2.2 (verified) | 1
|  | 38.533 | 6.5.3 | SCell Activation and Deactivation Delay | [6 empty] | 0.1
91 | Y | 38.533 | 6.5.3.4 | Direct SCell activation at SCell addition of known SCell in FR1 | Rel16 test requirements for Direct Scell activation |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.6.5.3.4 (New in 38.133 Rel-16) | 1
92 | Y | 38.533 | 6.5.3.5 | Direct SCell activation at handover with known SCell in FR1 | Rel16 test requirements for Direct Scell activation |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.6.5.3.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.5.5 | Beam Failure Detection and Link recovery procedures | [6 empty] | 0.1
93 | Y | 38.533 | 6.5.5.5 | Beam Failure Detection and Link Recovery Test for FR1 SCell configured with CSI-RS-based BFD and SSB-based LR in non-DRX mod | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.5.5.5 (New in 38.133 Rel-16) | 1
94 | Y | 38.533 | 6.5.5.6 | Beam Failure Detection and Link Recovery Test for FR1 SCell configured with CSI-RS-based BFD and SSB-based LR in DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.5.5.6 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.5.6 | Active BWP switch | [6 empty] | 0.1
|  | 38.533 | 6.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
95 | Y | 38.533 | 6.5.6.3.1 | NR FR1- NR FR1 DL active BWP switch on multiple CCs with non-DRX in SA | Rel16 test requirements for UE Active BW Switch | Huawei, HiSilicon | RAN5#99 (May-23) | finished in 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.6.3.1 (verified) | 1
|  | 38.533 | 6.5.6.4 | SCell dormancy switch | [6 empty] | 0.1
96 | Y | 38.533 | 6.5.6.4.1 | NR FR1 PCell SCell dormancy switch of single FR1 SCell outside active time | Rel16 test requirements for dormancy switch |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.6.4.1 (New in 38.133 Rel-16) | 1
97 | Y | 38.533 | 6.5.6.4.2 | NR FR1 PCell SCell dormancy switch of two FR1 SCells inside active time | Rel16 test requirements for dormancy switch |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.6.4.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
98 | Y | 38.533 | 6.5.6.5.1 | NR FR1- NR FR1 DL active BWP switch on multiple CCs with non-DRX in SA | Rel16 test requirements for active BWP switch |  |  | finished in 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.6.5.1 (verified) | 1
|  | 38.533 | 6.5.7 | DL interruptions at switching between two uplink carriers | [6 empty] | 0.1
99 | Y | 38.533 | 6.5.7.1 | DL interruptions at switching between two uplink carriers in FDD-TDD CA | Rel16 test requirements for DL interruptions at switching between two uplink carriers |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.6.5.7.1 (New in 38.133 Rel-16) | 1
100 | Y | 38.533 | 6.5.7.2 | DL interruptions at switching between two uplink carriers in TDD-TDD CA | Rel16 test requirements for DL interruptions at switching between two uplink carriers |  |  | finished. Need to check the Tdoc | done | Aligned with TS 38.133 Clause A.6.5.7.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.5.8 | UE specific CBW change | [6 empty] | 0.1
101 | Y | 38.533 | 6.5.8.1 | UE specific CBW change on PCell in FR1 in non-DRX | Rel16 test requirements for UE specific CBW change |  | RAN5#99 (May-23) | R5-232489 R5-236748 R5-241895 | done | Aligned with TS 38.133 Clause A.6.5.8.1 (verified) | 1
|  | 38.533 | 6.5.9 | Pathloss reference signal switching delay | [6 empty] | 0.1
102 | Y | 38.533 | 6.5.9.1 | MAC-CE based pathloss reference signal switch delay | Rel16 test requirements for Pathloss reference signal switching delay |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.5.9.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.1 | Intra-frequency Measurements | [6 empty] | 0.1
103 | Y | 38.533 | 6.6.1.7 | SA event triggered reporting tests under DRX for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for Intra-frequency Measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.1.7 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.2 | Inter-frequency Measurement | [6 empty] | 0.1
104 | Y | 38.533 | 6.6.2.9 | SA event triggered reporting tests with additional mandatory gap pattern | Rel16 test requirements for Mandatory Gap Patterns | Ericsson | RAN5#99 (May-23) | R5-227197 R5-227196 R5-241829 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.2.9 (verified) | 1
105 | Y | 38.533 | 6.6.2.10 | SA event triggered reporting tests for FR1 when DRX is used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227198 R5-237712 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.2.10 (verified) | 1
106 | Y | 38.533 | 6.6.2.11 | SA event triggered reporting tests for FR1 without gap when DRX is not used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227199 R5-237713 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.2.11 (verified) | 1
|  | 38.533 | 6.6.3 | Inter-RAT Measurements | [6 empty] | 0.1
107 | Y | 38.533 | 6.6.3.3 | SA NR - E-UTRAN event-triggered reporting in DRX in FR1 for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for Inter-RAT Measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.3.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.4 | L1-RSRP measurement for beam reporting | [6 empty] | 0.1
108 | Y | 38.533 | 6.6.4.5 | SSB based L1-RSRP measurement when DRX is used for UE configured with highSpeedMeasFlag-r16 | Rel16 test requirements for L1-RSRP measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.4.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.5 | SA NR - UTRAN FDD event-triggered reporting in non-DRX in FR1 | [6 empty] | 0.1
109 | Y | 38.533 | 6.6.5.1 | SA NR - UTRAN FDD event-triggered reporting in non-DRX in FR1 | Rel16 test requirements for SA NR - UTRAN FDD event-triggered reporting in non-DRX in FR1 |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.5.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.6 | CLI measurements | [6 empty] | 0.1
110 | Y | 38.533 | 6.6.6.1 | SRS-RSRP measurement with DRX | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.6.1 (New in 38.133 Rel-16) | 1
111 | Y | 38.533 | 6.6.6.2 | CLI-RSSI measurement with DRX | Rel16 test requirements for CLI measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.6.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.7 | NR Measurements with autonomous gaps | [6 empty] | 0
112 | Y | 38.533 | 6.6.7.1 | SA intra-frequency CGI identification of NR neighbor cell in FR1 | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237195 R5-237760 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.7.1 (verified) | 1
113 | Y | 38.533 | 6.6.7.2 | Identification of a new CGI of inter-RAT E-UTRA cell using autonomous gaps in NR SA | Rel16 test requirements for CGI Reading | Apple | RAN5#101 (Nov-23) | R5-237761 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.7.2 (verified) | 1
|  | 38.533 | 6.6.8 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
114 | Y | 38.533 | 6.6.8.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.8.1 (New in 38.133 Rel-16) | 1
115 | Y | 38.533 | 6.6.8.2 | L1-SINR measurement with SSB based CMR and dedicated IMR when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.8.2 (New in 38.133 Rel-16) | 1
116 | Y | 38.533 | 6.6.8.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR configured when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.8.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.9 | Idle Mode CA/DC Measurements | [6 empty] | 0.1
117 | Y | 38.533 | 6.6.9.1 | SA Idle mode CA/DC measurement for FR1 | Rel16 test requirements for Idle Mode CA/DC Measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.9.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.10 | CSI-RS based intra-frequency Measurements | [6 empty] | 0.1
118 | Y | 38.533 | 6.6.10.1 | SA event triggered reporting tests without gap under non-DRX | Rel16 test requirements for SA Idle mode CA/DC measurement for FR1 |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.10.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.11 | CSI-RS based inter-frequency Measurements | [6 empty] | 0.1
119 | Y | 38.533 | 6.6.11.1 | SA event triggered reporting tests with gap under DRX | Rel16 test requirements for CSI-RS based inter-frequency Measurements |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.11.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.12 | RSTD measurements | [6 empty] | 0.1
120 | Y | 38.533 | 6.6.12.1 | NR RSTD measurement reporting delay test case for single positioning frequency layer in FR1 SA | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.12.1 (New in 38.133 Rel-16) | 1
121 | Y | 38.533 | 6.6.12.2 | NR RSTD measurement reporting delay test case for dual positioning frequency layers in FR1 S | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.12.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.13 | PRS-RSRP measurements | [6 empty] | 0.1
122 | Y | 38.533 | 6.6.13.1 | PRS-RSRP reporting delay test case for single positioning frequency layer | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.13.1 (New in 38.133 Rel-16) | 1
123 | Y | 38.533 | 6.6.13.2 | PRS-RSRP reporting delay test case for dual positioning frequency layer | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.13.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.14 | UE Rx-Tx time difference measurements | [6 empty] | 0.1
124 | Y | 38.533 | 6.6.14.1 | UE Rx-Tx time difference measurement for single positioning frequency layer in FR1 SA | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.14.1 (New in 38.133 Rel-16) | 1
125 | Y | 38.533 | 6.6.14.2 | UE Rx-Tx time difference measurement for dual positioning frequency layers in FR1 SA | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.6.14.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.6.15 | Idle Mode inter-RAT CA/DC Measurements | [6 empty] | 0.1
126 | Y | 38.533 | 6.6.15.1 | Idle Mode measurements of inter-RAT DC candidate cells for early reporting | Rel16 test requirements for Idle Mode inter-RAT CA/DC Measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.6.15.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.8 | CLI measurements | [6 empty] | 0.1
127 | Y | 38.533 | 6.7.8.1 | SA SRS-RSRP measurement accuracy with FR1 serving cell | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.7.8.1 (New in 38.133 Rel-16) | 1
128 | Y | 38.533 | 6.7.8.2 | SA CLI-RSSI measurement accuracy with FR1 serving cell | Rel16 test requirements for CLI measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.8.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.9 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
|  | 38.533 | 6.7.9.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement | [6 empty] | 0.1
129 | Y | 38.533 | 6.7.9.1.1 | NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR absolute measurement accuracy | Rel16 test requirements for NR SA FR1 CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off L1-SINR measurement |  |  | finished in 38.533 | done | Aligned with TS 38.133 Rel-16 Clause A.6.7.9.1 (New in 38.133 Rel-16) | 1
130 | Y | 38.533 | 6.7.9.2 | L1-SINR measurement with SSB based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.6.7.9.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.9.3 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy | [6 empty] | 0.1
131 | Y | 38.533 | 6.7.9.3.1 | NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR absolute measurement accuracy | Rel16 test requirements for NR SA FR1 CSI-RS based CMR and dedicated IMR L1-SINR measurement accuracy |  |  | finished in 38.533 | done | Aligned with TS 38.133 Rel-16 Clause A.6.7.9.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.10 | CSI-RSRP | [6 empty] | 0.1
132 | Y | 38.533 | 6.7.10.1 | SA: intra-frequency case measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRP |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.10.1 (New in 38.133 Rel-16) | 1
133 | Y | 38.533 | 6.7.10.2 | SA inter-frequency case measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRP |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.10.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.11 | CSI-RSRQ | [6 empty] | 0.1
134 | Y | 38.533 | 6.7.11.1 | SA: Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241323 R5-241324 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.11.1 (New in 38.133 Rel-16) | 1
135 | Y | 38.533 | 6.7.11.2 | SA Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241325 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.11.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.12 | CSI-SINR | [6 empty] | 0.1
136 | Y | 38.533 | 6.7.12.1 | SA intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241326 R5-241327 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.12.1 (New in 38.133 Rel-16) | 1
137 | Y | 38.533 | 6.7.12.2 | SA Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241328 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.12.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.13 | RSTD measurements | [6 empty] | 0.1
138 | Y | 38.533 | 6.7.13.1 | RSTD measurement accuracy test case for single positioning frequency layer | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.13.1 (New in 38.133 Rel-16) | 1
139 | Y | 38.533 | 6.7.13.2 | RSTD measurement accuracy test case for dual positioning frequency layer | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.13.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.14 | PRS-RSRP measurements | [6 empty] | 0.1
140 | Y | 38.533 | 6.7.14.1 | SA: measurement accuracy with PRS in FR1 | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.14.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 6.7.15 | UE Rx-Tx time difference measurements | [6 empty] | 0.1
141 | Y | 38.533 | 6.7.15.1 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR1 SA | Rel16 test requirements for UE Rx-Tx time difference measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.6.7.15.1 (New in 38.133 Rel-16) | 1
NR Standalone in FR2
|  | 38.533 | 7.1.1 | Cell re-selection to NR | [6 empty] | 0.1
142 | Y | 38.533 | 7.1.1.3 | Cell reselection to FR2 intra-frequency NR case for UE fulfilling low mobility relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.1.1.3 (New in 38.133 Rel-16) | 1
143 | Y | 38.533 | 7.1.1.4 | Cell reselection to FR2 intra-frequency NR case for UE fulfilling not-at-cell edge relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.1.1.4 (New in 38.133 Rel-16) | 1
144 | Y | 38.533 | 7.1.1.5 | Cell reselection to FR2 inter-frequency NR case for UE fulfilling low mobility relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.1.1.5 (New in 38.133 Rel-16) | 1
145 | Y | 38.533 | 7.1.1.6 | Cell reselection to FR2 inter-frequency NR case for UE fulfilling not-at-cell edge relaxed measurement criterion | Rel16 test requirements for Cell re-selection to NR |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.1.1.6 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.3.1 | Handover | [6 empty] | 0.1
146 | Y | 38.533 | 7.3.1.4 | Inter-band inter-frequency synchronous DAPS handover from FR1 to FR2 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.3.1.4 (New in 38.133 Rel-16) | 1
147 | Y | 38.533 | 7.3.1.5 | Inter-band inter-frequency asynchronous DAPS handover from FR1 to FR2 | Rel16 test requirements for Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.3.1.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.3.2.2 | Random Access | [6 empty] | 0.1
148 | Y | 38.533 | 7.3.2.2.3 | 2-step RA type contention based random access test in FR2 for NR Standalone | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.7.3.2.2.3 (new in 38.133 Rel-16) | 1
149 | Y | 38.533 | 7.3.2.2.4 | 2-step RA type non-contention based random access test in FR2 for NR Standalone | Rel16 test requirements for Random Access |  |  | finished. Need to check the Tdoc | need to do TT analysis | Aligned with TS 38.133 Clause A.7.3.2.2.4 (new in 38.133 Rel-16) | 1
|  | 38.533 | 7.3.3 | Conditional Handover | [6 empty] | 0.1
150 | Y | 38.533 | 7.3.3.1 | Intra-frequency conditional handover from FR2 to FR2 | Rel16 test requirements for Conditional Handover |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.3.3.1 (New in 38.133 Rel-16) | 1
151 | Y | 38.533 | 7.3.3.2 | Inter-frequency conditional handover from FR2 to FR2; unknown target cell | Rel16 test requirements for Conditional Handover |  |  | finished in 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.3.3.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.5.2 | Interruption | [6 empty] | 0.1
152 | Y | 38.533 | 7.5.2.2 | SA interruptions at NR SRS carrier-based switching | Rel16 test requirements for Interruption | Apple | RAN5#101 (Nov-23) | R5-237198 R5-237762 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.2.2 (verified) | 1
|  | 38.533 | 7.5.3 | SCell Activation and Deactivation Delay | [6 empty] | 0.1
153 | Y | 38.533 | 7.5.3.3 | SCell Activation and deactivation for SCell in FR2 inter-band in non-DRX | Rel16 test requirements for FR2 Inter-Band CA |  | RAN5#100 (Aug-23) | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.3.3 (verified) | 1
154 | Y | 38.533 | 7.5.3.4 | Direct SCell activation at SCell addition of known SCell in FR2 | Rel16 test requirements for Direct Scell activation |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.3.4 (New in 38.133 Rel-16) | 1
155 | Y | 38.533 | 7.5.3.5 | Direct SCell activation at handover with known SCell in FR2 | Rel16 test requirements for Direct Scell activation |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.3.5 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.5.5 | Beam Failure Detection and Link recovery procedures | [6 empty] | 0.1
156 | Y | 38.533 | 7.5.5.6 | Beam Failure Detection and Link Recovery Test for FR2 SCell configured with CSI-RS-based BFD and LR in non-DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.5.6 (New in 38.133 Rel-16) | 1
157 | Y | 38.533 | 7.5.5.7 | Beam Failure Detection and Link Recovery Test for FR2 SCell configured with CSI-RS-based BFD and LR in DRX mode | Rel16 test requirements for Beam Failure Detection and Link recovery procedures |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.5.7 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.5.6 | Active BWP switch | [6 empty] | 0.1
|  | 38.533 | 7.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
158 | Y | 38.533 | 7.5.6.3.1 | Active BWP switch on multiple SCells with non-DRX in SA | Rel16 test requirements for BWP switching on multiple CCs | Apple | RAN5#101 (Nov-23) | R5-237200 R5-237763 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.6.3.1 (verified) | 1
|  | 38.533 | 7.5.6.4 | SCell dormancy switch | [6 empty] | 0.1
159 | Y | 38.533 | 7.5.6.4.1 | NR FR2 PCell SCell dormancy switch of single FR2 SCell inside active time | Rel16 test requirements for dormancy switch |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.6.4.1 (New in 38.133 Rel-16) | 1
160 | Y | 38.533 | 7.5.6.4.2 | NR FR1 PCell SCell dormancy switch of two FR2 SCells outside active time | Rel16 test requirements for dormancy switch |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.6.4.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs | [6 empty] | 0.1
161 | Y | 38.533 | 7.5.6.5.1 | Active BWP switch on multiple SCells with non-DRX in SA | Rel16 test requirements for active BWP switch |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.6.5.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.5.9 | Uplink Spatial Relation Switch Delay | [6 empty] | 0.1
|  | 38.533 | 7.5.9.1 | MAC-CE based Spatial Relation switch | [6 empty] | 0.1
162 | Y | 38.533 | 7.5.9.1.1 | NR PCell FR2 spatial relation associated with known DL-RS | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#100 (Aug-23) | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.9.1.1 (verified) | 1
|  | 38.533 | 7.5.9.2 | RRC based spatial relation switch | [6 empty] | 0.1
163 | Y | 38.533 | 7.5.9.2.1 | NR PCell FR2 spatial relation switch associated with a known DL-RS | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#100 (Aug-23) | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.5.9.2.1 (verified) | 1
|  | 38.533 | 7.5.10 | UE specific CBW change | [6 empty] | 0.1
164 | Y | 38.533 | 7.5.10.1 | NR FR2 UE specific CBW change of PCell with non-DRX in SA | Rel16 test requirements on UE specific CBW | Apple | RAN5#101 (Nov-23) | R5-237202 R5-237203 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.5.10.1 (verified) | 1
|  | 38.533 | 7.6.2 | Inter-frequency Measurements | [6 empty] | 0.1
165 | Y | 38.533 | 7.6.2.9 | SA event triggered reporting tests For FR2 without SSB time index detection when DRX is not used (PCell in FR2) (rel16 additional mandatory gap pattern 17) | Rel16 test requirements for Mandatory Gap Patterns | Apple | RAN5#101 (Nov-23) | R5-237764 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.2.9 (verified) | 1
166 | Y | 38.533 | 7.6.2.10 | SA event triggered reporting test without gap under non-DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 |  | RAN5#102 (Feb-24) | R5-243757 | Done | Aligned with TS 38.133 Clause A.7.6.2.10 (verified) | 1
167 | Y | 38.533 | 7.6.2.11 | SA event triggered reporting test without gap under DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 |  | RAN5#102 (Feb-24) | R5-243758 | Done | Aligned with TS 38.133 Clause A.7.6.2.11 (verified) | 1
|  | 38.533 | 7.6.4 | CLI measurements | [6 empty] | 0.1
168 | Y | 38.533 | 7.6.4.1 | SRS-RSRP measurement with non-DRX | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.6.4.1 (New in 38.133 Rel-16) | 1
169 | Y | 38.533 | 7.6.4.2 | CLI-RSSI measurement with non-DRX | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.4.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.5 | NR Measurements with autonomous gaps | [6 empty] | 0.1
170 | Y | 38.533 | 7.6.5.1 | SA interfrequency CGI reporting in autonomous gaps test (PCell in FR2) | Rel16 test requirements for Mandatory Gap Patterns | Apple | RAN5#101 (Nov-23) | R5-237205 R5-237765 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.5.1 (verified) | 1
|  | 38.533 | 7.6.6 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
171 | Y | 38.533 | 7.6.6.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured when DRX is not used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.6.6.1 (New in 38.133 Rel-16) | 1
172 | Y | 38.533 | 7.6.6.2 | L1-SINR measurement with SSB based CMR and dedicated IMR when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.6.6.2 (New in 38.133 Rel-16) | 1
173 | Y | 38.533 | 7.6.6.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR configured when DRX is used | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.6.6.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.7 | CSI-RS based intra-frequency Measurements | [6 empty] | 0.1
174 | Y | 38.533 | 7.6.7.1 | SA event triggered reporting test without gap under DRX for CSI-RS based intra-frequency measurement | Rel16 test requirements for CSI-RS based intra-frequency Measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.7.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.8 | CSI-RS based inter-frequency Measurements | [6 empty] | 0.1
175 | Y | 38.533 | 7.6.8.1 | SA event triggered reporting tests for FR2 CSI-RS based measurement when non-DRX is used (PCell in FR2) | Rel16 test requirements for CSI-RS based inter-frequency Measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.8.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.9 | RSTD measurements | [6 empty] | 0.1
176 | Y | 38.533 | 7.6.9.1 | NR RSTD measurement reporting delay test case for single positioning frequency layer in FR2 SA | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.9.1 (New in 38.133 Rel-16) | 1
177 | Y | 38.533 | 7.6.9.2 | NR RSTD measurement reporting delay test case for dual positioning frequency layers in FR2 SA | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.9.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.10 | PRS-RSRP measurements | [6 empty] | 0.1
178 | Y | 38.533 | 7.6.10.1 | PRS-RSRP reporting delay test case for single positioning frequency layer | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.10.1 (New in 38.133 Rel-16) | 1
179 | Y | 38.533 | 7.6.10.2 | PRS-RSRP reporting delay test case for dual positioning frequency layer | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.10.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.6.11 | UE Rx-Tx time difference measurements | [6 empty] | 0.1
180 | Y | 38.533 | 7.6.11.1 | UE Rx-Tx time difference measurements for single positioning frequency layer in FR2 SA | Rel16 test requirements for UE Rx-Tx time difference measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.11.1 (New in 38.133 Rel-16) | 1
181 | Y | 38.533 | 7.6.11.2 | UE Rx-Tx time difference measurement period for dual positioning frequency layers in FR2 SA | Rel16 test requirements for UE Rx-Tx time difference measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.6.11.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.5 | CLI measurements | [6 empty] | 0.1
182 | Y | 38.533 | 7.7.5.1 | SA SRS-RSRP measurement accuracy with FR2 serving cell | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.7.5.1 (New in 38.133 Rel-16) | 1
183 | Y | 38.533 | 7.7.5.2 | SA CLI-RSSI measurement accuracy with FR2 serving cell | Rel16 test requirements for CLI measurements |  |  | finished in 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.5.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.6 | L1-SINR measurement for beam reporting | [6 empty] | 0.1
184 | Y | 38.533 | 7.7.6.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured and CSI-RS resource set with repetition off | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.7.6.1 (New in 38.133 Rel-16) | 1
185 | Y | 38.533 | 7.7.6.2 | L1-SINR measurement with SSB based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.7.6.2 (New in 38.133 Rel-16) | 1
186 | Y | 38.533 | 7.7.6.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR | Rel16 test requirements for L1-SINR measurement for beam reporting |  |  | finished in 38.533 | done | Aligned with TS 38.133 Clause A.7.7.6.3 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.7 | CSI-RSRP | [6 empty] | 0.1
187 | Y | 38.533 | 7.7.7.1 | SA intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRP |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.7.1 (New in 38.133 Rel-16) | 1
188 | Y | 38.533 | 7.7.7.2 | SA inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRP |  | RAN5#102 (Feb-24) | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.7.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.8 | CSI-RSRQ | [6 empty] | 0.1
189 | Y | 38.533 | 7.7.8.1 | SA intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241329 R5-241330 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.8.1 (New in 38.133 Rel-16) | 1
190 | Y | 38.533 | 7.7.8.2 | SA Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Rel16 test requirements for CSI-RSRQ | Apple | RAN5#102 (Feb-24) | R5-241331 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.8.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.9 | CSI-SINR | [6 empty] | 0.1
191 | Y | 38.533 | 7.7.9.1 | SA intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241332 R5-241333 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.9.1 (New in 38.133 Rel-16) | 1
192 | Y | 38.533 | 7.7.9.2 | SA Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Rel16 test requirements for CSI-SINR | Apple | RAN5#102 (Feb-24) | R5-241831 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.9.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.10 | RSTD measurements | [6 empty] | 0.1
193 | Y | 38.533 | 7.7.10.1 | RSTD measurement accuracy test case for single positioning frequency layer | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.10.1 (New in 38.133 Rel-16) | 1
194 | Y | 38.533 | 7.7.10.2 | RSTD measurement accuracy test case for dual positioning frequency layer | Rel16 test requirements for RSTD measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.10.2 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.11 | PRS-RSRP measurements | [6 empty] | 0.1
195 | Y | 38.533 | 7.7.11.1 | SA measurement accuracy with PRS in FR2 | Rel16 test requirements for PRS-RSRP measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.11.1 (New in 38.133 Rel-16) | 1
|  | 38.533 | 7.7.12 | UE Rx-Tx time difference measurements | [6 empty] | 0.1
196 | Y | 38.533 | 7.7.12.1 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR2 SA | Rel16 test requirements for UE Rx-Tx time difference measurements |  |  | need to add TC to 38.533 | need to do TT analysis | Aligned with TS 38.133 Clause A.7.7.12.1 (New in 38.133 Rel-16) | 1
Annex A.3
197 |  | 38.533 | Annex A.13 | Channel bandwidth (CBW) configurations | Rel16 updates for DL and UL CBW patterns for UE specific CBW configuration |  | RAN5#100 (Aug-23) | R5-232490 |  | Aligned with TS 38.133 clause A.3.25 (verified) | 0.5
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 37.571-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 37.571-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 37.571-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 37.571-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 37.571-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 37.571-2 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 37.571-3: Applicability and ICS UE Positioning test cases
TBD |  | 37.571-3 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 37.571-3 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 37.571-1 and 37.571-2. |  | TBD |  |  |  | 0.1
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 37.571-4 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 37.571-5 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
IMS
TS 34.229-1: IMS over LTE protocol test cases
|  | 34.229-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 34.229-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 34.229-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 34.229-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 34.229-5: IMS over 5GS protocol test cases
|  | 34.229-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 34.229-5 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 34.229-5 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 34.229-5 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 34.229-2: Applicability and ICS for IMS protocol test cases
TBD |  | 34.229-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 34.229-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. |  | TBD |  |  |  | 0.1
TS 34.229-3: IMS test suite (TTCN)
|  | 34.229-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 34.229-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
Mission Critical Services
TS 36.579-1: MC Common test environment
|  | 36.579-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.579-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 36.579-2: MCPTT UE test cases
|  | 36.579-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.579-2 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.579-2 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.579-3: MCPTT Server Application test cases
|  | 36.579-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.579-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD |  | 36.579-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | TBD
TS 36.579-4: Applicability and ICS MC test cases
TBD |  | 36.579-4 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  |  | 0.1
TBD |  | 36.579-4 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 37.579-x. |  | TBD |  |  |  | 0.1
TS 36.579-5: MC Test suite (TTCN)
|  | 36.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-5 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  |  | TBD
TS 36.579-6: MC Video UE test cases
|  | 36.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-6 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.579-6 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.579-6 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
TS 36.579-7: MC Data UE test cases
|  | 36.579-7 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [6 empty] | TBD
TBD |  | 36.579-7 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  |  | 0
TBD |  | 36.579-7 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  |  | TBD
TBD | Y | 36.579-7 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  |  | 1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on L6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.