## Cover sheet
3GPP TSG-RAN5 Meeting # 103 | [10 empty] | R5-242835
Fukuoka City, Fukuoka , JP, May 20 - 24, 2024
Agenda Item: | 7.5.2
Source: | China Telecom, Huawei, Hisilicon
Title: | WP for UE Conformance - Further NR coverage enhancements
Work item code: | NR_cov_enh2-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The Rel-18 work item “Further NR coverage enhancements” has specified further uplink coverage enhancements including multiple PRACH transmission, increasing of UE Tx power and dynamic waveform switching.Multiple PRACH transmissions with same beams for 4-step RACH procedure target FR2 and short PRACH formats, and can also apply to FR1 and other formats when applicable. Power domain enhancements realize increasing UE power high limit for CA and DC, and reduce MPR/PAR, including frequency domain spectrum shaping. Dynamic switching between DFT-S-OFDM and CP-OFDM is effective because the lower PAPR of DFT-S-OFDM compared with CP-OFDM waveform is beneficial for UL coverage limited scenario. The overall completion level for the core part of NR_cov_enh2 WI is already 100% at the RAN #102 in December 2023. The corresponding UE conformance specifications are now required to be implemented in RAN5.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 8
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% | 0 | 8
FR1 |  | 5% | 0 | 8
FR2 |  | 5% | 0 | 7
NSA Option 3 (EN-DC) |  | 5% (+0%) | 0 | 8
FR1 |  | 5% | 0 | 8
FR2 |  | 5% | 0 | 7
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
NR RF/RRM
FR1 RF test cases - Common parts (general clauses, Annexes) | 38.521-1
FR1 RF test cases - Tx | 38.521-1 Tx | 0% |  |  | 0%
FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes) | 38.521-3
FR1 and FR2 Interworking operation with other radios RF test cases - Tx | 38.521-3 Tx | 0% | [9 empty] | 0%
Applicability for RF, Demod/CSI reporting and RRM test cases | 38.522 | 0% |  |  | 0% | [6 empty] | 0%
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 8 | 0% | 0 | 8 | 0% | 0 | 7 |  | 0% | 0 | 8 | 0% | 0 | 7
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0%
5 References
[1] RP-240345 | New WID NR_cov_enh2-UEConTest
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance - Further NR coverage enhancements | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_cov_enh2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to the WID on Further NR coverage enhancements. This work item will cover RF and Protocol conformance test specifications. | [13 empty] | vs Area
WP Resp: |  | Weichen Ning |  |  | ningwc@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 5% | 5% | 5% | 5%
[15 empty] | 23 (-1) | 15 | 20 (-1) | 16
[15 empty] | 19.7 (-1) | 12.7 | 16.2 (-1) | 13.2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.3.6.1.1 | Physical layer parameters for scheduling of PUSCH | Update default configuration of DCI format 0_1 and DCI format 0_2 to support DWS | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
2 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Update default configuration of RRC IEs for further coverage enhancement testing | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
3 |  | 38.508-1 | 5.4.1 | Radio resource control information elements | To add RF-specific default configuration of RRC IEs for further coverage enhancement testing |  | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | All companies | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-1: FR1 RF test cases - Tx
5 |  | 38.521-1 Tx | 6.2.2 | UE maximum output power reduction | Update testing for MPR Reduction impacted by this WI | China Mobile | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% |  |  | 0%
6 |  | 38.521-1 Tx | 6.2A.1.0.3 | UE maximum output power for Inter-band CA | Update testing for higherpowerlimit feature impacted by this WI | China Telecom | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% |  |  | 0%
7 |  | 38.521-1 Tx | 6.2.4 | Configured transmitted power | Update testing for MPR Reduction impacted by this WI | China Mobile | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% |  |  | 0%
8 |  | 38.521-1 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | Update testing for MPR Reduction impacted by this WI | China Mobile | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% |  |  | 0%
9 |  | 38.521-1 Tx | 6.2G.4 | Configured transmitted power for Tx Diversity | Update testing for MPR Reduction impacted by this WI | China Mobile | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
10 |  | 38.521-3 Tx | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 (1 E-UTRA CC, 1 NR CC) | Update testing for higherpowerlimit feature of EN-DC combos impacted by this WI | China Telecom | RAN5#109 (Nov-17) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
11 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements for cov_enh2 test cases | All companies | RAN5#109 (Nov-17) |  |  | 0.5 | 0% | 0% | 0% |  | 0% |  | 0%
12 |  | 38.522 | 4.1 | RF conformance test cases | Add test case applicability statements for the new cov_enh2 test cases introduced for 38.521-x. | All companies | RAN5#109 (Nov-17) |  |  | 0.5 | 0% | 0% | 0% |  | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
13 | Y | 38.523-1 | 7.1.1.1.X1 | Random access procedure / Msg1 repetition / Contention-based | [REF:38.321 cl.5.1.1, 5.1.1b, 5.1.1c, 5.1.3, 5.1.4, 5.1.5] TP1: WITH: UE is in RRC_idle state. UE is configured with RACH resources for both legacy RACH and Msg.1 repetition. WHEN: PL-RS RSRP results is higher than the threshold for Msg.1 repetition. THEN: UE performs legacy RACH procedure. TP2: WITH: UE is in RRC_idle state. UE is configured with RACH resources for both legacy RACH and Msg.1 repetition and UE is perfoming legacy RACH. WHEN: UE performs legacy RACH procedure and PREAMBLE_TRANSMISSION_COUNTER exceeds preambleTransMax. THEN: UE doesn't perform Msg.1 repetition. TP3: WITH: UE is in RRC_idle state. UE is configured with RACH resources for both legacy RACH and Msg.1 repetition. WHEN: PL-RS RSRP results is lower than the threshold for Msg.1 repetition. THEN: UE performs Msg.1 repetition. TP4: WITH: UE is in RRC_idle state. UE is configured with RACH resources for different Msg.1 repetition numbers and is perfoming Msg.1 repetition. WHEN: PREAMBLE_TRANSMISSION_COUNTER exceeds preambleTransMax-Msg1-Repetition or 2*preambleTransMax-Msg1-Repetition. THEN: UE fallbacks to next higher PRACH repetition number. TP5: WITH: UE is in RRC_idle state. UE is configured with RACH resources for Msg.1 repetition and is perfoming Msg.1 repetition. WHEN: UE receives a RAR scrambled by RA-RNTI based on the RO used by the last preamble of Msg.1 repetition. THEN: UE transmits Msg.3. | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
14 | Y | 38.523-1 | 7.1.1.1.X2 | Random access procedure / Msg1 repetition / Msg.1-based SI request | [REF:38.321 cl.5.1.1, 5.1.1b, 5.1.1c, 5.1.1d, 5.1.3, 5.1.4, 5.1.5. 38.331 cl.5.2.2.3.3] TP1: WITH: UE is in RRC_idle state. UE is configured with RACH resources for both legacy SI request and SI request with Msg.1 repetition. WHEN: PL-RS RSRP results is higher than the threshold for Msg.1 repetition. THEN: UE performs legacy SI request procedure. TP2: WITH: UE is in RRC_idle state. UE is configured with RACH resources for both legacy SI request and SI request with Msg.1 repetition. WHEN: PL-RS RSRP results is lower than the threshold for Msg.1 repetition. THEN: UE performs SI request with Msg.1 repetition of the highest applicable repetition number. | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
15 | Y | 38.523-1 | 7.1.1.1.X3 | Random access procedure / Msg1 repetition / CE-only BWP | [REF:38.321 cl.5.1.1, 5.1.1b, 5.1.1c, 5.1.3, 5.1.4, 5.1.5, 38.331 cl.5.2.2.3.3] TP1: WITH: UE is in RRC_connected state. only RACH resource for specific Msg.1 repetition number is configured on UE's active UL BWP. WHEN: UE receives a paging to inform the change of on demand SI. THEN: UE performs SI request with Msg.1 repetition of configured repetition number. | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
16 | Y | 38.523-1 | 7.1.1.1.X4 | Random access procedure / Msg1 repetition / Contention-free | [REF:38.321 cl.5.1.1, 5.1.1b, 5.1.1c, 5.1.3, 5.1.4, 5.1.5] TP1: WITH: UE is in RRC_connected state. UE is configured with RACH resources for legacy RACH and Msg.1 repetition. WHEN: UE receives an ReconfigurationWithSync with repetition number. THEN: UE performs CFRA procedure with PRACH repetition. | Lenovo | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
17 | Y | 38.523-1 | 7.1.1.3.Y1 | UE power headroom reporting / delta power class reporting | [REF:38.321 cl.5.4.6, 6.1.3, 38.213 cl.7.7.1] TP1: WITH: UE in RRC_CONNECTED state and is configured with dpc-Reporting-FR1. WHEN: phr-PeriodicTimer is configured in UE. THEN: UE transmits a MAC PDU containing Power Headroom MAC Control Element inclduing DPC field. TP2: WITH: UE in RRC_CONNECTED state with periodic power headroom reporting and dpc-Reporting-FR1 configured WHEN: phr-PeriodicTimer expires and UL resources allocated for new transmission THEN: UE transmits a MAC PDU containing Power Headroom MAC Control Element inclduing DPC field. TP3: WITH: UE in RRC_CONNECTED state with Power headroom reporting for phr-Tx-PowerFactorChange and dpc-Reporting-FR1 configured WHEN: phr-ProhibitTimer expires and power headroom report is triggered due to DL Pathloss change THEN: UE transmits a MAC PDU containing Power Headroom MAC Control Element inclduing DPC field. | Lenovo | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% |  | 0%
18 | Y | 38.523-1 | 7.1.1.3.Y2 | UE power headroom reporting / PCMAX for assumed PUSCH reporting | [REF:38.321 cl.5.1.1, 5.1.1b, 5.1.1c, 5.1.3, 5.1.4, 5.1.5] TP1: WITH: UE is in RRC_connected state. UE is configured with phr-AssumedPUSCH-Reporting and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 is set to disabled in active BWP. WHEN: phr-PeriodicTimer is configured in UE. THEN: UE doesn't transmit a MAC PDU containing Power Headroom with assumed PUSCH MAC Control Element. TP2: WITH: UE is in RRC_connected state. UE is configured with phr-Tx-PowerFactorChange, phr-AssumedPUSCH-Reporting and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 is set to enabled in active BWP. WHEN: phr-PeriodicTimer is configured in UE. THEN: UE transmits a MAC PDU containing Power Headroom with assumed PUSCH MAC Control Element. TP3: WITH: UE is in RRC_connected state. UE is configured with phr-AssumedPUSCH-Reporting and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 is set to enabled in active BWP. WHEN: phr-PeriodicTimer expires and UL resources allocated for new transmission. THEN: UE transmits a MAC PDU containing Power Headroom with assumed PUSCH MAC Control Element. TP4: WITH: UE is in RRC_connected state. UE is configured with phr-AssumedPUSCH-Reporting and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 is set to enabled in active BWP. WHEN: phr-ProhibitTimer expires and power headroom report is triggered due to DL Pathloss change. THEN: UE transmits a MAC PDU containing Power Headroom with assumed PUSCH MAC Control Element. | Lenovo | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
19 | Y | 38.523-1 | 7.1.1.3.Y3 | Correct Handling of UL grant / Dynamic waveform switch / DCI format 0_1 | [REF:38.212 cl.7.3.1.1, 38.214 cl.6.1.3] TP1: WITH: UE is in RRC_connected state and is configured with transformPrecoder = disabled and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 in active BWP. WHEN: UE receives an DCI format 0_1 with Transform precoder indicator = 0. THEN: UE transmits PUSCH with DFT-s-OFDM waveform. TP2: WITH: UE is in RRC_connected state and is configured with msg3-transformPrecoder = disabled, transformPrecoder not configured and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 in active BWP. WHEN: UE receives an DCI format 0_1 with Transform precoder indicator = 0. THEN: UE transmits PUSCH with DFT-s-OFDM waveform. TP3: WITH: UE is in RRC_connected state and is configured with transformPrecoder = enabled and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 in active BWP. WHEN: UE receives an DCI format 0_1 with Transform precoder indicator = 1. THEN: UE transmits PUSCH with CP-OFDM waveform. TP4: WITH: UE is in RRC_connected state and is configured with msg3-transformPrecoder = enabled, transformPrecoder not configured and dynamicTransformPrecoderFieldPresenceDCI-0-1-r18 in active BWP. WHEN: UE receives an DCI format 0_1 with Transform precoder indicator = 1. THEN: UE transmits PUSCH with CP-OFDM waveform. | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
20 | Y | 38.523-1 | 7.1.1.3.Y4 | Correct Handling of UL grant / Dynamic waveform switch / DCI format 0_2 | [REF:38.212 cl.7.3.1.1, 38.214 cl.6.1.3] TP1: WITH: UE is in RRC_connected state and is configured with transformPrecoder = disabled and dynamicTransformPrecoderFieldPresenceDCI-0-2-r18 in active BWP. WHEN: UE receives an DCI format 0_2 with Transform precoder indicator = 0. THEN: UE transmits PUSCH with DFT-s-OFDM waveform. TP2: WITH: UE is in RRC_connected state and is configured with msg3-transformPrecoder = disabled, transformPrecoder not configured and dynamicTransformPrecoderFieldPresenceDCI-0-2-r18 in active BWP. WHEN: UE receives an DCI format 0_2 with Transform precoder indicator = 0. THEN: UE transmits PUSCH with DFT-s-OFDM waveform. TP3: WITH: UE is in RRC_connected state and is configured with transformPrecoder = enabled and dynamicTransformPrecoderFieldPresenceDCI-0-2-r18 in active BWP. WHEN: UE receives an DCI format 0_2 with Transform precoder indicator = 1. THEN: UE transmits PUSCH with CP-OFDM waveform. TP4: WITH: UE is in RRC_connected state and is configured with msg3-transformPrecoder = enabled, transformPrecoder not configured and dynamicTransformPrecoderFieldPresenceDCI-0-2-r18 in active BWP. WHEN: UE receives an DCI format 0_2 with Transform precoder indicator = 1. THEN: UE transmits PUSCH with CP-OFDM waveform. | Lenovo | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
RRC
21 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | Add Rel-18 coverage further enhancement related UE capability check in NR SA UE capability transfer TC | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 0.5 | 0% | 0% |  |  | 0% | 0%
22 |  | 38.523-1 | 8.2.1.1.1 | UE capability transfer / Success / EN-DC | Add Rel-18 coverage further enhancement related UE capability check in EN-DC UE capability transfer TC | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 0.5 | 0% |  | 0% |  |  |  | 0% | 0%
23 |  | 38.523-1 | 8.2.1.1.2 | UE capability transfer / Success / NE-DC | Add Rel-18 coverage further enhancement related UE capability check in NE-DC UE capability transfer TC | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 0.5 | 0% |  | 0% |  |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
24 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
25 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. | Huawei, HiSilicon | RAN5#109 (Nov-17) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
26 |  | 38.523-3 | 5, 6 and 7 | Test models, System interface and Test methods | updates to Test models, System interface and Test methods for Rel-18 coverage further enhancements | MCC TF160 | RAN5#109 (Nov-17) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.