## Cover sheet
3GPP TSG-RAN WG5 Meeting #103 | [10 empty] | R5-243099
Fukouka, Japan, 20th – 24th May 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP of Rel-16 V2X WI after RAN5 103
Work item code: | 5G_V2X_NRSL_eV2XARC-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The core gropus Rel-16 WI 5G V2X with NR sidelink aims to specify enhancements to both Uu transport and PC5 transport in E-UTRAN/NR to support NR-based V2X (V2V, V2I/N, and V2P). The objective of the UE Conformance Test Aspects work item is to provide conformance test specifications for the core requirements of Rel-16 Security Aspects of eV2XARC, CT aspects of eV2XARC, and RAN aspects of 5G V2X with NR sidelink. The RAN5 areas of RF, RRM, Demodulation and Protocol conformance test specifications with NR-based V2X operation are to be covered. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR V2X was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 68% (+3%) | 84 (+14) | 175
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 65.5% (+6.1%) | 47 (+13) | 109
FR1 |  | 65.5% (+6.1%) | 47 (+13) | 110
FR2
FR1 + FR2
PC5 |  | 69.6% (+0.6%) | 59 (+1) | 103
FR1 |  | 69.6% (+0.6%) | 59 (+1) | 103
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | PC5
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% | [8 empty] | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% | [8 empty] | 100%
UE specific test functions | 38.509 | 100% |  |  | 100% | [8 empty] | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 45.8% (+4.2%) |  |  | 45.8% (+4.2%)
FR1 RF Tx test cases | 38.521-1 Tx | 53.8% (+14.1%) | 24 (+13) | 62 | 53.8% (+14.1%) | 24 (+13) | 62
FR1 RF Rx test cases | 38.521-1 Rx | 28.5% | 0 | 9 | 28.5% | 0 | 10
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 8.3% | [11 empty] | 8.3%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 65.2% | 0 | 10 | [9 empty] | 65.2% | 0 | 10
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 43.5% | 0 | 2 | [9 empty] | 43.5% | 0 | 2
RF Demod/QSI test cases | 38.521-4 | 99.2% | 7 | 7 | [9 empty] | 99.2% | 7 | 7
RRM test cases | 38.533 | 100% | 13 | 13 | 100% | 4 | 4 | [6 empty] | 100% | 13 | 13
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 57.5% (+5%) |  |  | 57.5% (+5%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% |  |  | 100% | [8 empty] | 100%
Test Point analysis receiver and transmitter test cases | 38.905 | 21.1% (+17.9%) |  |  | 20% (+20%) | [8 empty] | 22.5% (+15%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 57.1% (+0.6%) | 40 (+1) | 72 | 58% | 19 | 34 | [6 empty] | 56% (+1.4%) | 39 (+1) | 71
Applicability Protocol test cases | 38.523-2 | 57.5% (+5%) |  |  | 57.5% (+5%) | [8 empty] | 57.5% (+5%)
Test suites (TTCN) | 38.523-3 | 100% |  |  | 100% | [8 empty] | 100%
UE positioning test suites (TTCN) | 38.571-4 | 100% |  |  | 100% | [8 empty] | 100%
5 References
[1] RP-200894 | New WID on UE conformance test aspects for 5G V2X with NR sidelink; Huawei, Hisilicon
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects for NR V2X | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | 5G_V2X_NRSL_eV2XARC-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-16 Security Aspects of eV2XARC, CT aspects of eV2XARC, and RAN aspects of 5G V2X with NR sidelink. The RAN5 areas of RF, RRM, Demodulation and Protocol conformance test specifications with NR-based V2X operation are to be covered. | [13 empty] | vs Area
WP Resp: |  | Wang, Xuesong (Huawei) |  |  | wangxuesong743@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | PC5
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | PC5 |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 65.5% (+6.1%) |  |  | 69.6% (+0.6%)
[15 empty] | 294 | 0 | 0 | 345 | 0 | 0
[15 empty] | 184.5 | 0 | 0 | 217.4 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.3.1 | Test frequencies for NR V2X test | To add Test frequencies for NR V2X test | Huawei, Hisilicon | RAN5#95 (May-22) | R5-213997; R5-223359; R5-235822 | n47 and corresponding inter-band concurrent operation BC are completed | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
459 |  | 38.508-1 | 4.3.6.1 | Downlink physical layer parameters for NR V2X test | To add Default configuration for DCI scheduling NR SL communication, i.e. DCI format 3_0 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217878;R5-231423 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
460 |  | 38.508-1 | 4.3.6.2 | Sidelink physical layer parameters for NR V2X test | To add Default configuration for SCI scheduling NR SL communication, i.e. SCI format 1-A/2-A/2-B | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217878; R5-223360; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
2 |  | 38.508-1 | 4.4.3.1.2 | SI combination for NR V2X test | To add SI combination for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211462; R5-212203; | R5-212203 is the resubmission of R5-211462 | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
3 |  | 38.508-1 | 4.4.3.1.3 | Scheduling of SIBs for NR V2X test | To add Scheduling of SIBs for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211462; R5-212203 | R5-212203 is the resubmission of R5-211462 | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
4 |  | 38.508-1 | 4.4A | Test states for NR V2X test | To add Test states for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213559 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
5 |  | 38.508-1 | 4.5 | Generic procedures for NR V2X test | To add Generic procedures for NR V2X test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213557; R5-213558; R5-213443; R5-215071; R5-221499; | Only cl.4.5.1 part of R5-213443 belongs to V2X WI | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
6 |  | 38.508-1 | 4.6.1A | Contents of PC5 RRC messages | To add PC5 RRC messages used in PC5 unicast [Ref: 38.331 cl. 6.6.2] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211337; R5-211338; R5-211339; R5-213565; R5-213418; R5-213566; R5-213419; R5-221502; R5-221503; R5-221504; R5-221505; R5-221506; R5-221507; R5-221508; R5-225290 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
7 |  | 38.508-1 | 4.6.2 | System information blocks | To update SIBs related to NR sidelink, i.e. SIB12[Ref: 38.331 cl. 6.3.1] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206407; R5-217877; R5-220579; R5-225290; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
8 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | To update and add Uu RRC IEs related to NR sidelink[Ref: 38.331 cl. 6.3.2] | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-210713; R5-210714; R5-217766; R5-225290; R5-231424; R5-232576 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
11 |  | 38.508-1 | 4.6.6 | Sidelink information elements | To add NR sidelink ralated IEs used in Uu RRC messages and PC5 RRC messages[Ref: 38.331 cl. 6.3.5] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-210701; R5-211335; R5-210703; R5-210704; R5-210705; R5-210706; R5-210707; R5-210708; R5-210709; R5-210710; R5-210711; R5-211366; R5-212455; R5-212456; R5-212457; R5-212458; R5-212459; R5-212460; R5-212461; R5-212462; R5-212463; R5-212464; R5-212465; R5-213560; R5-213561; R5-212468; R5-212469; R5-213562; R5-213416; R5-213563; R5-212473; R5-213417; R5-212476; R5-213564; R5-212478; R5-212479; R5-213567; R5-220580; R5-220582; R5-223361; R5-223362; R5-223363; R5-223364; R5-222647; R5-225290; R5-241539 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
13 |  | 38.508-1 | 4.7D.1 | Contents of V2X layer messages | To add default configuration of V2X layer messages [Ref TS 24.501 clause D.5, TS 24.587 clasue 7] | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-217025; R5-217026; R5-217027; R5-217028; R5-217029; R5-217030; R5-217880; R5-217032; R5-217881; R5-217882; R5-217035; R5-217883; R5-217884; R5-217038; R5-217039; R5-217040; R5-217885; R5-217886; R5-217887; R5-217044; R5-217045; R5-217888; R5-221509; R5-221510; R5-221511; R5-221512; R5-221513; R5-221514; R5-221515; R5-222818; R5-227174; R5-241538 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
14 |  | 38.508-1 | 4.7D.2 | Contents of V2X layer information elements | To add default configuration of V2X information elements [Ref TS 24.501 clause D.6, TS 24.588 clause 5] | Huawei, Hisilicon | RAN5#95 (May-22) | R5-210699; R5-212921; R5-214800; R5-216263; R5-216264; R5-216265; R5-216266; R5-216267; R5-216268; R5-216269; R5-220590; R5-241538 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
452 |  | 38.508-1 | 4.7.6 | Contents of UE Policy Delivery messages | To add V2X related UE Policy Delivery messages | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-216270 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
476 |  | 38.508-1 | 4.7B | Contents of AT commands | To add rdefault AT command messages and Ies for NR sidelink test | Huawei, Hisilicon | RAN5#94 (Feb-22) | R5-220567 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
15 |  | 38.508-1 | 4.8.3.3.3 | Modified contents of the USIM Elementary Files and additional USIM Elements files at the DFV2X level | To add default USIM configuration of V2X [Ref TS 31.102 clause 4.6.5] | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-206408; R5-214808; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
453 |  | 38.508-1 | 4.8.4 | DNN/APN configurations | To add DNN/APN configurations for the V2X SST | Ericsson | RAN5#92 (Aug-21) | R5-215499 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
477 |  | 38.508-1 | 4.9 | Test procedures | To add test procedures for sidekink test | Huawei, Hisilicon | RAN5#94 (Feb-22) | R5-213558; R5-220569; R5-221500; R5-221501; R5-223365; R5-225291; R5-235306 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
228 |  | 38.508-1 | 4.10.1 | Pre-configuration for V2X | To add default configuration of V2X AS parameters [Ref TS 38.331 clause 9.3] | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-210698; R5-221815; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
427 |  | 38.508-1 | 4.11 | GNSS Requirements for NR sidelink | To add default configuration of V2X GNSS simulator | Huawei, Hisilicon | RAN5#95 (May-22) | R5-212921; R5-221816; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
483 |  | 38.508-1 | 5.4.3 | Sidelink information elements for Demod | To add reference configuration of SL IEs for NR V2X Demod test | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222617 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
461 |  | 38.508-1 | 6.2.1 | Physical Channel Allocation for signalling testing | To add Physical Channel Allocation for NR V2X SIG test | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217879 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
462 |  | 38.508-1 | 6.2.2 | Default settings of NR-SS-UE power and signal level uncertainty for signalling testing | To add default settings of NR-SS-UE power and signal level uncertainty for NR V2X SIG test | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217879 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
428 |  | 38.508-1 | 6.2.3 | Test frequencies for signalling testing | To add Test frequencies for NR V2X SIG test | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213997; R5-217390; R5-220591; R5-223359; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
469 |  | 38.508-1 | 7.3.2 | Sidelink information elements for RRM | To add reference configuration of SL IEs for NR V2X RRM test | Huawei, Hisilicon | RAN5#94 (Feb-22) | R5-220725 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
429 |  | 38.508-1 | Annex A | Connection Diagrams | To add connection diagrams for V2X | Huawei, Hisilicon | RAN5#95 (May-22) | R5-212924; R5-220788 | Connection diagrams for PC5 alone/con-current/SL MIMO are added | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
430 |  | 38.508-1 | Annex C | Calculation of test frequencies | To add calculation of test freuquencies for V2X bands | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213996 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
463 |  | 38.508-1 | Other Clauses | Miscellaneous changes for V2X test | To add miscellaneous changes for V2X test | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217024 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
TS 38.508-2: Common ICS
16 |  | 38.508-2 | A.4.3.10 | PICs for NR SL testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#95 (May-22) | R5-206410; R5-213406; R5-212931; R5-215135; R5-215078; R5-217889; R5-222618; R5-241707 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
TS 38.509: UE specific testing functions
425 |  | 38.509 | 5.2 | Test mode for NR SL | To add test mode E related description | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213568 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
426 |  | 38.509 | 5.3 | Loop back function for NR SL | To add Loop back mode E related description | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213568; R5-216069; R5-221516; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
478 |  | 38.509 | 5.9 | Test protocol procedure for NR SL | To add paclet counter reporting procedure for NR SL | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213569 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
479 |  | 38.509 | 6.9 | TMC messge for NR SL | To add TMC message used in SL packet counter reporting procedure | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-213569; R5-221517; |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
17 |  | 38.521-1 | 2 | Reference | Define References made in TS | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839; R5-217609 |  | 0.1 | 100% | 100% |  |  | 100%
18 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
19 |  | 38.521-1 | 4 | General | define categories of test requirements | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839 |  | 0.1 | 100% | 100% |  |  | 100%
20 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement | Bureau Veritas | RAN5#89-e (Nov-20) | R5-204839; R5-212739 |  | 0.1 | 100% | 100% |  |  | 100%
21 |  | 38.521-1 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | RAN5#91-e (May-21) | R5-205700; R5-217608 |  | 0.1 | 100% | 100% |  |  | 100%
22 |  | 38.521-1 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
23 |  | 38.521-1 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
24 |  | 38.521-1 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
25 |  | 38.521-1 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
26 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#99 (May-23) | R5-243630 |  | 0.1 | 50% (+50%) | 50% (+50%) |  |  | 50%
27 |  | 38.521-1 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
28 |  | 38.521-1 | Annex H | Statistical Testing |  |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
431 |  | 38.521-1 Tx | 6.1E | General | Adding common RB allocations | Huawei, Hisiicon | RAN5#89-e (Nov-20) | R5-212926； |  | 0 | 100% | 100% |  |  | 100%
29 |  | 38.521-1 Tx | 6.2E | Transmitter power for V2X | Sub-clause heading |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% |  |  | 100%
30 |  | 38.521-1 Tx | 6.2E.1 | UE maximum output power for V2X | Sub-clause heading |  | RAN5#89-e (Nov-20) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.2E.1.0 | Minimum conformance requirements | TS 38.101-1 cl 6,2E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) | R5-206764 R5-243134 |  | 1 | 100% | 100% |  |  | 100%
31 | Y | 38.521-1 Tx | 6.2E.1.1 | UE maximum output power for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.1.1 | Huawei, Hisiicon | RAN5#95 (May-22) | R5-206764 R5-221818 R5-222206 R5-227750 R5-237072 | Untestable due to lack of appropriate test points since there’s no configuration satisfying MPR=0dB requirements in TS 38.101-1 | 0 | 100% | 100% |  |  | 100%
32 | Y | 38.521-1 Tx | 6.2E.1.1D | UE maximum output power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-215073 R5-217609 R5-221818 R5-227750 R5-237072 | Untestable due to lack of appropriate test points since there’s no configuration satisfying MPR=0dB requirements in TS 38.101-1 | 0 | 100% | 100% |  |  | 100%
33 | Y | 38.521-1 Tx | 6.2E.1.2 | UE maximum output power for V2X / con-current operation | TS 38.101-1 cl 6,2E.1.2 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243134 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
34 |  | 38.521-1 Tx | 6.2E.2 | UE maximum output power reduction for V2X | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-212927 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.2E.2.0 | Minimum conformance requirements | TS 38.101-1 cl 6,2E.2 | Huawei, Hisiicon | RAN5#90-e (Feb-21) | R5-212927 |  | 1 | 100% | 100% |  |  | 100%
35 | Y | 38.521-1 Tx | 6.2E.2.1 | UE maximum output power reduction for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 | Huawei, Hisiicon | RAN5#95 (May-22) | R5-212927 R5-221818 R5-243136 | 38.905: R5-212929 38.522: R5-212932 | 1 | 100% | 100% |  |  | 100%
36 | Y | 38.521-1 Tx | 6.2E.2.1D | UE maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-215074 R5-243136 |  | 1 | 100% (+40%) | 100% (+40%) |  |  | 100%
37 | Y | 38.521-1 Tx | 6.2E.2.2 | UE maximum output power reduction for V2X / con-current operation | TS 38.101-1 cl 6,2E.2.3 | Huawei, Hisiicon | RAN5#95 (May-22) | R5-221819 R5-222205 |  | 1 | 100% | 100% |  |  | 100%
38 |  | 38.521-1 Tx | 6.2E.3 | UE additional maximum output power reduction for V2X | Sub-clause heading |  | RAN5#99 (May-23) | R5-241733 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.2E.3.0 | Minimum conformance requirements | TS 38.101-1 cl 6,2E.3 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-241733 R5-243629 |  | 1 | 100% | 100% |  |  | 100%
39 | Y | 38.521-1 Tx | 6.2E.3.1 | UE additional maximum output power reduction for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-241733 R5-243629 |  | 1 | 100% | 100% |  |  | 100%
40 | Y | 38.521-1 Tx | 6.2E.3.1D | UE additional maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-241733 R5-243629 |  | 1 | 100% | 100% |  |  | 100%
41 | Y | 38.521-1 Tx | 6.2E.3.2 | UE additional maximum output power reduction for V2X / con-current operation | TS 38.101-1 cl 6,2E.3.4 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-241733 R5-243629 |  | 1 | 100% | 100% |  |  | 100%
42 |  | 38.521-1 Tx | 6.2E.4 | Configured transmitted power for V2X | Sub-clause heading |  | RAN5#99 (May-23) | R5-243138 |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100%
|  | 38.521-1 Tx | 6.2E.4.0 | Minimum conformance requirements | TS 38.101-1 cl 6,2E.4 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243138 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
43 | Y | 38.521-1 Tx | 6.2E.4.1 | Configured transmitted power for V2X / non-concurrent operation | TS 38.101-1 cl 6,2E.4.1 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243138 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
44 | Y | 38.521-1 Tx | 6.2E.4.1D | Configured transmitted power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,2E.4.1 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243138 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
45 | Y | 38.521-1 Tx | 6.2E.4.2 | Configured transmitted power for V2X / con-current operation | TS 38.101-1 cl 6,2E.4.2 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243138 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
46 |  | 38.521-1 Tx | 6.3E.1 | Minimum output power for V2X | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-212928 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3E.1.0 | Minimum conformance requirements | TS 38.101-1 cl 6,3E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) | R5-212928 |  | 1 | 100% | 100% |  |  | 100%
47 | Y | 38.521-1 Tx | 6.3E.1.1 | Minimum output power for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.1.1 | Huawei, Hisiicon | RAN5#95 (May-22) | R5-212928 R5-221818 R5-243140 | 38.905: R5-212930 38.522: R5-212932 | 1 | 100% | 100% |  |  | 100%
48 | Y | 38.521-1 Tx | 6.3E.1.1D | Minimum output power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-215075 R5-222204 R5-243140 |  | 1 | 100% (+50%) | 100% (+50%) |  |  | 100%
49 | Y | 38.521-1 Tx | 6.3E.1.2 | Minimum output power for V2X / con-current operation | TS 38.101-1 cl 6,3E.1.2 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-243140 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
50 |  | 38.521-1 Tx | 6.3E.2 | Transmit OFF power for V2X | Sub-clause heading |  | RAN5#95 (May-22) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.3E.2.0 | Minimum conformance requirements | TS 38.101-1 cl 6,3E.2.1 | CAICT | RAN5#95 (May-22) | R5-221817 |  | 1 | 100% | 100% |  |  | 100%
51 | Y | 38.521-1 Tx | 6.3E.2.1 | Transmit OFF power for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.2.1 | CAICT | RAN5#99 (May-23) | R5-221817 R5-243141 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
52 | Y | 38.521-1 Tx | 6.3E.2.1D | Transmit OFF power for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.2.1 | CAICT | RAN5#99 (May-23) | R5-221817 R5-243141 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
53 | Y | 38.521-1 Tx | 6.3E.2.2 | Transmit OFF power for V2X / con-current operation | TS 38.101-1 cl 6,3E.2.2 | CAICT | RAN5#99 (May-23) | R5-221817 R5-243141 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
54 |  | 38.521-1 Tx | 6.3E.3 | Transmit ON/OFF time mask for V2X | Sub-clause heading |  | RAN5#99 (May-23) | R5-243142 |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100%
|  | 38.521-1 Tx | 6.3E.3.0 | Minimum conformance requirements | TS 38.101-1 cl 6.3E.3 | Samsung | RAN5#99 (May-23) | R5-243142 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
56 |  | 38.521-1 Tx | 6.3E.3.1 | General time mask for V2X | Sub-clause heading |  | RAN5#99 (May-23) | R5-243142 |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100%
57 | Y | 38.521-1 Tx | 6.3E.3.1.1 | General time mask for V2X / non-concurrent operation | TS 38.101-1 cl 6.3E.3.2 | Samsung | RAN5#99 (May-23) | R5-243142 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
58 | Y | 38.521-1 Tx | 6.3E.3.1.1D | General time mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.3E.3.2 | Samsung | RAN5#99 (May-23) | R5-243142 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
59 | Y | 38.521-1 Tx | 6.3E.3.1.2 | General time mask for V2X / con-current operation | TS 38.101-1 cl 6.3E.3.4 | Samsung | RAN5#99 (May-23) | R5-243142 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
60 |  | 38.521-1 Tx | 6.3E.3.2 | S-SSB time mask for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
61 | Y | 38.521-1 Tx | 6.3E.3.2.1 | S-SSB time mask for V2X / non-concurrent operation | TS 38.101-1 cl 6.3E.3.3 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
62 | Y | 38.521-1 Tx | 6.3E.3.2.1D | S-SSB time mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.3E.3.3 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
63 | Y | 38.521-1 Tx | 6.3E.3.2.2 | S-SSB time mask for V2X / con-current operation | TS 38.101-1 cl 6.3E.3.4 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
64 |  | 38.521-1 Tx | 6.3E.4 | Power control for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.3E.4.0 | Minimum conformance requirements | TS 38.101-1 cl 6,3E.4 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
66 |  | 38.521-1 Tx | 6.3E.4.1 | Absolute power tolerance for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
67 | Y | 38.521-1 Tx | 6.3E.4.1.1 | Absolute power tolerance for V2X / non-concurrent operation | TS 38.101-1 cl 6,3E.4.2 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
68 | Y | 38.521-1 Tx | 6.3E.4.1.1D | Absolute power tolerance for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,3E.4.2 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
69 | Y | 38.521-1 Tx | 6.3E.4.1.2 | Absolute power tolerance for V2X / con-current operation | TS 38.101-1 cl 6,3E.4.3 | Samsung | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
70 |  | 38.521-1 Tx | 6.4E.1 | Frequency error for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.4E.1.0 | Minimum conformance requirements | TS 38.101-1 cl 6,4E.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
71 | Y | 38.521-1 Tx | 6.4E.1.1 | Frequency error for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
72 | Y | 38.521-1 Tx | 6.4E.1.1D | Frequency error for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
73 | Y | 38.521-1 Tx | 6.4E.1.2 | Frequency error for V2X / con-current operation | TS 38.101-1 cl 6,4E.1.2 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
74 |  | 38.521-1 Tx | 6.4E.2 | Transmit modulation quality for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
75 |  | 38.521-1 Tx | 6.4E.2.1 | Minimum conformance requirements | TS 38.101-1 cl 6,4E.2 | LG Electronics | RAN5#90-e (Feb-21) | R5-210419 |  | 0.1 | 100% | 100% |  |  | 100%
76 |  | 38.521-1 Tx | 6.4E.2.2 | Error Vector Magnitude for V2X | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-210419 |  | 0 | 100% | 100% |  |  | 100%
77 | Y | 38.521-1 Tx | 6.4E.2.2.1 | Error Vector Magnitude for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.2 | LG Electronics | RAN5#99 (May-23) | R5-210419 R5-221818 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Test configuration is TBD - Target power level is TBD 38.522:R5-211610 | 1 | 70% | 70% |  |  | 70%
78 | Y | 38.521-1 Tx | 6.4E.2.2.1D | Error Vector Magnitude for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.2 | LG Electronics | RAN5#99 (May-23) | R5-214003 | Editor’s Note: - No test points are defined since there is no configuration satisfying MPR=0dB requirements in RAN4. - The test case is not completed due to the following aspects are not yet determined: - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
79 | Y | 38.521-1 Tx | 6.4E.2.2.2 | Error Vector Magnitude for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
80 |  | 38.521-1 Tx | 6.4E.2.3 | Carrier leakage for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
81 | Y | 38.521-1 Tx | 6.4E.2.3.1 | Carrier leakage for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.3 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
82 | Y | 38.521-1 Tx | 6.4E.2.3.1D | Carrier leakage for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.3 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
83 | Y | 38.521-1 Tx | 6.4E.2.3.2 | Carrier leakage for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
84 |  | 38.521-1 Tx | 6.4E.2.4 | In-band emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
85 | Y | 38.521-1 Tx | 6.4E.2.4.1 | In-band emissions for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.4 | MTCC, LGE | RAN5#99 (May-23) | R5-214004 R5-218300 R5-221818 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Test configuration is TBD - Target power level is TBD | 1 | 70% | 70% |  |  | 70%
86 | Y | 38.521-1 Tx | 6.4E.2.4.1D | In-band emissions for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.4 | MTCC, LGE | RAN5#99 (May-23) | R5-214004 R5-218301； R5-241208 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Test configuration is TBD - Target power level is TBD - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 75% | 75% |  |  | 75%
87 | Y | 38.521-1 Tx | 6.4E.2.4.2 | In-band emissions for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 | MTCC | RAN5#99 (May-23) | R5-218302； R5-241210 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Test configuration is TBD - Target power level is TBD - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 75% | 75% |  |  | 75%
88 |  | 38.521-1 Tx | 6.4E.2.5 | EVM equalizer spectrum flatness for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
89 | Y | 38.521-1 Tx | 6.4E.2.5.1 | EVM equalizer spectrum flatness for V2X / non-concurrent operation | TS 38.101-1 cl 6,4E.2.4 | MTCC | RAN5#99 (May-23) | R5-218303 R5-221818 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Test configuration is TBD - Target power level is TBD | 1 | 70% | 70% |  |  | 70%
90 | Y | 38.521-1 Tx | 6.4E.2.5.1D | EVM equalizer spectrum flatness for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,4E.2.4 | MTCC | RAN5#99 (May-23) | R5-218304 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
91 | Y | 38.521-1 Tx | 6.4E.2.5.2 | EVM equalizer spectrum flatness for V2X / con-current operation | TS 38.101-1 cl 6,4E.2.6 | MTCC | RAN5#99 (May-23) | R5-218305 | Editor’s Note: - The test case is not completed due to the following aspects are not yet determined: - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
92 |  | 38.521-1 Tx | 6.5.3.2 | Spurious emissions for UE co-existence | TS 38.101-1 cl 6,5.3.2 Adding band n47 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
93 |  | 38.521-1 Tx | 6.5E.1 | Occupied bandwidth for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.1.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
94 | Y | 38.521-1 Tx | 6.5E.1.1 | Occupied bandwidth for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
95 | Y | 38.521-1 Tx | 6.5E.1.1D | Occupied bandwidth for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.1.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
96 | Y | 38.521-1 Tx | 6.5E.1.2 | Occupied bandwidth for V2X / con-current operation | TS 38.101-1 cl 6,5E.1.2 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
97 |  | 38.521-1 Tx | 6.5E.2 | Out of band emission for V2X | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-211806 |  | 0 | 100% | 100% |  |  | 100%
98 |  | 38.521-1 Tx | 6.5E.2.1 | General | TS 38.101-1 cl 6,5E.2.1 | Oppo | RAN5#90-e (Feb-21) | R5-211806 |  | 0.1 | 100% | 100% |  |  | 100%
99 |  | 38.521-1 Tx | 6.5E.2.2 | Spectrum emission mask for V2X | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-211806 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.2.2.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.2.2 |  | RAN5#97 (Nov-22) | R5-211806 |  | 0 | 100% | 100% |  |  | 100%
100 | Y | 38.521-1 Tx | 6.5E.2.2.1 | Spectrum emission mask for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.2.1 | Oppo | RAN5#95 (May-22) | R5-211806 R5-213998 R5-221818 | 38.905: R5-212929 38.522: Editor’s Note: This clause is incomplete for PSFCH and PSBCH measurement. The following aspects are either missing or not yet determined: - Measurement period of PSFCH and PSBCH is FFS. | 1 | 100% | 100% |  |  | 100%
101 | Y | 38.521-1 Tx | 6.5E.2.2.1D | Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.2.1 | Oppo | RAN5#99 (May-23) | R5-210423 R5-217609 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
102 | Y | 38.521-1 Tx | 6.5E.2.2.2 | Spectrum emission mask for V2X / con-current operation | TS 38.101-1 cl 6,5E.2.2.2 | Oppo | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
103 |  | 38.521-1 Tx | 6.5E.2.3 | Additional Spectrum emission mask for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.2.3.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.2.3 | Oppo | RAN5#97 (Nov-22) | R5-210424； R5-241002 |  | 1 | 100% | 100% |  |  | 100%
104 | Y | 38.521-1 Tx | 6.5E.2.3.1 | Additional Spectrum emission mask for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 | Oppo | RAN5#99 (May-23) | R5-210424 R5-213999 R5-217609 R5-221818； R5-241002 | Editor’s Note: - Test config table is FFS | 1 | 100% | 100% |  |  | 100%
105 | Y | 38.521-1 Tx | 6.5E.2.3.1D | Additional Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 | Oppo | RAN5#99 (May-23) | R5-210425 R5-217609； R5-241002 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 100% | 100% |  |  | 100%
106 |  | 38.521-1 Tx | 6.5E.2.4 | Adjacent channel leakage ratio for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) | R5-210426 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.2.4.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.2.4 | Oppo | RAN5#97 (Nov-22) | R5-210426 |  | 1 | 100% | 100% |  |  | 100%
107 | Y | 38.521-1 Tx | 6.5E.2.4.1 | Adjacent channel leakage ratio for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.2.4.1 | Oppo | RAN5#95 (May-22) | R5-210426 R5-214000 R5-217609 R5-221818 | 38.905: R5-212929 38.522: Editor’s Note: . - Ceasurement period of PSFCH and PSBCH is FFS. | 1 | 100% | 100% |  |  | 100%
108 | Y | 38.521-1 Tx | 6.5E.2.4.1D | Adjacent channel leakage ratio for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.2.4.1 | Oppo | RAN5#99 (May-23) | R5-210427 R5-217609 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
109 | Y | 38.521-1 Tx | 6.5E.2.4.2 | Adjacent channel leakage ratio for V2X / con-current operation | TS 38.101-1 cl 6,5E.2.4.2 | Oppo | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
110 |  | 38.521-1 Tx | 6.5E.3 | Spurious emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
111 |  | 38.521-1 Tx | 6.5E.3.1 | General spurious emissions for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.3.1.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.3.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
112 | Y | 38.521-1 Tx | 6.5E.3.1.1 | General spurious emissions for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.3.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
113 | Y | 38.521-1 Tx | 6.5E.3.1.1D | General spurious emissions for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
114 |  | 38.521-1 Tx | 6.5E.3.2 | Spurious emissions for UE co-existence for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.3.2.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.3.2, 6.5E.3.3 | Oppo | RAN5#97 (Nov-22) | R5-210428 |  | 1 | 100% | 100% |  |  | 100%
115 | Y | 38.521-1 Tx | 6.5E.3.2.1 | Spurious emissions for UE co-existence / non-concurrent operation | TS 38.101-1 cl 6,5E.3.2 | Oppo | RAN5#99 (May-23) | R5-210428 R5-214001 R5-217609 R5-221818 | Editor’s Note: - Test config table is FFS | 1 | 80% | 80% |  |  | 80%
116 | Y | 38.521-1 Tx | 6.5E.3.2.1D | Spurious emissions for UE co-existence / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.2 | Oppo | RAN5#99 (May-23) | R5-210429 R5-217609 R5-230558 | Editor’s Note: - Test config table is FFS - Uplink RMC is TBD in RAN4 - Connection diagram is TBD - Preconfiguration is TBD in 38.508-1 - Test state and generic procedure are TBD in 38.508-1 | 1 | 50% | 50% |  |  | 50%
117 | Y | 38.521-1 Tx | 6.5E.3.2.2 | Spurious emissions for UE co-existence / con-current operation | TS 38.101-1 cl 6,5E.3.3 | Oppo | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
118 |  | 38.521-1 Tx | 6.5E.3.3 | Additional spurious emissions requirements for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Tx | 6.5E.3.3.0 | Minimum conformance requirements | TS 38.101-1 cl 6,5E.3.4.1, 6.5E.3.4.2, 6.5E.3.4.3 | Oppo | RAN5#97 (Nov-22) | R5-214002； R5-241003 |  | 1 | 100% | 100% |  |  | 100%
119 | Y | 38.521-1 Tx | 6.5E.3.3.1 | Additional spurious emissions requirements for V2X / non-concurrent operation | TS 38.101-1 cl 6,5E.3.4.1, 6.5E.3.4.2, 6.5E.3.4.3 | Oppo | RAN5#99 (May-23) | R5-214002 R5-217609 R5-221818； R5-241003 | Editor’s Note: - Test config table is FFS | 1 | 100% | 100% |  |  | 100%
120 | Y | 38.521-1 Tx | 6.5E.3.3.1D | Additional spurious emissions requirements for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6,5E.3.4.1, 6.5E.3.4.2, 6.5E.3.4.3 | Oppo | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
121 |  | 38.521-1 Tx | 6.5E.4 | Transmit intermodulation for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.5E.4.0 | Minimum conformance requirements | TS 38.101-1 cl 6.5E.4 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
122 | Y | 38.521-1 Tx | 6.5E.4.1 | Transmit intermodulation for V2X / non-concurrent operation | TS 38.101-1 cl 6.5E.4.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
123 | Y | 38.521-1 Tx | 6.5E.4.1D | Transmit intermodulation for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.5E.4.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
124 | Y | 38.521-1 Tx | 6.5E.4.2 | Transmit intermodulation for V2X / con-current operation | TS 38.101-1 cl 6.5E.4.2 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.6E | Time alignment error for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
125 | Y | 38.521-1 Tx | 6.6E.1D | Time alignment error for V2X / non-concurrent operation / SL-MIMO | TS 38.101-1 cl 6.6E |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
126 |  | 38.521-1 Rx | 7.3E | Reference sensitivity for V2X | Sub-clause heading |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% | 100% |  |  | 100%
127 |  | 38.521-1 Rx | 7.3E.1 | Minimum conformance requirements | TS 38.101-1 cl 7.3E.1 | Huawei, Hisiicon | RAN5#90-e (Feb-21) |  |  | 0.1 | 100% | 100% |  |  | 100%
128 | Y | 38.521-1 Rx | 7.3E.2 | Reference sensitivity for V2X / non-concurrent operation | TS 38.101-1 cl 7.3E.2 | Huawei, Hisiicon | RAN5#99 (May-23) | R5-206765 R5-217609 R5-221818， R5-233211 | Editor’s Note: The following aspects are not yet determined: - TP analysis is FFS | 0 | 90% | 90% |  |  | 90%
129 | Y | 38.521-1 Rx | 7.3E.3 | Reference sensitivity for V2X / con-current operation | TS 38.101-1 cl 7.3E.3 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
130 |  | 38.521-1 Rx | 7.4E | Maximum input level for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
|  | 38.521-1 Rx | 7.4E.0 | Minimum conformance requirements | TS 38.101-1 cl 7.4E | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
131 | Y | 38.521-1 Rx | 7.4E.1 | Maximum input level for V2X / non-concurrent operation | TS 38.101-1 cl 7.4E.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
132 | Y | 38.521-1 Rx | 7.4E.2 | Maximum input level for V2X / con-current operation | z | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
133 |  | 38.521-1 Rx | 7.5E | Adjacent channel selectivity for V2X | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
|  | 38.521-1 Rx | 7.5E.0 | Minimum conformance requirements | TS 38.101-1 cl 7.5E | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
134 | Y | 38.521-1 Rx | 7.5E.1 | Adjacent channel selectivity for V2X / non-concurrent operation | TS 38.101-1 cl 7.5E.1 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  | 0%
135 | Y | 38.521-1 Rx | 7.5E.2 | Adjacent channel selectivity for V2X / con-current operation | TS 38.101-1 cl 7.5E.2 | Huawei, Hisiicon | RAN5#99 (May-23) |  |  | 0 | 0% | 0% |  |  | 0%
136 |  | 38.521-1 Rx | 7.6E | Blocking characteristics for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-220084 |  | 0 | 100% | 100% |  |  | 100%
137 |  | 38.521-1 Rx | 7.6E.1 | General | TS 38.101-1 cl 7.6E.1 | CAICT | RAN5#95 (May-22) | R5-220084 |  | 0.1 | 100% | 100% |  |  | 100%
138 |  | 38.521-1 Rx | 7.6E.2 | In-band blocking for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-220084 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.6E.2.0 | Minimum conformance requirements | TS 38.101-1 cl 7.6E.2 | CAICT | RAN5#95 (May-22) | R5-220084，R5-233207 |  | 1 | 100% | 100% |  |  | 100%
139 | Y | 38.521-1 Rx | 7.6E.2.1 | In-band blocking for V2X / non-concurrent operation | TS 38.101-1 cl 7.6E.2.1 | CAICT | RAN5#99 (May-23) | R5-220084 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
140 | Y | 38.521-1 Rx | 7.6E.2.2 | In-band blocking for V2X / con-current operation | TS 38.101-1 cl 7.6E.2.2 | CAICT | RAN5#99 (May-23) | R5-220084 | Editor's note: Only sub-clause heading is added | 0 | 5% | 5% |  |  | 5%
141 |  | 38.521-1 Rx | 7.6E.3 | Out-of-band blocking for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-220084 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.6E.3.0 | Minimum conformance requirements | TS 38.101-1 cl 7.6E.3 | CAICT | RAN5#95 (May-22) | R5-220084， R5-233207 |  | 1 | 100% | 100% |  |  | 100%
142 | Y | 38.521-1 Rx | 7.6E.3.1 | Out-of-band blocking for V2X / non-concurrent operation | TS 38.101-1 cl 7.6E.3.1 | CAICT | RAN5#99 (May-23) | R5-220084 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
143 | Y | 38.521-1 Rx | 7.6E.3.2 | Out-of-band blocking for V2X / con-current operation | TS 38.101-1 cl 7.6E.3.2 | CAICT | RAN5#99 (May-23) | R5-220084 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
144 |  | 38.521-1 Rx | 7.7E | Spurious response for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-221820 |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-1 Rx | 7.7E.0 | Minimum conformance requirements | TS 38.101-1 cl 7.7E | CAICT | RAN5#95 (May-22) | R5-221820, R5-233212 |  | 1 | 100% | 100% |  |  | 100%
145 | Y | 38.521-1 Rx | 7.7E.1 | Spurious response for V2X / non-concurrent operation | TS 38.101-1 cl 7.7E.1 | CAICT | RAN5#99 (May-23) | R5-221821 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
146 | Y | 38.521-1 Rx | 7.7E.2 | Spurious response for V2X / con-current operation | TS 38.101-1 cl 7.7E.2 | CAICT | RAN5#99 (May-23) | R5-221822 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
147 |  | 38.521-1 Rx | 7.8E | Intermodulation characteristics for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-221823 |  | 0 | 100% | 100% |  |  | 100%
470 |  | 38.521-1 Rx | 7.8E.1 | General | TS 38.101-1 cl 7.8E.1 | CAICT | RAN5#95 (May-22) | R5-221824 |  | 0.1 | 100% | 100% |  |  | 100%
149 |  | 38.521-1 Rx | 7.8E.2 | Wide band Intermodulation for V2X | Sub-clause heading |  | RAN5#95 (May-22) | R5-221825 |  | 0 | 100% | 100% |  |  | 100%
471 |  | 38.521-1 Rx | 7.8E.2.0 | Minimum conformance requirements | TS 38.101-1 cl 7.8E.2 | CAICT | RAN5#95 (May-22) | R5-221826 |  | 1 | 100% | 100% |  |  | 100%
150 | Y | 38.521-1 Rx | 7.8E.2.1 | Wide band Intermodulation for V2X / non-concurrent operation | TS 38.101-1 cl 7.8E.2.1 | CAICT | RAN5#99 (May-23) | R5-221827 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
151 | Y | 38.521-1 Rx | 7.8E.2.2 | Wide band Intermodulation for V2X / con-current operation | TS 38.101-1 cl 7.8E.2.2 | CAICT | RAN5#99 (May-23) | R5-221828 | Editor's note: Only sub-clause heading is added | 1 | 5% | 5% |  |  | 5%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
229 |  | 38.521-3 | 2 | Reference | Define References made in TS | Bureau Veritas | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
230 |  | 38.521-3 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Bureau Veritas | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
231 |  | 38.521-3 | 4 | General | define categories of test requirements | Bureau Veritas | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
232 |  | 38.521-3 | 5 | Operating bands and Channel arrangement | define the frequency bands and channel arragement | Bureau Veritas | RAN5#93 (Nov-21) | R5-217610 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
233 |  | 38.521-3 | Annex A | measurement channels | define mesurement channels | Bureau Veritas | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
234 |  | 38.521-3 | Annex B | Propagation conditions | Define propagation conditions | Bureau Veritas | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
235 |  | 38.521-3 | Annex C | Downlink physical channels | Define downlink physical channels |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
236 |  | 38.521-3 | Annex D | Characteristics of the interfering signal | Define characteristics of the interfering signal |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
237 |  | 38.521-3 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
238 |  | 38.521-3 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
239 |  | 38.521-3 | Annex G | Uplink Physical Channels | Define uplink physical channels |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
240 |  | 38.521-3 | Annex H | Statistical Testing |  |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
241 |  | 38.521-3 Tx | 6.2E | Transmitter power for V2X in FR1 | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
242 |  | 38.521-3 Tx | 6.2E.1 | UE maximum output power for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.2E.1.0 | Minimum conformance requirements | TS38.101-3 cl 6,2E.1 | Huawei | RAN5#93 (Nov-21) | R5-217382 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
243 |  | 38.521-3 Tx | 6.2E.1.1 | UE maximum output power for Intra-band contiguous V2X | TS38.101-3 cl 6,2E.1.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-217382 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
244 |  | 38.521-3 Tx | 6.2E.1.2 | UE maximum output power for Intra-band non-contuous V2X | TS38.101-3 cl 6,2E.1.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-217383 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
245 | Y | 38.521-3 Tx | 6.2E.1.3.1 | UE maximum output power for Inter-band V2X with E-UTRA Uu and NR Sidelink | TS38.101-3 cl 6,2E.1.3.1 | Huawei | RAN5#99 (May-23) | R5-217384 | Editor's note: - Connection diagram is FFS - Generic test procedure is FFS - Message exception is FFS - Test requirements are FFS | 1 | 50% |  | 50% |  |  |  |  | 50%
454 | Y | 38.521-3 Tx | 6.2E.1.3.2 | UE maximum output power for Inter-band V2X with NR Uu and E-UTRA V2X | TS38.101-3 cl 6,2E.1.3.2 | Huawei | RAN5#99 (May-23) | R5-217385 | Editor's note: - Connection diagram is FFS - Generic test procedure is FFS - Message exception is FFS - Test requirements are FFS | 1 | 50% |  | 50% |  |  |  |  | 50%
246 |  | 38.521-3 Tx | 6.2E.2 | UE maximum output power reduction for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.2E.2.0 | Minimum conformance requirements | TS 38.101-3 cl 6.2E.2 | Huawei | RAN5#93 (Nov-21) | R5-217386 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
247 |  | 38.521-3 Tx | 6.2E.2.1 | UE maximum output power reduction for Intra-band V2X | TS 38.101-3 cl 6.2E.2.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-217386 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
248 | Y | 38.521-3 Tx | 6.2E.2.2.1 | UE maximum output power reduction for Inter-band V2X with E-UTRA Uu and NR Sidelink | TS 38.101-3 cl 6,2E.2.2.1 | Huawei | RAN5#99 (May-23) | R5-217387 | Editor's note: - Connection diagram is FFS - Generic test procedure is FFS - Message exception is FFS - Test requirements are FFS | 1 | 50% |  | 50% |  |  |  |  | 50%
455 | Y | 38.521-3 Tx | 6.2E.2.2.2 | UE maximum output power reduction for Inter-band V2X with NR Uu and E-UTRA V2X | TS 38.101-3 cl 6,2E.2.2.2 | Huawei | RAN5#99 (May-23) | R5-217388 | Editor's note: - Connection diagram is FFS - Generic test procedure is FFS - Message exception is FFS - Test requirements are FFS | 1 | 50% |  | 50% |  |  |  |  | 50%
249 |  | 38.521-3 Tx | 6.2E.3 | UE additional maximum output power reduction for V2X | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Tx | 6.2E.3.0 | Minimum conformance requirements | TS 38.101-3 cl 6,2E.3 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
250 |  | 38.521-3 Tx | 6.2E.3.1 | UE additional maximum output power reduction for Intra-band V2X | TS 38.101-3 cl 6,2E.3.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
251 |  | 38.521-3 Tx | 6.2E.3.2 | UE additional maximum output power reduction for Inter-band V2X | New sub-clause header | Huawei | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.2E.3.2.1 | UE additional maximum output power reduction for Inter-band V2X with E-UTRA Uu and NR Sidelink | TS 38.101-3 cl 6,2E.3.2 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.2E.3.2.2 | UE additional maximum output power reduction for Inter-band V2X with NR Uu and E-UTRA V2X | TS 38.101-3 cl 6,2E.3.2 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
252 |  | 38.521-3 Tx | 6.2E.4 | Configured transmitted power for V2X | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Tx | 6.2E.4.0 | Minimum conformance requirements | TS 38.101-3 cl 6,2E.4 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
253 |  | 38.521-3 Tx | 6.2E.4.1 | UE configured output power for Intra-band V2X | TS 38.101-3 cl 6,2E.4.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
254 |  | 38.521-3 Tx | 6.2E.4.2 | UE configured output power for Inter-band V2X | New sub-clause header | Huawei | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.2E.4.2.1 | UE configured output power for Inter-band V2X with E-UTRA Uu and NR Sidelink | TS 38.101-3 cl 6,2E.4.2 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.2E.4.2.2 | UE configured output power for Inter-band V2X with NR Uu and E-UTRA V2X | TS 38.101-3 cl 6,2E.4.2 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
456 |  | 38.521-3 Tx | 6.3E | Output power dynamics for V2X | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.3E.0 | Minimum conformance requirements | TS 38.101-3 cl 6,3E | Huawei | RAN5#93 (Nov-21) | R5-217389 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
457 |  | 38.521-3 Tx | 6.3E.1 | Output power dynamics for intra-band V2X operation | TS 38.101-3 cl 6,3E.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-217389 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
458 |  | 38.521-3 Tx | 6.3E.2 | Output power dynamics for inter-band V2X operation | TS 38.101-3 cl 6,3E.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#93 (Nov-21) | R5-217389 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
472 |  | 38.521-3 Tx | 6.4E | Transmit signal quality for V2X operation in FR1 | New sub-clause header |  | RAN5#95 (May-22) | R5-220539 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
255 |  | 38.521-3 Tx | 6.4E.1 | Frequency error for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-220539 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.4E.1.0 | Minimum conformance requirements | TS 38.101-3 cl 6,4E.1 | TTA | RAN5#95 (May-22) | R5-220539 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
256 |  | 38.521-3 Tx | 6.4E.1.1 | Frequency error for Intra-band V2X | TS 38.101-3 cl 6,4E.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-220539 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
257 |  | 38.521-3 Tx | 6.4E.1.2 | Frequency error for Inter-band V2X | TS 38.101-3 cl 6,4E.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-220539 R5-222194 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
258 |  | 38.521-3 Tx | 6.4E.2 | Transmit modulation quality for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-220540 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
259 |  | 38.521-3 Tx | 6.4E.2.1 | Error Vector Magnitude for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-220540 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
473 |  | 38.521-3 Tx | 6.4E.2.1.0 | Minimum conformance requirements | TS 38.101-3 cl 6,4E.2.1 |  | RAN5#95 (May-22) | R5-220540 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
260 |  | 38.521-3 Tx | 6.4E.2.1.1 | Error Vector Magnitude for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-220540 R5-222194 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
261 |  | 38.521-3 Tx | 6.4E.2.1.2 | Error Vector Magnitude for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-220540 R5-222194 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
262 |  | 38.521-3 Tx | 6.4E.2.2 | Carrier leakage for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-223703 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
263 |  | 38.521-3 Tx | 6.4E.2.2.1 | Carrier leakage for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei, Hisilicon | RAN5#95 (May-22) | R5-223703 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
264 |  | 38.521-3 Tx | 6.4E.2.2.2 | Carrier leakage for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
265 |  | 38.521-3 Tx | 6.4E.2.3 | In-band emissions for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-222884 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
266 |  | 38.521-3 Tx | 6.4E.2.3.1 | In-band emissions for intra-band V2X | TS 38.101-3 cl 6,4E.2.1.3 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222884 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
267 |  | 38.521-3 Tx | 6.4E.2.3.2 | In-band emissions for inter-band V2X | TS 38.101-3 cl 6,4E.2.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
268 |  | 38.521-3 Tx | 6.5E.1 | Occupied bandwidth for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-222421 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.1.0 | Minimum conformance requirements | TS 38.101-3 cl 6,5E.1 | TTA | RAN5#95 (May-22) | R5-222421 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
269 |  | 38.521-3 Tx | 6.5E.1.1 | Occupied bandwidth for intra-band V2X | TS 38.101-3 cl 6,5E.1.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-222421 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
270 |  | 38.521-3 Tx | 6.5E.1.2 | Occupied bandwidth for inter-band V2X | TS 38.101-3 cl 6,5E.1.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-222421 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
271 |  | 38.521-3 Tx | 6.5E.2 | Out of band emission for V2X | New sub-clause header |  | RAN5#95 (May-22) | R5-222422 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.2.0 | Minimum conformance requirements | TS 38.101-3 cl 6,5E.2 | TTA | RAN5#95 (May-22) | R5-222422 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.2.1 | Out of band emission for intra-band V2X | TS 38.101-3 cl 6,5E.2.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-222422 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.2.2 | Out of band emission for inter-band V2X | TS 38.101-3 cl 6,5E.2.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#95 (May-22) | R5-222422 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
281 |  | 38.521-3 Tx | 6.5E.3 | Spurious emissions for V2X | New sub-clause header | TTA | RAN5#99 (May-23) | R5-230659 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
282 |  | 38.521-3 Tx | 6.5E.3.1 | General spurious emissions for V2X | New sub-clause header | TTA | RAN5#99 (May-23) | R5-230659 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.3.1.0 | Minimum conformance requirements | TS 38.101-3 cl 6,5E.3.1.1, 6.5E.3.2.1 | TTA | RAN5#99 (May-23) | R5-230659 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
283 |  | 38.521-3 Tx | 6.5E.3.1.1 | General spurious emissions for intra-band V2X | TS 38.101-3 cl 6,5E.3.1.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#99 (May-23) | R5-230659 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
284 |  | 38.521-3 Tx | 6.5E.3.1.2 | General spurious emissions for inter-band V2X | TS 38.101-3 cl 6,5E.3.1.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#99 (May-23) | R5-230659 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
285 |  | 38.521-3 Tx | 6.5E.3.2 | Spurious emissions band UE co-existence for V2X | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Tx | 6.5E.3.2.0 | Minimum conformance requirements | TS 38.101-3 cl 6,5E.3.1.2, 6.5E.3.2.2 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
286 |  | 38.521-3 Tx | 6.5E.3.2.1 | Spurious emissions band UE co-existence for intra-band V2X | TS 38.101-3 cl 6,5E.3.2.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
287 |  | 38.521-3 Tx | 6.5E.3.2.2 | Spurious emissions band UE co-existence for inter-band V2X | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.5E.3.2.2.1 | Spurious emissions band UE co-existence for inter-band V2X with E-UTRA Uu and NR Sidelink | TS 38.101-3 cl 6,5E.3.2.2 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Tx | 6.5E.3.2.2.2 | Spurious emissions band UE co-existence for inter-band V2X with NR Uu and E-UTRA V2X | TS 38.101-3 cl 6,5E.3.2.2 |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
288 |  | 38.521-3 Tx | 6.5E.4 | Transmit intermodulation for V2X | New sub-clause header | TTA | RAN5#99 (May-23) | R5-232700 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Tx | 6.5E.4.0 | Minimum conformance requirements | TS 38.101-3 cl 6.5E.4 | TTA | RAN5#99 (May-23) | R5-232701 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
289 |  | 38.521-3 Tx | 6.5E.4.1 | Transmit intermodulation for intra-band V2X | TS 38.101-3 cl 6.5E.4.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#99 (May-23) | R5-232702 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
290 |  | 38.521-3 Tx | 6.5E.4.2 | Transmit intermodulation for inter-band V2X | TS 38.101-3 cl 6.5E.4.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | TTA | RAN5#99 (May-23) | R5-232703 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
291 |  | 38.521-3 Rx | 7.3E | Reference sensitivity for V2X operation in FR1 | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
292 |  | 38.521-3 Rx | 7.3E.1 | General | TS 38.101-3 cl 7.3E.1 | Huawei | RAN5#99 (May-23) |  |  | 0.1 | 0% |  | 0% |  |  |  |  | 0%
293 |  | 38.521-3 Rx | 7.3E.2 | Reference sensitivity for V2X | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Rx | 7.3E.2.0 | Minimum conformance requirements | TS 38.101-3 cl 7.3E.2 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
294 |  | 38.521-3 Rx | 7.3E.2.1 | Reference sensitivity for intra-band contiguous V2X | TS 38.101-3 cl 7.3E.2.1 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
295 |  | 38.521-3 Rx | 7.3E.2.2 | Reference sensitivity for intra-band non-contiguous V2X | TS 38.101-3 cl 7.3E.2.2 No exception requirement. Testing could refer to 36.521-1 and 38.521-1 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
296 |  | 38.521-3 Rx | 7.3E.2.3 | Reference sensitivity for Inter-band V2X | New sub-clause header | Huawei | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Rx | 7.3E.2.3.1 | Reference sensitivity for Inter-band V2X with E-UTRA Uu and NR Sidelink | TS 38.101-3 cl 7.3E.2.3 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.521-3 Rx | 7.3E.2.3.2 | Reference sensitivity for Inter-band V2X with NR Uu and E-UTRA V2X | TS 38.101-3 cl 7.3E.2.3 | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
297 |  | 38.521-3 Rx | 7.4E | Maximum input level for V2X operation in FR1 | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Rx | 7.4E.0 | Minimum conformance requirements | TS 38.101-3 cl 7.4E | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
298 |  | 38.521-3 Rx | 7.4E.1 | Maximum input level for V2X operation | TS 38.101-3 cl 7.4E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
300 |  | 38.521-3 Rx | 7.5E | Adjacent channel selectivity for V2X operation in FR1 | New sub-clause header |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
|  | 38.521-3 Rx | 7.5E.0 | Minimum conformance requirements | TS 38.101-3 cl 7.5E | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
301 |  | 38.521-3 Rx | 7.5E.1 | Adjacent channel selectivity for V2X operation | TS 38.101-3 cl 7.5E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | Huawei | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
303 |  | 38.521-3 Rx | 7.6E | Blocking characteristics for V2X in FR1 | New sub-clause header | CAICT | RAN5#95 (May-22) | R5-220087 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Rx | 7.6E.0 | Minimum conformance requirements | TS 38.101-3 cl 7.6E | CAICT | RAN5#95 (May-22) | R5-220087 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Rx | 7.6E.1 | In-band blocking for V2X operation | TS 38.101-3 cl 7.6E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | CAICT | RAN5#95 (May-22) | R5-220087 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Rx | 7.6E.2 | Out-of-band blocking for V2X operation | TS 38.101-3 cl 7.6E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | CAICT | RAN5#95 (May-22) | R5-220087 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
310 |  | 38.521-3 Rx | 7.7E | Spurious response for V2X in FR1 | New sub-clause header | CAICT | RAN5#95 (May-22) | R5-220088 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Rx | 7.7E.0 | Minimum conformance requirements | TS 38.101-3 cl 7.7E | CAICT | RAN5#95 (May-22) | R5-220088 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
311 |  | 38.521-3 Rx | 7.7E.1 | Spurious response for V2X operation | TS 38.101-3 cl 7.7E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | CAICT | RAN5#95 (May-22) | R5-220088 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
313 |  | 38.521-3 Rx | 7.8E | Intermodulation characteristics for V2X operation in FR1 | New sub-clause header | CAICT | RAN5#95 (May-22) | R5-220089 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
314 |  | 38.521-3 Rx | 7.8E.1 | Wide band Intermodulation for V2X | New sub-clause header | CAICT | RAN5#95 (May-22) | R5-220089 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.521-3 Rx | 7.8E.1.0 | Minimum conformance requirements | TS 38.101-3 cl 7.8E | CAICT | RAN5#95 (May-22) | R5-220089 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
315 |  | 38.521-3 Rx | 7.8E.1.1 | Wide band Intermodulation for V2X operation | TS 38.101-3 cl 7.8E No exception requirement. Testing could refer to 36.521-1 and 38.521-1 Apply to intra-band and inter-band V2X | CAICT | RAN5#95 (May-22) | R5-220089 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
TS 38.521-4: Demod/CSI reporting test cases
484 |  | 38.521-4 | 2 | References | To add reference for NR sidelink demod tests | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222627 |  | 0.1 | 100% |  | 100% |  |  |  |  | 100%
433 |  | 38.521-4 | 11 | V2X requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-224502 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
434 |  | 38.521-4 | 11.1 | Demodulation performance requirements (Conducted requirements) | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
435 |  | 38.521-4 | 11.1.1 | General | To add applicability for V2X demod requirements | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222619 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
436 |  | 38.521-4 | 11.1.2 | PSSCH demodulation requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-222619 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
488 |  | 38.521-4 | 11.1.2.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
489 |  | 38.521-4 | 11.1.2.1.1 | 2Rx FR1 PSSCH performance | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
437 | Y | 38.521-4 | 11.1.2.1.1_1 | 2Rx FR1 PSSCH performance - single active PSSCH link | Test Purpose(s): to verify the PSSCH for V2X demodulation performance with a single active PSSCH link | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222619 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
438 |  | 38.521-4 | 11.1.3 | PSCCH demodulation requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-222620 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
490 |  | 38.521-4 | 11.1.3.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
491 |  | 38.521-4 | 11.1.3.1.1 | 2Rx FR1 PSCCH performance | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
439 | Y | 38.521-4 | 11.1.3.1.1_1 | 2Rx FR1 PSCCH performance - single active PSSCH link | Test Purpose(s): to verify the PSCCH for V2X demodulation performance with a single active PSSCH link | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222620 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
440 |  | 38.521-4 | 11.1.4 | PSBCH demodulation requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-222621 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
490 |  | 38.521-4 | 11.1.4.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
441 |  | 38.521-4 | 11.1.4.1.1 | 2Rx FR1 PSBCH performance | Test Purpose(s): to verify the PSBCH demodulation performance with a single active link | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222621 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
442 |  | 38.521-4 | 11.1.5 | PSFCH demodulation requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-222622 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
492 |  | 38.521-4 | 11.1.5.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
493 |  | 38.521-4 | 11.1.5.1.1 | 2Rx FR1 PSFCH performance | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
443 | Y | 38.521-4 | 11.1.5.1.1_1 | 2Rx FR1 PSCCH performance - single active PSSCH link | Test Purpose(s): to verify NACK missed detection requirements | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222622 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
444 |  | 38.521-4 | 11.1.6 | Power imbalance performance with two links | New sub-clause header |  | RAN5#95 (May-22) | R5-222623 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
494 |  | 38.521-4 | 11.1.6.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
495 |  | 38.521-4 | 11.1.6.1.1 | 2Rx FR1 Power imbalance performance | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
445 | Y | 38.521-4 | 11.1.6.1.1_1 | 2Rx FR1 Power imbalance performance - two active PSSCH link | Test Purpose(s): to check the demodulation performance when receiving PSSCH transmissions from two Sidelink UEs with power imbalance in one slot. | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222623 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
446 |  | 38.521-4 | 11.1.7 | HARQ buffer soft combining | New sub-clause header |  | RAN5#95 (May-22) | R5-222624 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
496 |  | 38.521-4 | 11.1.7.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
497 |  | 38.521-4 | 11.1.7.1.1 | 2Rx FR1 Power imbalance performance | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
447 | Y | 38.521-4 | 11.1.7.1.1_1 | 2Rx FR1 HARQ buffer soft combining performance - maximum number of HARQ processes | Test Purpose(s): to verify the maximum number of HARQ processes per TTI supported by the V2X UE | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222624 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
448 |  | 38.521-4 | 11.1.8 | PSCCH decoding capability | New sub-clause header |  | RAN5#95 (May-22) | R5-222625 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
498 |  | 38.521-4 | 11.1.8.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
499 |  | 38.521-4 | 11.1.8.1.1 | 2Rx FR1 PSCCH decoding capability | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
449 | Y | 38.521-4 | 11.1.8.1.1_1 | 2Rx FR1 PSCCH decoding capability - maximum number of received PSCCHs | Test Purpose(s): to verify the maximum number of received PSCCHs per TTI supported by the V2X UE | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222625 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
450 |  | 38.521-4 | 11.1.9 | PSFCH decoding capability | New sub-clause header |  | RAN5#95 (May-22) | R5-223704 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
500 |  | 38.521-4 | 11.1.9.1 | 2Rx requirements | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
501 |  | 38.521-4 | 11.1.9.1.1 | 2Rx FR1 PSFCH decoding capability | New sub-clause header |  | RAN5#96 (Aug-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
451 | Y | 38.521-4 | 11.1.9.1.1_1 | 2Rx FR1 PSFCH decoding capability - maximum number of received PSFCHs | Test Purpose(s): to verify the maximum number of PSFCHs received by UE per slot in group cast scenario by using ACK/NACK feedback mode | Huawei, Hisilicon | RAN5#95 (May-22) | R5-223704 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
485 |  | 38.521-4 | Annex.A.6 | Sidelink reference measurement channels | To add NR SL RMCs for NR SL demod test | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222628 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
486 |  | 38.521-4 | Annex.F.1 | Measurement uncertainty and test tolerance for sidelink demod tests | To add MU & TT for NR SL demod test | Huawei, Hisilicon | RAN5#95 (May-22) | R5-222629 R5-224503 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
487 |  | 38.521-4 | Annex.G.5 | Statistical Testing of NR sidelink Performance Requirements | To add test methods for NR sidelink Demod test | Huawei, Hisilicon | RAN5#99 (May-23) | R5-222630 | Editor's note: Miinimum test time for NR SL demod testig is still missing | 1 | 90% |  | 90% |  |  |  |  | 90%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
152 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 | Huawei, HiSilicon, Bureau Veritas, LG Electronics | RAN5#97 (Nov-22) | R5-211610 R5-212932 R5-214006 R5-220787 R5-241004 R5-243144 |  | 1 | 30% (+20%) | 30% (+20%) |  |  | 30%
153 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-3. |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  | 0%
317 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. | Huawei, HiSilicon | RAN5#95 (May-22) | R5-222631 R5-224504 |  | 1 | 100% | 100% |  |  | 100%
318 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | Huawei, HiSilicon | RAN5#95 (May-22) | R5-222632 |  | 1 | 100% | 100% |  |  | 100%
TS 38.533: RRM test cases
474 |  | 38.533 | 3A.4.1 | NR operating bands in FR1 | To add Band group definition for NR sidelink bands in 38.533 Normative Ref： TS 38.133 cl.3A.4.1 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220726 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
321 |  | 38.533 | 9 | NR sidelink | New sub-clause header |  | RAN5#95 (May-22) | R5-220727 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
322 |  | 38.533 | 9.1 | NR sidelink in FR1 | New sub-clause header |  | RAN5#95 (May-22) | R5-220727 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
323 |  | 38.533 | 9.1.1 | UE transmit timing | New sub-clause header |  | RAN5#95 (May-22) | R5-220727 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
324 |  | 38.533 | 9.1.1.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220727 R5-224505 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
325 |  | 38.533 | 9.1.1.0.1 | Requirements for GNSS as synchronization reference source | To add NR sidelink transmit timing error limit requirements when GNSS is used as sync reference Normative Ref: TS 38.133 cl.12.2.2, 12.8 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220727 |  | 0.2 | 100% |  | 100% |  |  |  |  | 100%
326 |  | 38.533 | 9.1.1.0.2 | Requirements for SyncRef UE as synchronization reference source | To add NR sidelink transmit timing error limit requirements when SyncRef UE is used as sync reference Normative Ref: TS 38.133 cl.12.2.5 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220727 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
327 |  | 38.533 | 9.1.1.0.3 | Requirements for FR1 NR Cell as synchronization reference source | To add NR sidelink transmit timing error limit requirements when FR1 NR Cell is used as sync reference Normative Ref: TS 38.133 cl.12.2.3 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220727 R5-222633 |  | 0.2 | 100% |  | 100% |  |  |  |  | 100%
328 | Y | 38.533 | 9.1.1.1 | NR SA FR1 UE transmit timing accuracy for GNSS as synchronization reference source | Test Purpose(s): to verify the UE timing requirements when the GNSS is used as timing reference Normative Ref: TS 38.133 A.9.1.1.1 Minimum Conformance Ref: 9.1.1.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220728 R5-224506 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
329 | Y | 38.533 | 9.1.1.2 | NR SA FR1 UE transmit timing accuracy for SyncRef UE as synchronization reference source | Test Purpose(s): to verify the UE timing requirements when the SyncRef UE is used as timing reference Normative Ref: TS 38.133 A.9.1.1.2 Minimum Conformance Ref: 9.1.1.0.2 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220729 R5-224507 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
330 | Y | 38.533 | 9.1.1.3 | NR SA FR1 UE transmit timing accuracy for FR1 NR cell as synchronization reference source | Test Purpose(s): to verify the UE timing requirements when the FR1 NR Cell is used as timing reference Normative Ref: TS 38.133 A.9.1.1.3 Minimum Conformance Ref: 9.1.1.0.3 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220730 R5-224508 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
331 |  | 38.533 | 9.1.2 | Initiation/cease of S-SSB transmission | New sub-clause header |  | RAN5#95 (May-22) | R5-220731 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
332 |  | 38.533 | 9.1.2.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220731 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
333 |  | 38.533 | 9.1.2.0.1 | Requirements for FR1 NR cell as synchronization reference source | To add NR sidelink Initiation/Cease of S-SSB Transmissions related requirements when FR1 NR Cell is used as sync reference Normative Ref: TS 38.133 cl.12.3.1.1 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220731 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
334 |  | 38.533 | 9.1.2.0.2 | Requirements for SyncRef UE as synchronization reference source | To add NR sidelink Initiation/Cease of S-SSB Transmissions related requirements when SyncRef UE is used as sync reference Normative Ref: TS 38.133 cl.12.3.1.4 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220731 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
335 | Y | 38.533 | 9.1.2.1 | NR SA FR1 initiation/cease of S-SSB transmission for FR1 NR cell as synchronization reference source | Test Purpose(s): to verify that the NR sidelink UE meets the requirements related to the maximum evaluation time allowed to initiate and cease S-SSB transmissions requirements, when the reference timing used for sidelink transmissions is a NR serving cell in FR1 on a non sidelink carrier. Normative Ref: TS 38.133 A.9.1.2.1 Minimum Conformance Ref: 9.1.2.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221821 R5-224509 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
336 | Y | 38.533 | 9.1.2.2 | NR SA FR1 initiation/cease of S-SSB transmission for SyncRef UE as synchronization reference source | Test Purpose(s): to verify that the NR sidelink UE meets the requirements related to the maximum evaluation time allowed to initiate and cease S-SSB transmissions requirements, when the reference timing used for sidelink transmissions is a SyncRef UE. Normative Ref: TS 38.133 A.9.1.2.2 Minimum Conformance Ref: 9.1.2.0.2 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221822 R5-224510 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
337 |  | 38.533 | 9.1.3 | Synchronization reference selection/reselection | New sub-clause header |  | RAN5#95 (May-22) | R5-220734 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
338 |  | 38.533 | 9.1.3.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220734 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
339 |  | 38.533 | 9.1.3.0.1 | Requirements for GNSS configured as the highest priority synchronization reference source | To add NR sidelink Synchronization Reference Selection/Reselection related requirements when GNSS is configured as the highest priority sync reference Normative Ref: TS 38.133 cl.12.4 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220734 R5-224511 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
340 |  | 38.533 | 9.1.3.0.2 | Requirements for eNB/gNB configured as the highest priority synchronization reference source | To add NR sidelink Synchronization Reference Selection/Reselection related requirements when eNB/gNB is configured as the highest priority sync reference Normative Ref: TS 38.133 cl.12.4 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220734 R5-224511 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
341 | Y | 38.533 | 9.1.3.1 | NR SA FR1 synchronization reference selection/reselection for GNSS configured as the highest priority synchronization reference source | Test Purpose(s): to verify the requirements related to SyncRef UE selection / reselection when GNSS is configured as the highest priority. Normative Ref: TS 38.133 A.9.1.3.1 Minimum Conformance Ref: 9.1.3.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221823 R5-224512 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
342 | Y | 38.533 | 9.1.3.2 | NR SA FR1 synchronization reference selection/reselection for FR1 NR Cell configured as the highest priority synchronization reference source | Test Purpose(s): to verify the requirements related to SyncRef UE selection / reselection when FR1 NR Cell is configured as the highest priority. Normative Ref: TS 38.133 A.9.1.3.1 Minimum Conformance Ref: 9.1.3.0.2 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221824 R5-225851 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
343 |  | 38.533 | 9.1.4 | L1 SL-RSRP measurements | New sub-clause header |  | RAN5#95 (May-22) | R5-220737 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
344 |  | 38.533 | 9.1.4.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220737 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
345 |  | 38.533 | 9.1.4.0.1 | Requirements for resource selection/reselection, re-evaluation and pre-emption | To add NR sidelink L1 SL-RSRP Measurements for resource (re-)selection, re-evaluation and pre-emption related requirements Normative Ref: TS 38.133 cl.10.4.4, 12.5.2 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220737 R5-222633 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
346 | Y | 38.533 | 9.1.4.1 | NR SA FR1 L1 SL-RSRP measurement for autonomous resource selection/reselection | Test Purpose(s): to verify the requirements related to autonomous resource selection / reselection for NR sidelink UE in mode 2. Normative Ref: TS 38.133 A.9.1.4.1 Minimum Conformance Ref: 9.1.4.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220738 R5-224514 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
347 | Y | 38.533 | 9.1.4.2 | NR SA FR1 L1 SL-RSRP measurement for resource pre-emption | Test Purpose(s): to verify the requirements related to resource pre-emption for NR sidelink UE in mode 2. Normative Ref: TS 38.133 A.9.1.4.2 Minimum Conformance Ref: 9.1.4.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221825 R5-224515 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
348 | Y | 38.533 | 9.1.4.3 | NR SA FR1 L1 SL-RSRP measurement for resource re-evaluation | Test Purpose(s): to verify the requirements related to resource re-evaluation for NR sidelink UE in mode 2. Normative Ref: TS 38.133 A.9.1.4.3 Minimum Conformance Ref: 9.1.4.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221826 R5-222633 R5-225852 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
349 |  | 38.533 | 9.1.5 | Congestion control measurement | New sub-clause header |  | RAN5#95 (May-22) | R5-220741 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
350 |  | 38.533 | 9.1.5.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220741 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
351 |  | 38.533 | 9.1.5.0.1 | Requirements for congestion control measurements | To add NR sidelink congestion control measurements related requirements Normative Ref: TS 38.133 cl.10.4.3, 12.6 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220741 R5-222633 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
352 | Y | 38.533 | 9.1.5.1 | NR SA FR1 congestion control measurement for concurrent operation | Test Purpose 1: to verify that the V2X UE makes correct reporting of an event. Test Purpose 2: to verify the congestion control measurement requirements. Normative Ref: TS 38.133 A.9.1.5 Minimum Conformance Ref: 9.1.5.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220742 R5-224517 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
467 | Y | 38.533 | 9.1.5.2 | NR SA FR1 congestion control measurement for PC5-only operation | Test Purpose: to verify the congestion control measurement requirements. Normative Ref: TS 38.133 A.9.1.5 Minimum Conformance Ref: 9.1.5.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-221827 R5-224518 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
353 |  | 38.533 | 9.1.6 | Interruption | New sub-clause header |  | RAN5#95 (May-22) | R5-220744 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
354 |  | 38.533 | 9.1.6.0 | Minimum conformance requirements | New sub-clause header |  | RAN5#95 (May-22) | R5-220744 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
355 |  | 38.533 | 9.1.6.0.1 | Requirements for interruption to WAN due to NR sidelink communication | To add interruption to WAN due to NR sidelink communication related requirements Normative Ref: TS 38.133 cl.12.7.1 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220744 R5-222633 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
356 | Y | 38.533 | 9.1.6.1 | NR SA FR1 interruption to WAN due to NR sidelink communication | Test Purpose(s): to verify the requirements related to interruptions due to V2X sidelink communication under the following additional conditions: The UE is out of coverage on the V2X sidelink carrier and is associated with a serving cell on a non-V2X sidelink carrier Normative Ref: TS 38.133 A.9.1.6 Minimum Conformance Ref: 9.1.6.0.1 | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-220745 R5-224519 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
359 |  | 38.533 | A.11 | Reference configuration for NR sidelink | To add reference resource pool configuration for NR sidelink Normative Ref: TS 38.133 cl.A.3.21.2 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-221828 |  | 0.6 | 100% | 100% | 100% |  | 100% |  |  | 100%
360 |  | 38.533 | B.4 | Side conditions for NR sidelink | New sub-clause header |  | RAN5#95 (May-22) | R5-220747 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
361 |  | 38.533 | B.4.1 | Test parameters for GNSS signals | To add Test parameters for GNSS signals Normative Ref: TS 38.133 cl.B.4.1 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220747 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
362 |  | 38.533 | B.4.2 | Conditions for PSBCH-RSRP | To add Conditions for PSBCH-RSRP Normative Ref: TS 38.133 cl.B.4.2 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220747 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
363 |  | 38.533 | B.4.3 | Conditions for Selection/Reselection to Intra-frequency SyncRef UE | To add Conditions for Selection/Reselection to Intra-frequency SyncRef UE Normative Ref: TS 38.133 cl.B.4.3 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220747 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
364 |  | 38.533 | B.4.4 | Conditions for L1 SL-RSRP | To add Conditions for L1 SL-RSRP Normative Ref: TS 38.133 cl.B.4.4 | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220747 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
475 |  | 38.533 | E.1.7 | NR sidelink test cases | To clarify the test frequency selection for NR sidelink test cases | Huawei, HiSilicon, | RAN5#94 (Feb-22) | R5-220748 |  | 0.1 | 100% | 100% | 100% |  | 100% |  |  | 100%
365 |  | 38.533 | E.7 | Cell configuration mapping for NR sidelink test cases in Chapter 9 | To add Cell configuration mapping for those NR sidelink TCs which use both PC5 and Uu interfaces | Huawei, HiSilicon, | RAN5#95 (May-22) | R5-220748 |  | 0.1 | 100% | 100% | 100% |  | 100% |  |  | 100%
366 |  | 38.533 | F.1.1 | Acceptable uncertainty of test system (normative) | To add Maximum test system uncertainty for RRM requirements for NR sidelink TCs | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-225853 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
367 |  | 38.533 | F.1.3 | Test Tolerance and Derivation of Test Requirements (informative)Test Tolerance and Derivation of Test Requirements (informative) | To add derivation of TT for NR sidelink TCs | Huawei, HiSilicon, | RAN5#97 (Nov-22) | R5-225853 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
468 |  | 38.533 | G.3 | Statistical testing of measurement performance in NR SL CBR RRM tests | To add derivation Pass/Fail limit for CBR TCs | Huawei, HiSilicon, | RAN5#99 (May-23) | R5-220749 R5-231720 | Editor's note: - Pass/Fail limit in cl.G.3.3 and G.3.4 is still missing - Wrong subclause number of G.3.2 | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
TR 38.903: Test Tolerances analysis RRM and Demod test cases
369 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | To add TT analysis for NR sidelink RRM test cases. |  | RAN5#97 (Nov-22) | R5-224521 R5-224522 R5-224523 R5-224524 R5-224525 R5-224526 R5-224527 R5-224528 R5-224529 R5-225854 R5-224531 R5-224532 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
372 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | To add test point analysis for NR sidelink TCs | Huawei | RAN5#99 (May-23) | R5-212929 R5-212930 R5-221829 R5-222187 R5-241000 R5-243135 R5-243139 R5-243143 |  | 1 | 40% (+35%) | 40% (+40%) | 40% (+30%) |  | 40% |  |  | 40%
373 |  | 38.905 | 4.3 | Test point analysis for test cases in TS 38.521-3 | To add test point analysis for NR sidelink TCs | Huawei | RAN5#99 (May-23) | R5-217604 R5-218306 |  | 1 | 2.5% | 0% | 5% |  | 0% |  |  | 5%
RAN and CN protocol
TS 38.523-1: Protocol test cases
AS Layer
502 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | To add NR SL capabilities check in UE radio capability transfer TC | MCC TF160 | RAN5#96 (Aug-22) | R5-225384 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
154 |  | 38.523-1 | 12 | NR sidelink | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
155 |  | 38.523-1 | 12.1 | PC5-only operation | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
156 |  | 38.523-1 | 12.1.1 | PC5-only operation / Sidelink communication | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
157 | Y | 38.523-1 | 12.1.1.1 | PC5-only operation / Sidelink communication / Transmission | TP1:[TS 38.304: 8.2, TS 38.331: 5.8.8] WITH: UE being authorized for performing NR sidelink Communication. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in pre-configuration. | Huawei, Hisilicon | RAN5#99 (May-23) | R5-243534 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100%
158 | Y | 38.523-1 | 12.1.1.2 | PC5-only operation / Sidelink communication / Reception | TP1:[TS 38.304: 8.2, TS 38.331: 5.8.7] WITH: UE being authorized for performing NR sidelink Communication. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in pre-configuration. | TDIA/CATT | RAN5#97 (Nov-22) | R5-217894 R5-227463 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
159 |  | 38.523-1 | 12.1.2 | PC5-only operation / Sidelink synchronization related procedure | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
160 | Y | 38.523-1 | 12.1.2.1 | PC5-only operation / Sidelink synchronization related procedure / Synchonization reference source (re-)selection | TP1: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss in pre-configuration. WHEN: GNSS signal is reliable and a SyncRef UE which directly synchronized to GNSS is detected. THEN: UE selects GNSS as synchonization reference source. TP2: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss in pre-configuration. WHEN: Two SyncRef UEs, one directly synchronized to GNSS and the other indirectly synchronized to GNSS, are detected. THEN: UE selects the SyncRef UE directly synchronized to GNSS as synchonization reference source. TP3: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss in pre-configuration; WHEN: Two SyncRef UEs, one indirectly synchronized to GNSS and the other neither directly nor indirectly synchronized to GNSS, are detected. THEN: UE selects the SyncRef UE indirectly synchronized to GNSS as synchonization reference source; TP4: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss in pre-configuration. WHEN: A SyncRef UE which neither directly nor indirectly synchronized to GNSS is detected. THEN: UE selects the SyncRef UE which neither directly nor indirectly synchronized to GNSS as synchonization reference source. TP5: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission, and is configured with sl-SyncPriority = gnss in pre-configuration. WHEN: No SyncRef UE is detectable. THEN: UE uses its internal clock as synchronization reference source. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224559; R5-231425 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
161 | Y | 38.523-1 | 12.1.2.2 | PC5-only operation / Sidelink synchronization related procedure / SL-SSB transmission Initiation and Cease | TP1: [38.331: 5.8.5.2] WITH: UE is configured by upper layer to perform sidelink transmission. WHEN: UE selects GNSS as synchonization reference source. THEN: UE keeps transmitting S-SSB. TP2: [38.331: 5.8.5.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with syncTxThreshOoC in pre-configuration. WHEN: UE selects SyncRef UE as synchronization reference source. PSBCH-RSRP of the SyncRef UE is lower than syncTxThreshOoC. THEN: UE starts transmitting S-SSB. TP3: [38.331: 5.8.5.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with syncTxThreshOoC in pre-configuration. WHEN: UE selects SyncRef UE as synchronization reference source. PSBCH-RSRP of the SyncRef UE is above than syncTxThreshOoC. THEN: UE stops transmitting S-SSB. TP4: [38.331: 5.8.5.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with syncTxThreshOoC in pre-configuration. WHEN: UE selects SyncRef UE as synchronization reference source. PSBCH-RSRP of the SyncRef UE is below than syncTxThreshOoC. THEN: UE starts transmitting S-SSB. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224560; R5-231426 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
162 |  | 38.523-1 | 12.1.3 | PC5-only operation / Measurement configuration and reporting via PC5 RRC | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
163 | Y | 38.523-1 | 12.1.3.1 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement configuration | TP1: [38.331 cl.5.8.10.2] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to configure periodical PSBCH-RSRP measurement. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. | TDIA/CATT | RAN5#95 (May-22) | R5-217999 R5-223366 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
164 | Y | 38.523-1 | 12.1.3.2 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Event S1 and S2 | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB is below threshold. THEN: UE does not trigger PSBCH-RSRP measurement reporting. TP2: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S1 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB are above threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. TP3: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB are above threshold. THEN: UE does not trigger PSBCH-RSRP measurement reporting. TP4: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform event S2 PSBCH-RSRP measurement on SL-SSB via PC5 RRC. WHEN: PSBCH-RSRP measurement results of SL SSB are below threshold. THEN: UE triggers PSBCH-RSRP measurement reporting. | TDIA/CATT | RAN5#97 (Nov-22) | R5-217891 R5-224582 R5-226618 R5-230963 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
165 | Y | 38.523-1 | 12.1.3.3 | PC5-only operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Periodical reporting | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE being configured to perform periodical PSBCH-RSRP measurement reporting on SL SSB via PC5 RRC. WHEN: The first measurement result is available and thereafter every time periodical timer expires until sl-NumberOfReportsSent is equal to sl-ReportAmount. THEN: UE trigger PSBCH-RSRP measurement reporting. | TDIA/CATT | RAN5#93 (Nov-21) | R5-218007 R5-223375 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
166 |  | 38.523-1 | 12.1.4 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC | Sub-clause heading |  | RAN5#95 (May-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
167 | Y | 38.523-1 | 12.1.4.1 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / initiating UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to modify a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by high layer to transmit a PC5 RRCReconfiguration message to release a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. TP4: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receive an RRCReconfigurationCompleteSidelink from peer UE. THEN: UE apply the parameters in RRCReconfigurationSidelink. TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5-RRC connection with peer UE. WHEN: UE is indicated by upper layer to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB addition. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE establishes the SL DRB. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5-RRC connection with peer UE. WHEN: UE is indicated by upper layer to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB addition. After receiving RRCReconfigurationFailureSidelink message from peer UE, UE doesn't establish the SL DRB. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE is indicated by upper layer to modify the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB modification. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE modifies the SL DRB. TP5: [38.331: 5.8.9.1a.2] WITH: UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE is indicated by upper layer that no QoS flow is mapped to the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB release. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE releases the SL DRB. TP6: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE is indicated by upper layer to release the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB release. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE releases the SL DRB. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223371 R5-226619 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
168 | Y | 38.523-1 | 12.1.4.2 | PC5-only operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Peer UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to add an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP2: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to modify an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink that can comply to release an unicast SL DRB. THEN: UE applies the parameters in RRCReconfigurationSidelinksends and sends a RRCReconfigurationCompleteSidelink message to peer UE. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223374 R5-226620 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
169 |  | 38.523-1 | 12.1.5 | PC5-only operation / Sidelink CSI reporting | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
170 | Y | 38.523-1 | 12.1.5.1 | PC5-only operation / Sidelink CSI reporting / Configuration | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to configure SL CSI-RS resource to peer UE. THEN: UE sends an RRCReconfigurationSidelink message including sl-CSI-RS-Config to peer UE and starts to transmit SL CSI-RS. TP2: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to trigger SL CSI report. THEN: UE sends an SCI format 1-A to trigger SL CSI report. | TDIA/CATT | RAN5#95 (May-22) | R5-218000 R5-223367 R5-231427 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
171 | Y | 38.523-1 | 12.1.5.2 | PC5-only operation / Sidelink CSI reporting / Reporting | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE and is configuredby peer UE to perform CSI measurement. WHEN: UE receives a SCI format 1-A to trigger SL CSI report. THEN: UE sends an CSI reporting MAC-CE to peer UE. | TDIA/CATT | RAN5#95 (May-22) | R5-218001 R5-223368 R5-231427 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
172 |  | 38.523-1 | 12.1.6 | PC5-only operation / Sidelink failure | Sub-clause heading |  | RAN5#95 (May-22) | R5-221524 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
173 | Y | 38.523-1 | 12.1.6.1 | PC5-only operation / Sidelink failure / PC5 RRC reconfiguration failure / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationFailureSidelink from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-221524 R5-222942 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
174 | Y | 38.523-1 | 12.1.6.2 | PC5-only operation / Sidelink failure / PC5 RRC reconfiguration failure / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationSidelink that UE can't comply from peer UE. THEN: UE continue using the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a RRCReconfigurationFailureSidelink message. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-221525 R5-222941 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
175 | Y | 38.523-1 | 12.1.6.3 | PC5-only operation / Sidelink failure / Sidelink radio link failure / Transmission side | TP1: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink and has sent an RRCReconfigurationSidelink message to peer UE. WHEN: UE doesn't receive RRCReconfigurationCompleteSidelink or RRCReconfigurationFailure before T400 expires THEN: UE releases PC5-RRC connection and indicates the release to upper layer. TP2: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink and has established a AM SL DRB. WHEN: Retransmission number of the AM SL DRB reaches the maximum number of retransmissions. THEN: UE releases PC5-RRC connection and indicates the release to upper layer. TP3: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: MAC detects that maximum number of consecutive HARQ DTX has been reached. THEN: UE releases PC5-RRC connection and indicates the release to upper layer. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-221526 R5-225294 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
176 |  | 38.523-1 | 12.1.7 | PC5-only operation / Sidelink UE capability transfer via PC5 RRC | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0 | 100% |  | 100% |  |  |  |  | 100%
177 | Y | 38.523-1 | 12.1.7.1 | PC5-only operation / Sidelink UE capability transfer via PC5 RRC / One-way and two-way transfer | TP1: [38.331: 5.8.9.2.1, 5.8.9.2.4] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message from peer UE. THEN: UE sends a UECapabilityInformationSidelink message to peer UE. TP2: [38.331: 5.8.9.2.1, 5.8.9.2.2, 5.8.9.2.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure. THEN: UE sends a UECapabilityEnquirySidelink message to peer UE. TP3: [38.331: 5.8.9.2.1, 5.8.9.2.2, 5.8.9.2.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure and to provide UE radio access capabilities. THEN: UE sends a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelink to peer UE | R&S | RAN5#99 (May-23) | R5-213570 R5-231433 R5-240529 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
376 |  | 38.523-1 | 12.1.8 | PC5-only operation / MAC | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
377 |  | 38.523-1 | 12.1.8.1 | PC5-only operation / MAC / HARQ process | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
378 | Y | 38.523-1 | 12.1.8.1.1 | PC5-only operation / MAC / HARQ process / selected sidelink grant | TP1: [ref: TS 38.321 cl. 5.22.1.1, 5.22.1.2, 5.22.1.3.1, 5.22.1.3.1a] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: Data arrives at logical channel. Then: UE creates a selected SL grant and uses it for transmission. TP2: [ref: TS 38.321 cl. 5.22.1.1, 5.22.1.2, 5.22.1.7, 5.22.1.3.1, 5.22.1.3.1a] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: SL CSI reporting is triggered. Then: UE creates a one-shot selected SL grant and uses it to send SL CSI reporting MAC-CE. TP3: [ref: TS 38.321 cl. 5.22.1.1, 5.22.1.3.2] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: UE receives a NACK on PSFCH corresponding to the sent PSSCH. Then: UE re-transmits the SL-SCH MAC-CE. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
379 | Y | 38.523-1 | 12.1.8.1.2 | PC5-only operation / MAC / HARQ process / ACK-NACK HARQ reception | TP1: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and HARQ feedback is disabled by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE doesn't sent PSFCH. TP2: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and ACK-NACK HARQ feedback is indicated by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE sends an ACK feedback on PSFCH. TP3: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and ACK-NACK HARQ feedback is enabled by its associated SCI. UE fails to decode the SL-SCH MAC PDU. Then: UE sends a NACK feedback on PSFCH. TP4: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to unicast is received and its associated destination L2 ID doesn't match with any source L2 ID of the UE or its associated source L2 ID doesn't match with any destination L2 ID of the UE. Then: UE discards this MAC PDU. TP5: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to unicast is received and its associated destination L2 ID matches with a source L2 ID of the UE and its associated source L2 ID matches with a destination L2 ID of the UE. Then: UE submits MAC SDU(s) contained in the MAC PDU to upper layer. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
380 | Y | 38.523-1 | 12.1.8.1.3 | PC5-only operation / MAC / HARQ process / NACK-only HARQ reception | TP1: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and NACK-only HARQ feedback is indicated by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE doesn't send PSFCH. TP2: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and NACK-only HARQ feedback is enabled by its associated SCI. UE fails to decode the SL-SCH MAC PDU. Then: UE sends a NACK feedback on PSFCH. TP3: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to groupcast is successfully decoded and its associated destination L2 ID doesn't match with a destination L2 ID of the UE. Then: UE discards this MAC PDU. TP4: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to groupcast is successfully decoded and its associated destination L2 ID matches with a destination L2 ID of the UE. Then: UE submits MAC SDU(s) contained in the MAC PDU to upper layer. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
381 | Y | 38.523-1 | 12.1.8.1.4 | PC5-only operation / MAC / HARQ process / SL-SCH Transport block size selection | TP1: [ref:TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3, TS 38.214 cl.8.1.3.2] WITH: UE is configured to perform sidelink reception. WHEN: UE receives SCI format 1-A indicating a SL-SCH TB corresponding to Frequency resource assignment, Time resource assignment, Modulation and coding scheme and PSFCH overhead indication THEN: UE decodes the received SL-SCH TB transport block of size correctly and forwards it to higher layers |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
382 |  | 38.523-1 | 12.1.8.2 | PC5-only operation / MAC / Multiplexing and Assembly | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
383 | Y | 38.523-1 | 12.1.8.2.1 | PC5-only operation / MAC / Multiplexing and Assembly / Logical channel prioritization without mapping restriction | TP1: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at a SCCH and several STCHs with different destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the SCCH in assembled MAC PDU. TP2: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 5.22.1.4.2, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: UE has a SL CSI reporing MAC-CE to send and data arrives at several STCHs with different destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the MAC-CE in assembled MAC PDU. TP3: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with different destinations L2 IDs. Some of these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the logical channel with highest priority among all logical channels with SBj>0. TP4: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with different destinations L2 IDs. All these STCHs have SBj < 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the logical channel with highest priority. TP5: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is not enough to transmit all available data at all logical channels. THEN: UE includes MAC SDUs from logical channels in a strict decreasing priority order. TP6: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. Some of these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all data available at logical channels with SBj > 0 but not enough to transmit all available data at all logical channels. THEN: After including all SDUs from logical channels with SBj > 0. UE includes MAC SDUs from logical channels with SBj < 0 in a strict decreasing priority order. TP7: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: After including all SDUs from all logical channels, UE includes a subPDU with padding bits in MAC PDU. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
384 | Y | 38.523-1 | 12.1.8.2.2 | PC5-only operation / MAC / Multiplexing and Assembly / Logical channel prioritization with mapping restriction | TP1: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. and the SL grant used is a Type 1 configured sidelink grant. THEN: UE only considers those logical channels with sl-ConfiguredGrantType1Allowed in LCP procedure. TP2: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. and the SL grant used is a Type 1 configured sidelink grant. THEN: UE dosen't consider those logical channels, which are configured with sl-AllowedCG-List and CG ID of the Type 1 SL CG is not included sl-AllowedCG-List, in LCP procedure. TP3: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is not configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = disabled in LCP procedure. TP4: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. logical channels with highest priority is configured with sl-HARQ-FeedbackEnabled = enabled. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = enabled in LCP procedure. TP5: [ref: TS 38.321 cl.5.22.1.4, 5.22.1.4.1.1,5.22.1.4.1.2,5.22.1.4.1.3, 6.1.6] WITH: UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. logical channels with highest priority is configured with sl-HARQ-FeedbackEnabled = disabled. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = disabled in LCP procedure. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
385 |  | 38.523-1 | 12.1.8.3 | PC5-only operation / MAC / Sidelink CSI reporting | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
386 | Y | 38.523-1 | 12.1.8.3.1 | PC5-only operation / MAC / Sidelink CSI reporting / reception side | TP1: [TS 38.321 cl.5.22.1.7] WITH: UE has established PC5-RRC with peer UE. SL-CSI reporting has been triggered by SCI from peer UE and sl-CSI-ReportTimer is running. WHEN: UE has SL grant to send SL CSI report MAC-CE. THEN: UE sends SL CSI report MAC-CE |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
387 |  | 38.523-1 | 12.1.9 | PC5-only operation / RLC | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
388 |  | 38.523-1 | 12.1.9.1 | PC5-only operation / RLC / unacknowledged mode | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
389 | Y | 38.523-1 | 12.1.9.1.1 | PC5-only operation / RLC / unacknowledged mode / RLC SDU segmentation | TP1: [ref: TS 38.322 cl.5.2.2.1.1, 6.2.2.3, 6.2.3.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A RLC SDU arrives and transmission opportunity indicated by MAC is enough to transmit entire RLC SDU THEN: UE sends a UM PDU with SI = 00. TP2: [ref: TS 38.322 cl.5.2.2.1.1, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A RLC SDU arrives and transmission opportunity indicated by MAC is not enough to transmit entire RLC SDU. It is the first SDU needed to segment. THEN: UE segments the RLC SDU, sends a UM PDU with SN=0 and SI = 01 to contain the first segment, sends a UM PDU with SN=0 and SI = 10 to contain the last segment, and sends UM PDU(s) with SN=0 and SI = 11 to contain other segment(s). TP3: [ref: TS 38.322 cl.5.2.2.1.1, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: Subsequent RLC SDUs arrives and transmission opportunity indicated by MAC is not enough to transmit each RLC SDU entirely. THEN: UE increases SN by 1 for each UM SDU, and all UM PDUs corresponding to the same RLC SDU use the same SN. TP4: [ref: TS 38.322 cl.5.2.2.1.1, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: UE finishes sending all UM PDUs with SN = 63. A RLC SDU arrives and transmission opportunity indicated by MAC is not enough to transmit the entire RLC SDU. THEN: UE includes SN = 0 in each UM PDU corresponding to the RLC SDU. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
390 | Y | 38.523-1 | 12.1.9.1.2 | PC5-only operation / RLC / unacknowledged mode / RLC SDU reassembly | TP1: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A UM PDU with SI = 00 is received from lower layer. THEN: UE retrieves corresponding RLC SDU and submits it to upper layer. TP2: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6, t-reassembly timer is not running and reception buffer is empty. WHEN: UM PDUs with SN = RX_Next_Reassembly are received from lower layer and after receiving each UM PDU here is no missing byte segment before the last byte of all received segments. THEN: UE stores the UM PDU in reception buffer and doesn't start t-reassembly timer. TP3: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1, 7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6, t-reassembly timer is not running and reception buffer is not empty. WHEN: A UM PDU with SN falls outside of the reassembly window are received from lower layer. THEN: UE stores the UM PDU in reception buffer, updates RX_Next_Highest, discards all stored UM PDUs falls outside of the reassembly window and starts t-reassembly timer. TP4: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A UM PDU with SN falls within of the reassembly window is received from lower layer, and SN < RX_Next_Reassembly. THEN: UE discards the UM PDU. TP5: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1, 7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A UM PDU with SN falls within of the reassembly window and SN >= RX_Next_Reassembly is received from lower layer, and there is still missing SDU segments. THEN: UE stores the UM PDU in reception buffer. TP6: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1, 7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. WHEN: A UM PDU with SN falls within of the reassembly window and SN >= RX_Next_Reassembly is received from lower layer, and all byte segments are received. THEN: UE retrieves corresponding RLC SDU and submits it to upper layer. TP7: [ref: TS 38.322 cl.5.2.2.2.1, 5.2.2.2.2, 6.2.2.3, 6.2.3.3, 6.2.3.4, 7.1, 7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-UM and sl-SN-FieldLengthUM = size6. t-reassembly timer is running WHEN: t-reassembly timer is expired. THEN: UE discards all stored UM PDUs with SN less than the first SN >= RX_Timer_Trigger that has not been reassembled. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
391 |  | 38.523-1 | 12.1.9.2 | PC5-only operation / RLC / acknowledged mode | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
392 | Y | 38.523-1 | 12.1.9.2.1 | PC5-only operation / RLC / acknowledged mode / RLC SDU segmentation | TP1: [ref: TS 38.322 cl.5.2.3.1.1, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. No RLC SDU is sent after SL DRB establishment. WHEN: A RLC SDU arrives and transmission opportunity indicated by MAC is enough to transmit entire RLC SDU THEN: UE sends a AM PDU with SI = 00 and SN = 0. TP2: [ref: TS 38.322 cl.5.2.3.1.1, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: Subsequent RLC SDUs arrives and transmission opportunity indicated by MAC is enough to transmit each RLC SDU entirely. THEN: UE increases SN by 1 for each AM SDU. TP3: [ref: TS 38.322 cl.5.2.3.1.1, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: UE finishes sending AM PDU(s) with SN = 4095. A RLC SDU arrives and transmission opportunity indicated by MAC is not enough to transmit entire RLC SDU. It is the first SDU needed to segment. THEN: UE segments the RLC SDU, sends a AM PDU with SN=0 and SI = 01 to contain the first segment, sends a AM PDU with SN=0 and SI = 10 to contain the last segment, and sends AM PDU(s) with SN=0 and SI = 11 to contain other segment(s). TP4: [ref: TS 38.322 cl.5.2.3.1.1, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: Subsequent RLC SDUs arrives and transmission opportunity indicated by MAC is not enough to transmit each RLC SDU entirely. THEN: UE increases SN by 1 for each AM SDU, and all AM PDUs corresponding to the same RLC SDU use the same SN. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
393 | Y | 38.523-1 | 12.1.9.2.2 | PC5-only operation / RLC / acknowledged mode / RLC SDU reassembly | TP1: [ref: TS 38.322 cl.5.2.3.2.1, 5.2.3.2.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: An AM PDU with SN falls outside of the reception window is received from lower layer. THEN: UE discards the AM PDU. TP2: [ref: TS 38.322 cl.5.2.3.2.1, 5.2.3.2.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: An AM PDU with SN falls within of the reception window is received from lower layer and part of the byte segment it carries has already been stored in reception buffer. THEN: UE only store the non-duplicated byte segments in reception buffer. TP3: [ref: TS 38.322 cl.5.2.3.2.1, 5.2.3.2.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: All byte segements of a RLC SDU are stored in reception buffer. THEN: UE discards the duplicate byte segments. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
394 | Y | 38.523-1 | 12.1.9.2.3 | PC5-only operation / RLC / acknowledged mode / polling and retransmission | TP1: [ref: TS 38.322 cl.5.3.3, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: Multiple RLC SDUs arrives and SN of all SDUs except the first one fall outside of transmission window. THEN: UE sends AM PDU corresponding to the first RLC SDU with polling. TP2: [ref: TS 38.322 cl.5.3.3, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: A RLC SDU arrives and after sending this SDU there is no other newly-arrived SDUs and SDUs considered to be retransmitted. THEN: UE sends AM PDU corresponding to the RLC SDU with polling. TP3: [ref: TS 38.322 cl.5.3.3, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: A RLC SDU arrives and PDU_WITHOUT_POLL >= pollPDU after sending the AM PDU corresponding to the RLC SDU. THEN: UE sends AM PDU corresponding to the RLC SDU with polling. TP4: [ref: TS 38.322 cl.5.3.3, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: A RLC SDU arrives and BYTE_WITHOUT_POLL >= pollByte after sending the AM PDU corresponding to the RLC SDU. THEN: UE sends AM PDU corresponding to the RLC SDU with polling. TP5: [ref: TS 38.322 cl.5.3.3, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: t-PollRetransmit is expired. THEN: UE sends an AM PDU with polling. TP6: [ref: TS 38.322 cl.5.3.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: UE receives a STATUS PDU sent from peer UE. THEN: UE considers to retransmit all SDU/SDU segments indicated as NACK in the STATUS PDU. TP7: [ref: TS 38.322 cl.5.3.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: UE considers to retransmit a SDU segment but the transmission opportunity indicated by MAC is not enough to transmit entire segment. THEN: UE re-segments the SDU segment. TP8: [ref: TS 38.322 cl.5.3.2, 6.2.2.4, 6.2.3.3, 6.2.3.4, 7.1,7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. a RLC SDU can't be transmitted due to transmission window stalling. WHEN: SN of the RLC SDU falls within transmission window after UE receiving a STATUS PDU sent from peer UE. THEN: UE transmits AM PDU corresponding to the RLC SDU. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
395 | Y | 38.523-1 | 12.1.9.2.4 | PC5-only operation / RLC / acknowledged mode / STATUS PDU | TP1: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 7.1,7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: An AM PDU with polling is received from lower layer and the SN of the AM PDU is smaller than RX_Highest_Status and t-StatusProhibit is running. THEN: UE doesn't send a STATUS PDU until t-StatusProhibit is expired. TP2: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 7.1,7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: An AM PDU with polling is received from lower layer and the SN of the AM PDU is no smaller than RX_Highest_Status and t-StatusProhibit isn't running. THEN: UE doesn't send a STATUS PDU until RX_Highest_Status is smaller than the SN of the AM PDU. TP3: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 7.1,7.3] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. WHEN: t-Reassembly is expired and t-StatusProhibit isn't running. THEN: UE sends a STATUS PDU. TP4: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 6.2.3.10, 6.2.3.11, 6.2.3.12, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. UE is triggered to sent STATUS PDU. WHEN: there exists a SDU which isn't received entirely. THEN: UE includes a set of NACK_SN field for this SDU. TP5: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 6.2.3.10, 6.2.3.11, 6.2.3.12, 6.2.3.13, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. UE is triggered to sent STATUS PDU. WHEN: there exists a partly received SDU of which a continuous sequence of byte segments are missing. THEN: UE includes a set of NACK_SN/SOstart/Soend field for this SDU. TP6: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3.3, 6.2.3.4, 6.2.3.10, 6.2.3.11, 6.2.3.12, 6.2.3.13, 6.2.3.16, 6.2.3.17, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. UE is triggered to sent STATUS PDU. WHEN: there exists a continuous sequence of RLC SDUs which aren't received entirely. THEN: UE includes a set of NACK_SN/NACK range field for these SDUs. TP7: [ref: TS 38.322 cl.5.3.4, 6.2.2.4, 6.2.2.5, 6.2.3, 7.1] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with RLC-AM and sl-SN-FieldLengthAM = size12. UE is triggered to sent STATUS PDU. WHEN: there exists a continuous sequence of RLC SDUs satisfies: The ending byte segment of the first SDU is missing.The beginning byte segment of the last SDU is missing. And the rest SDUs are entirely missing. THEN: UE includes a set of NACK_SN/NACK range/ SOstart/Soend field for these SDUs. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
396 |  | 38.523-1 | 12.1.10 | PC5-only operation / PDCP | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
397 |  | 38.523-1 | 12.1.10.1 | PC5-only operation / PDCP / data transfer | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
398 | Y | 38.523-1 | 12.1.10.1.1 | PC5-only operation / PDCP / data transfer / PDCP SN numbering | TP1: [ref: TS 38.323 cl.5.2.3, 5.7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with sl-PDCP-SN-Size = len12bits. WHEN: A PDCP SDU arrives at the SL DRB THEN: UE increments SN with 1 for each transmitted PDU for PDCP_SN from 0 to maximum PDCP_SN (4095). TP2: [ref: TS 38.323 cl.5.2.3, 5.7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with sl-PDCP-SN-Size = len12bits. WHEN: A PDCP SDU arrives at the SL DRB, and after incrementation TX_NEXT is larger than the maximum PDCP_SN (4095) THEN: UE sets PDCP_SN to 0 in the next transmitted PDCP PDU. TP3: [ref: TS 38.323 cl.5.2.3, 5.7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with sl-PDCP-SN-Size = len18bits. WHEN: A PDCP SDU arrives at the SL DRB THEN: UE increments SN with 1 for each transmitted PDU for PDCP_SN from 0 to maximum PDCP_SN (262143). TP4: [ref: TS 38.323 cl.5.2.3, 5.7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB with sl-PDCP-SN-Size = len18bits. WHEN: A PDCP SDU arrives at the SL DRB, and after incrementation TX_NEXT is larger than the maximum PDCP_SN (262143) THEN: UE sets PDCP_SN to 0 in the next transmitted PDCP PDU. TP5: [ref: TS 38.323 cl.5.2.3, 5.3, 5.7.4] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. WHEN: The discard timer for a PDCP SDU expires THEN: UE discards the corresponding PDCP SDU |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
399 | Y | 38.523-1 | 12.1.10.1.2 | PC5-only operation / PDCP / data transfer / Reordering | TP1: [TS 38.323 cl.5.2.4, 5.7.5] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. WHEN: A PDCP PDU is received from the lower layer and the COUNT value of its corresponding PDCP SDU is smaller than RX_DELIV. THEN: UE discard the PDCP PDU and doesn't submit its corresponding PDCP SDU to upper layer. TP2: [TS 38.323 cl.5.2.4, 5.7.5] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. WHEN: A PDCP PDU is received from the lower layer and the COUNT value of its corresponding PDCP SDU is bigger than RX_DELIV. THEN: UE stores the corresponding PDCP SDU in reception buffer. TP3: [TS 38.323 cl.5.2.4, 5.7.5] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. WHEN: A PDCP PDU is received from the lower layer and the COUNT value of its corresponding PDCP SDU equals to the COUNT of a PDCP PDU stored in reception buffer. THEN: UE discards the PDCP PDU and doesn't submit more than one PDCP SDUs with same COUNT to upper layer. TP4: [TS 38.323 cl.5.2.4, 5.7.5] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. WHEN: A PDCP PDU is received from the lower layer and the COUNT value of its corresponding PDCP SDU equals to RX_DELIV. THEN: UE submit PDCP SDU with COUNT = RX_DELIV and all PDCP SDUs with consecutive COUNT values in ascending order. TP5: [TS 38.323 cl.5.2.4, 5.7.5] WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. t-Reordering timer is running. WHEN: After submitting PDCP PDU to upper layer RX_DELIV is no less than RX_REORD. THEN: UE stops t-Reordering timer. TP6: WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. t-Reordering timer is running. WHEN: t-Reordering timer expires. THEN: UE stops t-Reordering timer, delivers stored PDCP SDUs with COUNT less than RX_REORD and all PDCP SDUs with consecutive COUNT values from the PDCP SDU COUNT = RX_REORD, in ascending order. TP7: WITH: UE has established unicast link with peer UE and has established an unicast SL DRB. t-Reordering timer is running. WHEN: t-Reordering timer is reconfigured. THEN: UE sets RX_REORD = RX_NEXT, and restarts t-Reordering timer with new configuration value. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
405 |  | 38.523-1 | 12.1.11 | PC5-only operation / SDAP | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
406 |  | 38.523-1 | 12.1.11.1 | PC5-only operation / SDAP / QoS flow to SL DRB mapping | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
407 | Y | 38.523-1 | 12.1.11.1.1 | PC5-only operation / SDAP / QoS flow to SL DRB mapping / transmission side | TP1: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink transmission. UE has established PC5-RRC connection and multiple unicast SL DRBs with peer UE. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: UE is indicated by upper layer that data arrives on a QoS flow and UE has stored a mapping rule for this QoS flow. Then: UE builds an SDAP PDU with SDAP header, and maps it to the corresponding SL DRB. TP2: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink transmission. UE has established PC5-RRC connection and multiple unicast SL DRBs with peer UE. To each unicast SL DRB there are more than one PC5 QoS flows mapped and one of them is configured as the default SL DRB. WHEN: UE is indicated by upper layer that data arrives on a QoS flow and UE hasn't stored a mapping rule for this QoS flow. THEN: UE builds an SDAP PDU with header, and maps it to the default SL DRB. TP3: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink transmission. UE has established PC5-RRC connection and multiple unicast SL DRBs with peer UE. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: RRC configures a new mapping rule for a QoS flow, which is different from the existing mapping rule for this QoS flow. THEN: The UE stores the newly configured mapping rule as mapping rule for this QoS flow, transmits an end-marker control PDU on the SL DRB according to the old mapping rule, and uses the new mapping rule for future transmission. TP4: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink transmission. UE has established PC5-RRC connection and multiple unicast SL DRBs with peer UE. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: RRC configures a mapping rule for a QoS flow and UE hasn't stored mapping rule for this QoS flow before. THEN: The UE stores the newly configured mapping rule as mapping rule for this QoS flow, transmits an end-marker control PDU on the default SL DRB, and uses the new mapping rule for future transmission. TP5: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink transmission. UE has established multiple groupcast SL DRBs. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: UE is indicated by upper layer that data arrives on a QoS flow and UE has stored a mapping rule for this QoS flow. Then: UE builds an SDAP PDU without SDAP header, and maps it to the corresponding SL DRB. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
408 | Y | 38.523-1 | 12.1.11.1.2 | PC5-only operation / SDAP / QoS flow to SL DRB mapping / reception side | TP1: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink reception. UE has established PC5-RRC connection and multiple unicast SL DRBs with peer UE. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: UE receives an SDAP PDU with SDAP header on one SL DRB. Then: UE retrieves the SDAP SDU and delivers it to upper layer. TP2: [Ref: 37.324 cl. 5.2.3, 5.3.1] WITH: US is configured to perform sidelink reception. UE has established multiple groupcast SL DRBs. To each SL DRB there are more than one PC5 QoS flows mapped. WHEN: UE receives an SDAP PDU without SDAP header on one SL DRB. Then: UE retrieves the SDAP SDU and delivers it to upper layer. |  | RAN5#99 (May-23) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
179 |  | 38.523-1 | 12.2 | Inter-carrier concurrent operation | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
180 |  | 38.523-1 | 12.2.1 | Inter-carrier concurrent operation / Sidelink communication | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206411 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
181 | Y | 38.523-1 | 12.2.1.1 | Inter-carrier concurrent operation / Sidelink communication / RRC_IDLE and RRC_INACTIVE / Transmission | TP1:[TS 38.331: 5.2.2.4.13, 5.8.8] WITH: UE is in RRC_IDLE state and its serving cell broadcasts SIB12 which includes only a segment of SIB12-IEs which includes sl-TxPoolSelectedNormal. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the sidelink frequency included in sl-FreqInfoList. THEN: UE collects all segments of SIB12-IEs and performs NR sidelink transmission using sl-TxPoolSelectedNormal in SIB12 after assembling. TP2:[TS 38.331: 5.2.2.4.13, 5.8.8] WITH: UE is in RRC_IDLE state and its serving cell broadcasts SIB12 which includes only a segment of SIB12-IEs which includes sl-TxPoolSelectedNormal and UE is configured by upper layer to perform sidelink transmission on sidelink carrier included in SIB12. WHEN: valueTag of SIB12 is changed. THEN: UE discard all stored segments of SIB12-IEs and perform performs NR sidelink transmission using sl-TxPoolSelectedNormal in SIB12 with new valueTag after assembling. TP3:[TS 38.331: 5.2.2.4.13, 5.8.8] WITH: UE is in RRC_IDLE state and its serving cell broadcasts SIB12 which includes only a segment of SIB12-IEs which includes sl-TxPoolSelectedNormal and UE is configured by upper layer to perform sidelink transmission on sidelink carrier included in SIB12. WHEN: UE reselects to a neighbour cell which also broadcasts SIB12 which includes only a segment of SIB12-IEs which includes sl-TxPoolSelectedNormal. THEN: UE discard all stored segments of SIB12-IEs and perform performs NR sidelink transmission using sl-TxPoolSelectedNormal in SIB12 provided by new serving cell after assembling. TP4:[TS 38.331:5.2.2.4.13, 5.3.3.1a, 5.3.3.2, 5.3.3.3, 5.3.3.4] WITH: UE is in RRC_IDLE state. Its serving cell broadcasts SIB12 which includes a sidelink carrier in sl-FreqInfoList but no sl-TxPoolSelectedNormal is configured for this sidelink carrier. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the sidelink frequency included in sl-FreqInfoList and data to transmit is available. THEN: UE sends an RRCSetup message to trigger RRC connection establishment procedure. TP5:[TS 38.304: 5.2.4.1, 5.2.4.5, 8.1, 8.2] WITH: UE is in RRC_IDLE state and the cell on which UE camps broadcasts SIB12 including no sl-FreqInfoList but anchor carrier configuration. WHEN: An neighbour cell on anchor carrier starts broadcasting SIB12 which includes sl-TxPoolSelectedNormal and UE is configured by upper layer to perform NR sidelink transmission. THEN: UE considers the anchor carrier to be the highest priority, reselects to neighbour cell on anchor carrier and performs SL transmission using the resource pool indicated by sl-TxPoolSelectedNormal in SIB12. TP6:[TS 38.304: 8.2, TS 38.331: 5.2.2.4.13, 5.8.8] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using the resource pool indicated by sl-TxPoolSelectedNormal in pre-configuration. TP7:[TS 38.331: 5.2.2.4.13, 5.8.2, 5.3.3.2, 5.3.3.3, 5.3.3.4] WITH: UE is in RRC_IDLE state and is configured by upper layer to continuesly perform NR sidelink transmission, The cell on which UE camps broadcasts SIB12 which includes sl-TxPoolExceptional. WHEN: UE receives a Paging message including a matched identity ng-5G-S-TMSI. THEN: UE perform NR sidelink transmission using sl-TxPoolExceptional from the moment the UE initiates RRC connection establishment until receiving an RRCReconfiguration including sl-ConfigDedicatedNR. | Huawei, Hisilicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
182 | Y | 38.523-1 | 12.2.1.2 | Inter-carrier concurrent operation / Sidelink communication / RRC_IDLE and RRC_INACTIVE / Reception | TP1:[TS 38.304: 5.2.4.1, 5.2.4.5, 8.2, TS 38.331: 5.8.7] WITH: UE is in RRC_IDLE state and the cell on which UE camps broadcasts SIB12 including no sl-FreqInfoList but anchor carrier configuration. WHEN: An neighbour cell on anchor carrier starts broadcasting SIB12 which includes sl-RxPool and UE is configured by upper layer to perform NR sidelink reception. THEN: UE considers the anchor carrier to be the highest priority, reselects to neighbour cell on anchor carrier and is able to monitor NR sidelink transmission using the resource pool indicated by sl-RxPool in SIB12. TP2:[TS 38.304: 8.2, TS 38.331: 5.8.7] WITH: UE is in RRC_IDLE state and the cell on which UE camps doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using the resouce pool indicated by sl-RxPool in pre-configuration. | TDIA/CATT | RAN5#95 (May-22) | R5-222049 R5-224581 R5-226621 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
183 | Y | 38.523-1 | 12.2.1.3 | Inter-carrier concurrent operation / Sidelink communication / RRC_CONNECTED / Transmission / Network scheduling | TP1:[TS 38.331: 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12 including sl-ConfigCommonNR. WHEN: UE is configured by upper layer to perform NR sidelink transmission on the frequency included in sl-FreqInfoList. THEN: UE sends a SidelinkUEInfomationNR message to indicate it requires sidelink transmission resources. TP2:[TS 38.331: 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE receives an RRCReconfiguration message which includes sl-ScheduledConfig and no sl-ConfiguredGrantConfigList. THEN: UE performs NR sidelink tranmission based on dynamic scheduling. TP3:[TS 38.331: 5.3.5.9, 5.7.4.2, 5.7.4.3] WITH: UE is in RRC_CONNECTED state and UE has received a RRCReconfiguration message including sl-AssistanceConfigNR. WHEN: UE is configured by upper layer to provide configured grant assistance information for NR NR sidelink communication. THEN: UE sends a UEAssistanceInformation message includes sl-UE-AssistanceInformationNR. TP4:[TS 38.331: 5.7.4.2, 5.7.4.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE receives an RRCReconfiguration message which includes sl-ConfiguredGrantConfigList. THEN: UE performs NR sidelink tranmission using the configued grant included in sl-ConfiguredGrantConfigList. TP5:[TS 38.331: 5.3.5.14, 5.8.3.2, 5.8.3.3] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink transmission. WHEN: UE is no longer configured by upper layer to perform NR sidelink tranmission. THEN: UE sends a SidelinkUEInfomationNR message to indicate it no longer requires NR sidelink transmission resources. TP6:[TS 38.331: 5.3.5.3] WITH: UE is in RRC_CONNECTED state and has sent a SidelinkUEInformationNR message indicating a change of NR sidelink communication to PCell. WHEN: Less than 1 second after UE sending SidelinkUEInformationNR UE receives an RRCReconfiguration message including reconfigurationWithSync which indicates UE to handover to a neighbour Cell which also provides SIB12. THEN: UE sends a SidelinkUEInfomationNR message after it successfully handovers to target cell. TP7:[TS 38.331: 5.3.5.3] WITH: UE is in RRC_CONNECTED state and has sent a UEAssistanceInformation message to provide configured grant assistance information to PCell. WHEN: Less than 1 second after UE sending UEAssistanceInformation UE receives an RRCReconfiguration message including reconfigurationWithSync which indicates UE to handover to a neighbour Cell which also provides SIB12 and UE is still been configured by higher layer to provide configured grant assistance information. THEN: UE sends a UEAssistanceInformation message after it successfully handovers to target cell. | Huawei, Hisilicon | RAN5#99 (May-23) | R5-206411 |  | 1 | 30% | 30% | 30% |  | 30% |  |  | 30%
184 | Y | 38.523-1 | 12.2.1.4 | Inter-carrier concurrent operation/Sidelink communication / RRC_CONNECTED / Transmission / Resource sensing | TP1:[TS 38.331: 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in pre-configuration. TP2:[TS 38.331: 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE is configured by upper layer to perform NR sidelink transmission on sidelink carrier included in SIB12. THEN: UE performs NR sidelink transmission using sl-TxPoolSelectedNormal included in SIB12. TP3:[TS 38.331: 5.3.5.14, 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE receives an RRCReconfiguration message which includes sl-FreqInfoToAddModList and sl-UE-SelectedConfig, and UE is configured by upper layer to perform sidelink transmission on sidelink carrier included in sl-FreqInfoToAddModList. THEN: UE performs NR sidelink tranmission based on sensing using sl-TxPoolSelectedNormal included in sl-FreqInfoToAddModList. TP4:[TS 38.331: 5.3.5.14, 5.8.8] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. UE has received an RRCReconfiguration message which includes sl-FreqInfoToAddModList and sl-UE-SelectedConfig. WHEN: UE receives an RRCReconfiguration message which includes sl-FreqInfoToReleaseList to release previously configured sidelink carrier, and UE is configured by upper layer to perform sidelink transmission on sidelink carrier included in SIB12. THEN: UE performs NR sidelink tranmission based on sensing using sl-TxPoolSelectedNormal included in SIB12. | Huawei, Hisilicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
185 | Y | 38.523-1 | 12.2.1.5 | Inter-carrier concurrent operation / Sidelink communication / RRC_CONNECTED / Transmission / Exceptional pool | TP1: [38.331: cl 5.8.8] WITH: UE in RRC_CONNECTED state and performing NR sidelink tranmission based on network scheduling with sl-ScheduledConfig, and sl-TxPoolExceptional is included in sl-ConfigDedicatedNR. WHEN: UE receives an RRCReconfiguration message including reconfigurationWithSync THEN: UE performs NR sidelink transmission using sl-TxPoolExceptional included in sl-ConfigDedicatedNR during handover procedure TP2: [38.331: cl 5.8.8] WITH: UE in RRC_CONNECTED state and performing NR sidelink tranmission based on network scheduling with sl-ScheduledConfig, and sl-TxPoolExceptional is included in sl-ConfigDedicatedNR. WHEN: UE detects physical layer problems by receiving N310 consecutive out-of-sync indications from lower layers THEN: UE performs NR sidelink transmission using sl-TxPoolExceptional included in sl-ConfigDedicatedNR until receiving RRCReestablishment message | TDIA/CATT | RAN5#97 (Nov-22) | R5-227469 R5-231437 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
186 | Y | 38.523-1 | 12.2.1.6 | Inter-carrier concurrent operation / Sidelink communication / RRC_CONNECTED / Reception | TP1:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and its serving cell doesn't broadcast SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in pre-configuration. TP2:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and its serving cell broadcasts SIB12. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in SIB12. TP3:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and has received a RRCReconfiguration includes sl-RxPool. WHEN: UE is configured by upper layer to perform NR sidelink reception. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool ncluded in sl-ConfigDedicatedNR. TP4:[TS 38.331: 5.8.7] WITH: UE is in RRC_CONNECTED state and is configured by upper layer to perform NR sidelink reception. WHEN: UE receives a RRCReconfiguration includes reconfigurationWithSync and sl-RxPool. THEN: UE is able to monitor NR sidelink transmission using sl-RxPool included in the recieved RRCReconfiguration message during handover procedure. | TDIA/CATT | RAN5#93 (Nov-21) | R5-221518 R5-223369 R5-227465 R5-231583 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
187 |  | 38.523-1 | 12.2.2 | Inter-carrier concurrent operation / Sidelink synchronization related procedure | Sub-clause heading |  | RAN5#97 (Nov-22) | R5-224561 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
188 | Y | 38.523-1 | 12.2.2.1 | Inter-carrier concurrent operation / Sidelink synchronization related procedure / Synchonization reference source (re-)selection | TP1: [38.331: 5.8.6.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss. WHEN: GNSS signal is reliable and a SyncRef UE directly synchronized to GNSS is detected. THEN: UE selects GNSS as synchonization reference source. TP2: [38.331: 5.8.6.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss. WHEN: Two SyncRef UEs, one directly synchronized to GNSS and the other indirectly synchronized to GNSS, are detected. THEN: UE selects the SyncRef UE directly synchronized to GNSS as synchonization reference source. TP3: [38.331: 5.8.6.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss. WHEN: One SyncRef UE indirectly synchronized to GNSS is detected. THEN: UE selects the SyncRef UE indirectly synchronized to GNSS as synchonization reference source. TP4: [38.331: 5.8.6.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb. WHEN: A SyncRef UE directly synchronized to gNB is detected. THEN: UE selects serving cell as synchonization reference source. TP5: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: Two SyncRef UEs, one directly synchronized to gNB and the other indirectly synchronized to gNB, are detected. THEN: UE selects the SyncRef UE directly synchrinized to gNB as synchonization reference source TP6: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: GNSS is reliable and one SyncRef UE indirectly synchronized to gNB is detected. THEN: UE selects the SyncRef UE indirectly synchrinized to gNB as synchonization reference source. TP7: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: GNSS is reliable and one SyncRef UE directly synchronized to GNSS is detected. THEN: UE selects GNSS as synchonization reference source. TP8: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: Two SyncRef UEs, one directly synchronized to GNSS and the other indirectly synchronized to GNSS, are detected. THEN: UE selects the SyncRef UE directly synchronized to GNSS as synchonization reference source. TP9: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: Two SyncRef UEs, one indirectly synchronized to GNSS and the other one neither directly nor indirectly synchronized to GNSS or gNB, are detected. THEN: UE selects the SyncRef UE indirectly synchronized to GNSS as synchonization reference source TP10: [38.331: 5.8.6.2] WITH: UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb in pre-configuration. WHEN: A SyncRef UE which neither directly nor indirectly synchronized to GNSS or gNB is detected. THEN: UE selects the SyncRef UE which neither directly nor indirectly synchronized to GNSS or gNB as synchonization reference source. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224561 R5-231428 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
189 | Y | 38.523-1 | 12.2.2.2 | Inter-carrier concurrent operation / Sidelink synchronization related procedure / SL-SSB transmission Initiation and Cease | TP1: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb, syncTxThreshIC but no networkControlledSyncTx. WHEN: SS-RSRP of serving cell is higher than syncTxThreshIC. THEN: UE doesn’t transmit S-SSB. TP2: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb, syncTxThreshIC but no networkControlledSyncTx. WHEN: SS-RSRP of serving cell is lower than syncTxThreshIC. THEN: UE starts transmiting S-SSB. TP3: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb. WHEN: UE receives an RRCReconfiguration message with networkControlledSyncTx = off. THEN: UE doesn’t transmit S-SSB. TP4: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnbEnb. WHEN: UE receives an RRCReconfiguration message with networkControlledSyncTx = on. THEN: UE starts transmiting S-SSB. TP5: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss. syncTxThreshOoC is configured in pre-configuration. WHEN: UE selects a SyncRef UE as synchronization reference source. PSBCH-RSRP of the SyncRef UE is higher than syncTxThreshOoC. THEN: UE doesn’t transmit S-SSB. TP6: [38.331: 5.8.5.2] WITH: UE is on connected state. UE is configured by upper layer to perform sidelink transmission and is configured with sl-SyncPriority = gnss. syncTxThreshOoC is configured in pre-configuration. WHEN: UE selects a SyncRef UE as synchronization reference source. PSBCH-RSRP of the SyncRef UE is lower than syncTxThreshOoC. THEN: UE starts transmiting S-SSB. | TDIA/CATT | RAN5#97 (Nov-22) | R5-224562 R5-231429 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
190 |  | 38.523-1 | 12.2.3 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206412 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
191 | Y | 38.523-1 | 12.2.3.1 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC / CBR measurement reporting / Event C1 and C2 | TP1: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and is configured to perform event C1 triggered CBR measurement reporting on resource pool WHEN: CBR measurement result of indicated resource pool satisfies entering condition for event C1 THEN: UE sends MeasurementReport message to report CBR measurement results of indicated resource pool TP2: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and the periodical measurement reporting triggered by event C1 is ongoing WHEN: CBR measurement result of indicated resource pool satisfies leaving condition for event C1 THEN: UE stops sending MeasurementReport message TP3: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and is configured to perform event C2 triggered CBR measurement reporting on resource pool WHEN: CBR measurement result of indicated resource pool satisfies entering condition for event C1 THEN: UE sends MeasurementReport message to report CBR measurement results of indicated resource pool. TP4: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is in NR RRC_CONNECTED state and the periodical measurement reporting triggered by event C2 is ongoing WHEN: CBR measurement result of indicated resource pool satisfies leaving condition for event C2 THEN: UE stops sending MeasurementReport message | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-206412 R5-224563 R5-231430 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
192 | Y | 38.523-1 | 12.2.3.2 | Inter-carrier concurrent operation / Measurement configuration and reporting via Uu RRC / CBR measurement reporting / Periodical reporting | TP1: [38.331: 5.5.2, 5.5.3, 5.5.4.11, 5.5.4.12, 5.5.5] WITH: UE is configured to perform periodical CBR measurement reporting on resource pools. WHEN: The first measurement result is available and thereafter every time periodical timer expires. THEN: UE triggers CBR measurement reporting. | TDIA/CATT | RAN5#93 (Nov-21) | R5-217892 R5-225293 R5-227464 R5-231436 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
193 |  | 38.523-1 | 12.2.4 | Inter-carrier concurrent operation / Sidelink Reconfiguration via Uu RRC | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
194 | Y | 38.523-1 | 12.2.4.1 | Inter-carrier concurrent operation / Sidelink Reconfiguration via Uu RRC / SL DRB management / transmission side | TP1: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to establish a groupcast SL DRB. THEN: UE establish a SL DRB and sends an RRCReconfigurationComplete message. TP2: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB addition. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE establishes the SL DRB. TP3: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE. WHEN: UE receives an RRCReconfiguration message to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB addition. After receiving RRCReconfigurationFailureSidelink message from peer UE, UE doesn't establish the SL DRB and sends a SidelinkUEInformationNR message to inform about sidelink reconfiguration failure. TP4: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE receives an RRCReconfiguration message to modify the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB modification. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE modifies the SL DRB. TP5: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE receives an RRCReconfiguration message to reconfigure QoS-flow to SL DRB mapping. After reconfiguration no QoS flow is mapped to the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB release. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE releases the SL DRB. TP6: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE receives an RRCReconfiguration message to release the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB release. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE releases the SL DRB. | TDIA/CATT | RAN5#99 (May-23) | R5-218002 R5-222715 R5-227581 R5-231434 R5-234517 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
195 |  | 38.523-1 | 12.2.5 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
196 | Y | 38.523-1 | 12.2.5.1 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement configuration | TP1: [38.331 cl.5.8.10.2] WITH: UE is on connected state. UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfiguration message which provides PSBCH-RSRP measurement configuration. THEN: UE sends a RRCReconfigurationSidelink message to peer UE. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224564 R5-242912 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
197 | Y | 38.523-1 | 12.2.5.2 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Event S1 and S2 | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is on connected state. UE received an RRCReconfigurationSidelink message from peer UE to configure event S1 triggered PSBCH-RSRP measurement reporting.. WHEN: PSBCH-RSRP measurement on peer UE is below event S1 threshold.. THEN: UE doesn't transmit MeasurementReportSidelink message. TP2: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is on connected state. UE received an RRCReconfigurationSidelink message from peer UE to configure event S1 triggered PSBCH-RSRP measurement reporting.. WHEN: PSBCH-RSRP measurement on peer UE is above event S1 threshold. THEN: UE transmits an MeasurementReportSidelink message to peer UE. TP3: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is on connected state. UE received an RRCReconfigurationSidelink message from peer UE to configure event S2 triggered PSBCH-RSRP measurement reporting.. WHEN: PSBCH-RSRP measurement on peer UE is above event S2 threshold. THEN: UE doesn't transmit MeasurementReportSidelink message. TP4: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is on connected state. UE received an RRCReconfigurationSidelink message from peer UE to configure event S2 triggered PSBCH-RSRP measurement reporting. WHEN: PSBCH-RSRP measurement on peer UE is below event S2 threshold. THEN: UE transmits an MeasurementReportSidelink message to peer UE. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224565 R5-243535 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
198 | Y | 38.523-1 | 12.2.5.3 | Inter-carrier concurrent operation / Measurement configuration and reporting via PC5 RRC / PSBCH-RSRP measurement reporting / Periodical reporting | TP1: [38.331: 5.8.10.2, 5.8.10.3, 5.8.10.4, 5.8.10.5] WITH: UE is configured to perform periodical PSBCH-RSRP measurement reporting on SL SSB via PC5 RRC. WHEN: The first measurement result is avaible and afterforth every time periodical timer expires. THEN: UE trigger PSBCH-RSRP measurement reporting until the total number of measurement reports is 16. | TDIA/CATT | RAN5#95 (May-22) | R5-218003 R5-223370 R5-227466 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
199 |  | 38.523-1 | 12.2.6 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
200 | Y | 38.523-1 | 12.2.6.1 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Initiating UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE is in connected state and having established PC5-RRC connection with peer UE. WHEN: UE is indicated by upper layer to establish a unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB addition. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE establishes the SL DRB. TP2: [38.331: 5.8.9.1a.2] WITH: UE is in connected state and having established PC5-RRC connection with peer UE and has estabished a unicast SL DRB. WHEN: UE is indicated by upper layer to release the unicast SL DRB. THEN: UE sends a RRCReconfigurationSidelink message to peer UE to indicate SL DRB release. After receiving RRCReconfigurationCompleteSidelink message from peer UE, UE releases the SL DRB. | TDIA/CATT | RAN5#97 (Nov-22) | R5-218004 R5-227580 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
201 | Y | 38.523-1 | 12.2.6.2 | Inter-carrier concurrent operation / Sidelink Reconfiguration via PC5 RRC / SL DRB management / Peer UE side | TP1: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE. WHEN: UE receives an RRCReconfigurationSidelink message from peer UE to establish a unicast SL DRB. THEN: UE establish a SL DRB and sends an RRCReconfigurationCompleteSidelink message to peer UE and sends SidelinkUEInformationNR message to serving cell. TP2: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has established a unicast SL DRB. WHEN: UE receives an RRCReconfigurationSidelink message to modify the unicast SL DRB that UE can comply. THEN: UE modifies the SL DRB and sends an RRCReconfigurationCompleteSidelink message to peer UE. TP3: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has established a unicast SL DRB. WHEN: UE receives an RRCReconfigurationSidelink message to modify the unicast SL DRB that UE can't comply. THEN: UE doesn't modify the SL DRB and sends an RRCReconfigurationFailureSidelink message to peer UE. TP4: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has established a unicast SL DRB. WHEN: UE receives an RRCReconfigurationSidelink message to release the unicast SL DRB. THEN: UE releases the SL DRB and sends an RRCReconfigurationCompleteSidelink message to peer UE. TP5: [38.331: 5.8.9.1a.2] WITH: UE is in connected state. UE has established PC5-RRC connection with peer UE and has established a unicast SL DRB. WHEN: UE receives an RRCReconfigurationSidelink message to reconfigure QoS-flow to SL DRB mapping. After reconfiguration no QoS flow is mapped to the unicast SL DRB. THEN: UE releases the SL DRB and sends an RRCReconfigurationCompleteSidelink message to peer UE. | Huawei, Hisilicon | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
202 |  | 38.523-1 | 12.2.7 | Inter-carrier concurrent operation / Sidelink CSI reporting | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
203 | Y | 38.523-1 | 12.2.7.1 | Inter-carrier concurrent operation / Sidelink CSI reporting / Configuration | TP1: [38.331 5.8.9.1.1] WITH: UE in NR RRC_CONNECTED state and having established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to configure SL CSI-RS resource to peer UE. THEN: UE sends an RRCReconfigurationSidelink message including sl-CSI-RS-Config to peer UE and starts to transmit SL CSI-RS. TP2: [38.331 5.8.9.1.1] WITH: UE in NR RRC_CONNECTED state and having established PC5 RRC connection with peer UE. WHEN: UE is configured by upper layer to trigger SL CSI report. THEN: UE sends an SCI format 2-A to trigger SL CSI report. | TDIA/CATT | RAN5#97 (Nov-22) | R5-218005 R5-227582 R5-231427 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
204 | Y | 38.523-1 | 12.2.7.2 | Inter-carrier concurrent operation / Sidelink CSI reporting / Reporting | TP1: [38.331 5.8.9.1.1] WITH: UE has established PC5 RRC connection with peer UE and is configuredby peer UE to perform CSI measurement. WHEN: UE receives a SCI format 2-A to trigger SL CSI report. THEN: UE sends an CSI reporting MAC-CE to peer UE within SL CSI report latency requirement. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-225448 R5-231427 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
205 |  | 38.523-1 | 12.2.8 | Inter-carrier concurrent operation / Sidelink failure | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
206 | Y | 38.523-1 | 12.2.8.1 | Inter-carrier concurrent operation / Sidelink failure / PC5 RRC Reconfiguration Failure / Initiating UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE is in connected state. UE has established PC5 RRC connection with peer UE on unicast sidelink and has sent an RRCReconfigurationSidelink message to peer UE. WHEN: UE receives an RRCReconfigurationFailureSidelink from peer UE. THEN: UE continues to use the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a SidelinkUEInformation message to indicate sidelink reconfiguration failure. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224567 R5-227467 R5-231435 | Title in R5-224567 mismatches with WP. To be fixed in next meeting. | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
207 | Y | 38.523-1 | 12.2.8.2 | Inter-carrier concurrent operation / Sidelink failure / PC5 RRC Reconfiguration Failure / Peer UE side | TP1: [38.331: 5.8.9.1.8] WITH: UE in NR RRC_CONNECTED and having established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives an RRCReconfigurationSidelink that UE can't comply from peer UE. THEN: UE continues to use the configuration used prior to corresponding RRCReconfigurationSidelink message and sends a RRCReconfigurationFailureSidelink message. | TDIA/CATT | RAN5#97 (Nov-22) | R5-218006 R5-227468 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
208 | Y | 38.523-1 | 12.2.8.3 | Inter-carrier concurrent operation / Sidelink failure / Sidelink radio link failure / transmission side | TP1: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE is in connected state. UE has established PC5 RRC connection with peer UE on unicast sidelink and has sent an RRCReconfigurationSidelink message to peer UE. WHEN: UE doesn't receive RRCReconfigurationCompleteSidelink or RRCReconfigurationFailure before T400 expires THEN: UE releases PC5-RRC connection and indicates the release to upper layer and sends a SidelinkUEInformationNR message to indicate SL RLF. TP2: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE is in connected state. UE has established PC5 RRC connection with peer UE on unicast sidelink and has established a AM SL DRB. WHEN: Retransmission number of the AM SL DRB reaches the maximum number of retransmissions. THEN: UE releases PC5-RRC connection and indicates the release to upper layer and sends a SidelinkUEInformationNR message to indicate SL RLF. TP3: [38.331: 5.8.3.3, 5.8.9.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: MAC detects that maximum number of consecutive HARQ DTX has been reached. THEN: UE releases PC5-RRC connection and indicates the release to upper layer and sends a SidelinkUEInformationNR message to indicate SL RLF. | Huawei, Hisilicon | RAN5#97 (Nov-22) | R5-224568 R5-231432 R5-232716 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
209 |  | 38.523-1 | 12.2.9 | Inter-carrier concurrent operation / Sidelink UE capability transfer via PC5 RRC | Sub-clause heading |  | RAN5#99 (May-23) | R5-240766 |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
210 | Y | 38.523-1 | 12.2.9.1 | Inter-carrier concurrent operation / Sidelink UE capability transfer via PC5 RRC / One-way and two-way transfer | TP1: [38.331: 5.8.9.2.1, 5.8.9.2.4] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message from peer UE. THEN: UE sends a UECapabilityInformationSidelink message to peer UE. TP2: [38.331: 5.8.3.1, 5.8.3.2, 5.8.3.3, 5.8.9.2.1, 5.8.9.2.4] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelinkfrom peer UE. THEN: UE sends a UECapabilityInformationSidelink message to peer UE and sends a SidelinkUEInformationNR message to report sidelink UE capability information of peer UE. TP3: [38.331: 5.8.9.2.1, 5.8.9.2.2, 5.8.9.2.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure. THEN: UE sends a UECapabilityEnquirySidelink message to peer UE. TP4: [38.331: 5.8.9.2.1, 5.8.9.2.2, 5.8.9.2.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE is configured by upper layer to initiate capability transfer procedure and to provide UE radio access capabilities. THEN: UE sends a UECapabilityEnquirySidelink message with ue-CapabilityInformationSidelink to peer UE. TP5: [38.331: 5.8.3.1, 5.8.3.2, 5.8.3.3] WITH: UE has established PC5 RRC connection with peer UE on unicast sidelink. WHEN: UE receives a UECapabilityInformationSidelink message. THEN: UE sends a SidelinkUEInformationNR message to report sidelink UE capability information of peer UE. | Huawei, Hisilicon | RAN5#99 (May-23) | R5-240766 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
409 |  | 38.523-1 | 12.2.10 | Inter-concurrent operation / MAC | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
410 |  | 38.523-1 | 12.2.10.1 | Inter-concurrent operation / MAC / HARQ process | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
411 | Y | 38.523-1 | 12.2.10.1.1 | Inter-concurrent operation / MAC / HARQ process / dynamic sidelink grant | TP1: [ref: TS 38.321 cl.5.22.1.1] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UE receives a DCI format 3_0 scrambled with RNTI which is different with UE's SL-RNTI. Then: UE doesn't perform sidelink transmission. TP2: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UE receives a DCI format 3_0 scrambled with UE's SL-RNTI and NDI is toggled compared with the previous NDI value of the sidelink process indicated by the DCI. Then: UE uses the SL grant for the initial transmission of SL-SCH MAC PDU. TP3: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UE receives a DCI format 3_0 scrambled with UE's SL-RNTI and NDI is not toggled compared with the previous NDI value of the sidelink process indicated by the DCI. Then: UE uses the SL grant for the re-transmission of the SL-SCH MAC PDU associated with the indicated sidelink process. TP4: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and is configured with PUCCH resource for SL HARQ. WHEN: UE receives a DCI format 3_0 scrambled with UE's SL-RNTI and NDI is toggled while UE has no data to transmit. Then: UE sents a ACK on PUCCH associated with the SL grant. TP5: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and is configured with PUCCH resource for SL HARQ. ACK-NACK HARQ is applied. WHEN: UE is indicated by PHY layer that NACK is received on PSFCH corresponding to the sent PSSCH. Then: UE sents a NACK on PUCCH associated with the SL grant. TP6: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and is configured with PUCCH resource for SL HARQ. ACK-NACK HARQ is applied. WHEN: UE is indicated by PHY layer that ACK is received on PSFCH corresponding to the sent PSSCH. Then: UE sents an ACK on PUCCH associated with the SL grant. TP7: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and is configured with PUCCH resource for SL HARQ. NACK-only HARQ is applied. WHEN: UE is indicated by PHY layer that NACK is received on PSFCH corresponding to the sent PSSCH. Then: UE sents a NACK on PUCCH associated with the SL grant. TP8: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and is configured with PUCCH resource for SL HARQ. NACK-only HARQ is applied. WHEN: UE is indicated by PHY layer that no NACK is received on PSFCH corresponding to the sent PSSCH. Then: UE sents a ACK on PUCCH associated with the SL grant. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
412 | Y | 38.523-1 | 12.2.10.1.2 | Inter-concurrent operation / MAC / HARQ process / configured sidelink grant | TP1: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UE is configured with a type 1 sidelink configuration grant. Then: In each SL CG period UE uses the SL CG for initial transmission. TP2: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE is configured with a type 1 sidelink configuration grant WHEN: UE is configured to release the type 1 sidelink configuration grant. Then: UE stops to use the SL CG for transmission. TP3: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UE is configured with a deactivated type 2 sidelink configuration grant. Then: UE doesn't use the SL CG for initial transmission. TP4: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3, TS 38.213 cl.10.2A] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and a deactivated type 2 sidelink configuration grant. WHEN: UE receives a DCI format 3_0 scrambled with UE's SLCS-RNTI. in the DCI, NDI = 0, HARQ process number is set to all zero and Configuration index field indicates a deactivated type 2 sidelink configuration grant. Then: UE sends a Sidelink Configured Grant Confirmation MAC-CE and starts to use the SL CG for initial transmission. TP5: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3, TS 38.213 cl.10.2A] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and a activated sidelink configuration grant. WHEN: UE receives a DCI format 3_0 scrambled with UE's SLCS-RNTI. In the DCI, NDI = 1 and Configuration index field indicates an activated type 2 sidelink configuration grant associated to SL process indicated by HARQ process number field. Then: UE use the SL CG for re-transmission of SL-SCH MAC PDU associated with the indicated SL process. TP6: [ref: TS 38.321 cl.5.8.3, 5.22.1.1, 5.22.1.3, TS 38.213 cl.10.2A] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission and an activated type 2 sidelink configuration grant. WHEN: UE receives a DCI format 3_0 scrambled with UE's SLCS-RNTI. in the DCI, NDI = 1, HARQ process number is set to all one and Configuration index field indicates a activated type 2 sidelink configuration grant. Then: UE sends a Sidelink Configured Grant Confirmation MAC-CE and stops using the SL CG for transmission. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
413 | Y | 38.523-1 | 12.2.10.1.3 | Inter-concurrent operation / MAC / HARQ process / selected sidelink grant | TP1: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.2, 5.22.1.3] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: Data arrives at logical channel. Then: UE creates a selected SL grant and uses it for transmission. TP2: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.2, 5.22.1.3] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: SL CSI reporting is triggered. Then: UE creates a selected SL grant and uses it to send SL CSI reporting MAC-CE. TP3: [ref: TS 38.321 cl.5.22.1.1, 5.22.1.2, 5.22.1.3] WITH: UE is configured to perform mode 2 sidelink transmission. WHEN: UE receives a NACK on PSFCH corresponding to the sent PSSCH. Then: UE re-transmits the SL-SCH MAC-CE. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
414 | Y | 38.523-1 | 12.2.10.1.4 | Inter-concurrent operation / MAC / HARQ process / ACK-NACK HARQ reception | TP1: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and HARQ feedback is disabled by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE doesn't sent PSFCH. TP2: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and ACK-NACK HARQ feedback is indicated by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE sends an ACK feedback on PSFCH. TP3: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and ACK-NACK HARQ feedback is enabled by its associated SCI. UE fails to decode the SL-SCH MAC PDU. Then: UE sends a NACK feedback on PSFCH. TP4: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to unicast is received and its associated destination L2 ID doesn't match with any source L2 ID of the UE or its associated source L2 ID doesn't match with any destination L2 ID of the UE. Then: UE discards this MAC PDU. TP5: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to unicast is received and its associated destination L2 ID matches with a source L2 ID of the UE and its associated source L2 ID matches with a destination L2 ID of the UE. Then: UE submits MAC SDU(s) contained in the MAC PDU to upper layer. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
415 | Y | 38.523-1 | 12.2.10.1.5 | Inter-concurrent operation / MAC / HARQ process / NACK-only HARQ reception | TP1: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and NACK-only HARQ feedback is indicated by its associated SCI. UE successfully decodes the SL-SCH MAC PDU. Then: UE doesn't send PSFCH. TP2: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a SL-SCH TB is received from PHY layer and NACK-only HARQ feedback is enabled by its associated SCI. UE fails to decode the SL-SCH MAC PDU. Then: UE sends a NACK feedback on PSFCH. TP3: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to groupcast is successfully decoded and its associated destination L2 ID doesn't match with a destination L2 ID of the UE. Then: UE discards this MAC PDU. TP4: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3] WITH: UE is configured to perform sidelink reception. WHEN: a MAC PDU associated to groupcast is successfully decoded and its associated destination L2 ID matches with a destination L2 ID of the UE. Then: UE submits MAC SDU(s) contained in the MAC PDU to upper layer. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
416 | Y | 38.523-1 | 12.2.10.1.6 | Inter-concurrent operation / MAC / HARQ process / SL-SCH Transport block size selection | TP1: [ref: TS 38.321 cl.5.22.2.1, 5.22.2.2, 5.22.2.3, TS 38.214 cl.8.1.3.2] WITH: UE is configured to perform sidelink reception. WHEN: UE receives SCI format 1-A indicating a SL-SCH TB corresponding to Frequency resource assignment, Time resource assignment, Modulation and coding scheme and PSFCH overhead indication THEN: UE decodes the received SL-SCH TB transport block of size correctly and forwards it to higher layers |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
417 |  | 38.523-1 | 12.2.10.2 | Inter-concurrent operation / MAC / Multiplexing and Assembly | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
418 | Y | 38.523-1 | 12.2.10.2.1 | Inter-concurrent operation / MAC / Multiplexing and Assembly / Logical channel prioritization without mapping restriction | TP1: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at a SCCH and several STCHs with different destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the SCCH in assembled MAC PDU. TP2: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: UE has a SL CSI reporing MAC-CE to send and data arrives at several STCHs with different destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the MAC-CE in assembled MAC PDU. TP3: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with different destinations L2 IDs. Some of these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the logical channel with highest priority among all logical channels with SBj>0. TP4: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with different destinations L2 IDs. All these STCHs have SBj < 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: UE only includes MAC SDUs from those logical channels which have the same destination with the logical channel with highest priority. TP5: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is not enough to transmit all available data at all logical channels. THEN: UE includes MAC SDUs from logical channels in a strict decreasing priority order. TP6: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. Some of these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all data available at logical channels with SBj > 0 but not enough to transmit all available data at all logical channels. THEN: After including all SDUs from logical channels with SBj > 0. UE includes MAC SDUs from logical channels with SBj < 0 in a strict decreasing priority order. TP7: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is configured to perform sidelink transmission and no mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with the same destinations L2 IDs. All these STCHs have SBj > 0. Transmission opportunity indicated by PHY layer is enough to transmit all available data at all logical channels. THEN: After including all SDUs from all logical channels, UE includes a subPDU with padding bits in MAC PDU. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
419 | Y | 38.523-1 | 12.2.10.2.2 | Inter-concurrent operation / MAC / Multiplexing and Assembly / Logical channel prioritization with mapping restriction | TP1: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is in connected state. UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. and the SL grant used is a Type 1 configured sidelink grant. THEN: UE only considers those logical channels with sl-ConfiguredGrantType1Allowed in LCP procedure. TP2: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is in connected state. UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. and the SL grant used is a Type 1 configured sidelink grant. THEN: UE dosen't consider those logical channels, which are configured with sl-AllowedCG-List and CG ID of the Type 1 SL CG is not included sl-AllowedCG-List, in LCP procedure. TP3: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is in connected state. UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is not configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = disabled in LCP procedure. TP4: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is in connected state. UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. logical channels with highest priority is configured with sl-HARQ-FeedbackEnabled = enabled. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = enabled in LCP procedure. TP5: [ref: TS 38.321 cl.5.22.1.4] WITH: UE is in connected state. UE is configured to perform sidelink transmission and mapping restriction is configured for logical channels. Resource pool used for sidelink transmission is configured with PSFCH resources. WHEN: Data arrives at several STCHs with same destinations L2 IDs. All these STCHs have SBj > 0. logical channels with highest priority is configured with sl-HARQ-FeedbackEnabled = disabled. THEN: UE only considers those logical channels configured with sl-HARQ-FeedbackEnabled = disabled in LCP procedure. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
420 |  | 38.523-1 | 12.2.10.3 | Inter-concurrent operation / MAC / Uu procedures related to sidelink | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
421 | Y | 38.523-1 | 12.2.10.3.1 | Inter-concurrent operation / MAC / Uu procedures related to sidelink / Sidelink buffer status reporting | TP1: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 2 sidelink transmission. WHEN: UE is reconfigured to perform mode 1 sidelink transmission and data arrives at STCHs. THEN: UE sends a regular SL-BSR. TP2: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: Data arrives at one STCH and it is the only STCH which has data to send. THEN: UE sends a regular SL-BSR. TP3: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: Data arrives at one STCH and its priority is higher than other STCH which has data to send. THEN: UE sends a regular SL-BSR. TP4: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: sl-retxBSR-Timer is expired and there still is data to transmit. THEN: UE sends a regular SL-BSR. TP5: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: sl-periodicBSR-Timer is expired and there still is data to transmit. THEN: UE sends a periodic SL-BSR. TP6: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. WHEN: UL grant still has remaining resources after transmitting all UL data and padding BSR. THEN: UE sends a padding SL-BSR. TP7: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE has triggered a regular SL-BSR. WHEN: a SL LCG is prioritized over UL LCG and the UL grant can't accommodate a SL-BSR containing buffer status of all SL LCGs. THEN: UE sends a Truncated SL BSR MAC-CE only containing prioritized SL LCG(s). TP8: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE has triggered a regular SL-BSR. WHEN: No SL LCG is prioritized over UL LCG and the UL grant can't accommodate a SL-BSR containing buffer status of all SL LCGs. THEN: UE sends a Truncated SL BSR MAC-CE. TP9: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE has triggered a regular SL-BSR. WHEN: No SL LCG is prioritized over UL LCG and the UL grant can accommodate a SL-BSR containing buffer status of all SL LCGs that have data to send. THEN: UE sends a SL BSR MAC-CE. TP10: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission UE has triggered a padding SL-BSR. WHEN: UL grant can't accommodate a SL-BSR containing buffer status of all SL LCGs. THEN: UE sends a Truncated SL BSR MAC-CE. TP11: [TS 38.321 cl.5.22.1.6] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission UE has triggered a padding SL-BSR. WHEN: UL grant can accommodate a SL-BSR containing buffer status of all SL LCGs. THEN: UE sends a SL BSR MAC-CE. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
422 | Y | 38.523-1 | 12.2.10.3.2 | Inter-concurrent operation / MAC / Uu procedures related to sidelink / Scheduling request | TP1: [TS 38.321 cl.5.22.1.5] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE has triggered a Regular SL-BSR. UE is configured with SR resources. WHEN: UE dosen't has UL grant to send SL-BSR MAC-CE. THEN: UE triggers a scheduling request. TP2: [TS 38.321 cl.5.22.1.5] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE has triggered a Regular SL-BSR. UE is configured with SR resources. WHEN: UE has a UL grant but UE can't accommodate the SL-BSR MAC-CE due to LCP procedure. THEN: UE triggers a scheduling request. TP3: [TS 38.321 cl.5.22.1.5] WITH: UE is in connected state. UE is configured to perform mode 1 sidelink transmission. UE is configured with SR resources. UE has established PC5-RRC with peer UE. SL-CSI reporting has been triggered by SCI from peer UE and sl-CSI-ReportTimer is running. WHEN: UE doesn't has SL grant to send SL CSI report MAC-CE. THEN: UE triggers a scheduling request. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
423 |  | 38.523-1 | 12.2.10.4 | Inter-concurrent operation / MAC / Sidelink CSI reporting | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
424 | Y | 38.523-1 | 12.2.10.4.1 | Inter-concurrent operation / MAC / Sidelink CSI reporting / reception side | TP1: [TS 38.321 cl.5.22.1.7] WITH: UE is in connected state. UE has established PC5-RRC with peer UE. SL-CSI reporting has been triggered by SCI from peer UE and sl-CSI-ReportTimer is running. WHEN: UE has SL grant to send SL CSI report MAC-CE. THEN: UE sends SL CSI report MAC-CE |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% | 0% |  | 0% |  |  | 0%
212 |  | 38.523-1 | 12.3 | Intra-carrier concurrent operation | Sub-clause heading |  | RAN5#99 (May-23) |  |  | 0 | 0% | 0% | 0% |  | 0% |  |  | 0%
V2X Layer
213 |  | 38.523-1 | 13 | V2X layer | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% | 100% | 100% |  | 100% |  |  | 100%
214 |  | 38.523-1 | 13.1 | V2X policy provisioning | Sub-clause heading |  | RAN5#93 (Nov-21) |  |  | 0 | 100% | 100% |  |  | 100%
215 | Y | 38.523-1 | 13.1.1 | V2X policy provisioning / Precedence / Validity timer expires / geographical area changes | **** TP1: [TS 24.587 clause 5.2.2] WITH: UE having V2XP over PC5 configured in the USIM and UE being out of NR network coverage. WHEN: UE is required to start NR V2X communication. THEN: UE conducts V2X communication according to parameters of V2XP over PC5 from USIM **** TP2: [TS 24.587 clause 5.2.3 item a] WITH: UE having V2XP over PC5 configured in the USIM and UE being in NR network coverage WHEN: UE receives V2XP over PC5 from SS and then NR cell is off. THEN: UE conducts V2X communication according to parameters of V2XP over PC5 from SS **** TP3: [TS 24.587 clause 5.2.3 item i] WITH: UE having received V2XP over PC5 from SS WHEN: Validaty timer expires and NR is on. THEN: UE initiates a UE-requested V2X policy provisioning procedure. **** TP4: [TS 24.587 clause 5.2.3 item i] WITH: UE having received V2XP over PC5 from SS after UE initiate a UE-requested V2X policy provisioning procedure. WHEN: UE is located in the geographical area and UE is requested by a service to transmit a V2X packet. THEN: UE initiate a V2X communication on the frequency associated with the service. **** TP5: [TS 24.587 clause 5.2.3 item i] WITH: UE having initiated a V2X communication on the frequency associated with the service. WHEN: UE moves out of the geographical area. THEN: UE can not continue the V2X communication on the frequency associated with the service. | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-217890 R5-221523 R5-227171 |  | 1 | 100% | 100% |  |  | 100%
216 |  | 38.523-1 | 13.2 | PC5 unicast | Sub-clause heading |  | RAN5#95 (May-22) | R5-221519 |  | 0 | 100% |  | 100% |  |  |  |  | 100%
217 | Y | 38.523-1 | 13.2.1 | PC5 unicast / link establishment / Reject / Conflict Layer 2 ID | **** TP1: [TS 24.587 clause 6.1.2.2] WITH: UE is out of coverage, Test loopback activation and V2X Setup. WHEN: UE has a V2X packet to be transmitted over PC5. THEN: UE initiate PC5 unicast link establishment procedure. **** TP2: [TS 24.587 clause 6.1.2.2.5] WITH: UE has transmitted PC5 unicast link establishment Request message. WHEN: The Layer 2 ID is conflicted. THEN: the PC5 unicast link establishment procedure failed. | Huawei, Hisilicon | RAN5#95 (May-22) | R5-221520 R5-223064 R5-227172 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
218 | Y | 38.523-1 | 13.2.2 | PC5 unicast / link Security Mode | **** TP1: [TS 24.587 clause 6.1.2.7.3] WITH: UE receives a DIRECT LINK SECURITY MODE COMMAND message. WHEN: The DIRECT LINK SECURITY MODE COMMAND message includs not matching replayed UE security capabilities. THEN: UE transmits a DIRECT LINK SECURITY MODE REJECT message. | Huawei, Hisilicon | RAN5#95 (May-22) | R5-221521 R5-223065 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
219 | Y | 38.523-1 | 13.2.3 | PC5 unicast / link modification | **** TP1: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to add a QoS flow. THEN: UE can communicate using the newly added QoS flow. **** TP2: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to modify a QoS flow. THEN: UE can communicate using the newly modified QoS flow. **** TP3: [TS 24.587 clause 6.1.2.3.2] WITH: UE has set up a V2X PDU session over PC5. WHEN: UE receives a DIRECT LINK MODIFICATION REQUEST to delete a QoS flow. THEN: No V2X data is communicated using the deleted QoS flow. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223372 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
220 | Y | 38.523-1 | 13.2.4 | PC5 unicast / link Release / Reestablish PC5 unicast link to same UE | **** TP1: [TS 24.587 clause 6.1.2.4.4] WITH: UE has established a V2X DIRECT LINK with a K_NRP ID to a SS-UE, and Release the DIRECT LINK after receiving a DIRECT LINK RELEASE REQUEST message. WHEN: UE has a V2X packet to be transmitted over PC5 to the same SS-UE. THEN: UE transmit DIRECT LINK ESTABLISHMENT REQUEST with same K_NRP ID. | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223373 R5-225295 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
221 | Y | 38.523-1 | 13.2.5 | PC5 unicast / link identifier update | **** TP1: [TS 24.587 clause 6.1.2.5.6] WITH: UE having established a DIRECT LINK with Layer 2 ID-1 to a peer UE. WHEN: UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message with same Layer 2 ID-1 but with user info different from the user info IE included in this message. THEN: UE transmits a DIRECT LINK IDENTIFIER UPDATE REJECT message. **** TP2: [TS 24.587 clause 6.1.2.5.3, 6.1.2.5.4] WITH: UE having established a DIRECT LINK with old Layer 2 ID-1 to a peer UE. UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message and responds with a DIRECT LINK IDENTIFIER UPDATE ACCEPT message with new Layer 2 ID-2. WHEN: UE receives a V2X packet from the peer UE. THEN: the Layer 2 ID associated with the V2X packet is the old Layer 2 ID-1. **** TP3: [TS 24.587 clause 6.1.2.5.3, 6.1.2.5.4] WITH: UE having established a DIRECT LINK with old Layer 2 ID-1 to a peer UE. UE receives a DIRECT LINK IDENTIFIER UPDATE REQUEST message and responds with a DIRECT LINK IDENTIFIER UPDATE ACCEPT message with new Layer 2 ID-2. WHEN: UE receives a DIRECT LINK IDENTIFIER UPDATE ACK message from the peer UE. THEN: UE transmits a V2X packet and the Layer 2 ID associated with the V2X packet is the new Layer 2 ID-2. | TDIA/CATT | RAN5#97 (Nov-22) | R5-217893 R5-225292 R5-227470 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
222 | Y | 38.523-1 | 13.2.6 | PC5 unicast / link keep alive | **** TP1: [TS 24.587 clause 6.1.2.8.5.1] WITH: UE transmitted a DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n. WHEN: UE didn't receive DIRECT LINK KEEPALIVE RESPONSE message when T5003 expires. THEN: UE re-transmit a DIRECT LINK KEEPALIVE REQUEST message with same Keep-alive counter value of n. **** TP2: [TS 24.587 clause 6.1.2.8.5.2] WITH: UE received a first DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n1, and UE responed a DIRECT LINK KEEPALIVE RESPONSE message. WHEN: UE received a second DIRECT LINK KEEPALIVE REQUEST message with Keep-alive counter value of n2 < n1 THEN: UE does not transmit a DIRECT LINK KEEPALIVE RESPONSE message for the second DIRECT LINK KEEPALIVE REQUEST message. | Huawei, Hisilicon | RAN5#95 (May-22) | R5-221522 R5-223376 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
223 |  | 38.523-1 | 13.3 | PC5 groupcast | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0
224 |  | 38.523-1 | 13.4 | PC5 broadcast | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0
225 |  | 38.523-1 | 13.5 | Uu Unicast | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0
226 |  | 38.523-1 | 13.6 | PC5 Unicast security | Sub-clause heading |  | RAN5#97 (Nov-22) |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
227 |  | 38.523-2 | 4.1 | Applicibility for NR SL test cases | Add test case applicability statements for the new test cases introduced in 38.523-1 | Huawei, HiSilicon, CATT, TDIA | RAN5#99 (May-23) | R5-213572 R5-217895 R5-221527 R5-221528 R5-223377 R5-225296 R5-227471 R5-241540 |  | 0.1 | 55% | 55% | 55% |  | 55% |  |  | 55%
432 |  | 38.523-2 | 4.2 | ICS for NR SL test cases | Add test case applicability expressions for the new test cases introduced in 38.523-1 | Huawei, HiSilicon, CATT, TDIA | RAN5#99 (May-23) | R5-213572 R5-217895 R5-221527 R5-221528 R5-223377 R5-225296 R5-242914 |  | 0.1 | 60% (+10%) | 60% (+10%) | 60% (+10%) |  | 60% |  |  | 60%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
464 |  | 38.523-3 | 5.2.1 | Test model for NR sidelink test | To add test model for NR sidelink test | MCC TF160 | RAN5#93 (Nov-21) | R5-217896 R5-221529 R5-223378 R5-227583 R5-231565 R5-232194 R5-233833 R5-241541 | Test model for PDCP/RLC is FFS | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
480 |  | 38.523-3 | 6.1 | Upper tester interface | To add upper tester interfaces for NR sidelink test | MCC TF160 | RAN5#95 (May-22) | R5-221529 R5-227583 |  | 0.2 | 100% | 100% | 100% |  | 100% |  |  | 100%
465 |  | 38.523-3 | 7.3.8 | VOID | VOID | MCC TF160 | RAN5#95 (May-22) | R5-217896 |  | 0
481 |  | 38.523-3 | 7.4 | Test methods and design considerations for NR sidelink | To add test methods and design considerations for NR sidelink Signaling test | MCC TF160 | RAN5#94 (Feb-22) | R5-221529 R5-227583 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
466 |  | 38.523-3 | 9.2 | PIXIT for NR sidelink test | To add PIXIT for NR sidelink test | MCC TF160 | RAN5#93 (Nov-21) | R5-217896 |  | TBD | 100% |  | 100% |  |  |  |  | 100%
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.571-4: UE positioning test suites (TTCN)
|  | 38.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
482 |  | 38.571-4 | 6C | NR/5GC test models requiring GNSS support | To update GNSS test models to support NR sidelink test | MCC TF160 | RAN5#94 (Feb-22) | R5-220457 |  | 1 | 100% | 100% | 100% |  | 100% |  |  | 100%
TBD |  | 38.571-4 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.