## Cover sheet
3GPP TSG-RAN5 Meeting #103 | [10 empty] | R5-242851
Fukuoka, Japan, May 20-24, 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance - Network energy savings for NR
Work item code: | Netw_Energy_NR-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of UE Conformance - Network energy savings for NR is to define the UE conformance requirements corresponding to WID on Network energy savings for NR, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-18. At the RAN#103 meeting in March 2024 the Rel-18 RAN5 work item for UE Conformance - Network energy savings for NR was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 6 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 6 (+6)
FR1 |  | 5% (+5%) | 0 | 6 (+6)
FR2 |  | 5% (+5%) | 0 | 6 (+6)
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 6 (+6) | 0% | 0 | 6 (+6) | 0% | 0 | 6 (+6)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-240291 | New WID on UE Conformance - Network energy savings for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Network energy savings for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | Netw_Energy_NR-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Network energy savings for NR comprising the necessary new clauses/test cases and updates to existing clauses/test cases. | [13 empty] | vs Area
WP Resp: |  | Yaping Zhang |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 5% (+5%) | 5% (+5%)
[15 empty] | 7 (+7) | 7 (+7) | 0 | 0 | 0 | 0
[15 empty] | 6.1 (+6.1) | 6.1 (+6.1) | 0 | 0 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | 6.1.2 | NG-RAN Only Cell Selection |  |  | RAN5#108 (Aug-25) |  |  | 0
TBD | Y | 38.523-1 | 6.1.2.28 | Cell selection / NES mode | Verify that legacy UEs can't camp on the cells that adopt NES techniques. |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
Layer 2
TBD |  | 38.523-1 | 7.1.1.14 | Network Energy Saving | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
TBD |  | 38.523-1 | 7.1.1.14.1 | Cell DTX/DRX adaptations | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
TBD | Y | 38.523-1 | 7.1.1.14.1.1 | Cell DTX operation / Correct handling of DL assignment | Verify that UEs do not monitor PDCCH when cell DTX operation is activated and the Serving Cell is not in the cell DTX Active Period |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.14.1.2 | Cell DRX operation / Correct handling of UL grant | Verify that UEs do not transmit SR when cell DRX operation is activated and the Serving Cell is not in the cell DRX Active Period |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TBD |  | 38.523-1 | 7.1.1.14.2 | NES spatial and power domain adaptations | New sub-clause header |  | RAN5#108 (Aug-25) |  |  | 0
TBD | Y | 38.523-1 | 7.1.1.14.2.1 | NES spatial domain Type 1 adaptation / Periodic CSI reporting | Verify that UEs should perform periodic CSI reporting for each CSI report subconfiguration defined for NES spatial domain Type 1 adaptation |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.14.2.2 | NES spatial domain Type 2 adaptation / Aperiodic CSI reporting | Verify that UEs should perform aperiodic CSI reporting for each CSI report subconfiguration defined for NES spatial domain Type 2 adaptation |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TBD | Y | 38.523-1 | 7.1.1.14.2.3 | NES power domain adaptation / Semi-periodic CSI reporting on PUCCH | Verify that UEs should perform semi-periodic CSI reporting on PUCCH for each CSI report subconfiguration defined for NES power domain adaptation |  | RAN5#108 (Aug-25) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.