## Cover sheet
3GPP TSG-RAN5 Meeting #103 | [10 empty] | R5-242853
Fukuoka, Japan, May 20-24, 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18
Work item code: | LTE_NR_Simult_RxTx_R18-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 is to define the UE conformance requirements corresponding to WID on Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-18. At the RAN#103 meeting in March 2024 the Rel-18 RAN5 work item for UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core work item. The workplan is updated after each RAN5 meeting to give the status of the work item. In the WID on "LTE_NR _Simult_RxTx_R18", RAN4 tracks the request for NR band combinations supporting simultaneous Rx/Tx. Among those NR band combinations, only CA_n39A-n41A is in the status of "ongoing" in RAN5. Therefore, CA_n39A-n41A is selected as the example configuration to complete this WI. Other configurations will be marked as "Core requirements in Rel-18 core specifications should be followed if UE reports support of simultaneous RxTx capability" in PRD 21.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 58% (+58%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+100%)
FR1 |  | 100% (+100%)
FR2
FR1 + FR2
NSA Option 3 (EN-DC) |  | 5% (+5%)
FR1 |  | 5% (+5%)
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx | 100% (+100%) |  |  | 100% (+100%)
FR1 RF Rx test cases | 38.521-1 Rx | 100% (+100%) |  |  | 100% (+100%)
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 0% | [11 empty] | 0%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 0% | [11 empty] | 0%
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 0% | [11 empty] | 0%
Test Point analysis receiver and transmitter test cases | 38.905
5 References
[1] RP-240292 | New WID on UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_Simult_RxTx_R18-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 comprising the necessary new clauses/test cases and updates to existing clauses/test cases. | [13 empty] | vs Area
WP Resp: |  | Yaping Zhang |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 100% (+100%) |  |  | 5% (+5%)
[15 empty] | 5 (+5) | 0 | 0 | 4 (+4) | 0 | 0
[15 empty] | 5 (+5) | 0 | 0 | 4 (+4) | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
TBD |  | 38.521-1 | 5.2A | Operating bands for CA | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 | 5.2A.2 | Inter-band CA | Sub-clause header |  |  |  |  | 0
TS 38.521-1: FR1 RF test cases - Tx
TBD |  | 38.521-1 Tx | 6.2A.4 | Configured output power for CA | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2A.4.0 | Minimum conformance requirements | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2A.4.0.2 | ΔTIB,c for CA | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2A.4.0.2.3 | ΔTIB,c for Inter-band CA | Update the ΔTIB,c value for CA_n39A-n41A for UE supporting simultaneous RxTx capability | CMCC | RAN5#105 (Nov-24) | R5-243046 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
TBD |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.3A.0 | Minimum conformance requirements | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.3A.0.3 | ΔRIB,c for CA | Sub-clause header |  |  |  |  | 0
|  | 38.521-1 Rx | 7.3A.0.3.2 | ΔRIB,c for Inter-band CA | Update the ΔRIB,c value for CA_n39A-n41A for UE supporting simultaneous RxTx capability | CMCC | RAN5#105 (Nov-24) | R5-243047 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TBD |  | 38.521-1 Rx | 7.3A.0.4 | Reference sensitivity exceptions due to UL harmonic interference for CA | Add the MSD requirements for CA_n39A-n41A for UE supporting simultaneous RxTx capability | CMCC | RAN5#105 (Nov-24) | R5-243048 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TBD |  | 38.521-1 Rx | 7.3A.0.6 | Reference sensitivity exceptions due to cross band isolation for CA | Add the MSD requirements for CA_n39A-n41A for UE supporting simultaneous RxTx capability | CMCC | RAN5#105 (Nov-24) | R5-243049 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TBD |  | 38.521-1 Rx | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions | Add the exception test points and test requirements for CA_n39A-n41A for UE supporting simultaneous RxTx capability | CMCC | RAN5#105 (Nov-24) | R5-243838 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 | 5.5B | Configuration for DC | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 | 5.5B.4 | Inter-band EN-DC within FR1 | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 | 5.5B.4.1 | Inter-band EN-DC configurations within FR1 (two bands) | Update the indication of simultaneous RxTx capability for DC_39A_n41A and DC_40A_n41A |  | RAN5#105 (Nov-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx | 6.2B.4 | Configured Output Power for EN-DC | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 Tx | 6.2B.4.2 | ΔTIB,c for EN-DC | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 Tx | 6.2B.4.2.3 | Inter-Band EN-DC within FR1 | Update the ΔTIB,c value for DC_40A_n41A for UE supporting simultaneous RxTx capability |  | RAN5#105 (Nov-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx | 7.3B.2 | Reference sensitivity for EN-DC | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 Rx | 7.3B.2.0 | Minimum Conformance Requirements of Reference sensitivity for EN-DC | Sub-clause header |  |  |  |  | 0
TBD |  | 38.521-3 Rx | 7.3B.2.0.3 | Inter-band EN-DC within FR1 | Add the MSD requirements for DC_39A_n41A and DC_40A_n41A for UE supporting simultaneous RxTx capability |  | RAN5#105 (Nov-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TBD |  | 38.521-3 Rx | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) | Add the exception test points and test requirements for DC_39A_n41A and DC_40A_n41A for UE supporting simultaneous RxTx capability |  | RAN5#105 (Nov-24) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
TBD |  | 38.905 | 4.1.3.1 | Reference Sensitivity test cases for FR1 NR CA | Update the test point analysis for reference sensitivity for CA_n39A-n41A | CMCC | RAN5#105 (Nov-24) | R5-243836 |  | 0.5
TBD |  | 38.905 | 4.3.3.1 | Reference sensitivity test cases for EN-DC | Update the test point analysis for reference sensitivity for DC_39A_n41A and DC_40A_N41a |  | RAN5#105 (Nov-24) |  |  | 0.5
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.