## Slide 1
3GPP RAN WG2 Chair
Diana Pani
Status Report RAN WG2
RAN 106
RP-242420

## Slide 2: Executive Summary
Meetings | Date | Location | Scope
RAN2#127bis | October 14th – 18th, 2024 | Hefei, China | Maintenance, Rel-19
RAN2#128 | Nov. 18th – 22nd, 2024 | Orlando, US | Maintenance, Rel-19
RAN #106 | Dec 9th – 12th, 2024 | Madrid, Spain | 
Rel-18 Work Items
  Good progress on identified issues including UE capabilities.
  Workload remains high
Rel-19 Work Items – currently 1 Study Item and 9 WIs ongoing
  Progress on track for all SIs/WIs.
  Study on AIoT considered complete from RAN2 point of view.
  Started TEI19, BDS and NavIC positioning WIs
Rel-15/16/17 maintenance
  Workload similar to previous quarter

## Slide 3: Delegates in RAN2
RAN2#127bis had 710 delegates registered - 410 attended f2f
RAN2#128 had 674 delegates registered - 432 attended f2f
Chart: RAN2 Attendees
| 121bis-e | 122 | 123 | 123bis | 124 | 125 | 125bis | 126 | 127 | 127bis | 128
Attendees | 570 | 491 | 523 | 333 | 389 | 418 | 363 | 447 | 455 | 410 | 432

## Slide 4: Submitted contributions in RAN2
Contribution numbers stable compared to previous quarter
  Tdoc limits and reduced Rel-18 workload
Chart: Tdocs per meeting
| 121bis-e | 122 | 123 | 123bis | 124 | 125 | 125bis | 126 | 127 | 127bis | 128
Tdocs | 2087 | 2288 | 2269 | 2098 | 2369 | 2045 | 1813 | 1993 | 1620 | 1461 | 1716

## Slide 5: RAN2 Agreed CRs
Rel-17 workload stable
Rel-18 workload remains high with 200 Rel-18 CRs agreed in RAN2#128
Chart: Agreed CRs per meeting
| 119-e | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128
Rel-14/15/16 | 49 | 36 | 32 | 43 | 26 | 24 | 15 | 26 | 14 | 20
Rel-17 | 140 | 131 | 136 | 157 | 64 | 93 | 46 | 56 | 27 | 63
Rel-18 | 0 | 0 | 0 | 0 | 0 | 162 | 183 | 188 | 103 | 200

## Slide 6: Time in RAN2
Rel-19 WI/Sis | AI/ML | AI/ML Mob. | AIoT | NES | LP-WUS | NTN/IoT NTN | SL relay | XR | Mobility | SBFD | SON/ MDT | MIMO | Pos (BDS and NAVIC) | Maintenance
Assigned TUs (per meeting) | 2.5 | 2 | 2.5 | 1 | 1 | 3 | 1 | 2 | 2 | 0.75 | 0.5 | 0.75 | 0.75 | 14.75
Approx Online time spent RAN2#128 | 3 | 2.5 | 4 | 1.75 | 1.75 | 4.5 | 2 | 2.5 | 2.75 | 1 | 1 | .75 | .75 | 15.5
3 parallel sessions are used for official online discussions throughout the week.
  Online time spent for all Rel-19 WIs is generally 25-75% higher. Maintenance still continues to occupy a significant amount of time in RAN2 (~35% of the time)
1 offline session is used for official offline discussions

## Slide 7: Maintenance up to Rel-17

## Slide 8: Maintenance up to Rel-17
Number of CRs for Rel-17 lower than previous meetings
  63 Rel-17 CRs agreed
  20 Rel-15/16 CRs agreed
NBC CRs
This CR is considered mandatory for UE and NW which implement both one-shot HARQ Feedback and HARQ Feedback enabled/disabled in NR NTN.
  R2-2411118 Correction on HARQ-RTT-TimerDL-NTN in NR NTN CATT, LG Electronics Inc., Sharp CR Rel-17 38.321 17.10.0 2019 - F NR_NTN_solutions-Core
  R2-2411119 Correction on HARQ-RTT-TimerDL-NTN in NR NTN CATT, LG Electronics Inc., Sharp CR Rel-18 38.321 18.3.0 2020 - A NR_NTN_solutions-Core

## Slide 9: Rel-18 NR

## Slide 10: Maintenance up to Rel-18
Workload and number of CRs decreased compared to previous meeting, but load still remains high
  200 CR agreed for Rel-18
  No ASN.1 NBC RRC CR
NBC CR – Functional NBC
  IDC feature - This CR is mandatory to implement for UEs and networks supporting IDC enhancements for NR and MR-DC.
    R2-2411080 Correction on the idc-TDM-AssistanceConfig Huawei, HiSilicon, Xiaomi, Nokia, Intel Corporation, Ericsson, Apple, Samsung CR Rel-18 38.331 18.3.0 5062 2 F NR_IDC_enh-Core
  Positioning feature - This CR is considered mandatory for Positioning SRS bandwidth aggregation in RRC_INACTIVE with or without validity area.
    R2-2411189 Correction for positioning SRS CA in RRC_INACTIVE Huawei, HiSilicon, Ericsson, Samsung CR Rel-18 38.331 18.3.0 5150 1 F NR_pos_enh2

## Slide 11: Rel-19 NR

## Slide 12: Rel-19 RAN2 Led WID/SIDs
Updates in RED
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020084 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR | FS_NR_AIML_Mob | 9/15/2025 | 38% | RP-242393 | 50% | 
1021091 | Core part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Core | 9/15/2025 | 20% | RP-242356 | 50% | 
1021097 | Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Core | 9/15/2025 | 45% | RP-241789 | 55% | 
1021098 | Core part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Core | 9/15/2025 | 30% | RP-241771 | 55% | 
1040114 | NR sidelink multi-hop relay | NR_SL_relay_multihop | 9/15/2025 | 15% | RP-242349 | 40% | 
1050121 | Introduction of BDS B2b Signal in A-GNSS | LCS_BDS_B2b_LTE_NR | 6/9/2025 | 0% | RP-242413 | 70% | 
1050122 | Introduction of A-GNSS support for NavIC L1 SPS in NR and LTE | LCS_NAVIC_L1_SPS_NR_LTE | 6/9/2025 | 0% | RP-242414 | 50% | 
1021096 | Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Core | 9/15/2025 | 30% | RP-242397 | 50% | 
1031076 | Inter RAT mode mobility support from E-UTRAN TN to NR-NTN | LTE_TN_NR_NTN_mob | 9/15/2025 | 95% | RP-240924 | 96% | 
Notes: RP-241771
RP-241789

## Slide 13: Rel-19 WIs
Currently RAN2 has 15 WIs ongoing and 1 SI just completed
  Work on SL Relay and SBFD was kicked off in RAN#127
Good overall progress across WIs/SIs
  AI/ML
    Good progress on LCM and NW side data collection.
    Data collection work has stopped waiting for SA2 LS. Expecting guidance from RAN 106.
    No progress on model transfer study, initial discussions in Q2 but waiting for RAN1 progress.
  Ambient IoT – SI considered complete from RAN2 point of view. RAN Plenary discussion on scope of WI, which should be limited given short timeline.
  SON/MDT – Scope of WI has been reduced in RAN2

## Slide 14: TEI17/18 - Summary
21 Agreed CRs
  6 Cat B CRs
  10 Cat F
  5 Cat A
Details of each agreed TEI18 CR and corresponding identifier in Appendix
  [CG-SDTenh]
  [Intra-Band_EN-DC_Channelspacing]
  [SI-SCHEDULING]
  [2Rx_XR_Device]
  [RACH-lessHO]
  [EM_Call_Exemption]
  [Max-RRC-SegUL]

## Slide 15: Next Steps
Upcoming Meetings | Date | Location | Scope
RAN2#129 | February 17th – 21st, 2025 | Athens, Greece | Maintenance, R19
Rel-18
  Continue work on stabilizing Rel-18 specifications. CRs still expected for a number of WIs and corrections/finalization of UE capabilities issues.
Rel-19 work
  Continue Rel-19 progress

## Slide 16: THANK YOU!!!
Juha Korhonen (MCC) – for his excellent and efficient support
Vice Chairs - Kyeongin Jeong and Erlin Zeng for efficiently chairing and helping with RAN2 management
Session chairs - Sergio Parolari, Nathan Tenny, Dawid Koziol, and Mattias Bergstrom for efficiently chairing sessions in Q3
UE capability rapporteur (Ziyi Li) for coordinating all the UE capability work across all WGs
All WI and CR spec rapporteurs for managing all the Rel-18 corrections
All delegates for your hard work, dedication, willingness to compromise and work together towards consensus
Thank you to CSSA and ATIS for hosting in Hefei and Orlando

## Slide 17: Appendix – TEI identifiers and CRs

## Slide 18: Rel-17 RAN2 TEI (1/2)
[Max-RRC-SegUL]
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2411230 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Huawei, HiSilicon | CR | Rel-17 | 36.306 | 17.7.0 | TEI17 | 1904 |  | B
R2-2411231 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Huawei, HiSilicon | CR | Rel-18 | 36.306 | 18.3.0 | TEI17 | 1905 |  | A
R2-2411247 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Qualcomm Incorporated | CR | Rel-17 | 38.331 | 17.10.0 | TEI17 | 5004 | 3 | B
R2-2411248 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Qualcomm Incorporated | CR | Rel-18 | 38.331 | 18.3.0 | TEI17 | 5113 | 1 | A
R2-2411249 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Qualcomm Incorporated | CR | Rel-17 | 38.306 | 17.10.0 | TEI17 | 1202 | 1 | B
R2-2411250 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Qualcomm Incorporated | CR | Rel-18 | 38.306 | 18.3.0 | TEI17 | 1203 | 1 | A
R2-2411252 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Huawei, HiSilicon | CR | Rel-17 | 36.331 | 17.10.0 | TEI17 | 5083 | 1 | B
R2-2411253 | Introduction of network signalling of maximum number of UL segments [Max-RRC-SegUL] | Huawei, HiSilicon | CR | Rel-18 | 36.331 | 18.3.1 | TEI17 | 5084 | 1 | A

## Slide 19: Rel-17 TEI (2/2)
[SI-SCHEDULING]
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2411033 | Correction of maxSI messages [SI-SCHEDULING] | Xiaomi | CR | Rel-17 | 38.331 | 17.10.0 | TEI17 | 5107 | 1 | F
R2-2411034 | Correction of maxSI messages [SI-SCHEDULING] | Xiaomi | CR | Rel-18 | 38.331 | 18.3.0 | TEI17 | 5108 | 1 | A

## Slide 20: Rel18 – TEI18 (RAN2)
[CG-SDTenh]
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2410226 | Rapporteur CR for MT-SDT and CG-SDT enhancement [CG-SDTenh] | Huawei, HiSilicon | CR | Rel-18 | 38.321 | 18.3.0 | TEI18, NR_MT_SDT-Core | 2001 |  | F
R2-2410820 | Correction to co-existence of multi-PUSCH CG and CG-SDTenh [CG-SDTenh] | Huawei, HiSIlicon | CR | Rel-18 | 38.321 | 18.3.0 | TEI18, NR_XR_enh-Core | 1997 | 1 | F
R2-2411108 | Correction for Paging monitoring during SDT [CG-SDT-Enh] | Huawei, HiSilicon, LG Electronics Inc., ZTE Corporation, Sanechips, MediaTek Inc. | CR | Rel-18 | 38.331 | 18.3.0 | TEI18 | 4901 | 3 | F
R2-2411223 | Correction to RRC for CG-SDT enhancement [CG-SDTenh] | Huawei, HiSilicon | CR | Rel-18 | 38.331 | 18.3.0 | TEI18, NR_MT_SDT-Core | 5152 | 1 | F

## Slide 21: Rel-18 TEI
[2Rx_XR_Device]
[RACH-lessHO]
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2411075 | Correction for cell barring for 2Rx XR UE [2Rx_XR_Device] | Huawei, HiSilicon, Xiaomi, Ericsson, LGE, ZTE Corporation | CR | Rel-18 | 38.331 | 18.3.0 | TEI18 | 4851 | 3 | F
R2-2411109 | Clarifications on cell barring behaviour [2Rx_XR_Device] [EM_Call_Exemption] | Qualcomm Incorporated, Huawei, ZTE, Ericsson, LG Electronics Inc., Nokia, Samsung, Vivo | CR | Rel-18 | 38.331 | 18.3.0 | TEI18, NR_IAB-Core, NR_redcap-Core, NR_UAV-Core, NR_mobile_IAB-Core, NR_ATG-Core, NR_netcon_repeater, NR_redcap_enh-Core | 5112 | 1 | F
R2-2411110 | Clarifications on cell barring behaviour [2Rx_XR_Device] [EM_Call_Exemption] | Qualcomm Incorporated, Huawei, ZTE, Ericsson, LG Electronics Inc., Nokia, Samsung, Vivo | CR | Rel-18 | 38.304 | 18.3.0 | TEI18, NR_IAB-Core, NR_redcap-Core, NR_UAV-Core, NR_mobile_IAB-Core, NR_ATG-Core, NR_netcon_repeater, NR_redcap_enh-Core | 0421 | 1 | F
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2411093 | Correction on RACH-less handover fallback [RACH-lessHO] | Huawei, HiSilicon, Samsung, CATT, LG Electronics, Nokia, Nokia Shanghai Bell, Ericsson | CR | Rel-18 | 38.321 | 18.3.0 | NR_mobile_IAB-Core, NR_NTN_enh-Core, TEI18 | 1972 | 3 | F
R2-2411178 | Correction on RACH-less handover procedure in TS38.321 [RACH-lessHO] | CATT, Samsung, InterDigital, Ericsson, Qualcomm Incorporated, LG Electronics Inc., Huawei, HiSilicon, vivo | CR | Rel-18 | 38.321 | 18.3.0 | TEI18, NR_NTN_enh-Core, NR_mobile_IAB-Core | 2003 | 1 | F

## Slide 22: TEI18 – RAN4 led
[Intra-Band_EN-DC_Channelspacing] – RAN4
  Related to agreed CR in Q2: R4-2414423 - CR1292 for 38.101-3 (Reference missing from cover sheet)
TDoc | Title | Source | Type | Release | Spec | Version | Related WIs | CR | CR revision | CR category
R2-2410833 | Introduction of new capability for intra-band EN-DC channel spacing [Intra-Band_EN-DC_Channelspacing] | Huawei, HiSilicon | CR | Rel-18 | 38.331 | 18.3.0 | TEI18 | 5013 | 1 | B
R2-2410834 | Introduction of new capability for intra-band EN-DC channel spacing [Intra-Band_EN-DC_Channelspacing] | Huawei, HiSilicon | CR | Rel-18 | 38.306 | 18.3.0 | TEI18 | 1174 | 2 | B

## Slide 23: TEI18 – RAN1 Led/Impact
None

## Slide 24: TEI18 – RAN3 Led/Impact
None