## Slide 1: Way Forward Rel-14 RAN1/RAN2/RAN4-led
Qualcomm [Ericsson, DoCoMo, Nokia Networks, Alcatel-Lucent, Alcatel-Lucent SB, Dish, European Broadcasting Union, Sony, Interdigital, Mitsubishi Electric, Deutsche Telekom, Hughes Systems, NextNav]?
3GPP TSG RAN Meeting #71
Göteborg, Sweden, 7-10 March, 2016
RP-160663

## Slide 2: Following items proposed for approval
  RAN1-led:
  eMBMS
    Objectives d & f to be studied
    Objective a includes evaluation (exact CP length)
  FD-MIMO
    Deprioritize higher resolution for CSI reporting
  MUST
    No CSI enhancements
  UL Capacity Enhancements
    UL 256QAM only
    PUSCH UpPTS
  SRS carrier switching
  FeCOMP
    With very major downscope: two very minor items only
  Increase V2V WID of 0.5 TUs to cater for questions to RAN1
  RAN2-led:
  eLWA
  FeD2D
  VoLTE enhancement
    Remove RAN1 scope
  Latency reduction (L2)
    Remove contention based PUSCH
  Light connection
    Study phase w/ limited allocation in Q2-16
  Indoor positioning
    Limited allocation (0.25 TU in R1 & R2)
  # All proposals require to adjust their scope.
  RAN4-led:
  BS AAS
  Measurement gap enhancement
  MIMO OTA
  Increase V2V WID of 0.5 Tus for RAN4 task
Ensure ~3 TUs available for NB-IoT enhancement and from RAN#72

## Slide 3: RAN1 TU allocation
 | Q2/16 |  | Q3/16 | Q4/16 |  | Q1/17 | Total
 | #84bis | #85 | #86 | #86bis | #87 | #88 | 
MUST | 1 | 1 | 1.5 | 2 | 2 |  | 
FD-MIMO | 3 | 3 | 3 | 3 | 3 | 3 | 
UL enhancements | 1 | 1 | 1 | 1 | 1 |  | 
eMBMS | 1.5 | 1.5 | 1 | 1 | 1 |  | 
SRS carrier switching | 0.5 | 0.5 | 0.5 |  |  |  | 
eCoMP (removing SRS, CSI, LAA) |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 
V2V boost (ongoing) | 0.5 | 0.5 |  |  |  |  | 
Indoor positioning (RAN2 lead) | 0.25 |  | 0.25 |  | 0.25 |  | 
FeD2D (RAN2 lead) |  |  | ? | ? | ? | ? | 
VoLTE (RAN2 lead) |  |  | 0.5 |  |  |  | 
Total | 7.75 | 8 | 8.25 | 7.5 | 8.25 | 4 | 

## Slide 4: RAN2 TU allocation
 | Q2/16 |  | Q3/16 | Q4/16 |  | Q1/17 | Total
 | #93bis | #94 | #95 | #95bis | #96 | #97 | 
VOLTE | 1.5 | 1 | 1 | [x] | [x] | [x] | 3.5
Latency | 1 | 1 | 1 |  |  |  | 3
Light Connection | 0.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 7
Indoor Positioning | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 2.25
LWA enh. | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 9
FeD2D | 1.5 | 1.5 | [1.5] | [2] | [2] | [2] | 10.5
EMBMS |  | 0.5 | 0.5 | 1 | 1 | 1 | 
SRS carrier switching (RAN1 lead) |  |  |  | 0.5 | 0.5 |  | 1
Measurement Gap (RAN4 lead) |  |  |  | 1 | 1 | 0.5 | 
Total | 6.25 | 6.25 | 5.75 | 6.75 | 6.75 | 5.5 | 

## Slide 5: RAN4 TU for RAN4/RAN1 new WI/SI
 | Q2/16 |  | Q3/16 | Q4/16 |  | Q1/17 | Total
 | 78bis | 79 | 80 | 80bis | 81 | 82 | 
AAS | RF 1 | RF 1 | RF 2 | RF 2 | RF 2 RRM 0.5 | RF 2 RRM 0.5 | 
MIMO OTA | RF 0.5 | RF 0.5 | RF 0.5 | RF 0.5 | RF 0.5 | RF 0.5 | 
Measurement gap enhancement | RRM 0.5 | RRM 1 | RRM 1.5 | RRM 1.5 | RRM 1.5 | RRM 1.5 | 
MUST | -- | RRM 1 | RRM 1 | -- | -- | RRM 1.5 | 
eFD-MIMO | -- | -- | -- | -- | -- | -- | 
SRS Switching | RF 0.5 RRM 0.5 | RF 1 RRM 1 | RF 1 RRM 1 | RF 1 RRM 1 | RF 1 RRM 1 | RF 1 RRM 1 | 
UL enhancement | -- | -- | RRM 1 | -- | -- | RRM 2 | 
Indoor positioning | RF 0.25 | RF 0.25 | RF 0.5 RRM 1 | RF 0.5 RRM 2 | RF 0.5 RRM 2 | RRM 1 | 
Total |  |  |  |  |  |  | 
RAN1/RAN2 impact of RAN4 new items: only Measurement gap enhancement
RAN2: 1+0.5 TU in Q4/16, RAN1 (maybe some)