## Slide 1: NR schedule and phases
DRAFT
Input for lunchtime drafting 15/06 (Wednesday)
RP-161239

## Slide 2: TSG-RAN agreements on NR scope
  Overall Release-15 timeline unchanged, completion target June/2018
Target content for Rel-15
  Both Standalone and Non-Standalone included, work starting in conjunction and running together
    Non-standalone NR in this context implies using LTE as control plane anchor
    Standalone NR in this context implies full control plane capability for NR, potentially including components enabling configuration with LTE SCell
  eMBB, Low Latency, and High Reliability (to enable some URLLC use cases) in scope
  <6GHz and >6GHz in scope
  Detailed target content subject to eventual SI conclusions and agreed WID scope

## Slide 3: NR workplan in TSG-RAN
Ask RAN1/RAN2/RAN3/RAN4/SA2 to ensure availability of forward compatibility and report to RAN#75
  This report will aid the scoping of the WID and the expected NR timeline
Target functional requirements impacting L1 design should be available by WID approval (March/2017)
  Potential addition and/or removal of target functional requirements may be undertaken in subsequent TSG meetings as per normal process
L1/L2 NR aspects:
  Common aspects of Standalone/Non-standalone L1/L2 stage 3, and principles of Standalone-specific components  completion target Dec/2017 – see box 3 on timeplan
  Standalone specific L1/L2 stage 3  completion target March/2018
Higher Layers NR aspects:
  Non-Standalone higher layers completion target to be defined at RAN#75
  Standalone higher layers completion target June/2018.

## Slide 4: Overall timeline for NR in TSG-RAN
2. CHECKPOINT: RAN#75: March 2017:
- Completion of SI with corresponding performance evaluation and concepts;
- Approval of WID(s); - Report from RAN1/RAN2/RAN3/RAN4/SA2 on fwd compatibility of NSA and SA NR;
- Reconfirmation of NR timeplan, including completion target for NSA higher layer components (box 4)
4. RAN#78/RAN#79: Stage-3 freeze for Non-Standalone higher layers (including components common with standalone). Completion target TBD.
5. RAN#80, June 2018: Release 15 stage 3 freeze for NR, including Standalone.
1. RAN#73, September 2016:
5G NR Requirements TR completion
2017
2016
3. RAN#78, December 2017:
- Stage 3 freeze of L1/L2 for common aspects of NSA (focused on licensed bands) and SA NR;
- Principles agreed for SA-specific L1/L2 components.
2018
Note: SA: Standalone
NSA: Non-Standalone

## Slide 5: Issues for joint meeting with TSG-SA
NexGen core functionality and RAN Rel-15 content aligned with eachother, to be included in Rel-15 as per re-confirmed schedule
  Contineous coordination between RAN, SA, and CT should take place
Core network connectivity for LTE-assisted Non-standalone NR
Core network connectivity for Standalone NR
  Assumed to only consider connectivity to NexGen core
Consideration around Non-standalone and Standalone NR deployments existing in parallel (roaming, device capabilities, etc…)