## Slide 1: Release 16 WI/SI package
Source: TSG-RAN Chairman, RAN1 Chairman,
RAN2 Chairman,
RAN3 Chairman.
RP-180649
3GPP TSG-RAN#80
La Jolla, USA, 11-14 June, 2018

## Slide 2: Introduction
Based on analysis of input to RAN#80 the 4 chairmen compiled a potential starting point for a Rel-16 work package discussion
  The guiding principle was to compile a package that is manageable for the WGs in terms of load, and well represents the different interests of the 3GPP community
These slides focus on Rel16 SI/WIs for RAN1, RAN2, and RAN3
  Other WGs are not addressed here
The package presented here should be understood as the absolute maximum in terms of number of items and work amount that can be taken on board in these WGs
  It is assumed that each WI/SI is well scoped with precise objectives that fit within the allocated TUs

## Slide 3: Timeline
Rel-16 SI
Q2
Q3
Q4
2019
Q2
Q3
Q4
Q1
2020
Q1
Rel-16 SI/WI phase
Rel-16 freeze
Rel-16 ASN.1
Rel-15 SA (option-2) freeze
Rel-15 late drop freeze
2018
Q1
2017
Q4
Rel-15 NSA (option-3) freeze
Rel-15 NSA (option-3) ASN.1
Rel-15 SA (option-2) ASN.1
Rel-15 late drop ASN.1

## Slide 4: RAN1
2018 Q3
2018 Q4
2019 Q2
2019 Q3
2019 Q4
2019 Q1
NR MIMO WI
NR V2X SI
NR V2X WI
eURLLC SI
eURLLC WI
NR-U SI
NR-U WI
NOMA SI
NR non-terrestrial SI
IAB SI
IAB WI
RAN1 led
RAN2 led
RIM SI
NR Positioning WI
Misc impacts coming from other RAN2/3/4 SI/WI
NB-IoT enhancements (LTE track)
eMTC enhancements (LTE track)
NR:11 LTE: 5 | NR:32 LTE:14 | NR:18 LTE: 9 | NR:40 LTE:19 | NR:21 LTE:10 | NR:42 LTE:20
1 | 5 | 2 | 6 | 3 | 6
2 | 4 | 2 | 6 | 3 | 6
2.5 | 5 | 3 | 6 | 4 | 8
2.5 | 5 | 1 | 2 | 1 | 2
1 | 2 | 2 | 2 | 1 | 2
0 | 3 | 1 | 4 | 1 | 2
0 | 2 | 2 | 3 | 2 | 4
0 | 0 | 1 | 2 | 1 | 2
2 | 5 | 3 | 7 | 4 | 8
2 | 5 | 3 | 6 | 3 | 6
1 | 2 | 1 | 2 | 1 | 2
0 | 0 | 1 | 2 | 1 | 2
1 | 4 | 2 | 4 | 2 | 4
0 | 0 | 1 | 2 | 1 | 2
RAN1 TUs
Mobility enhancements WI
NR Positioning SI
NOMA continuation SI or WI
NR UE power consumption SI
NR UE power consumption WI
NR-NR DC WI
NR-NR DC sync (TBD for late drop)
2018 Q3
2018 Q4
2019Q1
2019Q2
2019Q3
2019Q4
RIM WI
Note: Yellow numbers show TUs from the LTE allocation, in some cases for NR WIs/SI

## Slide 5: RAN2 and RAN3
2018 Q3
2018 Q4
2019 Q2
2019 Q3
2019 Q4
2019 Q1
IAB SI
IAB WI
eURLLC SI
eURLLC SI
NR Mobility enhancement SI/WI
MR DC enh. SI
MR DC enh. WI
RAN2 led
RAN3 led
NR SON/MDT SI
NR SON/MDT WI
Misc impacts from RAN1 and RAN2 SI/WIs
NR:2 LTE:0 | NR:14 LTE:14 | NR:9 LTE:9 | NR:29 LTE:19 | NR:16 LTE:10 | NR:36 LTE:20
1 | 4 | 2 | 6 | 3 | 6
0 | 2 | 1 | 4 | 3 | 6
0 | 0 | 1 | 4 | 2 | 4
0 | 2 | 1 | 4 | 2 | 4
0 | 3 | 1 | 4 | 2 | 6
1 | 2 | 1 | 4 | 2 | 6
0* | 0* | 1 | 2 | 1 | 2
0 | 1,1 | 1,2 | 1, 4 | 1, 3 | 2, 6
RAN2 TUs
RAN3 TUs
NR V2X SI
NR V2X WI
NR-U SI
NR-U WI
RAN1 led
Misc. impacts from other RAN1/RAN3 NR WIDs*
NR-NR DC sync (TBD for late drop)
2018 Q3
2018 Q4
2019Q1
2019Q2
2019Q3
2019Q4
4 | 10 | 7.5 | 17 | 8 | 16
0 | 0 | 1.5 | 3 | 2 | 4
1 | 2 | 2 | 4 | 2 | 4
NR-NR DC WI
Note: Yellow numbers show TUs from the LTE allocation used for NR WIs/SI
* MIMO, NTN, UE power, Positioning, SON/MDT , NOMA

## Slide 6: TSG-RAN
It is proposed to take the >52.6GHz work on board as a RAN plenary SI focusing on higher level issues
  Target spectrum range and use cases, requirements, etc…
WG work can be initiated later potentially targeting Rel-17

## Slide 7: Summary and Way Forward
It is proposed to take the SI/WI package presented here as a starting point for further discussion during RAN#80