3GPP TSG RAN Meeting #80	RP- 180937

La Jolla, USA, 11 – 14 June 2018

Agenda item:	9.3.2

Source:	Huawei, Ericsson, Telecom Italia

Title:	Work plan for preparation of IMT-2020 self evaluation towards 3GPP updated submission

Document for:	Discussion / Decision

1	Introduction

It was agreed at RAN#78 in [1] that self evaluation for IMT-2020 submission will be further progressed in RAN WGs and RAN.

The simulation activities and evaluation for technical performance requirements are being well progressed in RAN WGs, which will form the foundation of self evaluation results of 3GPP for IMT-2020 submission. On the other hand, to complete Step 3 under IMT-2020 submission and evaluation process as defined in Document IMT-2020/02 (Rev. 1), description template and compliance template need to be prepared in addition to the self evaluation results. In [1], it is agreed that

- Consider the update of the description templates in RAN#79 (March 2018) or RAN#80 (June 2018) based on Rel-15 progress.

- Prepare the compliance templates in RAN#80 (June 2018) and finalize in RAN#81 (September 2018) for the submission to ITU-R WP 5D#31 according to self evaluation results.

This document provides the consideration on the above two aspects.

2	Discussion

2.1	Preparation of self evaluation

As mentioned in Section 1, the simulation activities and evaluation for technical performance requirements are being well progressed in RAN WGs. The continous work till 3GPP Updated submission in September can be done through email discussions and WG meetings as what was done in 2018 Q1 and Q2.

2.2	Preparation of update of description template

At RAN#78 meeting, the initial description template that provides the characteristics description of 3GPP’s “5G” technology towards IMT-2020 was developed, for SRIT and RIT, respectively, according to the agreed 3GPP submission format as in [2].

The initial description template was jointly submitted by more than fifty 3GPP members to ITU-R WP 5D#29 in Feb 2018, and 3GPP received positive feedback from WP 5D.

It is noted that the description template was initial and not complete. There are eleven items not addressed at that time. In 3GPP updated submission, these items need to be addressed.

On the other hand, after Feb 2018, 3GPP further developed NR RIT and SRIT (including NR and LTE component RITs) within Rel-15 framework towards IMT-2020. The further information of Rel-15 development need to be captured in the description template if there are any updates compared to the previous information provided.

In addition, the link budget information is not provided in the initial description template submitted to ITU-R in Feb 2018. It should be included in updated submission as well.

Therefore, to well prepare the 3GPP updated submission to ITU-R in September 2018, the description template needs to be updated. The following proposal is therefore made.

Proposal 1: Plan an email discussion in RAN ITU-R Ad-Hoc on preparation of the update of the description template.

  - Including addressing the eleven items that are not included in Feb submission; updating the information of other items if needed; preparing link budget template.

2.2	Preparation of compliance template

The compliance template is needed to complete Step 3 as defined in Document IMT-2020/02 (Rev. 1) for IMT-2020 submission. The compliance template is the template to demonstrate the compliance of the proposed IMT-2020 technology with the IMT-2020 requirements including spectrum requirement, service requirement, and technical performance requirements.

Self evaluation is needed to assess the compliance with the IMT-2020 requirements. Therefore compliance template needs to be prepared based on self evaluation results.

To well prepare the 3GPP compliance template to ITU-R in September 2018, the following proposal is made.

Proposal 2: Plan an email discussion in RAN ITU-R Ad-Hoc on preparation of the compliance template.

The organization of the work will be made by ITU-R Ad-Hoc contact person. Therefore it is proposed that,

Proposal 3: ITU-R Ad-Hoc contact person will kick off the scope and timing of the above e-mail discussions in the ITU-R Ad-Hoc mailing list.

3	Conclusion

In this document, the consideration on work plan for for preparation of IMT-2020 self evaluation towards 3GPP updated submission is provided. Based on the discussion, the following proposals are made.

Proposal 1: Plan an email discussion in RAN ITU-R Ad-Hoc on preparation of the update of the description template.

  - Including addressing the eleven items that are not included in Feb submission; updating the information of other items if needed; preparing link budget template.

Proposal 2: Plan an email discussion in RAN ITU-R Ad-Hoc on preparation of the compliance template.

Proposal 3: ITU-R Ad-Hoc contact person will kick off the scope and timing of the above e-mail discussions in the ITU-R Ad-Hoc mailing list.

Reference

- RP-172532, “Work plan for self evaluation towards 3GPP Update Submission to ITU-R”, Huawei, Ericsson, Telecom Italia, December 2017.

- RP-172098, “3GPP submission towards IMT-2020”, ITU-R Ad-Hoc Contact person (Telecom Italia), September 2017.