## Slide 1: Release 16 WI/SI package
Source: TSG-RAN Chairman, RAN1 Chairman,
RAN2 Chairman,
RAN3 Chairman.
RP-181307
3GPP TSG-RAN#80
La Jolla, USA, 11-14 June, 2018

## Slide 2: Introduction
Based on analysis of input to RAN#80 the 4 chairmen compiled a potential starting point for a Rel-16 work package discussion
  The guiding principle was to compile a package that is manageable for the WGs in terms of load, and well represents the different interests of the 3GPP community
These slides focus on Rel16 SI/WIs for RAN1, RAN2, and RAN3
  Other WGs are not addressed here
The package presented here should be understood as the absolute maximum in terms of number of items and work amount that can be taken on board in these WGs
  It is assumed that each WI/SI is well scoped with precise objectives that fit within the allocated TUs

## Slide 3: Timeline
Rel-16 SI
Q2
Q3
Q4
2019
Q2
Q3
Q4
Q1
2020
Q1
Rel-16 SI/WI phase
Rel-16 freeze
Rel-16 ASN.1
Rel-15 SA (option-2) freeze
Rel-15 late drop freeze
2018
Q1
2017
Q4
Rel-15 NSA (option-3) freeze
Rel-15 NSA (option-3) ASN.1
Rel-15 SA (option-2) ASN.1
Rel-15 late drop ASN.1

## Slide 4: RAN1
2018 Q3
2018 Q4
2019 Q2
2019 Q3
2019 Q4
2019 Q1
NR MIMO WI
NR V2X SI
NR V2X WI
eURLLC SI
eURLLC WI
NR-U SI
NR-U WI
NOMA SI
NR non-terrestrial SI
IAB SI
IAB WI
RAN1 led
RAN2 led
RIM SI
NR Positioning WI
Misc impacts coming from other RAN2/3/4 SI/WI
NB-IoT enhancements (LTE track)
eMTC enhancements (LTE track)
NR:11 LTE: 5 | NR:32 LTE:14 | NR:18 LTE: 9 | NR:40 LTE:19 | NR:21 LTE:10 | NR:42 LTE:20
0 | 4 | 2 | 6 | 3 | 6
3 | 6 | 3 | 6 | 3 | 6
2.5 | 5 | 3 | 6 | 4 | 8
2.5 | 5 | 1 | 2 | 1 | 2
1 | 2 | 1 | 3 | 1 | 2
0 | 3 | 1 | 4 | 1 | 2
0 | 2 | 2 | 3 | 2 | 4
0* | 0* | 1 | 2 | 1 | 2
2 | 5 | 3 | 7 | 4 | 8
2 | 5 | 3 | 6 | 3 | 6
1 | 2 | 1 | 2 | 1 | 2
0 | 2 | 1 | 2 | 1 | 2
1 | 2 | 1 | 2 | 1 | 2
0 | 0 | 1 | 2 | 1 | 2
1 | 3 | 2 | 4 | 2 | 4
0 | 0 | 1 | 2 | 1 | 2
RAN1 TUs
Mobility enhancements WI
NR Positioning SI
NOMA continuation SI or WI
NR UE power consumption SI
NR UE power consumption WI
NR-NR DC WI
NR-NR DC sync (TBD for late drop)
2018 Q3
2018 Q4
2019Q1
2019Q2
2019Q3
2019Q4
RIM+CLI WI
Note: Yellow numbers show TUs from the LTE allocation, in some cases for NR WIs/SI
LTE MIMO enhancements (LTE track)
ENTV enhancements (LTE track)
* TU numbers for NR-NR DC sync in late drop are accommodated in TU numbers deducted for Rel15 work

## Slide 5: RAN2
2018 Q3
2018 Q4
2019 Q2
2019 Q3
2019 Q4
2019 Q1
IAB SI
IAB WI
eURLLC SI
eURLLC SI
NR Mobility enhancement SI/WI
MR DC enh. SI
MR DC enh. WI
RAN2 led NR
NR:2 LTE:0 | NR:14 LTE:14 | NR:9 LTE:9 | NR:29 LTE:19 | NR:16 LTE:10 | NR:36 LTE:20
1 | 4 | 2 | 6 | 3 | 6
0 | 2 | 1 | 4 | 3 | 6
0 | 0 | 1 | 4 | 2 | 4
0 | 2 | 1 | 4 | 2 | 4
0 | 1 | 0.5 | 1 | 0.5 | 1
0 | 2 | 1 | 4 | 2 | 6
1 | 2 | 1 | 4 | 2 | 6
0* | 0* | 1 | 2 | 1 | 2
0 | 1, 2 | 1, 2 | 1, 7 | 1, 4 | 2, 5
0 | 2 | 1 | 2 | 1 | 2
0 | 8 | 4 | 8 | 4 | 8
0 | 0 | 0 | 0 | 0.5 | 1
RAN2 TUs
NR V2X SI
NR V2X WI
NR-U SI
NR-U WI
RAN1 led NR
Impacts from MIMO, NTN, UE power, Positioning, NOMA
NR-NR DC sync (TBD for late drop)
2018 Q3
2018 Q4
2019Q1
2019Q2
2019Q3
2019Q4
NR-NR DC WI
UE capabilities SI
UE capabilities WI
Impacts from NB-IoT and eMTC enhancements
LTE Mobility enhancement SI/WI
Impacts from LTE MIMO
RAN2 led LTE
RAN1 led LTE
* TU numbers for NR-NR DC sync in late drop are accommodated in TU numbers deducted for Rel15 work

## Slide 6: RAN3
2018 Q3
2018 Q4
2019 Q2
2019 Q3
2019 Q4
2019 Q1
NR SON/MDT SI
NR SON/MDT WI
2018 Q3
2018 Q4
2019Q1
2019Q2
2019Q3
2019Q4
4 | 10 | 10 | 20 | 10 | 20
0 | 0 | 1.5 | 3 | 2 | 4
1 | 2 | 0 | 0 | 0 | 0
1 | 2 | 1 | 0 | 0 | 0
1 | 2 | 1 | 2 | 1 | 2
1 | 4 | 3 | 4 | 2 | 4
0 | 0 | 0 | 2 | 2 | 4
0 | 0 | 2 | 4 | 2 | 4
IAB SI
IAB WIs
RAN2 led
NW sync SI
eURLLC SI
eURLLC WIs
NR non-terrestrial SI
RAN1 led
Mobility enhancements LTE and NR
RAN3 led
Other misc impacts from RAN1 and RAN2 LTE and NR

## Slide 7: TSG-RAN
It is proposed to take the >52.6GHz work on board as a RAN plenary SI focusing on higher level issues
  Target spectrum range and use cases, requirements, etc…
WG work can be initiated later potentially targeting Rel-17

## Slide 8: Open issues
CA enhancements / spectrum aggregation enhancements scope and potential inclusion into the package
Accommodating corresponding RAN4 work for the package for 2019

## Slide 9: Summary and Way Forward
It is proposed to endorse the SI/WI package presented here as the basis for Release 16

## Slide 10: Annex – drafting session outcome to be removed in the final version

## Slide 11: Way forward on LTE items
LTE items beyond NB-IoT and LTE-M
    MIMO enhancements WI: SRS improvements, [CSI enh.] 9 RAN1
    EN-TV enhancements SI: 38.913 requirements gap analysis 9 RAN1
    Mobility enhancements WI: interruption reduction, robustness improvement 8 RAN2

## Slide 12: Open issues addressed during drafting
Spectrum aggregation enhancements
  David to draft objectives for CA enhancements
V2X TUs
    More TUs are needed for the study
    SI WI Cut-through point
CLI together with RIM
  Scope out the CLI work accurately concisely for unpaired spectrum. Based on the scope decide if it can be fit together with RIM WI
NTN keep-alive
  Start SI in 2018, go for 9 months
UE capability mechanism in RAN2
  Draft a SI, coord with SA2 (Guillaume) try to fit it in
NR coverage
  Certain elements are covered in the IMT2020 link budget evaluation. No new SI in Rel16.