3GPP TSG RAN meeting #82										RP-182314

Sorrento, Italy, December 10-13, 2018

## Status Report to TSG

Agenda item:			10.2.1

| WI / SI Name |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: Yes |  | Testing part: No |
| Acronym | LTE_sTTIandPT |  |  |  |  |
| Unique ID | 720091 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) |  |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: | Core part: | Performance part: 03/2019 | Testing part: |  |
| Overall Completion level | Study Item: | Core part: | Performance Part: 90% | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | TSG RAN1 WG1 |
| --- | --- | --- |
| Rapporteur | Name | Florent Munier |
|  | Company | Ericsson |
|  | Email | florent.munier@ericsson.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | Yes |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

BS demodulation part

- Alignment of Slot/Subslot-PUSCH demodulation performance

- Alignment of SPUCCH demodulation performance

- CR for TS 36.104 for BS demodulation requirements (Slot/Subslot-PUSCH and SPUCCH)

- CR for TS 36.141 for BS demodulation requirements (Slot/Subslot-PUSCH and SPUCCH)

UE demodulation part

- Alignment of a part of Slot/Subslot-PDSCH demodulation performance

- Alignment of a part of SPDCCH demodulation performance

- Agreement of the requirements for CQI reporting test for CRS based and CSI-RS based CQI reporting

#### 2.4.2	Remaining Open issues

UE demodulation part

- Alignment of the remaining Slot/Subslot-PDSCH demodulation performance

- Alignment of the remaining of SPDCCH demodulation performance

- Set the test points for CQI reporting test for CRS based and CSI-RS based CQI reporting

- CR for TS 36.101 for UE demodulation requirements

- CR for TS 36.101 for CQI reporting test requirements

BS demodulation part

- None

## 2.5	RAN5

#### 2.5.1	Agreements

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

RAN4#88bis

R4-1812301		Simulation results for sPUCCH Format4	Samsung

R4-1812826		Way forward on sTTI BS demodulation requirements	Ericsson

R4-1812827		Introduction of PUSCH demodulation requirements for sTTI	Ericsson

R4-1812828		Introduction of SPUCCH demodulation requirements	Ericsson

R4-1813202		Simulation results for SPUCCH format 4	Nokia, Nokia Shanghai Bell

R4-1813255		Simulation results on sTTI BS SPUCCH demodulation performance requirements	Huawei, Hisilicon

R4-1813708		Way forward on sTTI BS demodulation requirements	Ericsson

R4-1813709		Introduction of SPUCCH demodulation requirements	Ericsson

R4-1812818		Summary of simulation results for sTTI UE demodulation requirements	Ericsson

R4-1812819		Simulation results of PDSCH for sTTI UE demodulation requirement	Ericsson

R4-1812820		Introduction of Slot/Subslot-PDSCH demodulation requirements	Ericsson

R4-1812821		Simulation results of SPDCCH for sTTI UE demodulation requirements	Ericsson

R4-1812822		Introduction of SPDCCH demodulation requirements	Ericsson

R4-1812823		CQI reporting tests for CRS-based PDSCH	Ericsson

R4-1812824		CQI reporting tests for DMRS-based PDSCH	Ericsson

R4-1812825		Introduction of CQI tests for sTTI	Ericsson

R4-1813251		Simulation results for sTTI PDCCH demodulation requirements	Huawei, Hisilicon

R4-1813252		Simulation results for UE sTTI PDSCH demodulation performance requirements	Huawei, Hisilicon

R4-1813253		Discussion on simulation assumption and demodulation requirements of SPDCCH	Huawei, Hisilicon

R4-1813254		Discussion on UE CSI test	Huawei, Hisilicon

R4-1813256		Updating sTTI simulation assumption for UE demod	Huawei, Hisilicon

R4-1813503		Simulation result for slot-based PDSCH demodulation in TDD	Qualcomm Incorporated

R4-1813710		Introduction of Slot/Subslot-PDSCH demodulation requirements	Ericsson

R4-1813711		Introduction of SPDCCH demodulation requirements	Ericsson

R4-1813712		Introduction of CQI tests for sTTI	Ericsson

RAN4#89

R4-1815226		Introduction of SPUCCH demodulation requirements	Ericsson

R4-1816326		Introduction of SPUCCH demodulation requirements	Ericsson

R4-1816487		Introduction of SPUCCH demodulation requirements	Ericsson

R4-1815220		Summary of simulation results for sTTI UE demodulation requirements	Ericsson

R4-1815221		Introduction of Slot/Subslot-PDSCH demodulation requirements	Ericsson

R4-1815222		Open issues for SPDCCH demodulation requirements	Ericsson

R4-1815223		Introduction of SPDCCH demodulation requirements	Ericsson

R4-1815224		sTTI CQI reporting tests	Ericsson

R4-1815225		Introduction of CQI tests for sTTI	Ericsson

R4-1815778		CQI mapping table for CRS-based PDSCH	Huawei, Hisilicon

R4-1815779		CQI mapping table for DMRS-based PDSCH	Huawei, Hisilicon

R4-1815780		Simulation results for sTTI PDCCH demodulation requirements	Huawei, Hisilicon

R4-1815781		Simulation results for sTTI PDSCH demodulation performance requirements	Huawei, Hisilicon

R4-1815871		On CQI2MCS tables for sub-slot sTTI fading tests	Qualcomm Incorporated

R4-1816323		Introduction of Slot/Subslot-PDSCH demodulation requirements	Ericsson

R4-1816324		Introduction of SPDCCH demodulation requirements	Ericsson

R4-1816325		Introduction of CQI tests for sTTI	Ericsson

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template