3GPP TSG RAN meeting #84										RP- 190979

Newport Beach, USA, June 3-6, 2019

## Status Report to TSG

Agenda item:			9.5.2

| WI / SI Name |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_n14 |  |  |  |  |
| Unique ID |  |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-190165 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: 06/2019 | Core part: 06/2019 | Performance part: 06/2019 | Testing part: |  |
| Overall Completion level | Study Item: 100 % | Core part: 100 % | Performance Part: 100 % | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  |  |
| --- | --- | --- |
| Rapporteur | Name | Marc Grant |
|  | Company | AT&T |
|  | Email | marc.grant@att.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

All work for this WID has been completed. See section 2.4.1 below.

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

| R4-1907783 | Introduction of band n14 - CR to TS 38.101-1 | Ericsson, AT&T |
| --- | --- | --- |
| R4-1905964 | Introduction of band n14 - CR to TS 38.104 | Ericsson |
| R4-1905965 | Introduction of band n14 - CR to TS 38.141-1 | Ericsson |
| R4-1905966 | Introduction of band n14 - CR to TS 38.141-2 | Ericsson |
| R4-1905967 | Introduction of band n14 - CR to TS 36.104 | Ericsson |
| R4-1905968 | Introduction of band n14 - CR to TS 36.141 | Ericsson |
| R4-1905969 | Introduction of band n14 - CR to TS 37.104 | Ericsson |
| R4-1905970 | Introduction of band n14 - CR to TS 37.141 | Ericsson |
| R4-1907836 | Introduction of Band n14 in TS 37.105 | Ericsson |
| R4-1907837 | Introduction of Band n14 in TS 37.145-1 | Ericsson |
| R4-1907838 | Introduction of Band n14 in TS 37.145-2 | Ericsson |
| R4-1905962 | Introduction of band n14 - CR to TS 38.133 | Ericsson, AT&T |

#### 2.4.2	Remaining Open issues

None

## 2.5	RAN5

#### 2.5.1	Agreements

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

RAN4#90b

| R4-1904005 | Introduction of band n14 - draft CR to TS 38.104 | Ericsson |
| --- | --- | --- |
| R4-1904006 | Introduction of band n14 - draft CR to TS 38.141-1 | Ericsson |
| R4-1904007 | Introduction of band n14 - draft CR to TS 38.141-2 | Ericsson |
| R4-1904008 | Introduction of band n14 - draft CR to TS 38.101-1 | Ericsson |
| R4-1904009 | Introduction of band n14 - draft CR to TS 38.133 | Ericsson |

RAN4#91

| R4-1907162 | n14 A-MPR | Qualcomm Incorporated |
| --- | --- | --- |
| R4-1907783 | Introduction of band n14 - CR to TS 38.101-1 | Ericsson, AT&T |
| R4-1905964 | Introduction of band n14 - CR to TS 38.104 | Ericsson |
| R4-1905965 | Introduction of band n14 - CR to TS 38.141-1 | Ericsson |
| R4-1905966 | Introduction of band n14 - CR to TS 38.141-2 | Ericsson |
| R4-1905967 | Introduction of band n14 - CR to TS 36.104 | Ericsson |
| R4-1905968 | Introduction of band n14 - CR to TS 36.141 | Ericsson |
| R4-1905969 | Introduction of band n14 - CR to TS 37.104 | Ericsson |
| R4-1905970 | Introduction of band n14 - CR to TS 37.141 | Ericsson |
| R4-1907836 | Introduction of Band n14 in TS 37.105 | Ericsson |
| R4-1907837 | Introduction of Band n14 in TS 37.145-1 | Ericsson |
| R4-1907838 | Introduction of Band n14 in TS 37.145-2 | Ericsson |
| R4-1905962 | Introduction of band n14 - CR to TS 38.133 | Ericsson, AT&T |

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template