## RAN4 TU cl
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation |  |  | RAN | R4RD | RAN | R4RD | R4RD | RAN | R4RD | RAN | R4RD | R4RD | RAN | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | 84 Jun 19 | 92 | 85 Sept 19 | 92bis | 93 | 86 Dec 19 | 94 | 87 Mar.20 | 94bis | 95 | 88 Jun.20 | 96 | 87 Sep.20
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-190213 | NTT DOCOMO |  | 1 |  | 0 | 0
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-190213 | NTT DOCOMO |  | 3 |  | 1 | 1
R1 | NR | NR_2step_RACH-Core | WI | Core part: 2-step RACH for NR | RP-190711 | ZTE
R4 | NR | NR_2step_RACH-Perf | WI | Perf part: 2-step RACH for NR | RP-190711 | ZTE | [6 empty] | 1 |  | 1 | 1 |  | 1
R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm |  | 1.5 |  | 2 | 2 |  | 1
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm | [8 empty] | 1 | 1 |  | 1
R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-190766 | LG Electronics |  | 1 |  | 1.5 | 1.5 |  | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-190766 | LG Electronics | [8 empty] | 1.5 | 1.5 |  | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-182863 | Samsung |  |  |  | 0.5 | 0.5
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-182863 | Samsung | [6 empty] | 1 |  | 1 | 1
R1 | NR | SI_NR-PowerSaving | SI | Study on UE Power Saving in NR | RP-181463 | CATT
R1 | NR | NR-PowerSaving-Core | WI | Core part: UE Power Saving in NR | RP-190727 | CATT |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-190727 | CATT | [6 empty] | 0.5 |  | 1 | 1 |  | 1
R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-190752 | Intel |  | 0.5 |  | 1 | 1 |  | 0.5
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-190752 | Intel | [6 empty] | 0.5 |  | 1 | 1 |  | 1
R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei |  | 0.25 |  | 0.25 | 0.1 |  | 0.1
R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei |  | 0.25 |  | 0.5 | 0.5 |  | 0.5 |  | 1.5 | 1.5 |  | 1.5
R1 | NR | NR_CLI_RIM-Core | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics |  | 0.25 |  | 0.25 | 0.25
R4 | NR | NR_CLI_RIM-Perf | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics |  | 0 |  | 0 | 0 |  | 0.25 |  | 0.25 | 0.25
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182862 | Ericsson
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI
R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm |  | 1 |  | 1.5 | 1.5 |  | 1.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm | [8 empty] | 1.5 | 1.5 |  | 1.5
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-190657 | MediaTek
R2 | NR | NR_IIoT | WI | NR Industrial IoT | RP-190728 | Nokia
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-190489 | Intel |  | 1 |  | 1 | 1 |  | 1
R4 | NR | NR_Mob_enh-Perf | WI | Perf part: NR mobility enhancements | RP-190489 | Intel | [8 empty] | 0.25 | 0.25 |  | 0.25
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-190452 | Ericsson |  | 1 |  | 1 | 1
R2 | NR | SRVCC_NR_to_UMTS-Core | WI | Core part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom |  | 0.25 |  | 0.25 | 0.25
R4 | NR | SRVCC_NR_to_UMTS-Perf | WI | Perf part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | [6 empty] | 0.25 |  | 0.25 | 0.25
R2 | NR, LTE |  |  | Reserved for SA2/3 with with no RAN WI/SI (as agreed in RP-182974)
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei
R3 | NR | LTE_NR_arch_evo-Core | WI | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | RP-181375 | China Unicom
R3 | NR | FS_NR_NTN_solutions | SI | Study on solutions for NR to support Non Terrestrial Network (NTN) | RP-190710 | Thales
R3 | NR, LTE | FS_LTE_NR_data_collect | SI | Study on RAN-centric Data Collection and Utilization for NR | RP-182105 | CMCC
R3 | NR | Direct_data_fw_NR-Core | WI | Direct data forwarding for inter-system mobility | RP-182886 | Ericsson
R3 | NR | ??? | WI | RAN-centric Data Collection and Utilization for NR |  | CMCC
R3 | NR | RANImp_5WWC | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190772 | Huawei
R3 | NR | FS_NR_NPN | WI | Private Network Support for NG-RAN | RP-190729 | China Telecom
R3 | NR | FS_NR_LOCAL_POS | SI | Study on Local NR Positioning in NG-RAN | RP-190754 | CMCC
R3 | NR | FS_eDisaggregated_gNB | SI | Study on Enhancement for Disaggregated gNB Architecture | RP-190702 | CATT
R4 | NR | FS_NR_test_methods | SI | Study on test methods for New Radio | RP-180546 | Intel
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Core part: RF requirement for FR1 | RP-190759 | Huawei
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Perf part: RF requirement for FR1 | RP-190759 | Huawei
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Core part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Perf part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia
R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom
R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom | [8 empty] | 0.25 | 0.25 |  | 0.25
R4 | NR,LTE, UTRA, E-UTRA, GSM | MSR_GSM_UTRA_LTE_NR | WI | New WID on introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | RP-190642 | Ericsson
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-181655 | Sprint
R4 | NR | n65_NR_newRAT | WI | New WID on Band 65 for New Radio for Region 1 | RP-181844 | DISH Network
R4 | NR | NR_band_48 | WI | New WID on an introduction of band n48 | RP-182865 | Nokia
R4 | NR | NR_band_18 | WI | New WID: Introduction of NR band n18 | RP-182826 | KDDI
R4 | NR | NR_wide_chs_n7 | WI | New WID on adding wider channel bandwidths in Band n7 | RP-182827 | BT
R4 | NR | NR_wide_chs_n50 | WI | New WID on adding wider channel bandwidths in Band n50 | RP-182829 | Huawei
R4 | NR | NR_n41_LTE_41_coex-Core | WI | New WI proposal: LTE/NR spectrum sharing in Band 41/n41 | RP-182883 | KDDI
R4 | NR | NR_n41_BW-Core | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI
R4 | NR | NR_n41_BW-Perf | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI
R4 | NR | FS_7to24GHz_NR | SI | Study on 7 - 24 GHz Frequency Range | RP-190373 | Huawei
R4 | NR | ENDC_UE_PC2_TDD_TDD-Core | WI | Core part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC
R4 | NR | ENDC_UE_PC2_TDD_TDD-Perf | WI | Perf part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC
R4 | NR | FS_ENDC_UE_PC2_FDD_TDD | SI | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-182895 | China Unicom
R4 | NR | NR_band_n14 | WI | FDD operating band in Band n14 | RP-190165 | AT&T
R4 | NR | NR_band_n30 | WI | FDD operating band in Band n30 | RP-190166 | AT&T
R4 | NR | NR_Band_n259_R16 | WI | New WID: introduction of Band n259 | RP-190765 | Ericsson |  |  |  |  | 0.1
R4 | NR |  | WI | Core part: Introduction of NR SUL (supplemental uplink) band with same uplink frequency range of NR band n5 | RP-190390 | Huawei
R4 | NR | NR_n38_BW | WI | Core part: addition of wider channel bandwidth in NR band n38 | RP-190392 | Huawei
R4 | NR | EN-DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) , New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) New WID: Basket Rel-16 WID NR Intra-band CA New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands New WID: Rel-16 NR Inter-band Carrier Aggregation for 3 bands DL with 1 band bands UL New WID: Rel-16 NR Inter-band Carrier Aggregation/Dual connectivity for 3 bands DL with 2 band bands UL | RP-190689 RP-190705 RP-190379 RP-190159 RP-190294 RP-190494 RP-190151 RP-190714 RP-190692 RP-190693 | NTT DOCOMO, etc
Last row in NR totals. Insert new NR items above this line. Do not remove
First row in LTE totals. Insert new LTE items below this line. Do not remove
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-190770 | Ericsson |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-190770 | Ericsson |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-190757 | Huawei |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-190757 | Huawei |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 | 0.5
R1 | LTE | LTE_terr_bcast-Core | WI | Core part: LTE-based 5G Terrestrial Broadcast | RP-190732 | Qualcomm |  |  |  | 0.5 | 0.5 |  |  |  | 1 | 1
R4 | LTE | LTE_Terr_bcast-Perf | WI | Performance part: LTE-based 5G terrestrial broadcast | RP-190732 | Qualcomm | [6 empty] | 0.5 |  | 1 | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei |  | 0 |  | 0 | 0 |  | 0 |  | 0.25 | 0.25 |  | 0.25
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom |  | 0 |  | 0 | 0 |  | 0 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO |  | 1.5 |  | 1.5 | 1.5
R4 | LTE | LTE410_Europe_PPDR-Core | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia
R4 | LTE | LTE410_Europe_PPDR-Perf | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia
R4 | LTE | LTE_PC2_B31_B72 |  | Power Class 2 UE for LTE bands 31 and 72 | RP-190665 | Nokia
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 | RP-181548 RP-181930 RP-181851 RP-181887 RP-181853 RP-181733 RP-181824 RP-181825 | Ericsson, etc.
Last row in LTE totals. Insert new LTE items above this line. Do not remove
First row in UMTS totals. Insert new UMTS items below this line. Do not remove.
Last row in UMTS totals. Insert new UMTS items above this line. Do not remove
First row in GERAN totals. Insert new GERAN items below this line. Do not remove
Last row in GERAN totals. Insert new GERAN items above this line. Do not remove
| NR |  |  | allocated above |  |  |  | 11.5 |  | 11.25 | 11.2 |  | 10.1 |  | 10.5 | 10.5 |  | 9
| NR |  |  | Legacy
| NR |  |  | TEI and other not planned issues
| NR |  |  | Reserve
| NR |  |  | total used capacity |  |  |  | 11.5 |  | 11.25 | 11.2 |  | 10.1 |  | 10.5 | 10.5 |  | 9
| NR |  |  | available capacity |  |  |  | 15 |  | 15 | 15 |  | 15 |  | 15 | 15 |  | 15
| NR |  |  | remaining/exceeded capacity |  |  |  | 3.5 |  | 3.75 | 3.8 |  | 4.9 |  | 4.5 | 4.5 |  | 6
| LTE |  |  | allocated above |  |  |  | 3 |  | 3.5 | 4.5 |  | 3 |  | 3.75 | 3.75 |  | 1.25
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity |  |  |  | 3 |  | 3.5 | 4.5 |  | 3 |  | 3.75 | 3.75 |  | 1.25
| LTE |  |  | available capacity |  |  |  | 3 |  | 3 | 3 |  | 3 |  | 3 | 3 |  | 3
| LTE |  |  | remaining/exceeded capacity |  |  |  | 0 |  | -0.5 | -1.5 |  | 0 |  | -0.75 | -0.75 |  | 1.75
| UTRA |  |  | allocated above |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status

## RAN4 TU rm
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation |  |  | RAN | R4RD | RAN | R4RD | R4RD | RAN | R4RD | RAN | R4RD | R4RD | RAN | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | 84 Jun 19 | 92 | 85 Sept 19 | 92bis | 93 | 86 Dec 19 | 94 | 87 Mar.20 | 94bis | 95 | 88 Jun.20 | 96 | 87 Sep.20
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-190213 | NTT DOCOMO |  | 1 |  | 0 | 0
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-190213 | NTT DOCOMO |  | 2 |  | 1 | 1
R1 | NR | NR_2step_RACH-Core | WI | Core part: 2-step RACH for NR | RP-190711 | ZTE
R4 | NR | NR_2step_RACH-Perf | WI | Perf part: 2-step RACH for NR | RP-190711 | ZTE | [6 empty] | 1 |  | 1 | 1 |  | 1
R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm |  | 1.5 |  | 2 | 2 |  | 1
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm | [8 empty] | 1 | 1 |  | 1
R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-190766 | LG Electronics |  | 1.5->1 |  | 1.5 | 1.5 |  | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-190766 | LG Electronics | [8 empty] | 1.5 | 1.5 |  | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-182863 | Samsung |  |  |  | 1->0.5 | 1->0.5
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-182863 | Samsung | [6 empty] | 1 |  | 1 | 1
R1 | NR | SI_NR-PowerSaving | SI | Study on UE Power Saving in NR | RP-181463 | CATT
R1 | NR | NR-PowerSaving-Core | WI | Core part: UE Power Saving in NR | RP-190727 | CATT |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-190727 | CATT | [6 empty] | 0.5 |  | 1 | 1 |  | 1
R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-190752 | Intel |  | 1->0.5 |  | 1 | 1 |  | 0.5
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-190752 | Intel | [6 empty] | 0.5 |  | 1 | 1 |  | 1
R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei |  | 0.25 |  | 0.25 | 0.1 |  | 0.1
R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei |  | 0.25 |  | 0.5 | 0.5 |  | 0.5 |  | 1->1.5 | 1->1.5 |  | 1->1.5
R1 | NR | NR_CLI_RIM-Core | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics |  | 0->0.25 |  | 0->0.25 | 0->0.25
R4 | NR | NR_CLI_RIM-Perf | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics |  | 0.25->0 |  | 0.25->0 | 0.25->0 |  | 0->0.25 |  | 0->0.25 | 0->0.25
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182862 | Ericsson
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI
R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm |  | 1 |  | 1.5 | 1.5 |  | 1.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm | [8 empty] | 1.5 | 1.5 |  | 1.5
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-190657 | MediaTek
R2 | NR | NR_IIoT | WI | NR Industrial IoT | RP-190728 | Nokia
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-190489 | Intel |  | 1 |  | 1 | 1 |  | 1
R4 | NR | NR_Mob_enh-Perf | WI | Perf part: NR mobility enhancements | RP-190489 | Intel | [8 empty] | 0.25 | 0.25 |  | 0.25
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-190452 | Ericsson |  | 1 |  | 1 | 1
R2 | NR | SRVCC_NR_to_UMTS-Core | WI | Core part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom |  | 0.25 |  | 0.25 | 0.25
R4 | NR | SRVCC_NR_to_UMTS-Perf | WI | Perf part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | [6 empty] | 0.25 |  | 0.25 | 0.25
R2 | NR, LTE |  |  | Reserved for SA2/3 with with no RAN WI/SI (as agreed in RP-182974)
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei
R3 | NR | LTE_NR_arch_evo-Core | WI | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | RP-181375 | China Unicom
R3 | NR | FS_NR_NTN_solutions | SI | Study on solutions for NR to support Non Terrestrial Network (NTN) | RP-190710 | Thales
R3 | NR, LTE | FS_LTE_NR_data_collect | SI | Study on RAN-centric Data Collection and Utilization for NR | RP-182105 | CMCC
R3 | NR | Direct_data_fw_NR-Core | WI | Direct data forwarding for inter-system mobility | RP-182886 | Ericsson
R3 | NR | ??? | WI | RAN-centric Data Collection and Utilization for NR |  | CMCC
R3 | NR | RANImp_5WWC | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190772 | Huawei
R3 | NR | FS_NR_NPN | WI | Private Network Support for NG-RAN | RP-190729 | China Telecom
R3 | NR | FS_NR_LOCAL_POS | SI | Study on Local NR Positioning in NG-RAN | RP-190754 | CMCC
R3 | NR | FS_eDisaggregated_gNB | SI | Study on Enhancement for Disaggregated gNB Architecture | RP-190702 | CATT
R4 | NR | FS_NR_test_methods | SI | Study on test methods for New Radio | RP-180546 | Intel
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Core part: RF requirement for FR1 | RP-190759 | Huawei
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Perf part: RF requirement for FR1 | RP-190759 | Huawei
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Core part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Perf part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia
R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom
R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom | [8 empty] | 0.25 | 0.25 |  | 0.25
R4 | NR,LTE, UTRA, E-UTRA, GSM | MSR_GSM_UTRA_LTE_NR | WI | New WID on introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | RP-190642 | Ericsson
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-181655 | Sprint
R4 | NR | n65_NR_newRAT | WI | New WID on Band 65 for New Radio for Region 1 | RP-181844 | DISH Network
R4 | NR | NR_band_48 | WI | New WID on an introduction of band n48 | RP-182865 | Nokia
R4 | NR | NR_band_18 | WI | New WID: Introduction of NR band n18 | RP-182826 | KDDI
R4 | NR | NR_wide_chs_n7 | WI | New WID on adding wider channel bandwidths in Band n7 | RP-182827 | BT
R4 | NR | NR_wide_chs_n50 | WI | New WID on adding wider channel bandwidths in Band n50 | RP-182829 | Huawei
R4 | NR | NR_n41_LTE_41_coex-Core | WI | New WI proposal: LTE/NR spectrum sharing in Band 41/n41 | RP-182883 | KDDI
R4 | NR | NR_n41_BW-Core | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI
R4 | NR | NR_n41_BW-Perf | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI
R4 | NR | FS_7to24GHz_NR | SI | Study on 7 - 24 GHz Frequency Range | RP-190373 | Huawei
R4 | NR | ENDC_UE_PC2_TDD_TDD-Core | WI | Core part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC
R4 | NR | ENDC_UE_PC2_TDD_TDD-Perf | WI | Perf part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC
R4 | NR | FS_ENDC_UE_PC2_FDD_TDD | SI | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-182895 | China Unicom
R4 | NR | NR_band_n14 | WI | FDD operating band in Band n14 | RP-190165 | AT&T
R4 | NR | NR_band_n30 | WI | FDD operating band in Band n30 | RP-190166 | AT&T
R4 | NR | NR_Band_n259_R16 | WI | New WID: introduction of Band n259 | RP-190765 | Ericsson |  |  |  |  | 0.1
R4 | NR |  | WI | Core part: Introduction of NR SUL (supplemental uplink) band with same uplink frequency range of NR band n5 | RP-190390 | Huawei
R4 | NR | NR_n38_BW | WI | Core part: addition of wider channel bandwidth in NR band n38 | RP-190392 | Huawei
R4 | NR | EN-DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) , New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) New WID: Basket Rel-16 WID NR Intra-band CA New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands New WID: Rel-16 NR Inter-band Carrier Aggregation for 3 bands DL with 1 band bands UL New WID: Rel-16 NR Inter-band Carrier Aggregation/Dual connectivity for 3 bands DL with 2 band bands UL | RP-190689 RP-190705 RP-190379 RP-190159 RP-190294 RP-190494 RP-190151 RP-190714 RP-190692 RP-190693 | NTT DOCOMO, etc
Last row in NR totals. Insert new NR items above this line. Do not remove
First row in LTE totals. Insert new LTE items below this line. Do not remove
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-190770 | Ericsson |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-190770 | Ericsson |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-190757 | Huawei |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-190757 | Huawei |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 | 0.5
R1 | LTE | LTE_terr_bcast-Core | WI | Core part: LTE-based 5G Terrestrial Broadcast | RP-190732 | Qualcomm |  |  |  | 0.5 | 0.5 |  |  |  | 1 | 1
R4 | LTE | LTE_Terr_bcast-Perf | WI | Performance part: LTE-based 5G terrestrial broadcast | RP-190732 | Qualcomm | [6 empty] | 0.5 |  | 1 | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei |  | 0.5->0 |  | 0.5->0 | 0.5->0 |  | 0.5->0 |  | 0->0.25 | 0->0.25 |  | 0->0.25
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom |  | 0.5 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom |  | 0.5->0 |  | 0.5->0 | 0.5->0 |  | 0.5->0 |  | 0.5 | 0.5 |  | 0.5
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO |  | 1.5 |  | 1.5 | 1.5
R4 | LTE | LTE410_Europe_PPDR-Core | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia
R4 | LTE | LTE410_Europe_PPDR-Perf | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia
R4 | LTE | LTE_PC2_B31_B72 |  | Power Class 2 UE for LTE bands 31 and 72 | RP-190665 | Nokia
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 | RP-181548 RP-181930 RP-181851 RP-181887 RP-181853 RP-181733 RP-181824 RP-181825 | Ericsson, etc.
Last row in LTE totals. Insert new LTE items above this line. Do not remove
First row in UMTS totals. Insert new UMTS items below this line. Do not remove.
Last row in UMTS totals. Insert new UMTS items above this line. Do not remove
First row in GERAN totals. Insert new GERAN items below this line. Do not remove
Last row in GERAN totals. Insert new GERAN items above this line. Do not remove
| NR |  |  | allocated above |  |  |  | 8.75 |  | 10.5 | 10.45 |  | 9.85 |  | 8.75 | 8.75 |  | 7.5
| NR |  |  | Legacy
| NR |  |  | TEI and other not planned issues
| NR |  |  | Reserve
| NR |  |  | total used capacity |  |  |  | 8.75 |  | 10.5 | 10.45 |  | 9.85 |  | 8.75 | 8.75 |  | 7.5
| NR |  |  | available capacity |  |  |  | 15 |  | 15 | 15 |  | 15 |  | 15 | 15 |  | 15
| NR |  |  | remaining/exceeded capacity |  |  |  | 6.25 |  | 4.5 | 4.55 |  | 5.15 |  | 6.25 | 6.25 |  | 7.5
| LTE |  |  | allocated above |  |  |  | 3 |  | 3.5 | 4.5 |  | 3 |  | 3.5 | 3.5 |  | 1
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity |  |  |  | 3 |  | 3.5 | 4.5 |  | 3 |  | 3.5 | 3.5 |  | 1
| LTE |  |  | available capacity |  |  |  | 3 |  | 3 | 3 |  | 3 |  | 3 | 3 |  | 3
| LTE |  |  | remaining/exceeded capacity |  |  |  | 0 |  | -0.5 | -1.5 |  | 0 |  | -0.5 | -0.5 |  | 2
| UTRA |  |  | allocated above |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status

## TU_overview_after_RAN_83
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 83 Mar 19 | 96bis | 105bis | 103bis | 90bis | 90bis | 97 | 106 | 104 | 91 | 91 | 12 | 84 Jun 19 | 98 | 107 | 105 | 92 | 92 | 13 | 85 Sept 19 | 98bis | 107bis | 105bis | 92bis | 92bis | 99 | 108 | 106 | 93 | 93 | 14 | 86 Dec 19 | 100 | 109 | 107 | 94 | 94 | 15 | 87 Mar.20 | 100bis | 109bis | 107bis | 94bis | 94bis | 101 | 110 | 108 | 95 | 95 | 16 | 88 Jun.20 | 102 | 111 | 109 | 96 | 96 | 17 | 87 Sep.20
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-190213 | NTT DOCOMO | Dec 18 | 32 | For RAN2 this row is the time allocation for late drop with NR Rel-15 maintenance time captured in the NR legacy row below. For other WGs this row is a combination of late drop and maintenance |  | 1 | 3 |  | 4 | 8 | 1 | 3 |  | 2 | 8 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-190213 | NTT DOCOMO | Jun 18 | 19 | [5 empty] | 4 | 4 |  |  |  | 2 | 4 | [5 empty] | 1 | 2 | [5 empty] | 0 | 1 |  |  |  | 0 | 1
R1 | NR | NR_2step_RACH-Core | WI | Core part: 2-step RACH for NR | RP-190711 | ZTE | Mar 20 | 10.5 |  |  | 1 | 0.5 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | [6 empty] | 1
R4 | NR | NR_2step_RACH-Perf | WI | Perf part: 2-step RACH for NR | RP-190711 | ZTE | Sep 20 | 4 | [37 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm | Mar 20 | 51.5 |  |  | 3 | 2 |  | 2 | 1 | 3 | 2 |  | 2 | 1 |  |  | 4 | 2 |  | 2 | 1.5 |  |  | 4 | 3 |  | 2 | 2 | 4 | 3 |  | 2 | 2 |  |  |  | 3 |  | 0 | 1
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-190706 | Qualcomm | Sep 20 | 3 | [44 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-190766 | LG Electronics | Mar 20 | 45 |  |  | 3 | 2 |  | 0.25 | 0.25 | 3 | 2 |  | 0.5 | 0.5 |  |  | 3 | 2 | 0.5 | 1 | 1.5 |  |  | 3 | 3 | 1 | 1 | 1.5 | 3 | 3 | 1 | 1 | 1.5 |  |  |  | 3 | 1 | 1 | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-190766 | LG Electronics | Sep 20 | 4.5 | [44 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-182863 | Samsung | Mar 20 | 19.5 |  |  | 3 |  |  |  |  | 3 | [6 empty] | 3 | 0.5 | [5 empty] | 3 | 0.5 |  |  | 1 | 3 | 0.5 |  |  | 1 |  |  |  | 1
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-182863 | Samsung | June 20 | 3 | [37 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | SI_NR-PowerSaving | SI | Study on UE Power Saving in NR | RP-181463 | CATT | Jun 19 | 2 |  |  |  | 1 |  |  |  |  | 1
R1 | NR | NR-PowerSaving-Core | WI | Core part: UE Power Saving in NR | RP-190727 | CATT | Mar 20 | 15.5 |  |  | 2 |  |  |  |  | 2 |  |  | 0.5 |  |  |  | 1 | 1 |  | 0.5 | 0.5 |  |  | 1 | 1 |  | 0.5 | 0.5 | 1 | 1 |  | 0.5 | 0.5 |  |  |  | 1 |  | 0.5 | 0.5
R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-190727 | CATT | Sep 20 | 3 | [37 empty] | 0,5 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-190752 | Intel | Mar 20 | 23.5 |  |  | 2 | 1 | 0.5 |  |  | 2 | 1 | 1 |  |  |  |  | 2 | 1 | 0.5 |  | 1 |  |  | 2 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5 |  | 1 |  |  |  | 1 | 1 |  | 0.5
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-190752 | Intel | Sep 20 | 3.5 | [37 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei | Mar 20 | 12.4 |  |  | 2 |  |  |  |  | 2 | [6 empty] | 2 | 0.5 |  | 0.1 |  |  |  | 2 |  |  | 0.1 |  | 2 | 0.5 |  | 0.1 |  |  |  |  | 1 |  | 0.1
R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-190726 | Huawei | Sep 20 | 3.25 | [37 empty] | 0.25 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_CLI_RIM-Core | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics | Dec 19 | 6 |  |  |  |  | 1 | 1 | 0.25 |  | 0.5 | 1 | 1 | 0.25 |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_CLI_RIM-Perf | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-190700 | LG Electronics | Dec 19 | 0.75 | [18 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182862 | Ericsson | Sept 19 |  |  |  | 0.25 |  |  |  |  | 0.25 | [6 empty] | [0.5]
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 5 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm | Mar 20 | 44.5 |  |  | 1 | 2 | 2 | 1 |  | 1 | 2 | 1.5 | 2 | 0.5 |  |  | 1 | 3 | 1 | 2 | 1 |  |  | 1 | 3 | 2 | 2 | 1.5 | 1 | 3 | 2 | 2 | 1.5 |  |  |  | 3 |  |  | 1.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-190712 | Qualcomm | Dec 20 | 4.5 | [44 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-190657 | MediaTek | Mar 20 | 4 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | 1
R2 | NR | NR_IIoT | WI | NR Industrial IoT | RP-190728 | Nokia | Mar 20 | 22 |  |  |  | 2 | 1 |  |  |  | 2 | 1 | [5 empty] | 2 | 1 | [5 empty] | 3 | 1 |  |  |  | 3 | 1 | [5 empty] | 3 | 2
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-190489 | Intel | Mar 20 | 27 |  |  | 1 | 1.5 |  |  | 1 | 1 | 1.5 | 1 |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1 | 2 | 0.5 |  | 1 | 1 | 2 | 0.5 |  | 1 |  |  |  | 2 | 1 |  | 1 |  |  |  |  | 1
R4 | NR | NR_Mob_enh-Perf | WI | Perf part: NR mobility enhancements | RP-190489 | Intel | Mar 20 | 0.75 | [44 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-190452 | Ericsson | Mar 20 | 26 |  |  | 1 | 1.5 |  | 1 |  | 1 | 1.5 |  | 1 |  |  |  | 1 | 2 |  | 1 | 1 |  |  | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 |  |  |  | 2
R2 | NR | SRVCC_NR_to_UMTS-Core | WI | Core part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Mar 20 | 5.5 | [8 empty] | 0.5 |  |  |  | 0.25 |  |  | 0.5 | 0.5 |  | 0.25 | 0.25 |  |  | 0.5 | 0.5 |  | 0.25 |  | 0.5 | 0.5 |  | 0.25 | 0.25 |  |  | 0.5
R4 | NR | SRVCC_NR_to_UMTS-Perf | WI | Perf part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Jun 20 | 0.75 | [37 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR, LTE |  |  | Reserved for SA2/3 with with no RAN WI/SI (as agreed in RP-182974) |  |  |  | 3 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0 |  |  |  | [0.5] |  |  |  |  | [0.5]
R3 | NR | LTE_NR_arch_evo-Core | WI | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | RP-181375 | China Unicom | Dec 19 | 4.5 |  |  |  |  | 0.5 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R3 | NR | FS_NR_NTN_solutions | SI | Study on solutions for NR to support Non Terrestrial Network (NTN) | RP-190710 | Thales | Dec 19 | 9.5 |  |  | 1 | 0.5 | 1 |  |  | 1 | 0.5 | 1 |  |  |  |  | 1 | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | 0.5 | [6 empty] | 0.5
R3 | NR, LTE | FS_LTE_NR_data_collect | SI | Study on RAN-centric Data Collection and Utilization for NR | RP-182105 | CMCC | Jun 19 | 5 |  |  |  | 1 | 2 |  |  |  | 0.5 | 1.5
R3 | NR | Direct_data_fw_NR-Core | WI | Direct data forwarding for inter-system mobility | RP-182886 | Ericsson |  | 1.5 |  |  |  |  | 1 |  |  |  |  | 0.5
R3 | NR | ??? | WI | RAN-centric Data Collection and Utilization for NR |  | CMCC | Mar 20 | 9 | [15 empty] | 1 | 1.5 | [5 empty] | 1 | 1.5 |  |  |  | 1 | 1 | [5 empty] | 1 | 1
R3 | NR | RANImp_5WWC | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190772 | Huawei | Dec 19 | 1.5 | [16 empty] | 0.5 | [11 empty] | 0.5 | [6 empty] | 0.5
R3 | NR | FS_NR_NPN | WI | Private Network Support for NG-RAN | RP-190729 | China Telecom | Mar 20 | 6 | [15 empty] | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  | 0.5 | 1 | [5 empty] | 0.5 | 1
R3 | NR | FS_NR_LOCAL_POS | SI | Study on Local NR Positioning in NG-RAN | RP-190754 | CMCC | Dec 19 | 1.5 | [16 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R3 | NR | FS_eDisaggregated_gNB | SI | Study on Enhancement for Disaggregated gNB Architecture | RP-190702 | CATT | Dec 19 | 1.5 | [16 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_test_methods | SI | Study on test methods for New Radio | RP-180546 | Intel | Dec 18 | 0
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung | Dec. 19 | 6 | [5 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 2
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Core part: RF requirement for FR1 | RP-190759 | Huawei | Mar. 20 | [18 empty] | 4 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Perf part: RF requirement for FR1 | RP-190759 | Huawei | Sep. 20 | [44 empty] | 0.25
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Core part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia | March 2020 | [18 empty] | 4 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Perf part: NR RF Requirement Enhancements for FR2 | RP-190761 | Nokia | March 2020 | [44 empty] | 0.25
R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom | Mar. 2020 | [11 empty] | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-190760 | China Telecom | Sept. 2020 | [44 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 | [5 empty] | 0.25 | 0.25
R4 | NR,LTE, UTRA, E-UTRA, GSM | MSR_GSM_UTRA_LTE_NR | WI | New WID on introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | RP-190642 | Ericsson | Sep 2019 | [6 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-181655 | Sprint | Jun 19 | 1 | [5 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | n65_NR_newRAT | WI | New WID on Band 65 for New Radio for Region 1 | RP-181844 | DISH Network | March 19 | 0
R4 | NR | NR_band_48 | WI | New WID on an introduction of band n48 | RP-182865 | Nokia | Mar. 19 | 0
R4 | NR | NR_band_18 | WI | New WID: Introduction of NR band n18 | RP-182826 | KDDI | Dec 19 | 1.25 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_wide_chs_n7 | WI | New WID on adding wider channel bandwidths in Band n7 | RP-182827 | BT | Sep 19 | 0.9 | [5 empty] | 0.4 |  |  |  |  | 0.3 | [6 empty] | 0.2
R4 | NR | NR_wide_chs_n50 | WI | New WID on adding wider channel bandwidths in Band n50 | RP-182829 | Huawei | Jun. 19 | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n41_LTE_41_coex-Core | WI | New WI proposal: LTE/NR spectrum sharing in Band 41/n41 | RP-182883 | KDDI | Jun. 19 | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n41_BW-Core | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI | Jun. 19 | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n41_BW-Perf | WI | New WI proposal: Addition of 30MHz channel bandwidth for NR band n41 | RP-182828 | KDDI | Jun. 19 | 0
R4 | NR | FS_7to24GHz_NR | SI | Study on 7 - 24 GHz Frequency Range | RP-190373 | Huawei | Dec 19 | 8 | [5 empty] | 1.5 |  |  |  |  | 2 | [6 empty] | 2 | [6 empty] | 1.5 |  |  |  |  | 1
R4 | NR | ENDC_UE_PC2_TDD_TDD-Core | WI | Core part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC | Dec 19 | 5 | [5 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R4 | NR | ENDC_UE_PC2_TDD_TDD-Perf | WI | Perf part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-1828722 | CMCC | Dec 19 | 0
R4 | NR | FS_ENDC_UE_PC2_FDD_TDD | SI | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-182895 | China Unicom | Jun 19 | 2.5 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_band_n14 | WI | FDD operating band in Band n14 | RP-190165 | AT&T | June 19 | 0.4 | [5 empty] | 0.2 |  |  |  |  | 0.2
R4 | NR | NR_band_n30 | WI | FDD operating band in Band n30 | RP-190166 | AT&T | June 19 | 0.4 | [5 empty] | 0.2 |  |  |  |  | 0.2
R4 | NR | NR_Band_n259_R16 | WI | New WID: introduction of Band n259 | RP-190765 | Ericsson | Dec. 19 | 2.6 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | 0.1
R4 | NR |  | WI | Core part: Introduction of NR SUL (supplemental uplink) band with same uplink frequency range of NR band n5 | RP-190390 | Huawei | Sep.19 | [6 empty] | 0.1 |  |  |  |  | 0.1 | [6 empty] | 0.2
R4 | NR | NR_n38_BW | WI | Core part: addition of wider channel bandwidth in NR band n38 | RP-190392 | Huawei | Dec.19 | [6 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | EN-DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) , New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) New WID: Basket Rel-16 WID NR Intra-band CA New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands New WID: Rel-16 NR Inter-band Carrier Aggregation for 3 bands DL with 1 band bands UL New WID: Rel-16 NR Inter-band Carrier Aggregation/Dual connectivity for 3 bands DL with 2 band bands UL | RP-190689 RP-190705 RP-190379 RP-190159 RP-190294 RP-190494 RP-190151 RP-190714 RP-190692 RP-190693 | NTT DOCOMO, etc | Dec 19 | 18 | [5 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3
|  |  |  | Last row in NR totals. Insert new NR items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in LTE totals. Insert new LTE items below this line. Do not remove |  |  |  | 0
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-190770 | Ericsson | Mar 20 | 39 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 | 3 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 | 3 | 2.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2.5 | 0.5 | 0.5 | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-190770 | Ericsson | Jun. 20 | 5 | [29 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-190757 | Huawei | Mar 20 | 41.5 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 | 4 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 4 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 4 | 2.5 | 0.5 | 0.5 | 0.5 | 4 | 2.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-190757 | Huawei | Jun. 20 | 4 | [29 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R1 | LTE | LTE_terr_bcast-Core | WI | Core part: LTE-based 5G Terrestrial Broadcast | RP-190732 | Qualcomm | Mar 20 | 10 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  | 0.5 | 0.5 | 1 |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0 | [6 empty] | 0 | 1 |  |  |  | 0 | 1
R4 | LTE | LTE_Terr_bcast-Perf | WI | Performance part: LTE-based 5G terrestrial broadcast | RP-190732 | Qualcomm | Jun 20 | [38 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Mar 20 | 8.5 |  |  | 1 |  |  | 0.25 |  | 1 |  |  | 0.5 |  |  |  | 1 |  |  | 0.5 |  |  |  | 1 |  |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  |  |  | 0.5 |  | 0.25
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Mar 20 | 2.5 | [11 empty] | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom | Dec 19 | 12.5 |  |  |  | 1 |  |  | 0.25 |  | 1 | 1 |  | 0.25 |  |  |  | 1 | 1 |  | 0.5 |  |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  |  | 1 | 1 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom | Dec 19 | 2 | [18 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 1.5 | [6 empty] | 0.5 |  | 0.25 |  |  | 0.5 |  |  |  | 0.25
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 6.5 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1.5 | [6 empty] | 1.5 |  |  |  |  | 1.5
R4 | LTE | LTE410_Europe_PPDR-Core | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia | June 19 | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | LTE | LTE410_Europe_PPDR-Perf | WI | WID on 410 – 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | RP-182898 | Nokia | June 19 | 0
R4 | LTE | LTE_PC2_B31_B72 |  | Power Class 2 UE for LTE bands 31 and 72 | RP-190665 | Nokia | Sep 19 | 0.75 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 | RP-181548 RP-181930 RP-181851 RP-181887 RP-181853 RP-181733 RP-181824 RP-181825 | Ericsson, etc. | 2018-12-19 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
|  |  |  | Last row in LTE totals. Insert new LTE items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in UMTS totals. Insert new UMTS items below this line. Do not remove. |  |  |  | 0
|  |  |  | Last row in UMTS totals. Insert new UMTS items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in GERAN totals. Insert new GERAN items below this line. Do not remove |  |  |  | 0
|  |  |  | Last row in GERAN totals. Insert new GERAN items above this line. Do not remove |  |  |  | 0
| NR |  |  | allocated above | [6 empty] | 21.25 | 19 | 9 | 24.4 | 14.75 | 21.25 | 20 | 9.5 | 22.55 | 15.5 |  |  | 20 | 21 | 9.5 | 25.75 | 11 |  |  | 20 | 23 | 11 | 22.6 | 11 | 20 | 23.5 | 11 | 23.1 | 11.1 |  |  | 0 | 24.5 | 8.5 | 13.1 | 9 |  |  | 0 | 0 | 1 | 0.75 | 9.75 | 0 | 0 | 0 | 0.25 | 9.75 |  |  | 0 | 0 | 0 | 0.25 | 8.5
| NR |  |  | Legacy | [7 empty] | 9 |  |  |  |  | 8 | [6 empty] | 6 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| NR |  |  | TEI and other not planned issues | [19 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| NR |  |  | Reserve
| NR |  |  | total used capacity | [6 empty] | 21.25 | 28 | 9 | 24.4 | 14.75 | 21.25 | 28 | 9.5 | 22.55 | 15.5 |  |  | 20 | 28 | 9.5 | 25.75 | 11 |  |  | 20 | 28 | 11 | 22.6 | 11 | 20 | 28.5 | 11 | 23.1 | 11.1 |  |  | #REF! | 29.5 | 8.5 | 13.1 | 9 |  |  | #REF! | 0 | 1 | 0.75 | 9.75 | #REF! | 0 | 0 | 0.25 | 9.75 |  |  | #REF! | 0 | 0 | 0.25 | 8.5
| NR |  |  | available capacity | [6 empty] | 21 | 23 | 7 | 24 | 15 | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15 | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15 | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15
| NR |  |  | remaining/exceeded capacity | [6 empty] | -0.25 | -5 | -2 | -0.4 | 0.25 | -0.25 | -5 | -2.5 | 1.45 | -0.5 |  |  | 1 | -5 | -2.5 | -1.75 | 4 |  |  | 1 | -5 | -4 | 1.4 | 4 | 1 | -5.5 | -4 | 0.9 | 3.9 |  |  | #REF! | -6.5 | -1.5 | 10.9 | 6 |  |  | #REF! | 23 | 6 | 23.25 | 5.25 | #REF! | 23 | 7 | 23.75 | 5.25 |  |  | #REF! | 23 | 7 | 23.75 | 6.5
| LTE |  |  | allocated above | [6 empty] | 8 | 6 | 1 | 2.75 | 2.75 | 9 | 6.25 | 2 | 3 | 3.25 |  |  | 9 | 6.25 | 2 | 2.75 | 4 |  |  | 9 | 6 | 1.5 | 3 | 4.5 | 9 | 6.5 | 1.5 | 4 | 5.5 |  |  | 0 | 7 | 2 | 1.75 | 3.5 |  |  | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 1 | 3 |  |  | 0 | 0 | 0 | 0.5 | 0.5
| LTE |  |  | Legacy | [6 empty] | 1 | 5 | 3 |  |  |  | 5 | 3 | [5 empty] | 4 | 3 | [5 empty] | 4 | 3 |  |  |  | 4 | 3 | [5 empty] | 3 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3 | [5 empty] | 0 | 3
| LTE |  |  | TEI and other not planned issues | [8 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1 | [5 empty] | 0 | 1
| LTE |  |  | Reserve | [8 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3
| LTE |  |  | total used capcaity | [6 empty] | 10 | 11 | 8 | 2.75 | 2.75 | 10 | 11.25 | 9 | 3 | 3.25 |  |  | 10 | 10.75 | 9 | 2.75 | 4 |  |  | 10 | 10.5 | 8.5 | 3 | 4.5 | 10 | 11.5 | 8.5 | 4 | 5.5 |  |  | 0 | 11 | 9 | 1.75 | 3.5 |  |  | 0 | 0 | 7 | 1 | 3 | 0 | 0 | 7 | 1 | 3 |  |  | 0 | 0 | 7 | 0.5 | 0.5
| LTE |  |  | available capacity | [6 empty] | 10 | 15 | 12 | 3 | 3 | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3 | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3 | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3
| LTE |  |  | remaining/exceeded capacity | [6 empty] | 0 | 4 | 4 | 0.25 | 0.25 | 0 | 3.75 | 3 | 0 | -0.25 |  |  | 0 | 4.25 | 3 | 0.25 | -1 |  |  | 0 | 4.5 | 3.5 | 0 | -1.5 | 0 | 3.5 | 3.5 | -1 | -2.5 |  |  | 10 | 4 | 3 | 1.25 | -0.5 |  |  | 10 | 15 | 5 | 2 | 0 | 10 | 15 | 5 | 2 | 0 |  |  | 10 | 15 | 5 | 2.5 | 2.5
| UTRA |  |  | allocated above | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | Legacy | [16 empty] | 0.1 | [6 empty] | 0.1 | [11 empty] | 0.1
| UTRAN |  |  | TEI and other not planned issues | [16 empty] | 0.25 | [6 empty] | 0.25 | [11 empty] | 0.25
| UTRAN |  |  | Reserve | [16 empty] | 0.1 | [6 empty] | 0.1 | [11 empty] | 0.1
| UTRAN |  |  | total used capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | available capacity | [16 empty] | 0.7 | [6 empty] | 0.7 | [11 empty] | 0.7
| UTRAN |  |  | remaining/exceeded capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| GERAN |  |  | allocated above | [16 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| GERAN |  |  | Legacy | [16 empty] | 0.2 | [6 empty] | 0.2 | [11 empty] | 0.2
| GERAN |  |  | TEI and other not planned issues | [16 empty] | 0.5 | [6 empty] | 0.5 | [11 empty] | 0.5
| GERAN |  |  | Reserve | [16 empty] | 0.1 | [6 empty] | 0.1 | [11 empty] | 0.1
| GERAN |  |  | total used capacity | [16 empty] | 0.8 | [6 empty] | 0.8 | [11 empty] | 0.8 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| GERAN |  |  | available capacity | [16 empty] | 0.8 | [6 empty] | 0.8 | [11 empty] | 0.8
| GERAN |  |  | remaining/exceeded capacity | [16 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
R3 |  |  |  | RAN3 overall Status | [8 empty] | 2 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | -0.5 |  |  |  |  | -0.5 | [6 empty] | 1.5 | [6 empty] | 11 |  |  |  |  | 12 | [6 empty] | 12