## Slide 1: Agenda Item : 9.4.1 Source : Samsung Title : Discussion on NR_eMIMO Work Item Document for : Discussion and Decision
3GPP TSG RAN meeting #84 RP-191188
Newport Beach, USA, June 3-7, 2019

## Slide 2: Planned vs. current status: 10% lag
 | 2018 |  | 2019 |  |  |  |  |  | 
Month | 10 (94B) | 11 (95) | 1 (AH) | 2 (96) | 4 (96B) | 5 (97) | 8 (98) | 10 (98B) | 11 (99)
# TUs | 2 | 2 | [3] | 2 | 3 | 3 | 3 | 3 | 3
Cumulative #TUs | 2 | 4 | 7 | 9 | 12 | 15 | 18 | 21 | 24
A
Sub-item | Status (03/19) | Phase A | Phase B
MU-MIMO (MU) | On track | Evaluation methodology | (1) Type II overhead reduction; (2) Type II extension to rank > 2
Multi-TRP (MTRP) | On track |  | (1) DL control for NC-JT; (2) UL control and/or RS for NC-JT
Multi-beam 1 (MB1) | Behind |  | (1) UL beam selection for multi-panel; (2) UL/DL beam selection with lower latency & overhead
Multi-beam 2 (MB2) | On track |  | (1) BFR for SCell; (2) L1-RSRQ/SINR
UL TX (UL) | Behind | Complete WI task | Maintenance
Low PAPR RS (RS) | Complete | Complete WI task | Maintenance
B
TU usage (per 06/19): 15/24  ~65%
Completion level ~55% (see next slide)  lagging by ~10%

## Slide 3: Assessment
Overall, online and offline sessions have been amply and strategically allocated
  5 out of 6 sub-items are currently progressing well
  3 sub-items were initially progress-challenged in 03/19 (MTRP, MB2, UL) but have caught up after
  Off-the-track issue seems to be specific to MB1
Sub-item | Approximate % completion | Expected % completion per 06/19 | Issues/impediment in progressing
MU-MIMO (MU) | 65% (on track) | 65% | None
Multi-TRP (MTRP) | 65% (on track) | 65% | None. Enhancements for UL channels may not be worked on “naturally” (time limitation)
Multi-beam 1 (MB1) | 25% (behind) | 65% | Enhanced support for UL multi-panel: even if UE assumption was agreed, it is unclear if the necessary scheme can be completed in time (“Alt2” UL TCI vs. “Alt3” amalgamation/union of 3-5 different schemes), and other issues (e.g. panel de/activation, UL PC, TC, panel ID definition) Beam indication for reduced overhead/latency: new topics unrelated to the existing ones keep being added/accommodated
Multi-beam 2 (MB2) | 65% (on track) | 65% | None. A decision in RAN1#97 resolves the key bottle neck
UL TX (UL) | 65% (behind) | 100% | None. Two key bottle necks were resolved, expecting progress to accelerate
Low PAPR RS (RS) | 100% (on track) | 100% | None

## Slide 4: Probable issues with MB1
The scope of MB1 may be too large for the given TU allocation
  UL multi-panel: companies are just starting to recognize use cases but still diverge in
    Methodology to approach the issue
    The type of enhancement needed on top of Rel.15 (UL multi-panel is already accommodated)
    The need for versatile and forward-compatible framework
  Beam indication with reduced overhead/latency:
    Problems can be clearly identified from the lacking of Rel.15 multi-beam support
    Solutions to problems are limited hence easy to identify (progress is good)
    Yet newly proposed problems (”study”) keep being entertained/accommodated before the existing problems are fully resolved
Note: The other four sub-items still require time and resource to be completed
  Equal time allocation is still normative for all (five) remaining sub-items

## Slide 5: Possible RAN-level solutions to resolve the MB1 issue
Opt 1. Increase TU allocation to accommodate MB1
  For example, to accommodate at least 2x online session time for MB1
Opt 2. Down scope MB1 and postpone the less mature part to future release(s)
  Postpone enhanced support for UL multi-panel to Rel.17