## Slide 1: NR RRM Load in 2020H1
Sitges
3GPP TSG-RAN #86 Meeting
Sitges, Spain, December 9-12, 2019
RP-192667
MediaTek inc.

## Slide 2: Introduction
RAN4 is expected to close Rel-16 RRM core requirement in 2020Q1. However, current progress is actually behind the planned schedule due to
  Late start of some R16 WI
  Insufficient TUs for online discussion
Since there is no urgent need to start R17 RAN4 work from 2020Q2. The suggestion is to extend selected Rel-16 RAN4 RRM works by one more quarter.

## Slide 3: Late start on R16 WI
Rel-16 WIs started from 2019Q2 but only initial analysis for RRM spec impact were discussed
  NR-based access to unlicensed spectrum,
  5G V2X with NR sidelink,
  Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements
Rel-16 WIs started from 2019Q3 but only workplans were discussed
  NR Positioning Support,
  NR RRM requirement enhancement,
  RRM requirements for CSI-RS based L3 measurement,
  NR support for high speed train scenario: core part
Observation 1: The technical discussion on many non-spectrum WIs actually started later than then originally-planned schedule.

## Slide 4: Insufficient TUs for Online Discussion
The planned TU already exceeds RAN4 capacity
Although chairmans, rapporteurs, topic leaders and delegates tried very hard, there is still no sufficient time to address open issues, e.g.,
  NR-U: Total 38 open issues listed by topic leader. Only 12 were discussed online with additional 11 in ad-hoc session.
  Positioning: Total 36 open issues listed by topic leader. Only 7 were discussed online with additional 6 in ad-hoc session.
  MR DC\CA enhancement: Total 18 open issues listed by topic leader. Only 6 were discussed online.
  CSI-RS L3 measurement: Total 6 sub-agenda item planned. Only managed to treat 2.
Observation 2: The current RAN4 RD TUs in 2019Q4 and 2020Q1 are insufficient for online discussion and decision.
NR Tus in RAN4 | 2019Q4 |  |  |  | 2020Q1 |  | 2020Q2 |  |  | 
 | RF | RD | RF | RD | RF | RD | RF | RD | RF | RD
 | 92bis | 92bis | 93 | 93 | 94 | 94 | 94bis | 94bis | 95 | 95
total used capacity | 27.55 | 18 | 28.5 | 18.85 | 17.75 | 20.55 | 1.25 | 15.25 | 1.25 | 15.25
available capacity | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15
remaining/exceeded capacity | -3.55 | -3 | -4.5 | -3.85 | 6.25 | -5.55 | 22.75 | -0.25 | 22.75 | -0.25

## Slide 5: Necessarity to start RAN4 R17 at 2020Q2?
Usually, RAN4 RRM core requirements highly depend on the design in RAN1 and RAN2. Without concrete RAN1 and RAN2 design, RAN4 has only limited thing to discuss
  Experience in Rel-16
      Physical signal structure of SLSS is needed before RAN4 starts simulation campaign
      PRS signal design should be concluded before RAN4 starts to discuss RSTD requirements
      SCell Dormancy behavior should be first agreed in other WGs before RAN4 can discuss the activation delay
      UE behavior on relaxed measurement in IDLE mode should be concluded in RAN2 before RAN4 introduces the corresponding requirements
      RACH-less HO was discussed in RAN4 for 3 meetings, but RAN2 agreed not to support it in Aug meeting
      …, etc.
Observation 3: Allocating RAN4 RD TUs in the early phase of a release does not always guarantee the progress as expected.

## Slide 6: Proposal
Proposal 1: The finalization of RAN4 RRM core requirements of the following Rel-16 WIs are further extended by one quarter to 2020Q2: NR-U, V2X, MR DC/CA enhancement, UE power saving, positioning, enhanced MIMO, RRM enhancement, CSI-RS L3 measurement.
Late start
Insufficient TU
Rel-16 core
Late start
Insufficient TU
Finalization: 2020Q1
Finalization: 2020Q2
Current situation:
Proposal:
Rel-16 perf + Rel-17 core
Rel-16 perf + Rel-17 core
Rel-16 core
Additional time for better requirement quality and concrete RAN1/RAN2 Rel-17 design

## Slide 7: Thank You!