## Slide 1: Release 17 package for RAN
Source: RAN Chairman,
RAN1 Chairman,
RAN2 Chairman,
RAN3 Chairman

## Slide 2: Introduction
These slides present an initial draft for a Release 17 work package for RAN1, RAN2 and RAN3
  RAN4 plans are to be addressed and finalized at RAN#87 in March/2020
This proposal is based on all the moderator summaries and company inputs streamlined through the chairmen’s view on what is feasible
The goal is to endorse an overall Rel-17 package by Tuesday evening at RAN#86
  Detailed SID/WID sheets of the items within the endorsed package will then be worked out and approved by the conclusion of RAN#86

## Slide 3: Overall timeline
Q2
Q3
Q4
2021
Q2
Q3
Q4
Q1
2022
Q1
2020
Q1
2019
Q4
Rel-16 RAN1 freeze
Rel-16 stage-3 freeze
Rel-16 ASN.1 freeze
Rel-16 RAN4
performance completion
Rel-17 RAN1,2,3 package approval
Rel-17 RAN4 package approval
Rel-17 RAN1 freeze
Rel-17 stage-3 freeze
Rel-17 ASN.1 freeze
Rel-17 RAN4
performance completion
Rel-18 RAN1,2,3 package approval (TBC)
Release 17 timeline
Release 16 completion
15-month release length

## Slide 4: Release 17 – timeline aspects
TSG#84 in June took the assumption of a 15 month-long release for Rel-17
  15 months between the completion of the same phases in Release-16 and Release-17
Cross-check timeline aspects at TSG#86
Irrespective of the final timeline decision the planning for the Rel-17 RAN package will be undertaken with a TU budget of a 15 month-long release

## Slide 5: RAN1 Rel17
Power saving: idle/inactive focus, critical element on connected mode
2020 Q1
2020 Q2
2020 Q4
2021 Q1
2020 Q3
NR MIMO: as per email discussion conclusion
NR Sidelink enhancements: Power efficiency, Resource allocation and potential other critical leftovers (TBD in March)
NR Positioning enh: IIoT
Other misc impacts coming from RAN2/3/4
TU*: 15 (27-12) | TU*: 42 (54-8-4) | TU*: 25 (27-2) | TU*: 52 (54-1-1) | TU*: 27
2 | 6 | 4 | 8 | 4
0 | 4 | 2 | 4 | 2
1 | 4 | 2 | 4 | 2
0 | 2 | 1 | 2 | 1
2 | 4 | 2 | 4 | 2
0 | 0 | 0 | 2 | 2
1 | 2 | 2 | 2 | 0
2 | 4 | 2 | 4 | 2
2 1 | 4 2 | 2 1 | 4 2 | 2 1
2 | 4 | 2 | 4 | 2
0 | 0 | 1 | 2 | 1
1 | 2 | 1 | 2 | 1
1 | 4 | 2 | 4 | 2
0 | 0 | 1 | 2 | 2
0 | 0 | 0 | 2 | 1
RAN1 TUs
2020Q1
2020 Q2
2020Q3
2020Q4
2021 Q1
NR-Light: based on SI outcome
NR IIoT/URLLC: as per email discussion conclusion
NR Coverage enh: based on SI outcome
NR Coverage enh: low mobility, incl voice, identify bottleneck channel(s)
NR XR Study: traffic modelling, evaluation methodology, [characterization]
Extending current NR operation upto 71 GHz
Impacts coming from RAN2/3-led items with specific RAN1 objectives (IAB, Multicast)
Study enhancements for 52.6-71 GHz with existing waveform (RAN1, RAN4)
NR over NTN: LEO, GEO and transparent only, GNSS assumed.
NB-IoT / eMTC enhancements: 16QAM, RLF enhancements
Reserved for TEI17
DSS enhancement
IOT over NTN GNSS assumed
NR Positioning enh: IIoT
NR Light: lower complexity UEs, Power saving, coverage

## Slide 6: RAN2 Rel17
2020 Q2
2020 Q3
2021Q1
2021 Q2
2020 Q4
NR Multicast: single cell with fw compatibility to multicell
Non-Public Networks enh (SA2 led): incl NB-IoT
MR DC/CA enhancements: SCG act/deact enh.
NR NTN: LEO, GEO and transparent case only
NR IAB enh: Topology enh (transparent to core), Duplexing enh (RAN1), as per email discussion
Impacts coming from RAN1/3/4-led items, SA/CT, TEI17
TU*: 9 | TU*: 20 | TU*: 52 | TU*: 29 | TU*: 56
1 | 2 | 4 | 2 | 4
0 | 0 | 2 | 1 | 2
0 | 1 | 3 | 1 | 3
0 | 1 | 2 | 1 | 2
1.5 | 2 | 2 2 | 1 1 | 4
1.5 | 1 | 4 | 2 | 4
1 | 2 | 4 | 3 | 5
0 | 2 | 3 | 1 | 3
0 | 1 | 2 | 1 | 2
0 | 0 | 0 | 1 | 1
1 | 2 | 2/0 | 1 | 2/1
0 | 1 | 1 | 1 | 1
0 | 1 | 1 | 1 | 0
1 | 2 | 4 | 2 | 4
0 | 1 | 2 | 1 | 2
0 | 2 | 12 | 6 | 16
RAN2 TUs
2020Q2
2020 Q3
2020Q4
2021 Q1
2021 Q2
Multi SIM: paging.handling, RRC release, as per email discussion
NR UDC: copy LTE solution
RAN slicing
NR Sidelink relay: identify minimal impact for both L2 and L3
NR IIoT/URLLC: TSC (beyond TSN)
NR positioning enh: IIoT, integrity
Small Data enh: UL and inactive only
NR for UAV: copy LTE solution
SON/MDT (RAN3-led)
UE Power Saving: Idle/inactive focus
* TUs available for Rel-17 work
IoT for NTN
RAN slicing (based on SI outcome)
NR Sidelink relay: either L2/L3 (based on SI outcome)
NR Positioning enh: IIOT, integrity

## Slide 7: RAN3 Rel17
2020 Q2
2020 Q3
2021 Q1
2021 Q2
2020 Q4
NR SON/MDT enhancements (excl QoE)
2020 Q2
2020 Q3
2020 Q4
2021 Q1
2021 Q2
TU*: 24 | TU*: 12 | TU*: 24 | TU*: 12 | TU*: 24
6 | 2 | 4 | 2 | 3
2 | 1 | 2 | 1 | 2
2 | 2 | 2 | 1 | 2
0 | 1 | 1.5 | 1 | 2
4 | 1 | 4 | 2 | 4
1.5 | 1 | 2 | 1.5 | 1
1 | 0.5 | 2 | 0.5 | 2
0 | 1 | 2 | 0 | 0
5 | 0.5 | 1 | 0 | 0
3.5 (+1) ** | 2.5 (+0.5) ** | 4.5 (+1) ** | 3.5 (+0.5) ** | 8 (+1)
NR Multicast (RAN2-led)
RAN3 TUs
NR Non-Public Networks enh (SA2 led)
Corrections / TEIx
IAB enhancements (RAN2-led)
NR over NTN
NR positioning enh: IIoT, integrity
NR QoE (based on SI outcome)
NR QoE
* TUs available for Rel-17 work Total TU figure for one RAN3 meeting: 12
** Additional overbudget TUs shown in brackets
NB-IOT over NTN
LTE CP/UP split
Misc. impacts coming from RAN1/2 and SA/CT

## Slide 8: Proposal
It is proposed to take these slides as a basis for working out an overall Rel-17 package at RAN#86
An overall package to the extent shown in these slides shall be endorsed by Tuesday evening at RAN#86
  This allows sufficient time for the corresponding SIDs/WIDs to be worked out and formally approved by the conclusion of RAN#86

## Slide 9: Thank You !