## R17
RAN2 work for R17 | 20Q2 |  | 20Q3 | 20Q4 |  | 21Q1 | 21Q2 |  | 21Q3
| 109bis | 110 | 111 | 111bis | 112 | 113 | 113bis | 114 | 115
NR Multicast Single cell with fw compatibility to multicell TBD if it can be somewhat lower e.g. 1.5 TU/meeting | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2
Non-Public Networks (NPN) SA2 led |  |  | 0.5 | 1 | 1 | 1 | 1 | 1
MR DC/CA enhancements SCG act/deact enh, FR2 mobility (should be further clarified), cond PScell change/add (ph2), TBD if it can be somewhat lower e.g. 1.5 TU/meeting. TBD 0.5TU in Q2 for early start of FR2 mob. |  | 0.5 | 2 | 2 | 2 | 2 | 2 | 2
DSS scheduling enhancements Part of above in this plan, no R2 impact assumed.
Multi SIM NR-NR, NR-LTE (with changes in NR). LTE-LTE TBD Paging handling (Idle, Conn), Release | bar: 111 to 114
[R1] NR Non-Terrestrial Networks (NTN) LEO, GEO and transparent case, implicitly covering HAPS and air-to-ground. L2 enhancements, Low ambition Mobility enh (e.g. for feeder link switch). Mobility parts need to be more focused. | 0.5 | 0.5 | 2 | 1.5 | 1 | 1 | 2 | 2
[R1] IoT NTN SI Laundry list of points to check. No MTC HO Enh is assumed. TBD if to spread the time of the SI into the last Q. | 111bis: 0.5; 112: 1; 113: 1
[R1] NR positioning enhancements SI and WI low latency (incl UE-based techniques), integrity, BDS and NAVIC NR | 0.5 | 0.5 | 1 | 2 | 2 | 2 | 2 | 2
NR IAB enhancements Topology enh (transparent to core), leftovers, Mobile IAB TBD (risk that this is not feasible within current TU allocation, depend on detail scope). |  |  | 2 | 2 | 2 | 2 | 2 | 2
NR IIoT/URLLC Enh Time Distribution, Multiplexing/prioritization, Lossless Mobility wo Data forwarding (DC based mobility) - TBD a risk that it cannot be done with this TU allocation. |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Small Data enhancements UL and inactive only, 2-step/4-step, preconfig resources, with/wo context relocation. |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
NR UDC Copy LTE solution | 113: 0.5; 113bis: 0.5; 114: 0.5
NR Sidelink relay SI and WI Study L2/L3 minimal scope, assume 2 TU/meeting after that (assume outcome of the study to be either L3 or L2). | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2
RAN slicing SI and WI RACH, Cell reselection, Paging, HO service continuity [R3]. |  |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5
NR for UAV copy LTE solution | 113: 0.5; 113bis: 0.5; 114: 0.5
UE Power Saving Idle/inactive mode (maybe limited conn mode) TU acc to new WID req. TBD if TU alloc can be reduced last Q. | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
[R3] SON/MDT Comment: The scope is potentially too big for this TU allocation. Possible Strategy to accept this, and do prioritization in WG. Assumption: No new L1/Radio measurements. | bar: 111 to 114
[R1] NR Sidelink enhancements SL DRX, Resource allocation Enh (TBD which, 1.5 or 2 TU per Meeting) |  |  | 2 | 2 | 2 | 2 | 2 | 2
[R1] NR-Light SI and WI UE cap fwk, eDRX, RRM rlx pow saving | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
[R1] NB-IoT / eMTC enhancements mobility, paging mon TBD, percarrier enh, |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
[R1] NR MIMO Link recovery FR2, HL aspects Acc to WID request | 111bis: 0.5; 112: 0.5; 113: 0.5; 113bis: 1; 114: 1
[R3] NR QoE LTE solution, signalling of Containers. Spread out in time to allow fixing of issues of any |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[R3] LMC No R2 time
[R1] SI (WI) Coverage Enhancements No R2 time. R2 impact not clear.
[R1] NR up to 71GHz Acc to WID req. Directionality of procedures NR-U in R2 scope. Comment: R2 impact not clear, could be more than the allocated TU. | 113: 0.5; 113bis: 0.5; 114: 0.5
[R1] SI XR Acc to SID Req, QC think Pow Saving and Mobility is R2 scope (no particular requirement for R2).
TEI17 NR, LTE and items from other groups | 113: 1; 113bis: 2; 114: 2
Other | 1 | 1.5 | 1 |  | 2 | 2 | 0.5 | 1
Impacts RAN1/3/4-led items, TEI17 - Total | 1.5 | 2 | 6 | 5.5 | 7.5 | 9 | 9 | 9.5 | 0
R17 Total | 4 | 5 | 24 | 25 | 27 | 30 | 30 | 30 | 0
RAN2 Capacity | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
R16 and earlier | 36 | 35 | 16 | 15 | 13 | 10 | 10 | 10 | 8
R17 | 4 | 5 | 24 | 25 | 27 | 30 | 30 | 30 | 0
RAN2 TU Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32