## TU_overview_after_RAN_86
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 100 | 109 | 107 | 94 | 94 | 15 | 87 Mar.20 | 100bis | 109bis | 107bis | 94bis | 94bis | 101 | 110 | 108 | 95 | 95 | 16 | 88 Jun.20 | 102 | 111 | 109 | 96 | 96 | 17 | 89 Sep.20 | 102bis | 111bis | 109bis | 96bis | 96bis | 103 | 112 | 110 | 97 | 97 | 18 | 90 Dec.20 | 104 | 113 | 111 | 98 | 98 | 19 | 91 Mar.21 | 104bis | 113bis | 111bis | 98bis | 98bis | 105 | 114 | 112 | 99 | 99 | 20 | 92 Jun.21
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-191971 | NTT DOCOMO | Dec 18 | 0
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-191971 | NTT DOCOMO | Jun 18 | 0
R1 | NR | NR_2step_RACH-Core | WI | Core part: 2-step RACH for NR | RP-192330 | ZTE | Mar 20 | 1 |  |  | 1
R4 | NR | NR_2step_RACH-Perf | WI | Perf part: 2-step RACH for NR | RP-192330 | ZTE | Sep 20 | 4 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Mar 20 | 6.5 |  |  | 3 |  | 2 | 1.5
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Sep 20 | 2 | [5 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-191723 | LG Electronics | Mar 20 | 6.5 |  |  | 3 | 1 | 1 | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-191723 | LG Electronics | Sep 20 | 4.5 | [12 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-192271 | Samsung | Mar 20 | 2.5 |  |  | 1 |  | 0.5 | 1
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-192271 | Samsung | June 20 | 4 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_UE_pow_sav-Core | WI | Core part: UE Power Saving in NR | RP-191607 | CATT | Mar 20 | 2.5 |  |  | 1 |  | 0.5 | 1
R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-191607 | CATT | Sep 20 | 1.5 | [12 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-191156 | Intel | Mar 20 | 3 |  |  | 1 | 1 |  | 1
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-191156 | Intel | Sep 20 | 3 | [12 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Mar 20 | 1.2 |  |  | 1 |  | 0.1 | 0.1
R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Sep 20 | 5 | [5 empty] | 0.5 | [6 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R1 | NR | NR_CLI_RIM-Core | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-191997 | LG Electronics | Dec 19 | 0
R4 | NR | NR_CLI_RIM-Perf | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-191997 | LG Electronics | Dec 19 | 1.25 | [5 empty] | 0.25 | [6 empty] | 0.5 |  |  |  |  | 0.5
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182862 | Ericsson | Sept 19
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 0
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 5 | REL-17 | [19 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 2
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | Jun 21 | 7.5 | REL-17 | [26 empty] | 1 | 0.5 |  |  |  | 1 | 1 | [5 empty] | 2 | 1 | [6 empty] | 1
R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | Sep.20 | 8 | REL-17 | 2 | [6 empty] | 2 | 0.5 |  |  |  | 2 | 0.5 | [6 empty] | 1
R1 | NR | NR_pos_enh (planned) | WI | NR positioning enhancements | RP-xxxxxx | CATT | Jun 21 | 12.5 | REL-17 | [19 empty] | 2 | [6 empty] | 2 |  | 1 |  |  | 2 |  | 1 |  |  |  |  | 2 |  | 0.5 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | Jun 20 | 7 | REL-17 | 2 | [6 empty] | 2 | 0.5 |  |  |  | 2 | 0.5
R1 | NR | NR_redcap (planned) | WI | Support of reduced capability NR devices | RP-xxxxxx | Ericsson | Jun 21 | 8 | REL-17 | [19 empty] | 2 | [6 empty] | 2 |  |  |  |  | 2 | [6 empty] | 2
R1 | NR | FS_NR_cov_enh | SI | Study on NR coverage enhancements | RP-193240 | China Telecom | Jun 20 | 6 | REL-17 | 2 | [6 empty] | 2 |  |  |  |  | 2
R1 | NR | NR_cov_enh (planned) | WI | NR coverage enhancements | RP-xxxxxx | China Telecom | Jun 21 | 8 | REL-17 | [19 empty] | 2 | [6 empty] | 2 |  |  |  |  | 2 | [6 empty] | 2
R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | Jun 20 | 8 | REL-17 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  | 3 |  |  | 1
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-193241 | Qualcomm | Mar 21 | 4 | REL-17 | [19 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Jun 21 | 26.5 | REL-17 | 2 | [6 empty] | 2 |  |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 4 |  |  |  |  | 4 | 0.5 | [5 empty] | 4 | 0.5 | [6 empty] | 0.5 |  |  |  |  | 1
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Dec.21 | 0 | REL-17
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Jun 21 | 10 | REL-17 | [19 empty] | 2 | [6 empty] | 2 |  |  |  |  | 2 | 0.5 | [5 empty] | 2 | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21 | 0 | REL-17
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | Jun 21 | 21 | REL-17 | [7 empty] | 2 |  |  |  |  | 2 | [6 empty] | 2 | 1.5 | [5 empty] | 2 | 1.5 |  |  |  | 2 | 1.5 | [5 empty] | 2 | 1.5 | [6 empty] | 1.5 |  |  |  |  | 1.5
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Dec.21 | 0 | REL-17
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | Mar 21 | 6.75 | REL-17 | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei, Ericsson | Jun 21 | 17.5 | REL-17 | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | 1 | [5 empty] | 1 | 1.5 | 0.5 |  |  | 1 | 1 | 0.5 |  |  |  |  | 1 | 1 | 0.5 | [5 empty] | 1 | 1 |  |  |  | 1.5 | 1
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei, Ericsson | Dec.21 | 0 | REL-17
R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Mar 20 | 7.5 |  |  | 3 | 1 | 2 | 1.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Dec 20 | 3 | [12 empty] | 1.5 |  |  |  |  | 1.5
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-191088 | MediaTek | Mar 20 | 1.5 |  |  | 0.5 | 1
R2 | NR | NR_IIoT | WI | NR Industrial IoT | RP-192324 | Nokia | Mar 20 | 5 |  |  | 3 | 2
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-192277 | Intel | Mar 20 | 4.5 |  |  | 2 | 1.5 |  | 1 |  |  |  |  | 0
R4 | NR | NR_Mob_enh-Perf | WI | Perf part: NR mobility enhancements | RP-192277 | Intel | Mar 20 | 0.75 | [12 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Mar 20 | 3.5 |  |  | 2 |  | 0.5 | 1
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Mar 20 | 3 | [12 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R2 | NR | SRVCC_NR_to_UMTS-Core | WI | Core part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Mar 20 | 0.75 |  |  | 0.5 |  |  | 0.25
R4 | NR | SRVCC_NR_to_UMTS-Perf | WI | Perf part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Jun 20 | 0.75 | [5 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR, LTE |  |  | Reserved for SA2/3 with with no RAN WI/SI (as agreed in RP-182974) |  |  |  | 0.5 |  |  | 0.5
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20 | 3 | REL-17 | [8 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 2
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | Dec.20 | 3 | REL-17 | [9 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | Jun 21 | 20 | REL-17 | 2 | [6 empty] | 2 |  |  |  |  | 2 | [6 empty] | 2 | 1 | [5 empty] | 2 | 1 |  |  |  | 2 | 1 | [5 empty] | 2 | 1 | [6 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | Dec. 21 | 3 | REL-17 | [21 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Jun 21 | 22 | REL-17 | 1 | [6 empty] | 1 | 0.5 | 0.5 |  |  | 1 | 0.5 | 1 |  |  |  |  | 2 | 2 | 1 |  |  |  |  | 1 | 1.5 | 1 |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 |  |  |  |  | 2
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Dec.21 | 0 | REL-17
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | Jun 21 | 14 | REL-17 | 1 | [6 empty] | 1 | 0.5 |  |  |  | 1 | 0.5 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [6 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Dec.21 | 0 | REL-17
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | Jun 21 | 26.5 | REL-17 | [7 empty] | 1 | 0.5 | 1 |  |  | 1 | 0.5 | 1 |  |  |  |  | 1 | 1.5 | 2 |  |  |  |  | 1 | 1.5 | 1 |  |  | 1 | 1.5 | 1 |  |  |  |  | 1 | 2 | 1 | [5 empty] | 2 | 1 |  |  |  | 2 | 1
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Jun 21 | 10.5 | REL-17 | [13 empty] | 0.5 | 0.5 | [5 empty] | 1 | 0.5 | [5 empty] | 1 | 1 |  |  |  | 1 | 0.5 | [5 empty] | 1 | 0.5 | [5 empty] | 1 | 0.5 |  |  |  | 1 | 0.5
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21 | 0 | REL-17
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Jun 21 | 25 | REL-17 | 1 | [6 empty] | 1 |  | 2 |  |  | 1 |  | 2 |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 2 | [5 empty] | 1 | 1 |  |  |  | 1 | 2
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Dec.21 | 0 | REL-17
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Jun 21 | 12 | REL-17 | [20 empty] | 1.5 | [6 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5 | 1 | [5 empty] | 1.5 | 1 |  |  |  | 1.5 | 1
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21 | 0 | REL-17
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-193263 | vivo | Jun 21 | 6 | REL-17 | [20 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | NR | NR_SON_MDT | WI | SON/MDT Support for NR | RP-191776 | CMCC | Mar 20 | 2.5 |  |  | 1 | 1 |  | 0.5
R3 | NR | 5WWC-NG_interface | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190999 | Huawei | Mar 20 | 0.5 |  |  |  | 0.5
R3 | NR | NG_RAN_PRN | WI | Private Network Support for NG-RAN | RP-191563 | China Telecom | Mar 20 | 1.5 |  |  | 0.5 | 1
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-193255 | CMCC | Jun 21 | 22 | REL-17 | [9 empty] | 3 |  |  |  |  | 3 | [5 empty] | 1 | 2 | [5 empty] | 1 | 2 |  |  |  | 1 | 2 | [5 empty] | 1 | 2 | [5 empty] | 1 | 1 |  |  |  | 1 | 1
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Dec 20 | 3 | REL-17 | [21 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R3 | NR | FS_NR_QoE | SI | Study on NR QoE (Quality of Experience) management and optimizations for diverse services | RP-193256 | China Unicom | Sep 20 | 3.5 | REL-17 | [9 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.5 | 1
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung | Dec. 19 | 1 |  |  |  |  | 1
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Core part: RF requirement for FR1 | RP-193266 | Huawei | Mar. 20 | 5 |  |  |  |  | 4 | 1
R4 | NR | NR_RF_FR1_Req_Enh-Perf | WI | Perf part: RF requirement for FR1 | RP-193266 | Huawei | Sep. 20 | 2.25 | [11 empty] | 0.25 | 0.5 |  |  |  | 0.25 | 0.5 | [5 empty] | 0.25 | 0.5
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Core part: NR RF Requirement Enhancements for FR2 | RP-192653 | Nokia | March 2020 | 4 |  |  |  |  | 4
R4 | NR | NR_RF_FR2_Req_Enh-Perf | WI | Perf part: NR RF Requirement Enhancements for FR2 | RP-192653 | Nokia | March 2020 | 0.75 | [11 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-191891 | China Telecom | Mar. 2020 | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-191891 | China Telecom | Sept. 2020 | 1.5 | [11 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 | [5 empty] | 0.25 | 0.25
R4 | NR | NR_RRM_Enh_Core | WI | WI on NR RRM enhancement in R16 | RP-193211 | Intel, ZTE | Mar 20 | 1.5 | [5 empty] | 1.5
R4 | NR | NR_RRM_Enh_Perf | WI | WI on NR RRM enhancement in R16 | RP-193211 | Intel, ZTE | Sep 20 | 4.5 | [12 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R4 | NR | NR_CSIRS_L3meas | WI | Core part: CSI-RS based L3 measurement requirements for NR | RP-191992 | CATT | Mar 20 | 0.5 | [5 empty] | 0.5
R4 | NR | NR_CSIRS_L3meas | WI | Perf. part: CSI-RS based L3 measurement requirements for NR | RP-191992 | CATT | Sep 20 | 2 | [5 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_HST | WI | Core part: NR support for high speed train scenario | RP-191788 | CMCC | Mar 20 | 1 | [5 empty] | 1
R4 | NR | NR_HST | WI | Perf part: NR support for high speed train scenario | RP-191788 | CMCC | Sep 20 | 4 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1
R4 | NR | NR_enh-Perf | WI | NR performance requirement enhancement | RP-192532 | China Telecom | June. 20 | 2.25 | [5 empty] | 0.75 | [6 empty] | 0.75 |  |  |  |  | 0.75 | [6 empty] | 0.75
R4 | NR, LTE, UMTS | OTA_BS_testing-Perf | WI | Over the air (OTA) base station (BS) testing TR | RP-193225 | Huawei | Mar. 20 | 0.5 |  |  |  |  | 0.3 | [6 empty] | 0.1 |  |  |  |  | 0.1 | [6 empty] | 0.1
R4 | NR | NR_n48_LTE_48_coex-Core | WI | LTE/NR spectrum sharing in band 48/n48 frequency range | RP-193213 | Apple | Mar. 20 | 0.5 |  |  |  |  | 0.5
R4 | NR, LTE | ENDC_UE_PC2_FDD_TDD-Core | WI | New WID on Power Class 2 UE for EN-DC (1 LTE FDD band +1 NR TDD band) | RP 193244 | China Unicom | Mar. 20 | 1 |  |  |  |  | 1
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-192738 | Sprint | Dec 19 | 0.25 |  |  |  |  | 0.25
R4 | NR | FS_7to24GHz_NR | SI | Study on 7 - 24 GHz Frequency Range | RP-192076 | Huawei | Dec 19 | 2 |  |  |  |  | 1 | 1
R4 | NR | NR_Band_n259_R16 | WI | New WID: introduction of Band n259 | RP-191880 | Ericsson | Dec. 19 | 1.5 |  |  |  |  | 0.5 | 1
R4 | NR | NR_n3_BW-Core | WI | Adding 40 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n3 | RP 193056 | Ericsson | Mar. 20 | 0.2 |  |  |  |  | 0.2
R4 | NR | NR_n3_BW-Perf | WI | Adding 40 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n3 | RP 193056 | Ericsson | Mar. 20 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n65_BW-Core | WI | Adding 50 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n65 | RP 193057 | Ericsson | Mar. 20 | 0.2 |  |  |  |  | 0.2
R4 | NR | NR_n65_BW-Perf | WI | Adding 50 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n65 | RP 193057 | Ericsson | Mar. 20 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n53-Core | WI | WID on Introduction of NR Band n53 | RP 192409 | Globalstar | Mar. 20 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n53-Perf | WI | WID on Introduction of NR Band n53 | RP 192409 | Globalstar | Mar. 20 | 0
R4 | NR | NR_n1_BW-Core | WI | Core part: Adding 30 MHz channel bandwidth to NR band n1 | RP-192009 | Ericsson | Mar 20 | 0.15 |  |  |  |  | 0.15
R4 | NR | NR_n1_BW-Perf | WI | Perf part: Adding 30 MHz channel bandwidth to NR band n1 | RP-192009 | Ericsson | Mar 20 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n77_n78_BW-Core | WI | Addition of wider channel bandwidth in Band n77 and n78 | RP-192349 | Huawei | Dec 19 | 0
R4 | NR | EN-DC, SUL, NR CA/DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) RP-192742 New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) RP-192815 New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) RP-192446 New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) RP-192768 New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) (stopped) New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL RP-192592 New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) RP-192089 New WID: Basket Rel-16 WID NR Intra-band CA RP‑192445 New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands RP‑192615 New WID: Rel-16 NR Inter-band Carrier Aggregation for 3 bands DL with 1 band bands UL RP‑193206 New WID: Rel-16 NR Inter-band Carrier Aggregation/Dual connectivity for 3 bands DL with 2 band bands UL RP‑192617 Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL RP-192447 Dual Connectivity (EN-DC) with 3 bands DL (max.2 NR) and 3 bands UL (max. 2 NR) RP-192537 Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band RP-192784 | RP-192742 RP-192815 RP-192446 RP-192768 RP-192592 RP-192089 RP‑192445 RP‑192615 RP‑193206 RP‑192617 RP-192447 RP-192537 RP-191604 RP-192784 | NTT DOCOMO, etc | Dec 19 | 3 |  |  |  |  | 3
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-192430 | Apple，CAICT | Sep 20 | 1.75 |  |  |  |  | 0.25 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_n28_BW-Core | WI | Addition of wider channel bandwidth in NR band n28 | RP-192656 | CBN | Dec 19 | 1 |  |  |  |  | 1
R4 | NR | NR_n28_BW-Perf | WI | Addition of wider channel bandwidth in NR band n28 | RP-192656 | CBN | Dec 19 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n26 | WI | Introduction of NR Band n26 | RP-192736 | Sprint | Dec 19 | 0.35 |  |  |  |  | 0.25 | 0.1
R4 | NR | NR_n1_BW_2-Core | WI | Adding new channel bandwidth in NR band n1 | RP-192801 | China Unicom | Dec 19 | 0.15 |  |  |  |  | 0.15
R4 | NR | NR_n1_BW_2-Perf | WI | Adding new channel bandwidth in NR band n1 | RP-192801 | China Unicom | Dec 19 | 0.1 |  |  |  |  | 0.1
R4 | NR | NR_n66_BW | WI | Addition of asymmetric channel bandwidth for NR band n66 | RP-192808 | Huawei | Dec 19 | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n38_BW_2-Core | WI | Adding wider channel bandwidth to NR band n38 | RP-192215 | Ericsson | Dec 19 | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n38_BW_2-Perf | WI | Adding wider channel bandwidth to NR band n38 | RP-192215 | Ericsson | Dec 19 | 0.1 |  |  |  |  | 0.1
|  |  |  | Last row in NR totals. Insert new NR items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in LTE totals. Insert new LTE items below this line. Do not remove |  |  |  | 0
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-191356 | Ericsson | Mar 20 | 4 |  |  | 2.5 | 0.5 | 0.5 | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-191356 | Ericsson | Sep. 20 | 4 |  |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-192313 | Huawei | Mar 20 | 4 |  |  | 2.5 | 0.5 | 0.5 | 0.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-192313 | Huawei | Sep. 20 | 4 |  |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5
R1 | LTE | LTE_terr_bcast-Core | WI | Core part: LTE-based 5G Terrestrial Broadcast | RP-191924 | Qualcomm | Mar 20 | 3 |  |  | 0.5 | 0.5 | 0 | [6 empty] | 0 | 1 |  |  |  | 0 | 1
R4 | LTE | LTE_Terr_bcast-Perf | WI | Performance part: LTE-based 5G terrestrial broadcast | RP-191924 | Qualcomm | Jun 20 | [6 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Mar 20 | 1.5 |  |  | 0.5 |  | 1
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Sep. 20 | 0.75 | [12 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom | Dec 19 | 2.5 |  |  | 1 | 1 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom | Sep. 20 | 1.5 | [12 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Sep 19 | 0
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 0.5 | [5 empty] | 0.5
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA RP-192444 New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL RP-192525 New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL RP‑192811 New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL RP-192423 New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL RP-192813 New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 RP-192586 | RP-192444 RP-192525 RP-192811 RP-192423 RP-192813 RP-192586 | Ericsson, etc. | 2019-03-20 | 1 |  |  |  |  | 1
R2 | LTE | LCS_NAVIC-Core | WI | Core Part: Support for NavIC Navigation Satellite System for LTE | RP-192350 | Reliance Jio | Mar 20 | 0
R4 | LTE | LCS_NAVIC-Perf | WI | Perf part: Support for NavIC Navigation Satellite System for LTE | RP-192350 | Reliance Jio | Oct 20 | 0.5 | [5 empty] | 0.5
|  |  |  | Last row in LTE totals. Insert new LTE items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in UMTS totals. Insert new UMTS items below this line. Do not remove. |  |  |  | 0
|  |  |  | Last row in UMTS totals. Insert new UMTS items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in GERAN totals. Insert new GERAN items below this line. Do not remove |  |  |  | 0
|  |  |  | Last row in GERAN totals. Insert new GERAN items above this line. Do not remove |  |  |  | 0
| NR |  |  | allocated above | [5 empty] | 15 | 24 | 10 | 27.05 | 22.2 |  |  | 19 | 3 | 8 | 2.35 | 15 | 23 | 3.5 | 9 | 2.35 | 15 |  |  | 25 | 17.5 | 9.5 | 2.25 | 11 |  |  | 25 | 14.5 | 9 | 0 | 0 | 25 | 15 | 8.5 | 0 | 0 |  |  | 26 | 15.25 | 9 | 0 | 0 |  |  | 0 | 15.25 | 7 | 0 | 0 | 0 | 16.25 | 8 | 0 | 0
| NR |  |  | Legacy | [6 empty] | 4 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 4 | [6 empty] | 0 |  |  |  |  | 0
| NR |  |  | TEI and other not planned issues | [6 empty] | 1 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | [5 empty] | 1 | 0 |  |  |  | 1 | 0 | [5 empty] | 1 | 1 | [6 empty] | 0 |  |  |  |  | 0
| NR |  |  | Reserve | [5 empty] | 12 | [6 empty] | 8 |  |  |  |  | 4 | [6 empty] | 2 | [6 empty] | 1 |  |  |  |  | 1
| NR |  |  | total used capacity | [5 empty] | 27 | 29 | 10 | 27.05 | 22.2 |  |  | 27 | 3 | 8 | 2.35 | 15 | 27 | 3.5 | 9 | 2.35 | 15 |  |  | 27 | 17.5 | 9.5 | 2.25 | 11 |  |  | 27 | 14.5 | 9 | 0 | 0 | 27 | 15 | 8.5 | 0 | 0 |  |  | 27 | 20.25 | 9 | 0 | 0 |  |  | #REF! | 15.25 | 7 | 0 | 0 | #REF! | 16.25 | 8 | 0 | 0
| NR |  |  | available capacity | [5 empty] | 27 | 23 | 7 | 24 | 15 |  |  | 27 | 23 | 7 | 24 | 15 | 27 | 23 | 7 | 24 | 15 |  |  | 27 | 23 | 7 | 24 | 15 |  |  | 27 | 23 | 7 | 24 | 15 | 27 | 23 | 7 | 24 | 15 |  |  | 27 | 23 | 7 | 24 | 15 |  |  |  | 23 | 7 | 24 | 15 |  | 23 | 7 | 24 | 15
| NR |  |  | remaining/exceeded capacity | [5 empty] | 0 | -6 | -3 | -3.05 | -7.2 |  |  | 0 | 20 | -1 | 21.65 | 0 | 0 | 19.5 | -2 | 21.65 | 0 |  |  | 0 | 5.5 | -2.5 | 21.75 | 4 |  |  | 0 | 8.5 | -2 | 24 | 15 | 0 | 8 | -1.5 | 24 | 15 |  |  | 0 | 2.75 | -2 | 24 | 15 |  |  | #REF! | 7.75 | 0 | 24 | 15 | #REF! | 6.75 | -1 | 24 | 15
| LTE |  |  | allocated above | [5 empty] | 0 | 7 | 2.5 | 4 | 4 |  |  | 0 | 0 | 0 | 1 | 3.75 | 0 | 0 | 0 | 1 | 3.75 |  |  | 0 | 0 | 0 | 1 | 1.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LTE |  |  | Legacy | [6 empty] | 3 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3 | [5 empty] | 0 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3 | [5 empty] | 3 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3
| LTE |  |  | TEI and other not planned issues | [6 empty] | 1 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1 | [5 empty] | 0 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1 | [5 empty] | 1 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1
| LTE |  |  | Reserve | [7 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3
| LTE |  |  | total used capcaity | [5 empty] | 0 | 11 | 9.5 | 4 | 4 |  |  | 0 | 0 | 7 | 1 | 3.75 | 0 | 0 | 7 | 1 | 3.75 |  |  | 0 | 0 | 7 | 1 | 1.75 |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0 |  |  | 0 | 4 | 7 | 0 | 0 |  |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0
| LTE |  |  | available capacity | [5 empty] | 0 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 | 0 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 | 0 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 | 0 | 15 | 12 | 3 | 3
| LTE |  |  | remaining/exceeded capacity | [5 empty] | 0 | 4 | 2.5 | -1 | -1 |  |  | 0 | 15 | 5 | 2 | -0.75 | 0 | 15 | 5 | 2 | -0.75 |  |  | 0 | 15 | 5 | 2 | 1.25 |  |  | 0 | 15 | 5 | 3 | 3 | 0 | 15 | 5 | 3 | 3 |  |  | 0 | 11 | 5 | 3 | 3 |  |  | 0 | 15 | 5 | 3 | 3 | 0 | 15 | 5 | 3 | 3
| UTRA |  |  | allocated above | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | Legacy | [10 empty] | 0.2 | [37 empty] | 0.2
| UTRAN |  |  | TEI and other not planned issues | [10 empty] | 0.3 | [37 empty] | 0.3
| UTRAN |  |  | Reserve | [10 empty] | 0.2 | [37 empty] | 0.2
| UTRAN |  |  | total used capacity | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | available capacity | [10 empty] | 0.7 | [37 empty] | 0.7
| UTRAN |  |  | remaining/exceeded capacity | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GERAN |  |  | allocated above | [10 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0
| GERAN |  |  | Legacy | [10 empty] | 0.2 | [37 empty] | 0.2
| GERAN |  |  | TEI and other not planned issues | [10 empty] | 0.4 | [37 empty] | 0.4
| GERAN |  |  | Reserve | [10 empty] | 0.2 | [37 empty] | 0.2
| GERAN |  |  | total used capacity | [10 empty] | 0.8 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0.8 | [11 empty] | 0
| GERAN |  |  | available capacity | [10 empty] | 0.8 | [37 empty] | 0.8
| GERAN |  |  | remaining/exceeded capacity | [10 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0
R3 |  |  |  | RAN3 overall Status | [7 empty] | -0.5 | [6 empty] | 4 |  |  |  |  | 3 | [6 empty] | 2.5 | [6 empty] | 3 |  |  |  |  | 3.5 | [6 empty] | 3 | [6 empty] | 5 |  |  |  |  | 4

## Sheet1
R5 | LTE | LTE_PC2_B31_B72-UEConTest | WI | UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72 | RP-192506 | Airbus | 2019-03-20
R5 | LTE | NB_IOTenh2-UEConTest | WI | UE Conformance Test Aspects - Further NB-IoT enhancements | RP-192850 | CATT | Dec.20
R5 | LTE | LTE_eMTC4-UEConTest | WI | UE Conformance Test Aspects - Even further enhanced MTC for LTE | RP-192894 | Ericsson | Dec.20
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | 2019-06-21
R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | Sep.20
R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | 2019-06-20
R1 | NR | FS_NR_cov_enh | SI | Study on on NR coverage enhancements | RP-193240 | China Telecom | 2019-06-20
R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | 2019-06-20
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | Dec.20
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | 2019-06-21
R1 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Dec.21
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | 2019-06-21
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | 2019-06-21
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Dec.21
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | 2019-03-21
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | 2019-06-21
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | Dec.21
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | 2019-06-21
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | 2019-06-21
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Dec.21
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | 2019-06-21
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Dec.21
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | 2019-06-21
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | 2019-06-21
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | 2019-06-21
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Dec.21
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | 2019-06-21
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Dec.20
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-193255 | CMCC | 2019-06-21
R4 | UTRA, LTE, NR | OTA_BS_testing-Perf | WI | Perf. part: Over the air (OTA) base station (BS) testing TR | RP-193225 | Huawei | 2019-06-20
R4 | LTE, NR | ENDC_UE_PC2_FDD_TDD-Core | WI | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-193244 | China Unicom | 2019-03-20
R4 | NR | NR_n53-Core | WI | Core part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20
R4 | NR | NR_n53-Perf | WI | Perf. part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Core | WI | Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Perf | WI | Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20
R4 | NR | NR_n3_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20
R4 | NR | NR_n3_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20
R4 | NR | NR_n65_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20
R4 | NR | NR_n65_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20
R4 | LTE, NR | NR_n48_LTE_48_coex-Core | WI | Core part: LTE/NR spectrum sharing in band 48/n48 frequency range | RP-193213 | Apple | 2019-03-20

## Sheet2
R5 | LTE | LTE_PC2_B31_B72-UEConTest | WI | UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72 | RP-192506 | Airbus | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new | - | BB | s | tested: REL-16 WI LTE_PC2_B31_B72-Core | 13.1 | 860030 | T
R5 | LTE | NB_IOTenh2-UEConTest | WI | UE Conformance Test Aspects - Further NB-IoT enhancements | RP-192850 | CATT | Dec.20 | REL-15 | - | Dec.19 | 0 | new | - | BB |  | tested: REL-15 WI NB_IOTenh2-Core | 13.1 | 860031 | T
R5 | LTE | LTE_eMTC4-UEConTest | WI | UE Conformance Test Aspects - Even further enhanced MTC for LTE | RP-192894 | Ericsson | Dec.20 | REL-15 | - | Dec.19 | 0 | new | - | BB |  | tested: REL-15 WI LTE_eMTC4-Core | 13.1 | 860032 | T
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | 2019-06-21 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx | 09.01.02 | 860033 | -
R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | Sep.20 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | compare REL-16 NR_pos WI; TR 38.8xx | 09.01.01 | 860034 | -
R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | 2019-06-20 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | TR 38.xxx | 09.01.01 | 860035 | -
R1 | NR | FS_NR_cov_enh | SI | Study on on NR coverage enhancements | RP-193240 | China Telecom | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.01 | 860036 | -
R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | 2019-06-20 | REL-17 | R4 | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.01 | 860037 | -
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20 | REL-17 | - | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.02 | 860038 | -
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | Dec.20 | REL-17 | R3 | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.02 | 860039 | -
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_eMIMO | 09.01.01 | 860140 | C
R1 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.01 | 860240 | P
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | 2019-06-21 | REL-17 | - | Dec.19 | 0 | new |  | BB |  |  | 09.01.01 | 860141 | C
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21 | REL-17 | - | Dec.19 | 0 | new |  | BB |  |  | 09.01.01 | 860241 | P
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI 5G_V2X_NRSL | 09.01.01 | 860142 | C
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.01 | 860242 | P
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | 2019-03-21 | REL-17 | R2 | Dec.19 | 0 | new | - | BB |  | no Perf. part | 09.01.01 | 860143 | C
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | 2019-06-21 | REL-17 | R2, R3, R4 | Dec.19 | 0 | new | - | BB |  |  | 10.1.1 | 860144 | C
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 10.1.1 | 860244 | P
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | 2019-06-21 | REL-17 | R1 | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC | 09.01.02 | 860145 | C
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | follow-up WI of REL-16 SI FS_NR_NTN_solutions | 09.01.02 | 860146 | C
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860246 | P
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | 2019-06-21 | REL-17 | R1, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_UE_pow_sav | 09.01.02 | 860147 | C
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860247 | P
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | 2019-06-21 | REL-17 | R1, R3 | Dec.19 | 0 | new | - | BB |  | no Perf. part | 09.01.02 | 860148 | C
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI LTE_NR_DC_CA_enh | 09.01.02 | 860149 | C
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860249 | P
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_IAB | 09.01.02 | 860150 | C
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860250 | P
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | 2019-06-21 | REL-17 | R1, R3 | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860151 | C
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860251 | P
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Dec.20 | REL-17 |  | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 WI LTE_NR_arch_evo | 09.01.03 | 860152 | C
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-193255 | CMCC | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes | 09.01.03 | 860153 | C
R4 | UTRA, LTE, NR | OTA_BS_testing-Perf | WI | Perf. part: Over the air (OTA) base station (BS) testing TR | RP-193225 | Huawei | 2019-06-20 | REL-16 | - | Dec.19 | 0 | new |  | BB |  | no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16 | 09.01.04 | 860254 | P
R4 | LTE, NR | ENDC_UE_PC2_FDD_TDD-Core | WI | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-193244 | China Unicom | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s | no Perf. part | 09.01.05 | 860155 | C
R4 | NR | NR_n53-Core | WI | Core part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860156 | C
R4 | NR | NR_n53-Perf | WI | Perf. part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860256 | P
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Core | WI | Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s (xLTE/2NR_FR1_FR2) | basket WI; suggested TR 37.716-41-22 | 09.01.05 | 860157 | C
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Perf | WI | Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s (xLTE/2NR_FR1_FR2) |  | 09.01.05 | 860257 | P
R4 | NR | NR_n3_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860158 | C
R4 | NR | NR_n3_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860258 | P
R4 | NR | NR_n65_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860159 | C
R4 | NR | NR_n65_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860259 | P
R4 | LTE, NR | NR_n48_LTE_48_coex-Core | WI | Core part: LTE/NR spectrum sharing in band 48/n48 frequency range | RP-193213 | Apple | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s | no Perf. part | 09.01.05 | 860160 | C