3GPP TSG RAN meeting #88e										RP-201207

Electronic Meeting, June 29 - July 3, 2020

Status Report to TSG

Agenda item:			9.9.9

| WI / SI Name | Study on NR QoE management and optimizations for diverse services |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: Yes | Core part: No | Performance part: No |  | Testing part: No |
| Acronym | FS_NR_QoE |  |  |  |  |
| Unique ID | 860061 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-193256 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: 12/2020 (changed from 9/2020) | Core part: mm/yyyy | Performance part: mm/yyyy | Testing part: mm/yyyy |  |
| Overall Completion level | Study Item: 0 % | Core part: xx% | Performance Part: xx% | Testing part: xx% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN3 |
| --- | --- | --- |
| Rapporteur | Name | Xiang Pan |
|  | Company | China Unicom |
|  | Email | panx14@chinaunicom.cn |

1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | Yes |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

2.1	RAN1

2.1.1	Agreements

2.1.2	Remaining Open issues

2.2	RAN2

2.2.1	Agreements

RAN2 haven’t started the work on this SI.

2.2.2	Remaining Open issues

Study the potential RAN side solution for supporting a generic framework for triggering, configuring, measurement collection and reporting for various 5G use cases.

2.3	RAN3

2.3.1	Agreements

RAN3 haven’t started the work on this SI.

2.3.2	Remaining Open issues

Study the potential RAN side solution for supporting a generic framework for triggering, configuring, measurement collection and reporting for various 5G use cases.

Study the potential interface impact and solutions (e.g. F1, NG, Xn interface) to support NR QoE functionality.

2.4	RAN4

2.4.1	Agreements

2.4.2	Remaining Open issues

2.5	RAN5

2.5.1	Agreements

2.5.2	Remaining Open issues

2.5.3	Remaining Open issues with cross-WG dependencies

2.6	RAN6

2.6.1	Agreements

2.6.2	Remaining Open issues

3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

3.1	SAx/CTs

3.1.1	Agreements with cross-TSG impacts

3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.