## Slide 1: Release 17 Timeline
MediaTek Inc.
3GPP TSG RAN#90E RP-202690
December 2020 Agenda Item 15

## Slide 2: Proposal 1
Final total 9-month delay (i.e. additional 6 months vs. TSG#87)
No reduction of Rel-17 content
 | TSG#86 / Dec19 | TSG#90/Dec20 [+9mo]
Stage 2 | TSG#89 / Sep20 | TSG#92 / Jun21
Stage 3 PHY | TSG#91 / Mar21 | TSG#94 / Dec21
Stage 3 Others | TSG#92 / Jun21 | TSG#95 / Mar22
ASN.1/NAS | TSG#93 / Sep21 | TSG#96 / Jun22
RAN4/Perf | TSG#94 / Dec21 | min. TSG#97 / Sep22

## Slide 3: Follow-up RAN1-led WIs with RAN2 dependencies
Issue: Q1 normative work in RAN1 in parallel with study work in RAN2
  Proposal 2.1:
    RAN1 to focus on topics with no RAN2 dependencies
    WI to be updated in RAN#91/March 2021 based on RAN2 conclusions
  Proposal 2.2:
    Any outstanding RAN1 issues from SID to be resolved during RAN#90e or latest during Q1 (RAN1)
Redcap, Pos, CovEnh.