## Slide 1: Considerations on Release 17
3GPP TSG RAN Meeting #90-e RP-202733
7th – 11th December 2020
Agenda Item: 9
Source: Intel Corporation
Document for: Discussion

## Slide 2: Release 17 completion
RAN#89e endorsed for the RAN leadership to perform detailed planning for the remainder of Rel-17 under the assumption of 6 month delay to the completion
Encouraging news of effective vaccines gives high hope of a return to F2F for the RAN WG meetings towards the end of Rel-17 (end of 2021, start of 2022)
This provides Increased confidence that completion with 6 month delay is a realistic target
Proposal: Release-17 completion is delayed by 6 months, i.e:
  Dec 2021 RAN1 completion
  March 2022 Core completion in RAN2/3/4
  June 2022 ASN.1 freeze
  Sept 2022 Performance completion in RAN4

## Slide 3: RAN1 led Rel-17 SIs
RAN1 has completed its work on 4 RAN1 led SIs:
  Positioning enhancements
  NR in 52.6-71 GHz
  Reduced capability devices
  Coverage enhancements
Follow on WIs expected to be approved at RAN#90e
Study in other RAN WGs is not complete (expected in March 2021)
It would be premature to try to conclude any RAN2/3/4 objectives before study in other WGs is complete.
Proposal: Follow on WIs approved at RAN#90e are to include RAN1 objectives only.

## Slide 4: Expectation for Rel-18 schedule
If RAN#90e agrees 6 months delay to Rel-17 completion, RAN1 completion will be in Dec 2021
Consequently, we expect the following schedule for Rel-18 discussions in RAN:
  June 2021 (RAN#92) – Opportunity for companies to share views on Rel-18
  June-Dec 2021 – Consensus building by email and by discussion at RAN#93
  Dec 2021 (RAN#94) – Rel-18 packaged approval for RAN1/2/3

## Slide 5: Summary
Proposal: Release-17 completion is delayed by 6 months, i.e:
  Dec 2021 RAN1 completion
  March 2022 Core completion in RAN2/3/4
  June 2022 ASN.1 freeze
  Sept 2022 Performance completion in RAN4
Proposal: Follow on WIs approved at RAN#90e are to include RAN1 objectives only.