## Cover sheet
3GPP TSG-RAN WG5 meeting #92-e | [8 empty] | R5-214908
Electronic meeting, 16th-27th Aug 2021
Agenda Item: | 7.4.2
Source: | Nokia, Apple
Title: | WP UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
Work item code: | NR_RF_FR2_req_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID (830089) on NR RF requirement enhancements for FR2. This work item will cover RF conformance test specifications for NR RF requirement enhancements for FR2. At the RAN#91-e meeting in March 2021 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2 was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 30% (+30%) | 1.9 (+1.9) | 7.6 (+7.6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 29.7% (+29.7%) | 1.9 (+1.9) | 7.6 (+7.6)
FR2 |  | 29.7% (+29.7%) | 1.9 (+1.9) | 7.6 (+7.6)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 33.3% (+33.3%) |  |  | 33.3% (+33.3%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%)
NR RF/RRM
FR2 RF common parts | 38.521-2 | 25% (+25%) |  |  | 25% (+25%)
FR2 RF Tx test cases | 38.521-2 Tx | 28.4% (+28.4%) | 1.2 (+1.2) | 5.2 (+5.2) | 28.4% (+28.4%) | 1.2 (+1.2) | 5.2 (+5.2)
FR2 RF Rx test cases | 38.521-2 Rx | 25.6% (+25.6%) | 0.7 (+0.7) | 1.4 (+1.4) | 25.6% (+25.6%) | 0.7 (+0.7) | 1.4 (+1.4)
EN-DC FR2 RF test cases | 38.521-3 | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 50% (+50%) |  |  | 50% (+50%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-210363 | New WID on UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
[2] R5-215765 | Revised WID - UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR2_req_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for FR2 RF Enhancements for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Tuomo Säynäjäkangas, Nokia Ashwin Mohan, Apple |  |  | tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
29.7% (+29.7%)
147 (+147)
20.4 (+20.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3 | Reference test conditions | Add necessary test conditions for Rel-16 NR RF FR2 aspects | Nokia | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for new Rel-16 NR RF FR2 features | Nokia | RAN5#92 (Aug-21) | R5-214026 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Nokia | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A,4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for Rel-16 NR RF FR2 aspects | Nokia | RAN5#92 (Aug-21) | R5-214027 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 2 | References | Define References made in TS | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreaviations respectively | Apple | RAN5#94 (Feb-22) | R5-215980 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 | 4 | General | Define categories of test requirements | Nokia | RAN5#92 (Aug-21) |  | No changes required | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 | 5 | Operating bands and Channel arrangement | Frequency Separation Classes, Intra-band and Inter-band CA configuration updates | Apple | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex A | Measurement channels | Annex A.3 updates for Rel-16 Beam Correspondence | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex B | Propagation conditions | Possible propagation conditions updates in Rel-16 NR RF FR2 tests (IBM) |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex C | Downlink physical channels | Define new downlink physical channels in Rel-16 |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex D | Interfering signals | Define any updates to characteristics of the interfering signal updates in Rel-16 NR RF FR2 tests |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process (Rel-16 Updates, if any) |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for updated Rel-16 test cases/bands |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex G | Uplink Physical Channels | Define uplink physical channels (Rel-16 updates) |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex H | Statistical Testing | TBD |  | RAN5#95 (May-22) |  |  | TBD | 0% | 0% |  | 0%
TBD |  | 38.521-2 | Annex P | Modified MPR Behavior | Rel-16 MPR enhancements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | Rel-16 MBR enhancements (check accessStratumrelease for Rel-16 support) | Apple | RAN5#93 (Nov-21) |  | Should separate TC/clause be planned for Rel-16 MBR? | 1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | Rel-16 MBR enhancements | Apple | RAN5#93 (Nov-21) |  | Should separate TC/clause be planned for Rel-16 MBR? | 1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Tx | 6.2.3 | UE maximum output power reduction | Update minimum requirement for n259 and power boost IE updates for Rel-16, Beam Management Config updates | Apple | RAN5#93 (Nov-21) |  | Should separate TC be planned for checking modifiedMPR-Behaviour UE capability? Will ACLR be impacted as well? | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2.4 | Configured transmitted power | P-MPR updates, support for powerboost IE in minimum conformance requirements | Nokia | RAN5#92 (Aug-21) | R5-212225 | No core spec changes in CA section 6.2A.4 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-2 Tx | 6.2A | Transmit power for CA | Existing sub-clause header
|  | 38.521-2 Tx | 6.2A.1 | UE maximum output power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Tx | 6.2A.1.1 | UE maximum output power - EIRP and TRP for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.1.1 | UE maximum output power - EIRP and TRP for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.2 | UE maximum output power - EIRP and TRP for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.3 | UE maximum output power - EIRP and TRP for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.4 | UE maximum output power - EIRP and TRP for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.5 | UE maximum output power - EIRP and TRP for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.6 | UE maximum output power - EIRP and TRP for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.1.7 | UE maximum output power - EIRP and TRP for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Tx | 6.2A.1.2 | UE maximum output power - Spherical coverage for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.2.1 | UE maximum output power - Spherical coverage for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.2 | UE maximum output power - Spherical coverage for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.3 | UE maximum output power - Spherical coverage for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.4 | UE maximum output power - Spherical coverage for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.5 | UE maximum output power - Spherical coverage for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.6 | UE maximum output power - Spherical coverage for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.1.2.7 | UE maximum output power - Spherical coverage for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Tx | 6.2A.2 | UE maximum output power reduction for CA | Existing sub-clause header
|  | 38.521-2 Tx | 6.2A.2.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.1 | UE maximum output power reduction for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.2 | UE maximum output power reduction for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.3 | UE maximum output power reduction for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.4 | UE maximum output power reduction for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.5 | UE maximum output power reduction for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.6 | UE maximum output power reduction for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.2.7 | UE maximum output power reduction for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Tx | 6.2A.4 | Configured transmitted power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.4.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.1 | Configured transmitted power for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.2 | Configured transmitted power for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.3 | Configured transmitted power for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.4 | Configured transmitted power for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.5 | Configured transmitted power for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.6 | Configured transmitted power for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.4.7 | Configured transmitted power for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements |  | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.1 | Minimum output power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.1.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.2 | Transmit OFF power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.2.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.3 | Transmit ON/OFF time mask for CA | Existing sub-clause header |  |  |  | Sub-clause structure aligned with Rel-15 WP.
TBD |  | 38.521-2 Tx | 6.3A.3.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#93 (Nov-21) | R5-212227, R5-214914 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.3.1 | General ON/OFF time mask for CA | Measure the general ON/OFF time mask of 5G-NR FR2 UE. | [5 empty] | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.4.2 | Absolute power tolerance for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.4.2.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.3 | Relative power tolerance for CA | New sub-clause header |  |  | R5-215858 | Clause introduced by Rel-15 WP | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.4.3.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#94 (Feb-22) | R5-215858 | Clause introduced by Rel-15 WP | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.4.4 | Aggregate power tolerance for CA | New sub-clause header |  |  |  | Clause will be introduced by Rel-15 WP | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.4.4.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#94 (Feb-22) |  | Clause will be introduced by Rel-15 WP | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.4.2.2.3 | Carrier Leakage, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) | Apple | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.4.2.3.3 | In-band emissions, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) | Nokia | RAN5#92 (Aug-21) | R5-212226 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.4A.1.0 | Frequency error for CA | Include intra-band non-contiguous CA for minimum conformace | Nokia | RAN5#92 (Aug-21) | R5-214104, R5-214915 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.4A.2 | Transmit modulation quality for CA | Include intra-band non-contiguous CA for minimum conformace | Nokia | RAN5#92 (Aug-21) | R5-214104, R5-215975 |  | 0.5 | 10% (+10%) | 10% (+10%) |  | 10%
TBD |  | 38.521-2 Tx | 6.5.2.3 | ACLR, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) |  | RAN5#93 (Nov-21) |  | Check if needed. Relate to MPR in 6.2.3 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.5A.1 | Occupied bandwidth for CA | Existing sub-clause header | Nokia |  | R5-212229
TBD |  | 38.521-2 Tx | 6.5A.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212229 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-212229 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.1 | Occupied bandwidth for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212229 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.2 | Occupied bandwidth for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212229 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.2.1 | Spectrum emission mask for CA | Existing sub-clause header | Nokia |  | R5-212230
TBD |  | 38.521-2 Tx | 6.5A.2.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212230 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-212230 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.1 | Spectrum emission mask for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212230 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.2 | Spectrum emission mask for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212230 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.2.2 | Adjacent channel leakage ratio for CA | Existing sub-clause header | Nokia |  | R5-212231
TBD |  | 38.521-2 Tx | 6.5A.2.2.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212231 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.2.0.1 | Adjacent channel leakage ratio for CA intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212231 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.2.0.2 | Adjacent channel leakage ratio for CA intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212231 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3 | Spurious emissions for CA | Existing sub-clause header | Nokia |  | R5-214028
TBD |  | 38.521-2 Tx | 6.5A.3.1 | General spurious emissions for CA | Clause title change from transmitter to general | Nokia | RAN5#94 (Feb-22) | R5-214028 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-214028 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-214028 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.1 | Spurious emissions for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-214028 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.2 | Spurious emissions for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-214028 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3.2 | Spurious emission band UE co-existence for CA | Include UL, intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212233 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.6.0 | Beam Correspondence - General | Update text to cover Enhanced (Rel-16) Beam Correspondence | Apple, Nokia | RAN5#93 (Nov-21) | R5-214029 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.6.1 | Beam Correspondence - EIRP | Align sub-clause structure with 38.101-2. This clause continue to cover Rel-15 aspects | Apple, Nokia | RAN5#93 (Nov-21) | R5-214029, R5-215636, R5-215637 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Tx | 6.6.2 | Enhanced Beam Correspondence - EIRP | New sub-clause to cover Rel-16 content | Apple, Nokia | RAN5#93 (Nov-21) | R5-214029 | MU and TT are FFS. Min conformance requirements section can be combined to include both REL15 and REL16 requirements. Test Procedure and Test requirements sections are FFS | 1 | 20% (+20%) | 20% (+20%) |  | 20%
TBD | Y | 38.521-2 Tx | 6.6.2.3.1.2 | Enhanced Beam Correspondence - EIRP | New sub-clause; Applicability rules based on support for type of enhanced beam correspondence | Apple | RAN5#93 (Nov-21) | R5-216081 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Tx | 6.6A | Beam Correspondence for CA | Rel-16 Requirements Updates | Apple | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | Possible requirements updates | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | Possible requirements updates | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Rx | 7.3A.2 | Reference sensitivity power level for CA | Existing sub-clause header |  |  |  | Check if need to include DL into clause 7.3A heading.
TBD |  | 38.521-2 Rx | 7.3A.2.0 | Minimum requirements | Requirements updates | Apple | RAN5#93 (Nov-21) | R5-213329, R5-215979 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.2.0.3 | Inter-band CA | Add Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-213329, R5-214910 | New clause included in 38.521-2. Remove brackets and correct clause references. | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.3A.2.1 | Reference sensitivity power level for CA (2DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-213329 | MU and TT are FFS. Beam peak search is FFS Extreme conditions for FR2 are FFS Some references in square brackets for inter-band DL CA | 0.1 | 10% (+10%) | 10% (+10%) |  | 10%
TBD |  | 38.521-2 Rx | 7.3A.2.2 | Reference sensitivity power level for CA (3DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.3 | Reference sensitivity power level for CA (4DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.4 | Reference sensitivity power level for CA (5DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.5 | Reference sensitivity power level for CA (6DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.6 | Reference sensitivity power level for CA (7DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.3A.2.7 | Reference sensitivity power level for CA (8DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3 | EIS spherical coverage for CA | New clause for EIS spherical coverage for CA | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0 | Minimum conformance requirements | New clause | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.1 | Void | New clause to align with 38.101-2 | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.2 | Void | New clause to align with 38.101-2 | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.3 | EIS spherical coverage for Inter-band CA | New clause for Inter-band CA | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.1 | EIS spherical coverage for CA (2DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.2 | EIS spherical coverage for CA (3DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.3 | EIS spherical coverage for CA (4DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.4 | EIS spherical coverage for CA (5DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.5 | EIS spherical coverage for CA (6DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.6 | EIS spherical coverage for CA (7DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.3A.3.7 | EIS spherical coverage for CA (8DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | Align spec structure with other WIs | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Rx | 7.4A | Maximum input level for CA | Existing sub-clause header
TBD |  | 38.521-2 Rx | 7.4A.0 | Minimum requirements | Requirement updates | Apple | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% |  | 0%
TBD | Y | 38.521-2 Rx | 7.4A.0.3 | Maximum input level for Inter-band CA | New clause for Inter-band CA | Apple, Nokia | RAN5#95 (May-22) | R5-215976 | RAN4 WI introduced new clause added. Align spec structure with other Wis. Check if need to include DL into clause 7.4A heading. Correct 7.4A.0.3 heading | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.4A.1 | Maximum input level for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.2 | Maximum input level for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.3 | Maximum input level for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.4 | Maximum input level for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.5 | Maximum input level for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.6 | Maximum input level for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.4A.7 | Maximum input level for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A | Adjacent channel selectivity for CA | Existing sub-clause header |  | RAN5#93 (Nov-21) |  | Check if need to include DL into clause 7.5A heading.
TBD |  | 38.521-2 Rx | 7.5A.0 | Minimum requirements | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.0.1 | Adjacent channel selectivity for Intra-band contiguous CA | Placeholder for Intra-band contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.0.2 | Adjacent channel selectivity for Intra-band non-contiguous CA | Placeholder for Intra-band non-contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.0.3 | Adjacent channel selectivity for Inter-band CA | Include inter-band CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.1 | Adjacent channel selectivity for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.2 | Adjacent channel selectivity for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.3 | Adjacent channel selectivity for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.4 | Adjacent channel selectivity for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.5 | Adjacent channel selectivity for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.6 | Adjacent channel selectivity for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.5A.7 | Adjacent channel selectivity for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Rx | 7.6A | Blocking characteristics for CA | Existing sub-clause header |  |  |  | Check if need to include DL into clause 7.6A heading.
TBD |  | 38.521-2 Rx | 7.6A.1 | General | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.521-2 Rx | 7.6A.2 | In-band blocking for CA | Existing sub-clause header |  | RAN5#94 (Feb-22)
TBD |  | 38.521-2 Rx | 7.6A.2.0 | Minimum requirements | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.0.1 | In-band blocking for Intra-band contiguous CA | Placeholder for Intra-band contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.0.2 | In-band blocking for Intra-band non-contiguous CA | Placeholder for Intra-band non-contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.0.3 | In-band blocking for Inter-band CA | Include inter-band CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.1 | In-band blocking for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.2 | In-band blocking for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.3 | In-band blocking for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.4 | In-band blocking for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.5 | In-band blocking for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.6 | In-band blocking for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Rx | 7.6A.2.7 | In-band blocking for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 0% | 0% |  | 0%
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.521-3 | 6.6B.1.6 | Enhanced Beam Correspondence for Inter-band EN-DC within FR2 (2 CCs) | WP adds a new SA test in TS 38.521-2. Add equivalent EN-DC Rel.16 Enhanced Beam correspondence test. | Apple | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF FR2 test cases
TBD |  | 38.522 | 4,1,2 | FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.521-2. | Nokia | RAN5#94 (Feb-22) | R5-215981 |  | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | RAN5#95 (May-22) |  |  | 0.2 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TP analysis for FR2 RF Test cases |  | RAN5#94 (Feb-22) |  |  | 0.2 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.