## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [10 empty] | R5-215167
Electronic Meeting, 16th August 2021 - 27th August 2021
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16
Work item code: | LTE_bands_R16_M1_NB1-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The RAN5 WID [1] on additional LTE bands (7, 42, 43 and 65) introduced in Rel-16 for UE category M1 and/or NB1 was approved at RP#90-e, Dec-20. The present work plan covers the necessary changes to be introduced in 3GPP RF, RRM and Protocol conformance test specifications and its status.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+20%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 100% (+20.5%)
FDD |  | 100% (+20.5%)
TDD |  | 100% (+20.5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% |  |  | 100% |  |  | 100%
LTE RF/RRM
RF common parts | 36.521-1 | 100% |  |  | 100% |  |  | 100%
RF Rx test cases | 36.521-1 Rx | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
RF Tx test cases | 36.521-1 Tx | 100% |  |  | 100% |  |  | 100%
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
LTE RAN and CN protocols
Applicability Protocol test cases | 36.523-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-202522 | New WID: UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_bands_R16_M1_NB1-UEConTest
WP Scope: |  | The present work plan covers necessary changes to be introduced in 3GPP RAN WG5 RF, RRM and Protocol conformance test specifications for Band 7, 42, 43 and 65 for UE category M1 and/or NB1 in Release 16. | [12 empty] | vs Area
WP Resp: |  | Mats Johansson, Ericsson |  |  | mats.e.johansson@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
900052 |  | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[14 empty] | 100% (+20.5%) | 100% (+20.5%)
[14 empty] | 7 | 7
[14 empty] | 5.1 | 5.1
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 | Common test env | 36.508 | 4.3 | Introduction of FDD/TDD Mode Test Frequencies for operating band 7, 42 and 43. | Check if test frequencies for new Rel-16 band introduced by R16_M1_NB1 need to be added to clause 4.3.1. |  | RAN5#90-e (Feb-21) |  | Not needed? Current TS 36.508 covers the new bands. | 1
2 | Common test env | 36.508 | 8.1.3.1 | Introduction of FDD/TDD Mode Test Frequencies for operating band 7, 42 and 43. | Check if test frequencies for new Rel-16 band introduced by R16_M1_NB1 need to be added to clause 8.1.3.1. |  | RAN5#90-e (Feb-21) | R5-214013 | Add NB-IoT FDD Test frequencies for band 7, 42, 43 and 65. | 1 | 100% | 100% |  | 100% | 100%
3 | Signalling test | 36.508 | 8.3.2.3 | Update existing band table 8.3.2.3.1-1 with the new bands |  |  | RAN5#90-e (Feb-21) | R5-214013 | Add NB-IoT FDD Test frequencies for band 7, 42, 43 and 65. | 1 | 100% | 100% |  | 100% | 100%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
4 | Common definitions in 36.521-1 | 36.521-1 | 5 | Addition of new bands for UE category M1 and NB1. |  |  | RAN5#91-e (May-21) | R5-211834 | Operating bands for UE category M1 and NB1 needs to be updated for band 7, 42, 43 and 65. | 1 | 100% | 100% |  | 100% | 100%
TS 36.521-1: RF test cases - Tx
5 | Transmitter Characteristics | 36.521-1 Tx | 6 | Transmitter tests for category M1 and NB1. |  | Ericsson | RAN5#91-e (May-21) | R5-211835, R5-212672, R5-212673, R5-214015, R5-214722 | All new bands should be added by one CR unless a specific need appears. | 1 | 100% | 100% |  | 100% | 100%
TS 36.521-1: RF test cases - Rx
6 | Receiver Characteristics | 36.521-1 Rx | 7 | Receiver tests for category M1 and NB1. |  |  | RAN5#91-e (May-21) | R5-214723 | All new bands should be added by one CR unless a specific need appears. | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 36.521-1: Demod/QSI reporting test cases
7 | Performance Characteristics | 36.521-1 Demod | 8.12.1.x | Demodulation of Narrowband IoT, NPDSCH |  |  | RAN5#91-e (May-21) |  | Not needed? | TBD
8 | Performance Characteristics | 36.521-1 Demod | 8.12.2.x | Demodulation of Narrowband IoT, NPDCCH |  |  | RAN5#91-e (May-21) |  | Not needed? | TBD
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
9 | ICS proforma tables | 36.521-2 | Annex A | ICS proforma tables | Check if test frequencies for new Rel-15 band introduced by R16_M1_NB1 needs to be added. |  | RAN5#91-e (May-21) |  | Not needed? Current TS 36.521-2 covers band 7, 42, 43 and 65. | TBD | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 36.521-3: RRM test cases
10 | General sections and Annexes | 36.521-3 | 3.5.1 Annex I | 3.5.1 Groups of bands Annex I: Conditions for RRM requirements applicability for operating bands |  |  | RAN5#91-e (May-21) |  | Not needed? Current TS 36.521-3 covers band 7, 42, 43 and 65? | TBD
LTE RAN and CN protocols
TS 36.523-2: Applicability for Protocol test cases
11 | ICS proforma tables | 36.523-2 | Annex A.4 | Update existing table A.4.3.1-1 with new bands. | Add new ICS statements. |  | RAN5#91-e (May-21) |  | Not needed? Current TS 36.571-1 covers band 7, 42, 43 and 65? | 0.1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.