## Slide 1: Progress of Rel-17 and proposed actions on the scope
3GPP TSG RAN Meeting #93-e
Electronic Meeting, Sept 13 – 17, 2021
Document for: Approval
Agenda Item: 9.9
Source: Huawei, HiSilicon
RP-212146

## Slide 2
Background
There is one quarter left for RAN1 to provide the first specifications for Rel-17, as well as complete the dependencies to other WGs (e.g. RRC parameters, UE capabilities).
Rel-18 package approval is planned for RAN#94.
 3GPP RAN should avoid a delay in the completion of Rel-17 and the start of Rel-18
Rel-17 has been progressing steadily, although at a slower pace compared to F2F meetings. RAN1 still struggles with hard decisions (e.g. selections among options) and with a few optimizations (e.g. lots of FFS points remaining in agreements).
Some targeted actions on Rel-17 work/study items could be useful to mitigate risks on the completion of RAN1 work by RAN#94.
Actions for RAN2/3/4 could be taken as needed at RAN#94, unless a critical issues already need to be already addressed at RAN#93.

## Slide 3: Status of RAN1-led Rel-17 WID/SID
Name | WID | Status before RAN#93e
Additional enhancements for NB-IoT and LTE-MTC | RP-211340 | Good progress, although progress a bit slow in RAN2
Rel-17 enhancements on MIMO for NR | RP-211586 | RAN1: Good progress on mTRP, SRS and CSI. Progress is slow for a few topics under BM, e.g. fast UL panel selection/switching and advanced beam refinement/tracking. May consider to postpone to Rel-18.
NR sidelink enhancement | RP-202846 | Good progress on Inter-UE coordination, particularly for Scheme 1 To focus the work, RAN could agree that RAN1 can stop discussing some remaining FFS points on “other options”, etc., and remove need to study relating partial sensing to SL DRX.
NR Dynamic spectrum sharing (DSS) | RP-211345 | Advanced UE capability Type B (where the UE monitors PDCCH on both cells in overlapping slot/symbol) is not essential for the WI and could be down-scoped if needed, focusing on the basic UE capability Type A in Rel-17
NB-IoT/eMTC suppport for NTN | RP-211601 | On track
Study for XR Evaluations for NR | RP-210460 | Good progress on capacity/power evaluations. Additional work is popping up along the way, e.g. RAN1 just agreed to additionally perform evaluations for coverage and had initial discussions on mobility.
Support of reduced capability NR devices | RP-211574 | New scaling factor on peak data rate: discussion triggered in RAN2 (no consensus), LS to RAN1. This is not in scope of the WID. Optional support for SUL by a RedCap UE is in scope of the WID, RAN may need to clarify this again to stop such discussions in WGs. Controversial discussions on the support of BWP without SSB in RAN1. BWP without SSB is a key to address the nature of reduced bandwidth from 100MHz to 20MHz for RedCap and beneficial from network perspective e.g. avoid frequency resource fragmentation, but some UE vendors have concern due to potential impact on UE power consumption.
NR positioning enhancements | RP-210903 | Good progress in general, including for objectives on positioning in inactive state (DL) and second priority objectives on positioning in inactive state (UL, UL+DL).
NR coverage enhancement | RP-211566 | On track
Extending NR operation up to 71GHz | RP-211584 | It is likely not possible to discuss additional UE processing time capabilities, so RAN1 should only discuss the agreed timelines based on 120 kHz SCS and complete the design for these already agreed timelines.
New bands and band allocations for LTE terrestrial broadcast (R1 part) | RP-211144 | Completed in a single meeting.

## Slide 4: Status of RAN2-led Rel-17 WID/SID
Name | WID | Status before RAN#93e
NR Multicast and Broadcast Services | RP-201038 | RAN1: Confirm the support of gNB-DU SFN in Rel-17 with necessary specification work, e.g. configuring TRS as a QCL source in inactive/idle state. Add RAN1 to objective “Study the support for dynamic control of the Broadcast/Multicast transmission area within one gNB-DU and specify what is needed to enable it, if anything [RAN1, RAN2, RAN3] ”. RAN1: For CFR configuration for broadcast, the proposal from RAN1 chair’s notes should be taken, i.e., support case C and working assumption on support at least one of case D and case E. Working assumption was not made due to strong concern from one company. Please see RP-212267 Discussion on the progress of Rel-17 NR MBS Huawei (rapporteur), RAN#93e
Multi-Radio Dual-Connectivity enhancements | RP-201040 | Good progress, no need for action
Solutions for NR to support non-terrestrial networks (NTN) | RP-211557 | Good progress, no need for action
Enhanced IIoT and URLLC support | RP-210854 | RAN1: Scenarios involving SUL should not be precluded for PUCCH carrier switching, including the scenario of a single cell configured with SUL and NUL, and the scenario of more than one cell with at least one cell configured with SUL and NUL. Same motivation for the support of PUCCH switching between FDD cell and TDD cell, and between FDD cell and FDD cell, and almost zero additional specification impact.
Support for Multi-SIM devices in Rel-17 | RP-211561 | Dependency on SA2 for the need for NAS Assistance information
UE Power Saving Enhancements | RP-200938 | RAN1: Working assumption on PDCCH-based PEI supported by 20 companies was not made due to concern from 3 companies, even though it was concluded before that one candidate from PDCCH based PEI and SSS based PEI shall be selected. PDCCH-based PEI should be selected.
IAB enhancements | RP-211548 | Fair progress
NR small data transmissions in INACTIVE state | RP-210870 | Fair progress. The main unresolved issue is the issue with non-SDT data arrival during SDT procedure
NR Sidelink Relaying | RP-211050 | Good progress in general. Stage 2 design of discovery and relay (re)selection which are common for L2 and L3 is completed. For L2 CP and service continuity procedure, stage 2 design is almost done with some detailed issues to be concluded. For L2 protocol stack, support of PC5 AL was concluded in RAN2 #115. Basic functions of Uu AL are clear with some stage 3 issues left.
Enhancement of RAN Slicing | RP-211290 | Good progress, no need for action
Supporting NR Uplink Data Compression | RP-211203 | The WID scope is small and only one RAN2 meeting is planned. No need for action

## Slide 5: Status of RAN3-led Rel-17 WID/SID
Name | WID | Status before RAN#93e
Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-201620 | Good progress, no need for action
Study NR QoE management and optimizations for diverse services | RP-211406 | Good progress, no need for action
Enhanced eNB(s) architecture evolution for E-UTRAN | RP-211406 | Completed
Study on further enhancements for data collection | RP-201304 | Good progress, no need for action
Enhancement of Private Network Support for NG-RAN | RP-202363 | Good progress, no need for action

## Slide 6
Proposal
Discuss possible actions on Rel-17 work/study items (e.g. as summarized in previous slides) in order to ensure no delay of Rel-17 and a timely start of the work on 5G-Advanced in Rel-18.