## TU_overview_after_RAN_96
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 96 Jun.22 | 110 | 119 | 117 | 104 | 104 | 97 Sep.22 | 110bis | 119bis | 117bis | 104bis | 104bis | 111 | 120 | 118 | 105 | 105 | 98 Dec.22 | 112 | 121 | 119 | 106 | 106 | 99 Mar.23 | 112bis | 121bis | 119bis | 106bis | 106bis | 113 | 122 | 120 | 107 | 107 | 100 Jun.23 | 114 | 123 | 121 | 108 | 108 | 101 Sep.23 | 114bis | 123bis | 121bis | 108bis | 108bis | 115 | 124 | 122 | 109 | 109 | 102 Dec.23
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Mar 22 | 0 | REL-17
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Sept 22 | 1 | REL-17 | [5 empty] | 1
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-213540 | Qualcomm | Sep.22 | 1.5 | REL-17 |  |  |  |  | 1 | 0.5
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-213540 | Qualcomm | Dec.22 | 4.5 | REL-17 |  |  |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | Intel | Mar 22 | 0 | REL-17
R4 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | Intel | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.5
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP-220966 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP-220966 | Ericsson | Sept 22 | 2.25 | REL-17 | [5 empty] | 1 | [5 empty] | 0.75 |  |  |  |  | 0.5
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-211566 | China Telecom | Mar 22 | 0 | REL-17
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-211566 | China Telecom | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-220529 | Huawei, Ericsson | Mar 22 | 0 | REL-17
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-220529 | Huawei, Ericsson | Sept 22 | 0.25 | REL-17 | [5 empty] | 0.25
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-221863 | LG Electronics | Mar 22 | 0 | REL-17
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-221863 | LG Electronics | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.5
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-210460 | Qualcomm | Dec 21 | 0 | REL-17
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 | MediaTek | Dec 21 | 0 | REL-17
R1 | LTE | LTE_NBIOT_eMTC_NTN | WI | NB-IoT/eMTC support for Non-Terrestrial Networks | RP-211601 | MediaTek, Eutelsat, ZTE | June 22 | 0 | REL-17
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Sept 22 | 0 | REL-17
R1 | LTE | LTE_terr_bcast_bands-Core | WI | Revised WID for New bands and bandwidth allocation for 5G terrestrial broadcast (Part 1) | RP-211144 | EBU | Mar 22 | 0 | REL-17
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 0 | REL-17
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-220152 | Nokia | Mar 22 | 0 | REL-17
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Perf part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-220152 | Nokia | Sept 22 | 0.25 | REL-17 | [5 empty] | 0.25
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-221169 | Thales | June 22 | 0 | REL-17
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-221169 | Thales | Dec 22 | 3.75 | REL-17 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  | 0.75 | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-221543 | MediaTek | Mar 22 | 0 | REL-17
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-221543 | MediaTek | Sept 22 | 0.25 | REL-17 | [5 empty] | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-221177 | Qualcomm | Jun 22 | 0 | REL-17
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-221177 | Qualcomm | Sept 22 | 0.75 | REL-17 |  |  |  |  | 0.5 | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-220428 | Huawei | Mar.22 | 0 | REL-17
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-220428 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay | WI | NR Sidelink Relay | RP-212819 | OPPO | Mar.22 | 0 | REL-17
R2 | NR | NR_SL_Relay-Perf | WI | NR Sidelink Relay | RP-212819 | OPPO | Sep.22 |  | REL-17 | [5 empty] | 0.25
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP-221377 | CMCC | 2022-06-01 | 0 | REL-17
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-211290 | CMCC | Jun.21 | 0 | REL-17
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Mar.22 | 0 | REL-17
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Dec.21 | 0.25 | REL-17 | [5 empty] | 0.25
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Mar.22 | 0 | REL-17
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Dec.21 | 0.25 | REL-17 | [5 empty] | 0.25
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-213679 | vivo | Mar 22 | 0 | REL-17
R2 | NR | NR_UDC-Core | WI | NR UDC | RP-220140 | CATT | Mar 22 | 0 | REL-17
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Jun 21 | 0 | REL-16
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Jun 21 | 0 | REL-16
R2 | NR |  |  | R1 Misc items (DSS etc) |  |  |  | 0 | REL-17
R2 | NR, LTE |  |  | R17 Other (R4 items etc) |  |  |  | 0 | REL-17
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-220821 | CMCC | Mar 22 | 0 | REL-17
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-213667 | China Unicom | Mar 22 | 0 | REL-17
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | CMCC | Mar 22 | 0 | REL-17
R3 | NR | NR_QoE | WI | NR QoE management and optimizations for diverse services | RP-211406 | China Unicom | Mar 22 | 0 | REL-17
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-212585 | China Telecom | Mar 22 | 0 | REL-17
R3 | NR | UPIP_SEC_LTE-RAN-Core | WI | User Plane Integrity Protection support for EPC connected architectures WI | RP-213669 | Vodafone | Mar 22 | 0 | REL-17
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | China Unicom | Sep 21 | 0 | REL-17
R4 | NR | FS_NR_600MHz_ext | SI | Study on extended 600MHz NR band | RP-202924 | Spark NZ Ltd | Sep 21 | 0 | REL-17
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-213101 | CAICT | Mar 22 | 0 | REL-17
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-213101 | CAICT | Sep 22 | 1 | REL-17 |  |  |  |  | 1
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-221285 | China Telecom | Mar 22 | 1 | REL-17 | [5 empty] | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-213654 | Ericsson | Sep 21 | 0 | REL-17
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-213654 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-213067 | Apple | Mar 22 | 0 | REL-17
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-213067 | Apple | Sep 22 | 0.5 | REL-17 | [5 empty] | 0.5
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Mar 22 | 0 | REL-17
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Sep 22 | 0.5 | REL-17 | [5 empty] | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-221784 | Nokia | Mar 22 | 0 | REL-17
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-221784 | Nokia | Jun 22 | 0.5 | REL-17 | [5 empty] | 0.5
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Mar 22 | 0 | REL-17
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Sep 22 | 1 | REL-17 | [5 empty] | 1
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-220772 | MediaTek | Mar 22 | 0 | REL-17
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-220772 | MediaTek | Sep 22 | 0.5 | REL-17 | [5 empty] | 0.5
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-221502 | Huawei | Mar 22 | 0 | REL-17
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-221502 | Huawei | Sep 22 | 0 | REL-17
R4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-213514 | Qualcomm, Commscope | Mar 22 | 0 | REL-17
R4 | NR | NR_repeaters-Perf | WI | NR Repeaters | RP-213514 | Qualcomm, Commscope | Sep 22 |  | REL-17 |  |  |  |  | 0.5
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-221785 | vivo, OPPO, CMCC | Mar 22 | 0 | REL-17
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-221785 | vivo, OPPO, CMCC | Sep 22 | 0.5 | REL-17 |  |  |  |  | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-213535 | Qualcomm | Mar 22 | 0 | REL-17
R4 | NR | NR_RF_TxD-Core | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0 | RAN2 TU in R17 Other
R4 | NR | NR_RF_TxD-Perf | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0
R4 | LTE | LTE_NR_HPUE_FWVM-Core |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 0 | REL-17
R4 | LTE | LTE_NR_HPUE_FWVM-Perf |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 0.25 | REL-17 |  |  |  |  | 0.25
R4 | NR | R17 NR Basket Wis | [5 empty] | 0 | REL-17
R4 | NR | R17 NR spectrum related WI/SI |  | RP-210878 Introduction of 900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer | RP-210878 |  |  | 0.1 | REL-17 |  |  |  |  | 0.1
R4 | LTE | R17 LTE basket WIs | [5 empty] | 0 | REL-17
R4 | LTE | R17 LTE spectrum related WI/SI | [5 empty] | 0 | REL-17
R4 | LTE,NR | R17 LTE/NR spectrum Perf part | [5 empty] | 0 | REL-17
R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance | RP-210710 | Qualcomm, AT&T |  | 0 | REL-17
R1 | NR | NR_MIMO_evo_DL_UL-Core | WI | Core part: NR MIMO evolution for downlink and uplink | RP-213598 | Samsung | Dec.23 | 29.75 | REL-18 |  | 3 | [5 empty] | 3 |  |  |  |  | 3 | [5 empty] | 3 |  |  | 0.25 | 0.25 |  | 3 | 0.5 |  | 0.5 | 0.5 | 3 | 0.5 |  | 0.5 | 0.5 |  | 3 | 0.75 |  | 0.5 | 0.5 |  |  | 0.75 |  | 0.5 | 0.5 |  | 0.75 |  | 0.5 | 0.5
R4 | NR | NR_MIMO_evo_DL_UL-Perf | WI | Perf. part: NR MIMO evolution for downlink and uplink | RP-213598 | Samsung | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_cov_enh2-Core | WI | Core part: Further NR coverage enhancements | RP-221858 | China Telecom | Dec.23 | 13.25 | REL-18 | [7 empty] | 1 |  |  | 0.25 |  | 1 |  |  | 0.25 |  |  | 1 |  |  | 0.25 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 1 |  |  |  | 0.5 |  | 1 |  |  | 0.5 |  | 1
R4 | NR | NR_cov_enh2-Perf | WI | Perf. part: Further NR coverage enhancements | RP-221858 | China Telecom | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_DSS_enh-Core | WI | Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | RP-221622 | Ericsson | Dec.23 | 1 | REL-18 |  | 1
R4 | NR | NR_DSS_enh-Perf | WI | Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | RP-221622 | Ericsson | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_MC_enh-Core | WI | Core part: Multi-carrier enhancements for NR | RP-221435 | NTT DOCOMO | Dec.23 | 5 | REL-18 |  | 1 |  |  | 0.25 |  |  | 0.5 |  |  | 0.5 | 0.25 | 0.5 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_MC_enh-Perf | WI | Perf. part: Multi-carrier enhancements for NR | RP-221435 | NTT DOCOMO | June 24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_SL_enh2-Core | WI | Core part: NR sidelink evolution | RP-221798 | OPPO | Dec.23 | 32.75 | REL-18 |  | 2 | [5 empty] | 2 | 0.5 |  |  |  | 2 | 0.5 |  |  |  |  | 2 | 1 |  | 0.5 | 0.25 |  | 2 | 1 |  | 1 | 0.5 | 2 | 1 |  | 1.5 | 0.5 |  | 2 | 1 |  | 1.5 | 1 |  |  | 1 |  | 1.5 | 1 |  | 1 |  | 1.5 | 1
R4 | NR | NR_SL_enh2-Perf | WI | Perf. part: NR sidelink evolution | RP-221798 | OPPO | Sep.23 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_NR_netcon_repeater | SI | Study on NR network-controlled repeaters | RP-221229 | ZTE | Sep.22 | 3.5 | REL-18 |  | 1 | 0.5 | 0.5 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5
R1 | NR | FS_NR_AIML_air | SI | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | RP-221348 | Qualcomm | Dec.23 | 31.5 | REL-18 |  | 3 | [5 empty] | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  | 0.5 | 3 | 1 |  |  | 0.5 |  | 3 | 1 |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.5
R1 | NR | FS_NR_duplex_evo | SI | Study on evolution of NR duplex operation | RP-221352 | CMCC | Dec.23 | 18.75 | REL-18 |  | 2 |  |  | 0.25 |  |  | 2 |  |  | 0.5 |  | 2 |  |  | 0.5 |  |  | 2 |  |  | 1 |  |  | 2 |  |  | 0.5 |  | 2 |  |  | 1 |  |  | 2 |  |  | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_NR_pos_enh2 | SI | Study on expanded and improved NR positioning | RP-221814 | Intel | Dec.22 | 29.75 | REL-18 |  | 3 | 1.5 | 0.5 | 0.25 |  |  | 3 | 2 | 0.5 | 0.25 | 0.5 | 3 | 2 | 0.5 | 0.25 | 0.5 |  |  | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R1 | NR | FS_Netw_Energy_NR | SI | Study on network energy savings for NR | RP-221443 | Huawei | Dec.22 | 13.5 | REL-18 |  | 1 | 1 | 0.5 |  |  |  | 1 | 1 | 0.5 |  |  | 1 | 1 | 0.5 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R1 | NR | FS_NR_LPWUS | SI | Study on low-power wake-up signal and receiver for NR | RP-221271 | vivo | Dec.23 | 10.75 | REL-18 | [7 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 |  |  | 0.25 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 0.25 |  |  | 0.5 |  | 0.25
R1 | NR | FS_NR_redcap_enh | SI | Study on further NR RedCap (reduced capability) UE complexity reduction | RP-221161 | Ericsson | Sep.22 | 7 | REL-18 |  | 1 | [17 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Sep.23 | 11 | REL-18 |  | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2
R2 | NR | NR_Mob_enh2-Core | WI | Core part: Further NR mobility enhancements | RP-221799 | MediaTek | Dec.23 | 45.25 | REL-18 |  |  | 2 | 1 |  | 0.5 |  | 1 | 2 | 1 |  | 0.5 | 1 | 2 | 1 |  | 0.5 |  | 1 | 2 | 1 | 0.25 | 1 |  | 1 | 2 | 1 | 0.5 | 1.5 | 1 | 2 | 1 | 0.5 | 1.5 |  | 1 | 2 | 1 | 0.5 | 1.5 |  |  | 2 | 1 | 0.25 | 1.5 |  | 2 | 1 | 0.25 | 1.5
R4 | NR | NR_Mob_enh2-Perf | WI | Perf. part: Further NR mobility enhancements | RP-221799 | MediaTek | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR | FS_NR_XR_enh | SI | Study on XR Enhancements for NR | RP-220285 | Nokia | Dec.22 | 21 | REL-18 |  | 1 | 2 |  |  |  |  | 1 | 2 |  |  |  | 1 | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R2 | LTE | IoT_NTN_enh-Core | WI | Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | RP-221806 | MediaTek | Dec.23 | 22.25 | REL-18 |  | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 |  |  | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.25 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 |  |  | 1 | 0.5 | 0.5 | 0.25 |  | 1 | 0.5 | 0.5 | 0.25
R4 | LTE | IoT_NTN_enh-Perf | WI | Perf. part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | RP-221806 | MediaTek | [41 empty] | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R2 | NR | NR_NTN_enh-Core | WI | Core part: NR NTN (Non-Terrestrial Networks) enhancements | RP-221819 | Thales | Dec.23 | 26.75 | REL-18 |  | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 1 | 0.25 |  | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0.5 |  | 0.5 | 1 | 0.5 | 1 | 0.5 |  |  | 1 | 0.5 | 1 | 0.5 |  | 1 | 0.5 | 1 | 0.5
R4 | NR | NR_NTN_enh-Perf | WI | Perf. part: NR NTN (Non-Terrestrial Networks) enhancements | RP-221819 | Thales | Jun.24 | 1 | REL-18 | [44 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R2 | NR | NR_UAV-Core | WI | Core part: NR support for UAV (Uncrewed Aerial Vehicles) | RP-213600 | Nokia | Dec.23 | 12.5 | REL-18 |  |  | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 1 | 0.5 |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R2 | NR | NR_SL_relay_enh | WI | Core part: Enhanced NR Sidelink Relay | RP-221262 | LG Electronics | Dec.23 | 20.5 | REL-18 |  |  | 1 | 0.5 |  |  |  |  | 1.5 | 0.5 |  |  |  | 1.5 | 0.5 |  |  |  |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  | 1.5 | 0.5 |  | 0.5
R4 | NR | NR_SL_relay_enh | WI | Perf. part: Enhanced NR Sidelink Relay | RP-221262 | LG Electronics | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Core | WI | Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | RP-220955 | vivo | Dec.23 | 9 | REL-18 | [5 empty] | 0.25 |  |  | 1 |  |  | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 |  |  | 1 |  |  | 0.5 |  |  |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Perf | WI | New WID on Dual Tx/Rx MUSIM | RP-220955 | vivo | Jun.24 | 0.25 | REL-18 | [50 empty] | 0.25
R2 | NR | NR_IDC_enh-Core | WI | Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC | RP-221281 | Xiaomi | Dec.23 | 4.5 | REL-18 |  |  | 1 | [10 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 |  |  | 0.25 | [5 empty] | 0.25
R2 | NR | NR_MT_SDT-Core | WI | Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR | RP-213583 | ZTE | Sep.23 | 4 | REL-18 | [13 empty] | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R2 | NR | NR_MBS_enh-Core | WI | Core part: Enhancements of NR Multicast and Broadcast Services | RP-221458 | CATT | Dec.23 | 10 | REL-18 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R2 |  | Misc Impacts |  | Misc Impacts from Other RAN WGs and TSGs (incl MC Enhancements) |  |  |  | 13.5 | REL-18 |  |  | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R3 | NR | NR_mobile_IAB-Core | WI | Core part: Mobile IAB (Integrated Access and Backhaul) for NR | RP-221815 | Qualcomm | Dec.23 | 22 | REL-18 |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 1.5 |  |  |  | 0.5 | 1.5 |  |  |  |  | 0.5 | 1 | 0.25 | 0.25 |  |  | 0.5 | 1.5 | 0.5 | 0.5 |  | 0.5 | 1.5 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 0.5 |  |  | 0.5 | 1.5 | 0.5 | 0.5 |  | 0.5 | 1.5 | 0.5 | 0.5
R4 | NR | NR_mobile_IAB-Perf | WI | Perf part: Mobile IAB (Integrated Access and Backhaul) for NR | RP-221815 | Qualcomm |  |  | REL-18 | [49 empty] | 0.25 | 0.25
R3 | NR | NR_ENDC_SON_MDT_enh2-Core | WI | Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-221825 | CMCC | Dec.23 | 17.5 | REL-18 |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
R3 | NR | NR_AIML_NGRAN-Core | WI | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | RP-220635 | CMCC | Jun.23 | 12 | REL-18 |  |  |  | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R3 | NR | NR_QoE_enh-Core | WI | Core part: Enhancement on NR QoE management and optimizations for diverse services | RP-221803 | China Unicom | Dec.23 | 15.5 | REL-18 |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 0.5 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 0.5 | 1
R3 | NR | FS_gNB_CU_CP_resiliency | SI | Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane) | RP-221438 | NTT DOCOMO | Sep.22 | 0.5 | REL-18 |  |  |  | 0.5
R4 | NR | R18 RAN4-led spectrum items | SI/WI | RP-221464 Study on enhancement for 700/800/900MHz band combinations for NR [New RAN4 SI: FS_NR_700800900_combo_enh] CATT RP-220971 Introduction of LTE TDD band in 1670-1675 MHz [New RAN4 WI: LTE_TDD_1670_1675MHz] Ligado RP-220518 New bands and BW allocation for 5G terrestrial broadcast - part 2 [RAN4 WI: LTE_terr_bcast_bands_part2-Core] EBU RP-221846 New WID on LTE intra-band contiguous CA for band 8 CMCC RP-221845 New WID on Introduction of additional 6GHz NR licensed bands Huawei, HiSilicon RP-221778 New WID on APT 600 MHz NR band Spark NZ Ltd RP-221813 New WID: Introduction of evolved shared spectrum bands Apple RP-221831 New WID: Rel-18 LTE inter-band CA for X (X=2, 3, 4, 5) bands DL with 2 band UL LTE_CA_R18_xBDL_yBUL Huawei RP-221264 New WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) DC_R18_1BLTE_1BNR_2DL2UL CHTTL RP-221832 New WID: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) DC_R18_2BLTE_1BNR_3DL2UL Huawei RP-221833 Rel-18 WID on DC of x bands LTE inter-band CA (x=3,4,5) and 1 NR band DC_R18_xBLTE_1BNR_yDL2UL Nokia RP-221800 New Rel-18 WID: DC of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) DC_R18_xBLTE_2BNR_yDL2UL LGE RP-221834 New WID: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) DC_R18_xBLTE_yBNR_zDL2UL ZTE RP-221400 New Rel-18 WID: DC of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4, y=1, 2; 3=z=6) DC_R18_xBLTE_yBNR_zDL3UL Samsung RP-221835 New WID on Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) NR_CA_R18_intra Ericsson RP-221876 New WID: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) NR_CADC_R18_2BDL_xBUL ZTE RP-221877 New WID: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) NR_CADC_R18_3BDL_xBUL ZTE RP-221838 New WID on NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2) NR_CADC_R18_yBDL_xBUL Ericsson RP-221839 New WID: Rel-18 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) NR_SUL_combos_R18 Huawei RP-221879 Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band NR_LTE_V2X_PC5_combos_R18 CATT RP-221841 New WID High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands LTE_NR_HPUE_FWVM_REL18 Nokia RP-221878 New WID High Power UE support for band n100 and n101 for Rail Mobile Radio (RMR) in Europe RAIL_HPUE_n100_n101 Union Inter. Chemins de Fer RP-221843 Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx switching DL_intrpt_combos_TxSW_R18 China Telecom RP-221844 New WID: Additional NR bands for UL-MIMO in Rel-18 NR_bands_UL_MIMO Huawei |  |  | Dec.23 | 60.5 | REL-18 |  |  |  |  | 6.5 | 0 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25
R4 | NR | NR_FR1_lessthan_5MHz_BW-Core | WI | Core part: NR support for dedicated spectrum less than 5MHz for FR1 | RP-220401 | Nokia | Dec.23 | 4.75 | REL-18 | [12 empty] | 0.5 | [5 empty] | 0.5 |  |  | 0.25 | 0.25 |  |  |  |  | 0.5 | 0.25 | 0.5 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_FR1_lessthan_5MHz_BW-Perf | WI | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | RP-220401 | Nokia | Jun.23 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_ENDC_ RF_FR1_enh2-Core | WI | Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | RP-221496 | Huawei, HiSilicon | Dec.23 | 10.5 | REL-18 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1.5
R4 | NR | NR_ENDC_ RF_FR1_enh2-Perf | WI | Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | RP-221496 | Huawei, HiSilicon | Jun. 24 | 8.5 | REL-18 | [11 empty] | 1.5 |  |  |  |  | 1.5 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5
R4 | NR | NR_RF_FR2_req_Ph3-Core | WI | Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | RP-221862 | Nokia, Xiaomi | Dec.23 | 7.5 | REL-18 |  |  |  |  | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.75 | [5 empty] | 0.5 |  |  |  |  | 0.75 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_RF_FR2_req_Ph3--Perf | WI | Perf. Part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | RP-221862 | Nokia, Xiaomi | Mar. 24 | 0.75 | REL-18 | [39 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_FR2_multiRX_DL-Core | WI | Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | RP-221753 | Qualcomm, Vivo | Sep.23 | 9.5 | REL-18 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_FR2_multiRX_DL-Perf | WI | Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | RP-221753 | Qualcomm, Vivo | Mar.24 | 3 | REL-18 | [22 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.5
R4 | NR | NR_RRM_enh3 | WI | Core part: Even Further RRM enhancement for NR and MR-DC | RP-221696 | Apple, OPPO | Dec.23 | 7 | REL-18 | [5 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_RRM_enh3 | WI | Perf. part: Even Further RRM enhancement for NR and MR-DC | RP-221696 | Apple, OPPO | Jun.24 | 0.75 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.5
R4 | NR | [NR_MG_enh2-core] | WI | Core part: Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | RP-221018 | MediaTek inc., Intel Corporation | Dec.23 | 6.5 | REL-18 | [5 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | [NR_MG_enh2-perf] | WI | Perf. part: Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | RP-221018 | MediaTek inc., Intel Corporation | Jun.24 | 0.5 | REL-18 | [45 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_demod_enh3-Perf | WI | Perf. part: NR demodulation performance evolution | RP-221288 | China Telecom, Intel | Dec.23 | 5.5 | REL-18 | [11 empty] | 0.5 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_SimBC | SI | Study on simplification of band combination specification for NR and LTE | RP-221790 | ZTE | Jun.23 | 3.75 | REL-18 |  |  |  |  | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 1 | [5 empty] | 0.5 |  |  |  |  | 0.25
R4 | NR | FS_NR_700800900_combo_enh | SI | Study on enhancement for 700/800/900MHz band combinations for NR (TU is covered by resereved TU for spectrum) | RP-221464 | CATT | Mar.23 |  | REL-18
R4 | NR | FS_NR_BS_RF_evo | SI | Study on NR BS RF requirement evolution | RP-221001 | Huawei | Jun.23 | 2 | REL-18 |  |  |  |  | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.25
R4 | NR | FS_NR_FR2_OTA_enh | SI | Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements | RP-220988 | Qualcomm Incorporated | Dec. 23 | 8 | REL-18 |  |  |  |  | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R4 | NR | NonCol_intraB_ENDC_NR_CA-Core | WI | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | RP-221809 | KDDI | Sep.23 | 3.5 | REL-18 |  |  |  |  | 0.25 | [5 empty] | 0.5 |  |  |  |  | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 | [5 empty] | 0.25
R4 | NR | NonCol_intraB_ENDC_NR_CA-Perf | WI | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment | RP-221809 | KDDI | Dec.23 | 1.25 | REL-18 | [28 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_HST_FR2_enh_Core | WI | Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | RP-220985 | Samsung | Sep.23 | 5.75 | REL-18 | [10 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.25 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_HST_FR2_enh_Perf | WI | Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | RP-220985 | Samsung | Mar.24 | 2.5 | REL-18 | [28 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE, NR | NR_LTE_EMC_enh-Core | WI | Core part: UE EMC enhancements for NR and LTE | RP-220916 | Ericsson | Sep.23 | 1.5 | REL-18 | [10 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25
R4 | LTE, NR, UTRA, GERAN | NR_LTE_EMC_enh-Perf | WI | Perf part: BS/UE EMC enhancements for NR and LTE | RP-220916 | Ericsson | Dec.23 | 0.5 | REL-18 | [44 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_ATG | WI | Core part: Air-to-ground network for NR | RP-221369 | CMCC | Dec.23 | 9.75 | REL-18 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.25 | 0.25 |  |  |  |  | 1 | 0.25 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_ATG | WI | Perf. part:Air-to-ground network for NR | RP-221369 | CMCC | Mar. 24 | 3.5 | REL-18 | [22 empty] | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-220461 | Ericsson | Sep 22 | 0.5 | REL-18 |  |  |  |  | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-211600 | Apple，CAICT | Jun 22 | 0 | REL-18
R4 | LTE | LTE_NBIoT_eMTC_NTN_req-Core | WI | Core Part: NB-IoT/eMTC core & performance requirements for NTN | RP-221556 | MediaTek Inc. | Dec.22 | 2.25 | REL-18 |  |  |  |  | 0.25 | 0.5 |  |  |  |  | 0.5 | 0.25 |  |  |  | 0.5 | 0.25
R4 | LTE | LTE_NBIoT_eMTC_NTN_req-Perf | WI | Perf. Part: NB-IoT/eMTC core & performance requirements for NTN | RP-221556 | MediaTek Inc. | Jun.23 | 1.25 | REL-18 | [11 empty] | 0.25 |  |  |  |  | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | Nominal TUs for Maintenance (remaining) | [11 empty] | 3 | 3.5 |  |  |  |  | 3.75 | 4.25 |  |  |  | 3.75 | 6.5 |  |  |  |  | 3 | 5 |  |  |  |  | 3 | 2 |  |  |  | 3 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  | 2 | 2
R4 |  | Reserved TUs ([5%-15%] capacity) | [6 empty] | REL-18 |  |  |  |  | 1.4 | 1.25 |  |  |  |  | 2.5 | 1.5 |  |  |  | 2.5 | 1.5 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 3 | 2 |  |  |  | 2.75 | 2
R4 | LTE, NR | Rel-17 performance part (remaining) | [6 empty] | REL-17 |  |  |  |  | 1.5 | 0.25 | [5 empty] | 3 |  |  |  |  | 0
R4 | NR | Rel-18 TEIs & additional reserved TU | [17 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | 0 |  |  |  |  | 0.5 | 0 |  |  |  | 0.25 | 0 |  |  |  |  | 0.5 | 0 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | LTE, NR | Misc. impacts from other RAN WGs and TSGs (Rel-18 LS reply) | [6 empty] | REL-18 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| NR |  |  | allocated above | [5 empty] | 0 | 21 | 14.5 | 10 | 24.5 | 20.5 | 0 | 21 | 17 | 10 | 24.5 | 20.5 | 21 | 17.5 | 10 | 24.5 | 20.5 | 0 | 17 | 21.25 | 9 | 24.25 | 20 | 0 | 16.5 | 21.75 | 9.5 | 23.75 | 18.5 | 16.5 | 22.25 | 9.5 | 23.5 | 18 | 0 | 16 | 23 | 7 | 23.5 | 17.5 | 0 | 0 | 22.25 | 7 | 23.5 | 18 | 0 | 21.75 | 7 | 23.5 | 18 | 0
| NR |  |  | Legacy | [7 empty] | 25.5 | [5 empty] | 20 |  |  |  |  | 19.5 | [5 empty] | 15.75 | [5 empty] | 14 |  |  |  |  | 13 | [5 empty] | 13 | [5 empty] | 13 |  |  |  |  | 13
| NR |  |  | TEI and other not planned issues | [8 empty] | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 |  |  |  |  | 1 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
| NR |  |  | Reserve | [8 empty] | 1 |  |  |  |  | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 4 | 1 |  |  |  | 4 | 1.5
| NR |  |  | total used capacity | [5 empty] | 0 | 21 | 40 | 12 | 24.5 | 20.5 | 0 | 21 | 40 | 11.5 | 24.5 | 20.5 | 21 | 40 | 11.5 | 24.5 | 20.5 | 0 | 17 | 40 | 10.5 | 24.25 | 20 | 0 | 16.5 | 39.75 | 10.5 | 23.75 | 18.5 | 16.5 | 39.25 | 11 | 23.5 | 18 | 0 | 16 | 40 | 8.5 | 23.5 | 17.5 | 0 | 0 | 40.25 | 8.5 | 23.5 | 18 | 0 | 39.75 | 9 | 23.5 | 18 | 0
| NR |  |  | available capacity | [7 empty] | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5
| NR |  |  | remaining/exceeded capacity | [5 empty] | 0 | -21 | 0 | 0 | 0 | 0 | 0 | -21 | 0 | 0.5 | 0 | 0 | -21 | 0 | 0.5 | 0 | 0 | 0 | -17 | 0 | 1.5 | 0.25 | 0.5 | 0 | -16.5 | 0.25 | 1.5 | 0.75 | 2 | -16.5 | 0.75 | 1 | 1 | 2.5 | 0 | -16 | 0 | 3.5 | 1 | 3 | 0 | 0 | -0.25 | 3.5 | 1 | 2.5 | 0 | 0.25 | 3 | 1 | 2.5 | 0
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status

## TU_overview_in_RP_221019
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 95 Mar.22 | 109 | 118 | 116 | 103 | 103 | 96 Jun.22 | 110 | 119 | 117 | 104 | 104 | 97 Sep.22 | 110bis | 119bis | 117bis | 104bis | 104bis | 111 | 120 | 118 | 105 | 105 | 98 Dec.22 | 112 | 121 | 119 | 106 | 106 | 99 Mar.23 | 112bis | 121bis | 119bis | 106bis | 106bis | 113 | 122 | 120 | 107 | 107 | 100 Jun.23 | 114 | 123 | 121 | 108 | 108 | 101 Sep.23 | 114bis | 123bis | 121bis | 108bis | 108bis | 115 | 124 | 122 | 109 | 109 | 102 Dec.23
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Mar 22 | 0 | REL-17
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Sept 22 | 2 | REL-17 | [5 empty] | 1 | [5 empty] | 1
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-213540 | Qualcomm | Jun 21 | 3 | REL-17 |  |  |  |  | 2 | 1
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-213540 | Qualcomm | Sep.22 | 6 | REL-17 |  |  |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | Intel | Mar 22 | 0 | REL-17
R4 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | Intel | Sept 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP-220966 | Ericsson | Mar 22 | 1.5 | REL-17 |  |  |  |  | 0.5 | 1
R4 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP-220966 | Ericsson | Sept 22 | 3 | REL-17 | [5 empty] | 0.75 | [5 empty] | 1 | [5 empty] | 0.75 |  |  |  |  | 0.5
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-211566 | China Telecom | Mar 22 | 0 | REL-17
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-211566 | China Telecom | Sept 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-220529 | Huawei, Ericsson | Mar 22 | 0 | REL-17
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-220529 | Huawei, Ericsson | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.25 | [5 empty] | 0.25
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-202846 | LG Electronics | Mar 22 | 0 | REL-17
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-202846 | LG Electronics | Sept 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-210460 | Qualcomm | Dec 21 | 0 | REL-17
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 | MediaTek | Dec 21 | 0 | REL-17
R1 | LTE | LTE_NBIOT_eMTC_NTN | WI | NB-IoT/eMTC support for Non-Terrestrial Networks | RP‑211601 | MediaTek, Eutelsat, ZTE | June 22 | 0.5 | REL-17 |  |  | 0.5
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Sept 22 | 0 | REL-17
R1 | LTE | LTE_terr_bcast_bands-Core | WI | Revised WID for New bands and bandwidth allocation for 5G terrestrial broadcast (Part 1) | RP-211144 | EBU | Mar 22 | 0 | REL-17
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 0 | REL-17
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-220152 | Nokia | Mar 22 | 0 | REL-17
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Perf part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-220152 | Nokia | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.25 | [5 empty] | 0.25
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-220208 | Thales | Mar 22 | 2.5 | REL-17 |  |  |  |  | 2 | 0.5
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-220208 | Thales | Sept 22 | 4.25 | REL-17 | [5 empty] | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  | 0.75 | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-220748 | MediaTek | Mar 22 | 0 | REL-17
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-220748 | MediaTek | Sept 22 | 0.5 | REL-17 | [5 empty] | 0.25 | [5 empty] | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-213668 | Qualcomm | Jun 22 | 0.5 | REL-17 |  | 0.25 | 0.25
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-213668 | Qualcomm | Sept 22 | 1.5 | REL-17 |  |  |  |  | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-220428 | Huawei | Mar.22 | 0 | REL-17
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-220428 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay | WI | NR Sidelink Relay | RP-212819 | OPPO | Mar.22 | 0 | REL-17
R2 | NR | NR_SL_Relay-Perf | WI | NR Sidelink Relay | RP-212819 | OPPO | Sep.22 |  | REL-17 | [5 empty] | 0.25 | [5 empty] | 0.25
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP-212534 | CMCC | 2022-06-01 | 1 | REL-17 |  |  |  | 1
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-211290 | CMCC | Jun.21 | 0 | REL-17
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Mar.22 | 0 | REL-17
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Dec.21 | 0.75 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.25
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Mar.22 | 0 | REL-17
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Dec.21 | 0.5 | REL-17 | [5 empty] | 0.25 | [5 empty] | 0.25
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-213679 | vivo | Mar 22 | 0 | REL-17
R2 | NR | NR_UDC-Core | WI | NR UDC | RP-220140 | CATT | Mar 22 | 0 | REL-17
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Jun 21 | 0 | REL-16
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Jun 21 | 0 | REL-16
R2 | NR |  |  | R1 Misc items (DSS etc) |  |  |  | 0 | REL-17
R2 | NR, LTE |  |  | R17 Other (R4 items etc) |  |  |  | 0 | REL-17
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-220821 | CMCC | Mar 22 | 0 | REL-17
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-213667 | China Unicom | Sep 21 | 0 | REL-17
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | CMCC | Mar 22 | 0 | REL-17
R3 | NR | NR_QoE | WI | NR QoE management and optimizations for diverse services | RP-211406 | China Unicom | Mar 22 | 0 | REL-17
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-212585 | China Telecom | Mar 22 | 0 | REL-17
R3 | NR | UPIP_SEC_LTE-RAN-Core | WI | User Plane Integrity Protection support for EPC connected architectures WI | RP-213669 | Vodafone | Mar 22 | 0 | REL-17
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | China Unicom | Sep 21 | 0 | REL-17
R4 | NR | FS_NR_600MHz_ext | SI | Study on extended 600MHz NR band | RP-202924 | Spark NZ Ltd | Sep 21 | 0 | REL-17
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-213101 | CAICT | Mar 22 | 0.5 | REL-17 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-213101 | CAICT | Sep 22 | 2 | REL-17 |  |  |  |  | 1 | [5 empty] | 1
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-213656 | China Telecom | Mar 22 | 2 | REL-17 | [5 empty] | 1 | [5 empty] | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-213654 | Ericsson | Sep 21 | 0 | REL-17
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-213654 | Ericsson | Mar 22 | 0.5 | REL-17 |  |  |  |  | 0.25 | 0.25
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-213067 | Apple | Mar 22 | 0 | REL-17
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-213067 | Apple | Sep 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Mar 22 | 0 | REL-17
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Sep 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-220968 | Nokia | Mar 22 | 3 | REL-17 |  |  |  |  | 2 | 1
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-220968 | Nokia | Jun 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Mar 22 | 0 | REL-17
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Sep 22 | 2 | REL-17 | [5 empty] | 1 | [5 empty] | 1
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-220772 | MediaTek | Mar 22 | 0 | REL-17
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-220772 | MediaTek | Sep 22 | 1 | REL-17 | [5 empty] | 0.5 | [5 empty] | 0.5
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-220681 | Huawei | Mar 22 | 0 | REL-17
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-220681 | Huawei | Sep 22 | 0.25 | REL-17 | [5 empty] | 0.25
R4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-213514 | Qualcomm, Commscope | Mar 22 | 0 | REL-17
R4 | NR | NR_repeaters-Perf | WI | NR Repeaters | RP-213514 | Qualcomm, Commscope | Sep 22 |  | REL-17 |  |  |  |  | 0.5 | [5 empty] | 0.5
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-212030 | vivo, OPPO, CMCC | Mar 22 | 0 | REL-17
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-212030 | vivo, OPPO, CMCC | Sep 22 | 1 | REL-17 |  |  |  |  | 0.5 | [5 empty] | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-213535 | Qualcomm | Mar 22 | 0 | REL-17
R4 | NR | NR_RF_TxD-Core | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0 | RAN2 TU in R17 Other
R4 | NR | NR_RF_TxD-Perf | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0
R4 | LTE | LTE_NR_HPUE_FWVM-Core |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 0 | REL-17
R4 | LTE | LTE_NR_HPUE_FWVM-Perf |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 0.5 | REL-17 |  |  |  |  | 0.25 | [5 empty] | 0.25
R4 | NR | R17 NR Basket Wis |  | RP-220825 Rel-17 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) Ericsson RP-220144 Rel-17 NR Inter-band CA/DC for 2 bands DL with x bands UL (x=1,2) ZTE RP-220738 Rel-17 NR inter-band CA for 3 bands DL with 1 band UL CATT RP-220146 Rel-17 NR inter-band CA/DC for 3 bands DL with 2 bands UL ZTE RP-220827 Rel-17 NR inter-band CA for 4 bands DL with 1 band UL Ericsson RP-220676 Rel-17 NR inter-band CA/DC for DL 4 bands and 2UL bands Samsung RP-220692 Rel-17 NR inter-band CA for 5 bands DL with x bands UL (x=1, 2) Huawei RP-220398 Rel-17 DC of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL) CHTTL RP-220689 Rel-17 DC of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) Huawei RP-220826 Rel-17 DC of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) Ericsson RP-220999 Rel-17 DC of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) Nokia RP-220302 Rel-17 DC of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)inter-band CA (2DL/1UL) LG RP-220205 Rel-17 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL) ZTE RP-220202 Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL) ZTE RP-220712 DC of x bands (x=1,2) LTE inter-band CA (xDL/1UL) and 4 bands NR inter-band CA (4DL/1UL) Huawei RP-220695 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) Huawei RP-220160 Revised Basket WID: adding new channel bandwidth(s) support to existing NR bands Ericsson RP-220707 Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC Huawei RP-213297 Revised WID for band combinations for Uu and V2X concurrent operation CATT RP-220704 WID revision: Additional NR bands for UL-MIMO in Rel-17 Huawei, HiSilicon RP-220930 WID revision: High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1 Huawei, HiSilicon RP-220388 Rel-17 High power UE (PC2) for EN-DC with 1 LTE band + 1 NR TDD band China Unicom RP-220828 Revised WID: Power Class 2 for EN-DC with x LTE band + y NR TDD band Ericsson RP-220567 Revised WID: High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x =1,2) China Telecom RP-220701 WID revision: Rel-17 Power Class 2 UE for NR inter-band Carrier Aggregation/Dual Connectivity with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL Huawei, HiSilicon |  |  |  | 3 | REL-17 |  |  |  |  | 3
R4 | NR | R17 NR spectrum related WI/SI |  | RP-220686 Introduction of 6GHz NR licensed bands Huawei, Ericsson, Nokia, ZTE RP-210878 Introduction of 900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-212622 Core part: Increasing UE power high limit for CA and DC, Qualcomm, China Telecom RP-220767 Revised WID High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands Nokia |  |  |  | 2 | REL-17 |  |  |  |  | 2
R4 | LTE | R17 LTE basket WIs |  | RP-220552 Rel-17 LTE inter-band CA for 2 bands DL with 1 band UL Qualcomm RP-220715 Rel-17 LTE inter-band CA for 3 bands DL with 1 band UL Huawei RP-220718 Rel-17 LTE inter-band CA for 2 bands DL with 2 band UL Huawei RP-220175 Rel-17 LTE inter-band CA for x bands DL (x=4, 5, 6) with 1 band UL Nokia RP-220295 Rel-17 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 bands UL LG |  |  |  | 1 | REL-17 |  |  |  |  | 1
R4 | LTE | R17 LTE spectrum related WI/SI |  | RP-220816 Additional LTE bands for UE cat. M1/M2/NB1/NB2 in Rel-17 Ericsson RP-220971 New WI: Introduction of LTE TDD band in 1670-1675 MHz Ligado |  |  |  | 0.5 | REL-17 |  |  |  |  | 0.5
R4 | LTE,NR | R17 LTE/NR spectrum Perf part |  | All potential performance part for WIs in R17 NR Basket Wis, R17 NR spectrum related WI/SI, R17 LTE basket Wis,R17 LTE/NR spectrum Perf part |  |  |  | 0.25 | REL-17 | [5 empty] | 0.25
R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance | RP-210710 | Qualcomm, AT&T |  | 0 | REL-17
R1 | NR | NR_MIMO_evo_DL_UL-Core | WI | Core part: NR MIMO evolution for downlink and uplink | RP-213598 | Samsung | Dec.23 | 31.75 | REL-18 |  | 2 | [5 empty] | 3 | [5 empty] | 3 |  |  |  |  | 3 | [5 empty] | 3 |  |  | 0.25 | 0.25 |  | 3 | 0.5 |  | 0.5 | 0.5 | 3 | 0.5 |  | 0.5 | 0.5 |  | 3 | 0.75 |  | 0.5 | 0.5 |  |  | 0.75 |  | 0.5 | 0.5 |  | 0.75 |  | 0.5 | 0.5
R4 | NR | NR_MIMO_evo_DL_UL-Perf | WI | Perf. part: NR MIMO evolution for downlink and uplink | RP-213598 | Samsung | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_cov_enh2-Core | WI | Core part: Further NR coverage enhancements | RP-220937 | China Telecom | Dec.23 | 13.25 | REL-18 | [13 empty] | 1 |  |  | 0.25 |  | 1 |  |  | 0.25 |  |  | 1 |  |  | 0.25 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 1 |  |  |  | 0.5 |  | 1 |  |  | 0.5 |  | 1
R4 | NR | NR_cov_enh2-Perf | WI | Perf. part: Further NR coverage enhancements | RP-220937 | China Telecom | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_DSS_enh-Core | WI | Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | RP-213575 | Ericsson | Dec.23 | 2 | REL-18 |  | 1 | [5 empty] | 1
R4 | NR | NR_DSS_enh-Perf | WI | Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | RP-213575 | Ericsson | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_MC_enh-Core | WI | Core part: Multi-carrier enhancements for NR | RP-220834 | NTT DOCOMO | Dec.23 | 6 | REL-18 |  | 1 | [5 empty] | 1 |  |  | 0.25 |  |  | 0.5 |  |  | 0.5 | 0.25 | 0.5 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_MC_enh-Perf | WI | Perf. part: Multi-carrier enhancements for NR | RP-220834 | NTT DOCOMO | June 24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | NR_SL_enh2-Core | WI | Core part: NR sidelink evolution | RP-220300 | OPPO | Dec.23 | 33.75 | REL-18 |  | 1 | [5 empty] | 2 | [5 empty] | 2 | 0.5 |  |  |  | 2 | 0.5 |  |  |  |  | 2 | 1 |  | 0.5 | 0.25 |  | 2 | 1 |  | 1 | 0.5 | 2 | 1 |  | 1.5 | 0.5 |  | 2 | 1 |  | 1.5 | 1 |  |  | 1 |  | 1.5 | 1 |  | 1 |  | 1.5 | 1
R4 | NR | NR_SL_enh2-Perf | WI | Perf. part: NR sidelink evolution | RP-220300 | OPPO | Sep.23 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_NR_netcon_repeater | SI | Study on NR network-controlled repeaters | RP-213700 | ZTE | Sep.22 | 4.5 | REL-18 |  | 1 | [5 empty] | 1 | 0.5 | 0.5 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5
R1 | NR | FS_NR_AIML_air | SI | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | RP-213599 | Qualcomm | Dec.23 | 33.5 | REL-18 |  | 2 | [5 empty] | 3 | [5 empty] | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  | 0.5 | 3 | 1 |  |  | 0.5 |  | 3 | 1 |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.5
R1 | NR | FS_NR_duplex_evo | SI | Study on evolution of NR duplex operation | RP-220633 | CMCC | Dec.23 | 20.75 | REL-18 |  | 2 | [5 empty] | 2 |  |  | 0.25 |  |  | 2 |  |  | 0.5 |  | 2 |  |  | 0.5 |  |  | 2 |  |  | 1 |  |  | 2 |  |  | 0.5 |  | 2 |  |  | 1 |  |  | 2 |  |  | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_NR_pos_enh2 | SI | Study on expanded and improved NR positioning | RP-213588 | Intel | Dec.22 | 31.75 | REL-18 |  | 2 | [5 empty] | 3 | 1.5 | 0.5 | 0.25 |  |  | 3 | 2 | 0.5 | 0.25 | 0.5 | 3 | 2 | 0.5 | 0.25 | 0.5 |  |  | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R1 | NR | FS_Netw_Energy_NR | SI | Study on network energy savings for NR | RP-220297 | Huawei | Dec.22 | 14.5 | REL-18 |  | 1 | [5 empty] | 1 | 1 | 0.5 |  |  |  | 1 | 1 | 0.5 |  |  | 1 | 1 | 0.5 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R1 | NR | FS_NR_LPWUS | SI | Study on low-power wake-up signal and receiver for NR | RP-213645 | vivo | Dec.23 | 10.75 | REL-18 | [13 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 |  |  | 0.25 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 0.25 |  |  | 0.5 |  | 0.25
R1 | NR | FS_NR_redcap_enh | SI | Study on further NR RedCap (reduced capability) UE complexity reduction | RP-213661 | Ericsson | Sep.22 | 8 | REL-18 |  | 1 | [5 empty] | 1 | [17 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Sep.23 | 11 | REL-18 | [7 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2
R2 | NR | NR_Mob_enh2-Core | WI | Core part: Further NR mobility enhancements | RP-213565 | MediaTek | Dec.23 | 45.25 | REL-18 | [8 empty] | 2 | 1 |  | 0.5 |  | 1 | 2 | 1 |  | 0.5 | 1 | 2 | 1 |  | 0.5 |  | 1 | 2 | 1 | 0.25 | 1 |  | 1 | 2 | 1 | 0.5 | 1.5 | 1 | 2 | 1 | 0.5 | 1.5 |  | 1 | 2 | 1 | 0.5 | 1.5 |  |  | 2 | 1 | 0.25 | 1.5 |  | 2 | 1 | 0.25 | 1.5
R4 | NR | NR_Mob_enh2-Perf | WI | Perf. part: Further NR mobility enhancements | RP-213565 | MediaTek | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR | FS_NR_XR_enh | SI | Study on XR Enhancements for NR | RP-220285 | Nokia | Dec.22 | 22 | REL-18 |  | 1 | [5 empty] | 1 | 2 |  |  |  |  | 1 | 2 |  |  |  | 1 | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R2 | LTE | IoT_NTN_enh-Core | WI | Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | RP-220979 | MediaTek | Dec.23 | 22.75 | REL-18 |  | 0.5 | [5 empty] | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 |  |  | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.25 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 | 0.5 |  |  | 1 | 0.5 | 0.5 | 0.25 |  | 1 | 0.5 | 0.5 | 0.25
R4 | LTE | IoT_NTN_enh-Perf | WI | Perf. part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | RP-220979 | MediaTek | [47 empty] | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R2 | NR | NR_NTN_enh-Core | WI | Core part: NR NTN (Non-Terrestrial Networks) enhancements | RP-220953 | Thales | Dec.23 | 27.25 | REL-18 |  | 0.5 | [5 empty] | 0.5 | 1 | 0.5 |  |  |  | 0.5 | 1 | 0.5 | 0.5 |  | 0.5 | 1 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 1 | 0.25 |  | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0.5 |  | 0.5 | 1 | 0.5 | 1 | 0.5 |  |  | 1 | 0.5 | 1 | 0.5 |  | 1 | 0.5 | 1 | 0.5
R4 | NR | NR_NTN_enh-Perf | WI | Perf. part: NR NTN (Non-Terrestrial Networks) enhancements | RP-220953 | Thales | Jun.24 | 1 | REL-18 | [50 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R2 | NR | NR_UAV-Core | WI | Core part: NR support for UAV (Uncrewed Aerial Vehicles) | RP-213600 | Nokia | Dec.23 | 12.5 | REL-18 | [8 empty] | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 1 | 0.5 |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R2 | NR | NR_SL_relay_enh | WI | Core part: Enhanced NR Sidelink Relay | RP-221010 | LG Electronics | Dec.23 | 20.5 | REL-18 | [8 empty] | 1 | 0.5 |  |  |  |  | 1.5 | 0.5 |  |  |  | 1.5 | 0.5 |  |  |  |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  |  | 1.5 | 0.5 |  | 0.5 |  | 1.5 | 0.5 |  | 0.5
R4 | NR | NR_SL_relay_enh | WI | Perf. part: Enhanced NR Sidelink Relay | RP-221010 | LG Electronics | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Core | WI | Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | RP-220955 | vivo | Dec.23 | 9 | REL-18 | [11 empty] | 0.25 |  |  | 1 |  |  | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 |  |  | 1 |  |  | 0.5 |  |  |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Perf | WI | New WID on Dual Tx/Rx MUSIM | RP-220955 | vivo | Jun.24 | 0.25 | REL-18 | [56 empty] | 0.25
R2 | NR | NR_IDC_enh-Core | WI | Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC | RP-213589 | Xiaomi | Dec.23 | 4.5 | REL-18 | [8 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 |  |  | 0.25 | [5 empty] | 0.25
R2 | NR | NR_MT_SDT-Core | WI | Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR | RP-213583 | ZTE | Dec.23 | 4 | REL-18 | [19 empty] | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R2 | NR | NR_MBS_enh-Core | WI | Core part: Enhancements of NR Multicast and Broadcast Services | RP-213568 | CATT | Dec.23 | 10 | REL-18 | [8 empty] | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.75 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R2 |  | Misc Impacts |  | Misc Impacts from Other RAN WGs and TSGs (incl MC Enhancements) |  |  |  | 13.5 | REL-18 | [8 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R3 | NR | NR_mobile_IAB-Core | WI | Core part: Mobile IAB (Integrated Access and Backhaul) for NR | RP-220843 | Qualcomm | Dec.23 | 22 | REL-18 | [8 empty] | 0.5 | 1 |  |  |  |  | 0.5 | 1.5 |  |  |  | 0.5 | 1.5 |  |  |  |  | 0.5 | 1 | 0.25 | 0.25 |  |  | 0.5 | 1.5 | 0.5 | 0.5 |  | 0.5 | 1.5 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 0.5 |  |  | 0.5 | 1.5 | 0.5 | 0.5 |  | 0.5 | 1.5 | 0.5 | 0.5
R4 | NR | NR_mobile_IAB-Perf | WI | Perf part: Mobile IAB (Integrated Access and Backhaul) for NR | RP-220843 | Qualcomm |  |  | REL-18 | [55 empty] | 0.25 | 0.25
R3 | NR | NR_ENDC_SON_MDT_enh2-Core | WI | Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-221000 | CMCC | Dec.23 | 17.5 | REL-18 | [8 empty] | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
R3 | NR | NR_AIML_NGRAN-Core | WI | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | RP-220635 | CMCC | Jun.23 | 12 | REL-18 | [9 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2 | [5 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R3 | NR | NR_QoE_enh-Core | WI | Core part: Enhancement on NR QoE management and optimizations for diverse services | RP-213594 | China Unicom | Dec.23 | 15.5 | REL-18 | [8 empty] | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 0.5 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 0.5 | 1
R3 | NR | FS_gNB_CU_CP_resiliency | SI | Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane) | RP-213677 | NTT DOCOMO | Sep.22 | 0.5 | REL-18 | [9 empty] | 0.5
R4 | NR | R18 RAN4-led spectrum items | SI/WI | RP-220518 New WID: New bands and bandwidth allocation for 5G terrestrial broadcast (Part 2) EBU RP-220971 New WI: Introduction of LTE TDD band in 1670-1675 MHz Ligado RP-221016 Study on enhancement for 700/800/900MHz band combinations CATT | RP-211145 |  | Dec.23 | 60.5 | REL-18 | [10 empty] | 6.5 | 0 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  |  | 6.5 | 0.25 |  |  |  | 6.5 | 0.25
R4 | NR | NR_FR1_lessthan_5MHz_BW-Core | WI | Core part: NR support for dedicated spectrum less than 5MHz for FR1 | RP-220401 | Nokia | Dec.23 | 4.75 | REL-18 | [18 empty] | 0.5 | [5 empty] | 0.5 |  |  | 0.25 | 0.25 |  |  |  |  | 0.5 | 0.25 | 0.5 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_FR1_lessthan_5MHz_BW-Perf | WI | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | RP-220401 | Nokia | Jun.23 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_RF_FR1_Fenh-Core | WI | Core part: Further RF requirements enhancement for NR frequency range 1 (FR1) | RP-220987 | Huawei, HiSilicon | Dec.23 | 10.5 | REL-18 | [10 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1.5
R4 | NR | NR_RF_FR1_Fenh-Perf | WI | Perf. part: Further RF requirements enhancement for NR frequency range 1 (FR1) | RP-220987 | Huawei, HiSilicon | Jun. 24 | 8.5 | REL-18 | [17 empty] | 1.5 |  |  |  |  | 1.5 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5
R4 | NR | NR_RF_FR2_Ph3-Core | WI | Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | RP-220967 | Nokia, Xiaomi | Dec.23 | 7.5 | REL-18 | [10 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.75 | [5 empty] | 0.5 |  |  |  |  | 0.75 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_RF_FR2_Ph3-Perf | WI | Perf. Part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | RP-220967 | Nokia, Xiaomi | Mar. 24 | 0.75 | REL-18 | [45 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | TBA | WI | Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | RP-220974 | Qualcomm, Vivo | Sep.23 | 9.5 | REL-18 | [10 empty] | 0.5 | 0.5 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 1 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | TBA | WI | Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | RP-220974 | Qualcomm, Vivo | Mar.24 | 3 | REL-18 | [28 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | TBA | WI | Core part: Even Further RRM enhancement for NR and MR-DC | RP-220977 | Apple, OPPO | Dec.23 | 7 | REL-18 | [11 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | TBA | WI | Perf. part: Even Further RRM enhancement for NR and MR-DC | RP-220977 | Apple, OPPO | Jun.24 | 0.75 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.5
R4 | NR | [NR_MG_enh2-core] | WI | Core part: Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | RP-221018 | MediaTek inc., Intel Corporation | Dec.23 | 6.5 | REL-18 | [11 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | [NR_MG_enh2-perf] | WI | Perf. part: Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | RP-221018 | MediaTek inc., Intel Corporation | Jun.24 | 0.5 | REL-18 | [51 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_demod_evo-Perf | WI | Perf. part: NR demodulation performance evolution | RP-220932 | China Telecom, Intel | Dec.23 | 5.5 | REL-18 | [17 empty] | 0.5 |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_SimBC | SI | Study on simplification of band combination specification | RP-220956 | ZTE | Jun.23 | 3.75 | REL-18 | [10 empty] | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 1 | [5 empty] | 0.5 |  |  |  |  | 0.25
R4 | NR | FS_700800900Comb_Enh | SI | Study on enhancement for 700/800/900MHz band combinations (TU is covered by resereved TU for spectrum) | RP-221016 | CATT | Mar.23 |  | REL-18
R4 | NR | TBA | SI | Study on NR BS RF requirement evolution | RP-221001 | Huawei | Jun.23 | 2 | REL-18 | [10 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.25
R4 | NR | FS_NR_FR2_OTA_enh | SI | Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements | RP-220988 | Qualcomm Incorporated | Dec. 23 | 8 | REL-18 | [10 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R4 | NR | NonCol_EN-DC_CA_Core | WI | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | RP-221012 | KDDI | Sep. 2023 | 3.5 | REL-18 | [10 empty] | 0.25 | [5 empty] | 0.5 |  |  |  |  | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 | [5 empty] | 0.25
R4 | NR | NonCol_EN-DC_CA_Perf | WI | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment | RP-221012 | KDDI | Dec. 2023 | 1.25 | REL-18 | [34 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_HST_FR2_enh_Core | WI | Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | RP-220985 | Samsung | Sep. 23 | 5.75 | REL-18 | [16 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.25 | 0.5 |  |  |  |  | 0.5 | 0.5
R4 | NR | NR_HST_FR2_enh_Perf | WI | Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | RP-220985 | Samsung | Mar. 24 | 2.5 | REL-18 | [34 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE, NR | NR_LTE_EMC_enh-Core | WI | Core part: UE EMC enhancements for NR and LTE | RP-220916 | Ericsson | Sep.23 | 1.5 | REL-18 | [16 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [5 empty] | 0.25
R4 | LTE, NR, UTRA, GERAN | NR_LTE_EMC_enh-Perf | WI | Perf part: BS/UE EMC enhancements for NR and LTE | RP-220916 | Ericsson | Dec.23 | 0.5 | REL-18 | [50 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | TBA | WI | Core part: Air-to-ground network for NR | RP-220962 | CMCC | Dec. 23 | 9.75 | REL-18 | [10 empty] | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.25 | 0.25 |  |  |  |  | 1 | 0.25 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | TBA | WI | Perf. part:Air-to-ground network for NR | RP-220962 | CMCC | Mar. 24 | 3.5 | REL-18 | [28 empty] | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-220461 | Ericsson | Sep 22 | 1 | REL-18 |  |  |  |  | 0.5 | [5 empty] | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-211600 | Apple，CAICT | Jun 22 | 0.5 | REL-18 |  |  |  |  | 0.5
R4 | LTE | LTE_IoT_NTN_req-Core | WI | Core Part: NB-IoT/eMTC core & performance requirements for NTN | RP-220938 | MediaTek Inc. | Dec.22 | 2.25 | REL-18 | [10 empty] | 0.25 | 0.5 |  |  |  |  | 0.5 | 0.25 |  |  |  | 0.5 | 0.25
R4 | LTE | LTE_IoT_NTN_req-Perf | WI | Perf. Part: NB-IoT/eMTC core & performance requirements for NTN | RP-220938 | MediaTek Inc. | Jun.23 | 1.25 | REL-18 | [17 empty] | 0.25 |  |  |  |  | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | Nominal TUs for Maintenance (remaining) | [11 empty] | 5 | 3 |  |  |  |  | 3 | 3.5 |  |  |  |  | 3.75 | 4.25 |  |  |  | 3.75 | 6.5 |  |  |  |  | 3 | 5 |  |  |  |  | 3 | 2 |  |  |  | 3 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  | 2 | 2
R4 |  | Reserved TUs ([5%-15%] capacity) | [6 empty] | REL-18 | [10 empty] | 2.5 | 1.75 |  |  |  |  | 2.5 | 1.5 |  |  |  | 2.5 | 1.5 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 3 | 2 |  |  |  | 2.75 | 2
R4 | LTE, NR | Rel-17 performance part (remaining) | [6 empty] | REL-17 |  |  |  |  | 1.5 | 2.5 |  |  |  |  | 1.5 | 0.25 | [5 empty] | 3 |  |  |  |  | 0
R4 | NR | Rel-18 TEIs & additional reserved TU | [23 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 | 0 |  |  |  |  | 0.5 | 0 |  |  |  | 0.25 | 0 |  |  |  |  | 0.5 | 0 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | LTE, NR | Misc. impacts from other RAN WGs and TSGs (Rel-18 LS reply) | [6 empty] | REL-18 | [10 empty] | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
| NR |  |  | allocated above | [5 empty] | 0 | 16.25 | 0.75 | 1 | 24.5 | 20.5 | 0 | 21 | 14.5 | 10 | 24.5 | 20.5 | 0 | 21 | 17 | 10 | 24.5 | 20.5 | 21 | 17.5 | 10 | 24.5 | 20.5 | 0 | 17 | 21.25 | 9 | 24.25 | 20 | 0 | 16.5 | 21.75 | 9.5 | 23.75 | 18.5 | 16.5 | 22.25 | 9.5 | 23.5 | 18 | 0 | 16 | 23 | 7 | 23.5 | 17.5 | 0 | 0 | 22.25 | 7 | 23.5 | 18 | 0 | 21.75 | 7 | 23.5 | 18 | 0
| NR |  |  | Legacy | [7 empty] | 37.25 | [5 empty] | 25.5 | [5 empty] | 20 |  |  |  |  | 19.5 | [5 empty] | 15.75 | [5 empty] | 14 |  |  |  |  | 13 | [5 empty] | 13 | [5 empty] | 13 |  |  |  |  | 13
| NR |  |  | TEI and other not planned issues | [7 empty] | 2 | 11 | [5 empty] | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [5 empty] | 0.5 |  |  |  |  | 1 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
| NR |  |  | Reserve | [7 empty] | 0 | [6 empty] | 1 |  |  |  |  | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  | 3 | 1 |  |  |  |  | 3 | 1 |  |  |  |  | 4 | 1 |  |  |  | 4 | 1.5
| NR |  |  | total used capacity | [5 empty] | 0 | 16.25 | 40 | 12 | 24.5 | 20.5 | 0 | 21 | 40 | 12 | 24.5 | 20.5 | 0 | 21 | 40 | 11.5 | 24.5 | 20.5 | 21 | 40 | 11.5 | 24.5 | 20.5 | 0 | 17 | 40 | 10.5 | 24.25 | 20 | 0 | 16.5 | 39.75 | 10.5 | 23.75 | 18.5 | 16.5 | 39.25 | 11 | 23.5 | 18 | 0 | 16 | 40 | 8.5 | 23.5 | 17.5 | 0 | 0 | 40.25 | 8.5 | 23.5 | 18 | 0 | 39.75 | 9 | 23.5 | 18 | 0
| NR |  |  | available capacity | [7 empty] | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5
| NR |  |  | remaining/exceeded capacity | [5 empty] | 0 | -16.25 | 0 | 0 | 0 | 0 | 0 | -21 | 0 | 0 | 0 | 0 | 0 | -21 | 0 | 0.5 | 0 | 0 | -21 | 0 | 0.5 | 0 | 0 | 0 | -17 | 0 | 1.5 | 0.25 | 0.5 | 0 | -16.5 | 0.25 | 1.5 | 0.75 | 2 | -16.5 | 0.75 | 1 | 1 | 2.5 | 0 | -16 | 0 | 3.5 | 1 | 3 | 0 | 0 | -0.25 | 3.5 | 1 | 2.5 | 0 | 0.25 | 3 | 1 | 2.5 | 0
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status