## Cover sheet
3GPP TSG RAN WG5#95-e | [10 empty] | R5-222687
<Electronic meeting, 9th - 20th May, 2022>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | UE Conformance – Support of reduced capability NR devices
Work item code: | NR_redcap_plus_ARCH-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance – Support of reduced capability NR devices work item is to define the UE conformance requirements corresponding to WID on Support of reduced capability NR devices, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the RedCap UE work item in Rel-17. At the RAN#95 meeting the Rel-17 RAN5 work item for UE Conformance – Support of reduced capability NR devices (NR_redcap_plus_ARCH-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 13% (+13%) | 0 | 72 (+72)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 12.8% (+12.8%) | 0 | 72 (+72)
FR1 |  | 14.2% (+14.2%) | 0 | 72 (+72)
FR2 |  | 5.5% (+5.5%) | 0 | 9 (+9)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 6.4% (+6.4%) |  |  | 7.5% (+7.5%) |  |  | 1.2% (+1.2%)
Common ICS | 38.508-2 | 5% (+5%) |  |  | 5% (+5%) |  |  | 5% (+5%)
NR RF/RRM
FR1 RF common parts | 38.521-1 | 73.2% (+73.2%) |  |  | 73.2% (+73.2%)
FR1 RF Tx test cases | 38.521-1 Tx | 3.7% (+3.7%) | 0 | 52 (+52) | 3.7% (+3.7%) | 0 | 52 (+52)
FR1 RF Rx test cases | 38.521-1 Rx | 24.8% (+24.8%) | 0 | 9 (+9) | 24.8% (+24.8%) | 0 | 9 (+9)
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
RF Demod/QSI test cases | 38.521-4 | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1)
RRM test cases | 38.533 | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 4.5% (+4.5%) |  |  | 4.5% (+4.5%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 4.1% (+4.1%) |  |  | 5% (+5%) |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 9 (+9) | 0% | 0 | 9 (+9) | 0% | 0 | 9 (+9)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220830 | New WID on UE Conformance – Support of reduced capability NR devices for RAN#95e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of reduced capability NR devices | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_redcap_plus_ARCH-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item Support of reduced capability NR devices comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID | [12 empty] | vs Area
WP Resp: |  | Yu Shi(China Unicom),Yang, Zhaobing (Huawei) ,Calle Hagenfeldt (Ericsson),Yogesh Tugnawat (Qualcomm) |  |  | shiyu19@chinaunicom.cn;yangzhaobing@hisilicon.com;calle.hagenfeldt@ericsson.com;yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 14.2% (+14.2%) | 5.5% (+5.5%)
[14 empty] | 124 (+124) | 26 (+26)
[14 empty] | 92.4 (+92.4) | 17.5 (+17.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | common test environment for RedCap | Definition of common test environment for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223410 R5-222650 R5-223784 |  | 1 | 17.5% (+17.5%) | 17.5% (+17.5%) |  | 30% | 5%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
3 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
4 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0% | 0%
5 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for RedCap |  | TBD | R5-222827 |  | 1 | 5% (+5%) | 5% (+5%) |  | 5% | 5%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
6 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223790 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
7 |  | 38.521-1 | 4 | General | Define categories of test requirements for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | Define the frequency bands and channel arragement for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
9 |  | 38.521-1 | Annex |  | Check if necesarry to update Annex |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
Transmitter characteristics (Clause 6)
Transmitter power for RedCap（Clause 6.2I）
10 | Y | 38.521-1 Tx | 6.2I.1 | Maximum output power for RedCap | Adding TC of UE maximum output power for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223785 | TC is not complete. Generice procedure, message content are FFS denpending on R17 ASN.1. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
11 | Y | 38.521-1 Tx | 6.2I.1C | Maximum output power for RedCap and SUL | Adding TC of UE maximum output power for RedCap on SUL bands | Huawei | RAN5#96 (Aug-22) |  | AP：Further investigate and conclude whether existence of SUL in RedCap test cases is justified | 1 | 0% | 0% |  | 0%
12 | Y | 38.521-1 Tx | 6.2I.2 | UE maximum output power reduction for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) | R5-223786 | TC is not complete. Generice procedure, message content are FFS denpending on R17 ASN.1. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
13 | Y | 38.521-1 Tx | 6.2I.2C | UE maximum output power reduction for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) |  | AP：Further investigate and conclude whether existence of SUL in RedCap test cases is justified | 1 | 0% | 0% |  | 0%
14 | Y | 38.521-1 Tx | 6.2I.3 | UE additional maximum output power reduction for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) | R5-223787 | TC is not complete. Generice procedure, message content are FFS denpending on R17 ASN.1. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
15 | Y | 38.521-1 Tx | 6.2I.3C | UE additional maximum output power reduction for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) |  | AP：Further investigate and conclude whether existence of SUL in RedCap test cases is justified | 1 | 0% | 0% |  | 0%
16 | Y | 38.521-1 Tx | 6.2I.4 | Configured output power for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) | R5-223788 | TC is not complete. Generice procedure, message content are FFS denpending on R17 ASN.1. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
17 | Y | 38.521-1 Tx | 6.2I.4C | Configured output power for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. | Huawei | RAN5#96 (Aug-22) |  | AP：Further investigate and conclude whether existence of SUL in RedCap test cases is justified | 1 | 0% | 0% |  | 0%
Output power dynamics for RedCap (Clause 6.3I)
18 | Y | 38.521-1 Tx | 6.3I.1 | Minimum output power for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
19 | Y | 38.521-1 Tx | 6.3I.1C | Minimum output power for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
20 | Y | 38.521-1 Tx | 6.3I.2 | Transmit OFF power for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
21 | Y | 38.521-1 Tx | 6.3I.2C | Transmit OFF power for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
22 |  | 38.521-1 Tx | 6.3I.3 | Transmit ON/OFF time mask for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
23 | Y | 38.521-1 Tx | 6.3I.3.1 | General ON/OFF time mask for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
24 | Y | 38.521-1 Tx | 6.3I.3.1C | General ON/OFF time mask for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
25 | Y | 38.521-1 Tx | 6.3I.3.2 | PRACH time mask for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-1 Tx | 6.3I.3.2C | PRACH time mask for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
27 | Y | 38.521-1 Tx | 6.3I.3.3 | SRS time mask for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
28 | Y | 38.521-1 Tx | 6.3I.3.3C | SRS time mask for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
25 |  | 38.521-1 Tx | 6.3I.4 | Power control for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
26 | Y | 38.521-1 Tx | 6.3I.4.1 | Absolute power tolerance for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
27 | Y | 38.521-1 Tx | 6.3I.4.1C | Absolute power tolerance for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
28 | Y | 38.521-1 Tx | 6.3I.4.2 | Relative power tolerance for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
29 | Y | 38.521-1 Tx | 6.3I.4.2C | Relative power tolerance for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
30 | Y | 38.521-1 Tx | 6.3I.4.3 | Aggregate power tolerance for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
31 | Y | 38.521-1 Tx | 6.3I.4.3C | Aggregate power tolerance for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
Transmit signal quality for RedCap(Clause 6.4I)
32 | Y | 38.521-1 Tx | 6.4I.1 | Frequency error for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
33 | Y | 38.521-1 Tx | 6.4I.1C | Frequency error for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
34 |  | 38.521-1 Tx | 6.4I.2 | Transmit modulation quality for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
35 | Y | 38.521-1 Tx | 6.4I.2.1 | Error Vector Magnitude for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
36 | Y | 38.521-1 Tx | 6.4I.2.1C | Error Vector Magnitude for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
37 | Y | 38.521-1 Tx | 6.4I.2.2 | Carrier leakage for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
38 | Y | 38.521-1 Tx | 6.4I.2.2C | Carrier leakage for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
39 | Y | 38.521-1 Tx | 6.4I.2.3 | In-band emissions for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
40 | Y | 38.521-1 Tx | 6.4I.2.3C | In-band emissions for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
41 | Y | 38.521-1 Tx | 6.4I.2.4 | EVM equalizer spectrum flatness for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
42 | Y | 38.521-1 Tx | 6.4I.2.4C | EVM equalizer spectrum flatness for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
Output RF spectrum emissions for RedCp(Clause 6.5I)
43 | Y | 38.521-1 Tx | 6.5I.1 | Occupied bandwidth for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
44 | Y | 38.521-1 Tx | 6.5I.1C | Occupied bandwidth for RedCap for SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
45 |  | 38.521-1 Tx | 6.5I.2 | Out of band emission for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
46 |  | 38.521-1 Tx | 6.5I.2.1 | General | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
47 | Y | 38.521-1 Tx | 6.5I.2.2 | Spectrum emission mask for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
48 | Y | 38.521-1 Tx | 6.5I.2.2C | Spectrum emission mask for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
49 | Y | 38.521-1 Tx | 6.5I.2.3 | Additional spectrum emission mask for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
50 | Y | 38.521-1 Tx | 6.5I.2.3C | Additional spectrum emission mask for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
51 |  | 38.521-1 Tx | 6.5I.2.4 | Adjacent channel leakage ratio for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
52 | Y | 38.521-1 Tx | 6.5I.2.4.1 | NR ACLR for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
53 | Y | 38.521-1 Tx | 6.5I.2.4.1C | NR ACLR for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
54 | Y | 38.521-1 Tx | 6.5I.2.4.2 | UTRA ACLR for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
55 | Y | 38.521-1 Tx | 6.5I.2.4.2C | UTRA ACLR for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
56 |  | 38.521-1 Tx | 6.5I.3 | Spurious emissions for RedCap | sub-clause |  |  |  |  | 0.1 | 0% | 0% |  | 0%
57 | Y | 38.521-1 Tx | 6.5I.3.1 | General spurious emissions for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
58 | Y | 38.521-1 Tx | 6.5I.3.1C | General spurious emissions for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
59 | Y | 38.521-1 Tx | 6.5I.3.2 | Spurious emissions for UE co-existence for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
60 | Y | 38.521-1 Tx | 6.5I.3.2C | Spurious emissions for UE co-existence for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
61 | Y | 38.521-1 Tx | 6.5I.3.3 | Additional spurious emissions for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
62 | Y | 38.521-1 Tx | 6.5I.3.3C | Additional spurious emissions for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
63 | Y | 38.521-1 Tx | 6.5I.4 | Transmit intermodulation for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
64 | Y | 38.521-1 Tx | 6.5I.4C | Transmit intermodulation for RedCap and SUL | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
Receiver characteristics(Clause 7)
|  | 38.521-1 Rx | 7.1I | General | Adding general info introudction for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Rx | 7.2 | Diversity characteristics | Update of diveristy characteristics intrdocution for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 38.521-1 | 7.3I | Reference sensitivity for RedCap | sub-clause |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.3I.1 | General | Adding general info introudction for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TBD | Y | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | TC of reference sensitivity power level for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 | TC is not complete. Generice procedure, message content are FFS denpending on R17 ASN.1. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
| Y | 38.521-1 Rx | 7.4I | Maximum input level for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.5I | Adjacent channel selectivity for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6I | Blocking characteristics for RedCap | sub-clause |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6I.1 | General | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.6I.2 | In-band blocking for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.6I.3 | Out-of-band blocking for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.6I.4 | Narrow band blocking for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.7I | Spurious response for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8I | Intermodulation characteristics for RedCap | sub-clause |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.521-1 Rx | 7.8I.1 | Wide band Intermodulation for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
| Y | 38.521-1 Rx | 7.9I | Suprious emissions for RedCap | No new requirement. Check if general procedure could be reused. Test applicablity R17 onwards. |  |  |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD | 0% | 0% |  | 0%
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | All test case owners | RAN5#100 (Aug-23) | R5-223791 |  | 1 | 5% (+5%) | 5% (+5%) |  | 5%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD | 0% | 0% |  | 0%
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0%
TBD |  | 38.903 | 3 | Definitions, symbols and abbreviations |  |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD |  | 38.903 | 4 | General Principles |  |  | TBD |  |  | TBD | 0% | 0% |  | 0%
TBD |  | 38.903 | 5 | Determination of Test System Uncertainties |  |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD |  | 38.903 | 6 | Determination of Test Tolerances |  |  | TBD |  |  | TBD | 0% | 0% |  | 0%
|  | 38.903 | Annex | [10 empty] | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | 4 | Test coverage analysis | Add header, general text and table to list test point analysis for RedCap | Huawei | RAN5#98 (Feb-23) | R5-222903 |  | 1 | 2.5% (+2.5%) | 2.5% (+2.5%) |  | 5% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0% | 0%
Idle Mode
|  | 38.523-1 | 6.6 | Idle mode and RRC Inactive state operations / Redcap | Sub-clause heading |  |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 | 6.6.1 | Idle mode / Redcap | Sub-clause heading |  |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 6.6.1.1 | Access and camping restrictions | **** TP1: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status "true" for Redcap THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP2: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except intraFreqReselectionRedCap in SIB1 is absent THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP3: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status not "true" for Redcap THEN: the UE considers the cell suitable and camps on it | Huawei, Hisilicon | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 6.6.1.2 | Access and camping restrictions / inter-freguency cell reselection | **** TP1: [Ref: 38.331 clause 6.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: the serving cell broadcasts SIB4 with system information indication of frequencies which accept RedCap UEs THEN: the UE reselects the inter-frequency neighbor cell depending on SIB4 indication | Qualcomm | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
Layer 2
|  | 38.523-1 | 7.1.1.13 | MAC / Redcap | Sub-clause heading |  |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 7.1.1.13.1 | RACH / Redcap UE identification / Msg3-based / CCCH | **** TP1: [Ref: 38.321 clause 5.1 and 6.2.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific LCID in Mag3 | Qualcomm | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 7.1.1.13.2 | RACH / Redcap UE identification / Msg3-based / CCCH1 | **** TP1: [Ref: 38.321 clause 5.1 and 6.2.1] WITH: UE surpporting Redcap and in NR RRC_Inactive state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific LCID in Mag3 | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 7.1.1.13.3 | RACH / Redcap UE identification / Msg1-based | **** TP1: [Ref: 38.321 clause 5.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific random access resource in Msg1 | Huawei, Hisilicon | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 7.1.1.13.4 | Separate BWP / IDLE | **** TP1: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialDownlinkBWP-RedCap is configured THEN: the UE shall monitor the PDCCH on the BWP configured by initialDownlinkBWP-RedCap **** TP2: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialUplinkBWP-RedCap is configured and the UE needs to perform the Random Access procedure THEN: the UE shall perform the Random Access procedure by using the BWP configured by initialUplinkBWP-RedCap | Huawei, Hisilicon | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.9 | RRC / Redcap | Sub-clause heading |  |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 8.1.9.1 | Measurement relaxation / Stationary criterion | **** TP1: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the UE does not transmit a UEAssistanceInformation message with rrm-MeasRelaxationFulfilment as true since it was configured to provide indications of RRM measurement relaxation criterion fulfilment THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled **** TP2: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is not fulfilled and the last UEAssistanceInformation message indicated fulfilment of the criterion with rrm-MeasRelaxationFulfilment as true THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is not fulfilled **** TP3: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the last UEAssistanceInformation message indicated the criterion is not fulfilled with rrm-MeasRelaxationFulfilment as false THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled | Ericsson | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
NAS
|  | 38.523-1 | 11.7 | Multi-layer / Redcap | Sub-clause heading |  |  |  |  | 0.1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 11.7.1 | eDRX / IDLE | **** TP1: [Ref: 24.501 clause 5.3.16] WITH: UE surpporting Redcap and in NR RRC_IDLE state and configured eDRX (eDRX cycle >= 10.24s) WHEN: network sends Paging message within a PTW THEN: UE establishes RRC connection **** TP2: [Ref: 24.501 clause 5.3.16] WITH: UE surpporting Redcap and in NR RRC_IDLE state and configured eDRX (eDRX cycle < 10.24s) WHEN: network sends Paging message within a paging occassion THEN: UE establishes RRC connection | Qualcomm | RAN5#96 (Aug-22) |  | Optional supported by UE | 1 | 0% | 0% |  | 0% | 0%
| Y | 38.523-1 | 11.7.2 | eDRX / Inactive | **** TP1: [Ref: 24.501 clause 5.3.16] WITH: UE surpporting Redcap and in NR RRC_Inactive state and configured eDRX (eDRX cycle < 10.24s) WHEN: network sends Paging message within a paging occassion THEN: UE resumes RRC connection | Ericsson | RAN5#96 (Aug-22) |  | Optional supported by UE | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR Redcap |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR Redcap |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.