## R16 NR bands and CBW extensions
WP Title: | UE Conformance Test Aspects - Rel-16 NR bands and extension of existing NR bands (NR_bands_BW_R16-UEConTest) | [10 empty] | Overall config. Completion | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common clauses (chapter 5) | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis | End of work plan columns. Note! Do not remove this column.
WP Scope: | This work plan covers the tasks needed to include new Rel-16 NR bands and new channel bandwidths added to existing Rel-15 bands. NOTE! The company listed in column H is responsible to secure that required information for the NR bands or extended channel bandwidth is complete in the TSs and TRs as listed in columns P to Y. New NR bands and CBW extensions since previous version are highlighted in red text.
WP Resp: | Leif Mattisson, Ericsson
TS Resp: | -
WP Item ID | Source TS | Type | RAN4 WI code | RAN4 WID | RAN4 completion | Sub-WI Scope | Company | Target | TDOC(s) | Comments | Weight | [11 empty] | WP | 5% | (Work plan contribution to WI completion)
[23 empty] | Grp | completion | #configs | #assigned | #completed | #ongoing
[6 empty] | (New band/Ref. Config/New CBW) | [16 empty] | Overall | 76.4% | 26 | 22 | 18 | 3
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [12 empty] | 2 | 1 | 1 | 3 | 3 | 0.1 | 1 | 5 | 5
| 38.101-1 | New Rel-16 NR FR1 bands | [20 empty] | 1 | 84.65% | 7 | 7 | 5 | 1
1 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n14 | RP-190965 | 100% | n14 | AT&T | RAN5#90 (Feb-21) | 38.508-1: R5-205701 (4.3.1.0) R5-206738 (4.3.1.1.14) R5-206388 (6.2.3.1) 38.508-2: R5-205707 38.521-1: R5-205537, R5-205550, R5-205551, R5-205552, R5-205553, R5-206742, R5-206743, R5-206744, R5-206890, R5-211657, R5-213160 38.523-3: R5-210355 |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n18 | RP-191556 | 100% | n18 | KDDI | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
17 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n26 | RP-192736 | 100% | n26 | Dish Network | RAN5#89 (Nov-20) | 38.508-1: R5-201997 R5-201998 R5-203278 38.508-2: R5-203279 38.521-1: R5-204961 R5-204962 R5-204828 R5-206743 R5-206750 38.533: R5-203280 38.905: R5-206131 |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
4 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n30 | RP-190967 | 100% | n30 | AT&T | RAN5#96 (Aug-22) | 38.508-1: R5-203769 R5-203794 R5-205701 (4.3.1.0) 38.508-2: R5-204902 R5-205707 38.521-1: R5-203777 R5-203778 R5-203780 R5-203783 R5-203786 R5-203788 R5-203789 R5-204828 R5-204962 R5-206745 R5-206746 R5-206747 R5-206888 R5-206889 38.523-3 R5-206369 38.905: R5-205558 | Everything complete except for a number of UL MIMO test clauses. | 1 | 92.55% | 100% | 100% | 100% | 60% | 100% | 100% | 100% |  | 100%
5 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n48 | RP-190908 | 100% | n48 | Ericsson | RAN5#88 (Aug-20) | 38.508-1: R5-198125 R5-198721 R5-200532 R5-201065 R5-201837 38.508-2: R5-198964 38.521-1: R5-199434 (ch 5) R5-200922 (6.5.3.2) R5-201054 (ch 5) R5-201764 (6.3.2, 6.5.3.2, 6.5.3.3) R5-202430 (7.3.2) R5-204824 (6.2.1, 6.2.2) R5-204962 (7.6.2) R5-204837 (7.6.3, 7.6.4) TR 38.905: R5-201765 |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
27 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n53 | RP-192409 | 100% | n53 | Globalstar, Nokia | RAN5#90 (Feb-21) | R5-206736, R5-205249, R5-205250, R5-206890, R5-205252, R5-206740, R5-206743, R5-205254, R5-206741, R5-206751, R5-205257, R5-206752, R5-210081, R5-210355, R5-211328 | RAN5#90-e: 38.523-3 => clause 11 updated 38.508-2 => Add Band n53 into A.4.3.9 38.508-1 => Correction of test frequencies | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
6 | 38.101-1 | New Rel-16 NR FR1 bands | NR_band_n65 | RP-190360 | 100% | n65 | Dish Network | RAN5#87 (May-20) | Discussion paper: R5-200819 (TP analysis) 38.508-1: R5-198019 R5-198997 R5-200533 R5-201065 38.508-2: R5-198964 38.521-1: R5-198755 (ch7) R5-199435 (ch 6.2.1) R5-199434 (ch 5) R5-200922 (6.5.3.2) R5-201069, R5-202887 (6.2.1, 6.2.2, 6.2.3) 38.533: R5-199436 38.905: R5-202111 |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
| 38.101-1 | New Rel-16 NR FR1 SDL bands and reference CA configurations included in the associated RAN4 WID (if any) | [20 empty] | 2 | 100% | 1 | 1 | 1 | 0
7 | 38.101-1 | New Rel-16 NR FR1 SDL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_n29 | RP-192236 | 100% | n29 and CA_n29A-n66A | Dish Network | RAN5#87 (May-20) | 38.508-1: R5-198018 R5-198961 R5-198997 R5-200531 R5-201065 R5-203793 38.508-2: R5-198964 38.521-1: R5-199433 (ref sense CA_n29-n66] R5-199434 (ch 5) R5-199435 (ch 6.2.1) 38.533: R5-199436 | For CA_n29A_n66A , the configuration specific work is 100%. | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
| 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | [20 empty] | 3 | 50% | 2 | 1 | 1 | 0
8 | 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_SUL_UL_n5 | RP-191116 | 100% | n89 SUL |  | TBD |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
18 | 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_SUL_band_2010_2025MHz | RP-192584 | 100% | n95 SUL | CMCC | RAN5#87 (May-20) | 38.508-1: R5-200605 R5-216603 38.508-2: R5-200923 38.521-1: R5-200895 (6.2.1, 6.2.3) R5-200922 (6.5.3.2) R5-201054 (ch 5) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
| 38.101-2 | New Rel-16 NR FR2 bands | [20 empty] | 4 | 53.84% | 1 | 1 | 0 | 1
9 | 38.101-2 | New Rel-16 NR FR2 bands | NR_n259 | RP-200249 | 100% | n259 | NTT DOCOMO, INC. | RAN5#96 (Aug-22) | Discussion paper: R5-201035 (MU) R5-203526 (MU/TT ratio) R5-206788 (MU/Relaxation) R5-211923 (MU/TT) 38.508-1: R5-206794 (RRM Test Freq) R5-204032 R5-204346 R5-213977 (RRM Test Freq) 38.521-2: R5-200992 (Annex F) R5-211946 R5-213984 (cl 5, 6.2.4.3) | Remains: - 38.508-1: Low,Mid and High channel BW to be added (cl 4.3.1) - 38.521-2, 3: MU and TT | 1 | 53.84% | 70% | 0% | 50% | 50% | 40% | 60% | 20% | 60% | 70%
| 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | [20 empty] | 5 | 73.85% | 15 | 12 | 11 | 1
10 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n1_BW | RP-192009 | 100% | n1 adding CBW 30 and 40 MHz | China Unicom | RAN5#89 (Nov-20) | 38.521-1: R5-202927（ch5） R5-202484（7.3.2） |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
19 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n1_BW2 | RP-192801 | 100% | n1 adding CBW 25 and 50 MHz | China Unicom | RAN5#89 (Nov-20) | 38.508-1; R5-203998 R5-204041 38.521-1 R5-204828（ch5） R5-204827（7.3.2） R5-204825（6.5.3.2 7.3.2） R5-204826（6.2.3） 38.905 R5-204829（TP for NS_48） |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
25 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n3_BW | RP-200305 | 100% | n3 adding CBW 40MHz | China Telecom | RAN5#91 (May-21) | R5-205490 R5-206737 R5-213983 |  | 1 | 100% | 100% |  | 100% |  | 100%
11 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n7_BW | RP-190137 | 100% | n7 adding CBW 25MHz, 30MHz, 40MHz and 50MHz | Orange | RAN5#96 (Aug-22) | 38.521-1: R5-221117 R5-223695 |  | 1 | 7.786% | 0% |  | 100% | 3% | 0% |  |  |  | 0%
20 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n25_BW | RP-192401 | 100% | n25 adding CBW 25, 30 and 40 MHz | T-Mobile, Ericsson, Rhode&Schwarz | TBD | 38.508-1: R5-220541 R5-221787 38.521-1: R5-221788 R5-221789 R5-221790 | RAN5#93-e: CBW 35 MHz removed from the Sub-WI scope as deferred by RAN4 to Rel-17. | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
21 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n28_BW | RP-192261 | 100% | n28 adding CBW 30 MHz | CMCC, CBN | RAN5#88-e (Aug-20) | 38.508-1： R5-204896 38.521-1： R5-204960 R5-204828 R5-205882 38.905： R5-204963 R5-204964 R5-206853 |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
12 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n38_BW | RP-191472 | 100% | n38 adding CBW 40MHz | Huawei | RAN5#89 (Nov-20) | 38.508-1: R5-205881 38.521-1: R5-205879 R5-206748 38.905: R5-205880 |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
22 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n38_BW2 | RP-192215 | 100% | n38 adding CBW 25 MHz and 30 MHz | Anritsu | RAN5#94 (Feb-21) | 38.508-1: R5-217589 38.521-1: R5-217631 (clause 5) R5-221790 (TC 7.3.2) R5-221870 (TC 7.3.2) | RAN5#93-e: CBW 50 MHz removed from the Sub-WI scope as not included in the RAN4 Rel-16 CR for the RAN4 WI. | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
13 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n41_BW | RP-191681 | 100% | n41 adding CBW 30MHz | Softbank | RAN5#89 (Nov-20) | 38.508-1: R5-198126 38.521-1: R5-199434 R5-201772 (6.2.3, 6.5.2.3, 6.5.3.3) R5-203261 (6.5D.3.3) R5-202783 (7.3.2) R5-205569 (7.7D.5) TR 38.905: R5-201773 |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
14 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n50_BW | RP-182829 | 100% | n50 adding CBW 30MHz |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
26 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n65_BW | RP-200306 | 100% | n65 adding CBW 50MHz |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
23 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n66_BW | RP-200265 | 100% | n66 adding CBW 25, 30 MHz and asymmetric channel bandwidth combination set 1 | Huawei | RAN5#87 (May-20) | 38.508-1: R5-203057 38.521-1: Chapter 5: R5-202927 Rx: R5-201861, R5-222450 |  | 1 | 100% | 100% |  | 100% |  | 100%
24 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n75_BW | RP-192216 | 100% | n75 adding CBW 25 MHz, 30 MHz, 40 MHz and 50 MHz |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
15 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n77_n78_BW | RP-192349 | 100% | n77 adding CBW 25MHz, 30MHz and 70MHz | China Unicom | RAN5#95 (May-22) | 38.508-1: R5-203767 R5-211604 38.521-1: R5-200721 (6.3.2, 7.4) R5-201054 (ch 5) R5-211040 (6.3A.1) R5-211041 (6.3D) R5-212682（6.3D.3） R5-212704（6.3.3.2） R5-213978（6.5.1） R5-213979（6.5.2.2） R5-213980（6.5.2.4） R5-213981（6.5.2.2） R5-213982（6.3A.4.1） R5-216110（6.3.3.6） R5-215406（6.3.4.2） R5-215438（6.3.4.3） R5-215439（6.3A.3.1） R5-215513（6.3A.3.1_1） R5-217631 (clause 5) R5-218280（6.3D.4.1） R5-217665（6.3D.4.2） R5-218281（6.5A） R5-218282（6.5C）R5-221198(6.5D) R5-221200 (Rx TC except refesens) R5-223694 (Rx refsense) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
16 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n77_n78_BW | RP-192349 | 100% | n78 adding CBW 25MHz, 30MHz and 70MHz | China Unicom | RAN5#95 (May-22) | 38.508-1: R5-203998 R5-211604 38.521-1: R5-200721 (6.3.2, 7.4) R5-201054 (ch 5) R5-211040 (6.3A.1) R5-211041 (6.3D) R5-212682（6.3D.3） R5-212704（6.3.3.2） R5-213978（6.5.1） R5-213979（6.5.2.2） R5-213980（6.5.2.4） R5-213981（6.5.2.2） R5-213982（6.3A.4.1） R5-216110（6.3.3.6） R5-215406（6.3.4.2） R5-215438（6.3.4.3） R5-215439（6.3A.3.1） R5-215513（6.3A.3.1_1） R5-217631 (clause 5) R5-218280（6.3D.4.1） R5-217665（6.3D.4.2） R5-218281（6.5A） R5-218282（6.5C） R5-221198(6.5D) R5-221200 (Rx TC except refesens) R5-223694 (Rx refsense) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on P1: Todo for 38.508-1: - Add test frequencies to clause 4.3.1 for the new band. - Add test frequencies to clause 6.2.3.1 for protocol testing based on the default CBW chosen for protocol testing of teh band. - Add RF low, Mid and High test channel bandwidth in clause 4.3.1
Note on Q1: To do 38.508-2: - Add the new band to the relevant table in clause A.4.3.1
Note on R1: To do 38.521-x chapter 5: - Add operating band to clause 5.2. - Add the channel bandwidth for the band to clause 5.3.5. - Add the applicable NR-ARFCN for teh band to Table 5.4.2.3-1. - Add the applicable SS raster for teh band to Table 5.4.3.3-1. - Add the default UE TX-RX frequency separation for teh band to Table 5.4.4-1.
Note on U1: Todo for 38.523-3: If the band's overall bandwidth is less than 4*default CBW for protocol testing then thenexecution guidelineneed to be added to 38.523-3 clause 11. Remark: Some protocol test cases use up to 4 inter-frequency cells. If not then there is no impact on 38.523-3 and the completion can be set to 100%.
Note on V1: 38.533: Add band to NR band groups in clause 3A.4 in TS 38.533. This clause is referenced from TSuse is referenced from TS 37.571-1 clause 4.12.3 for defintion of NR band groups.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on L6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.