3GPP TSG RAN Meeting #96	RP-221249

Electronic Meeting, June 6 - 9 , 2022

## Status Report to TSG

Agenda item:			13.4.20

| WI / SI Name | NR-based access to unlicensed spectrum |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: No |  | Testing part: Yes |
| Acronym | NR_unlic-UEConTest-UEConTest |  |  |  |  |
| Unique ID | 911003 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-210708 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: - | Core part: - | Performance part: - | Testing part: 12/2022 |  |
| Overall Completion level | Study Item: - | Core part: . | Performance Part: - | Testing part: 20% (+2%) |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | TSG RAN WG5 |
| --- | --- | --- |
| Rapporteur | Name | Vijay Balasubramanian |
|  | Company | Qualcomm |
|  | Email | vijayb[at]qti.qualcomm.com |

## 1	Work plan related evaluation

N/A

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

#### 2.4.2	Remaining Open issues

## 2.5	RAN5

#### 2.5.1	Agreements

At RAN#91-e the WID for NR based access to unlicensed spectrum was approved. Work Plan was created in [1].

#### 2.5.2	Remaining Open issues

See WP for more details [3]

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

Work plan:

[1] R5-213365	WP UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum; Source: Qualcomm

[2] R5-215647	WP UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum; Source: Qualcomm

[3] R5-222579	WP UE Conformance Test Aspects for NR-based Access to Unlicensed Spectrum; Source: Qualcomm

Tdocs:

[3] R5-214334	Introduction of ICS for NR-U; 	Source: Ericsson

[4] R5-215983	Introduction of NR-U MOP test case 	Source: Ericsson

[5] R5-215984	Introduction of NR-U in general clauses	Source: Ericsson

[6] R5-215985	Introduction of general spurious emission for NR-U	Source: Qualcomm

[7] R5-215564	Introduction of Spectrum emission mask for NR-U	Source: Qualcomm

[8] R5-215562	Introduction of Reference sensitivity for NR-U	Source: Qualcomm

[9] R5-217234	Introduction of ACLR for NR-U	Source: Qualcomm

[10] R5-218411	Introduction of NR-U A-MPR test case		Source: Ericsson

[11] R5-217235	Introduction of 7.3F.3 for NR-U	Source: Qualcomm

[12] R5-218371	NR U test case applicability	Source: Qualcomm

[13] R5-217949	Update IE MeasObjectNR	Source: Ericsson

[14] R5-217950	Update IE ServingCellConfigCommon		Source: Ericsson

[15] R5-217951	Update IE ServingCellConfigCommonSIB	Source: Ericsson

[16] R5-216773	Update IE SSB-PositionQCL-Relation		Source: Ericsson

[17] R5-221894	Introduction of NR-U OFF power test case	Source: Ericsson

[18] R5-221895	Introduction of NR-U General ON/OFF time mask test case	Source: Ericsson

[19] R5-222738	Update 7.3F.2 Ref sensitivity power level	Source: Qualcomm

[20] R5-222739	Introduction of 7.6F.2 IBB for NR_U	Source: Qualcomm

[21] R5-222746	Introduction of ACS for NR_U	Source: Qualcomm

[22] R5-222174	Correction to n46 ARFCN	Source: Rohde & Schwarz

[23] R5-223754	Add MU and TT for 7.5F.1 and 7.6F.2	Source: Qualcomm

[24] R5-222736	Add 7.5F.1 and 7.6F.2	Source: Qualcomm

[25] R5-222733	Update for 38.521-1_TPanalysis_7.3_RefSense	Source: Qualcomm

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template