## Cover sheet
3GPP TSG-RAN WG5 Meeting #95-e | [8 empty] | R5-222213
Electronic Meeting, May 9 – May 20, 2022
Agenda Item: | 7.4.2
Source: | CMCC
Title: | WP - UE Conformance Test Aspects for NR support for high speed train scenario
Work item code: | NR_HST-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At RAN#90e meeting in December 2020, a Release 16 work item for UE Conformance Test Aspects for NR support for high speed train scenario (NR_HST-UEConTest) was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on NR HST with Unique identifier 840092. This work item will cover Demod and RRM conformance test specifications with NR HST. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+8%) | 17 (+2) | 17
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 100% (+7.2%) | 15 (+2) | 15
FR1 |  | 100% (+7.2%) | 15 (+2) | 15
NSA Option 3 (EN-DC) |  | 100% (+8.5%) | 10 (+2) | 10
FR1 |  | 100% (+8.5%) | 10 (+2) | 10
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+70%) |  |  | 100% (+70%) |  |  |  |  | 100% (+70%)
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  |  |  | 100%
NR RF/RRM
RF Demod/QSI test cases | 38.521-4 | 100% (+0.9%) | 8 (+2) | 8 | 100% (+0.9%) | 8 (+2) | 8 |  |  | 100% (+0.9%) | 8 (+2) | 8
RRM test cases | 38.533 | 100% | 9 | 9 | 100% | 7 | 7 |  |  | 100% | 2 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+93.8%) |  |  | 100% (+90%) |  |  |  |  | 100% (+100%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% (+51.6%) |  |  | 100% (+52.5%) |  |  |  |  | 100% (+50%)
5 References
[1] RP-202328 | New WID on UE Conformance Test Aspects for NR support for high speed train scenario - CMCC (Supporting companies: China Unicom, Ericsson, FirstNet, Huawei, HiSilicon, Lenovo, Motorola Mobility, NTT DOCOMO, Orange, Qualcomm, Samsung, Telecom Italia, Verizon, ZTE)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR support for high speed train scenario | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_HST-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR support for high speed train scenario comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title |  | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 100% (+7.2%) | 100% (+8.5%)
[15 empty] | 47 | 42
[15 empty] | 33.1 (-0.5) | 28.1 (-0.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
LTE - RAN and CN
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
35 |  | 36.508 | 4, 7 | General and RRM Test Environment | Introduction of General and RRM Test Environment for Rel-16 HST in LTE | CMCC | RAN5#95 (May-22) |  | CMCC Dan Song <songdan@chinamobile.com> No changes are needed. | 0 | 0% | 0% | 0% |  | 0% | 0%
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4, 7 | General and RRM Test Environment | Introduction of General and RRM Test Environment for Rel-16 HST | CMCC | RAN5#95 (May-22) | R5-216905 R5-217950 R5-217951 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% (+70%) | 100% (+70%) | 100% (+70%) |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4.3.11 | <Title> | Introduction of common implementation conformance statements for Rel-16 HST | CMCC | RAN5#93 (Nov-21) | R5-211815, R5-221853, R5-223721 | CMCC Luting Kong <kongluting@chinamobile.com> | 0.3 | 100% | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.521-4 | 3.3 | Abbreviations | To update section 3.3 for abbreviations of DPS. (R4-2017540) | CMCC | RAN5#93 (Nov-21) | R5-211820 | CMCC Dan Song <songdan@chinamobile.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
4 |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | To update the applicability of requirements for optional UE features of NR HST-SFN joint transmission scheme (R4-2017542) | CMCC | RAN5#93 (Nov-21) | R5-211819 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
5 |  | 38.521-4 | 5.1.1.4 | Applicability of requirements for mandatory UE features with capability signalling | To update the applicability of requirements for mandatory UE features with capability signalling for NR HST (R4-2017548) | CMCC | RAN5#93 (Nov-21) | R5-211818, R5-215944, R5-215944 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
6 |  | 38.521-4 | 5.1.1.7 | Applicability of different requirements for HST | To update the applicability of different requirements for HST (R4-2017548) | CMCC | RAN5#93 (Nov-21) | R5-211817, R5-215944, R5-215944 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.1.1 | 2Rx FDD FR1 PDSCH mapping Type A performance | [5 empty] | TBD
7 |  | 38.521-4 | 5.2.2.1.1.0 | Minimum conformance requirements |  | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-216908 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
8 |  | 38.521-4 | 5.2.2.1.1_1 | 2Rx FDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA | To specify FDD HST Single-Tap and Multipath Fading requirements for 2Rx FDD FR1 (R4-2017682) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-216908 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.1.9 | 2Rx FDD FR1 HST-SFN performance | [5 empty] | TBD
9 |  | 38.521-4 | 5.2.2.1.9.0 | Minimum conformance requirements |  | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215946 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
10 | Y | 38.521-4 | 5.2.2.1.9_1 | 2Rx FDD FR1 HST-SFN performance - 2x2 MIMO with baseline receiver for both SA and NSA | To verify PDSCH performance under 2 receive antenna conditions in the HST-SFN scenario defined in B.3.2 when highSpeedDemodFlag-r16 IE is configured (R4-2017542) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215946, R5-220678, R5-220651, R5-222231 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.1.10 | 2Rx FDD FR1 HST DPS performance | [5 empty] | TBD
11 |  | 38.521-4 | 5.2.2.1.10.0 | Minimum conformance requirements |  | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215947 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
12 | Y | 38.521-4 | 5.2.2.1.10_1 | 2Rx FDD FR1 HST DPS performance - 2x2 MIMO with baseline receiver for both SA and NSA | To verify UE performance in the HST-DPS scenario defined in B.3.3 of TS 38.521-4 (R4-2017540) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215947, R5-220678, R5-220651 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> R5-220651 has been captured in Annex F for adding TT | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.2.1 | 2Rx TDD FR1 PDSCH mapping Type A performance | [5 empty] | TBD
13 |  | 38.521-4 | 5.2.2.2.1.0 | Minimum conformance requirements |  | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-216909 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
14 |  | 38.521-4 | 5.2.2.2.1_1 | 2Rx TDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA | Update to verify the PDSCH mapping Type A normal performance under 2 receive antenna conditions and with different channel models, MCSs and number of MIMO layers (R4-2017545) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-216909 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.2.9 | 2Rx TDD FR1 HST-SFN performance | [5 empty] | TBD
16 |  | 38.521-4 | 5.2.2.2.9.0 | Minimum conformance requirements |  | Ericsson | RAN5#93 (Nov-21) |  | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
16 | Y | 38.521-4 | 5.2.2.2.9_1 | 2Rx TDD FR1 HST-SFN performance - 2x2 MIMO with baseline receiver for both SA and NSA | To verify PDSCH performance under 2 receive antenna conditions in the HST-SFN scenario defined in B.3.2 when highSpeedDemodFlag-r16 is configured (R4-2017541) | Ericsson | RAN5#93 (Nov-21) | R5-218347, R5-218350 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> Minimum test time in annex G .1.5 is missing | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.2.2.10 | 2Rx TDD FR1 HST DPS performance | [5 empty] | TBD
17 |  | 38.521-4 | 5.2.2.2.10.0 | Minimum conformance requirements |  | Ericsson | RAN5#93 (Nov-21) |  | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
18 | Y | 38.521-4 | 5.2.2.2.10_1 | 2Rx TDD FR1 HST DPS performance - 2x2 MIMO with baseline receiver for both SA and NSA | To verify UE performance in the HST-DPS scenario defined in B.3.3 of TS 38.521-4 (R4-2017540) | Ericsson | RAN5#95 (May-22) | R5-218348, R5-218350, R5-223722 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% | 100%
|  | 38.521-4 | 5.2.3.1.1 | 4Rx FDD FR1 PDSCH mapping Type A performance | [5 empty] | TBD
19 |  | 38.521-4 | 5.2.3.1.1.0 | Minimum conformance requirements |  | LG Electronics | RAN5#93 (Nov-21) | R5-211816 | LG Electronics Tae Howan Hong <taehowan.hong@LGE.COM> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
20 |  | 38.521-4 | 5.2.3.1.1_1 | 4Rx FDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA | To specify FDD HST Single-Tap and Multipath Fading requirements for 4Rx FDD FR1 (R4-2017682) | LG Electronics | RAN5#95 (May-22) | R5-211816, R5-222232 | LG Electronics Tae Howan Hong <taehowan.hong@LGE.COM> | 1 | 100% (+10%) | 100% (+10%) | 100% (+10%) |  | 100% | 100%
|  | 38.521-4 | 5.2.3.1.9 | 4Rx FDD FR1 HST-SFN performance | [5 empty] | TBD
21 |  | 38.521-4 | 5.2.3.1.9.0 | Minimum conformance requirements |  | CMCC | RAN5#93 (Nov-21) | R5-218345, R5-220664 | CMCC Luting Kong <kongluting@chinamobile.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
22 | Y | 38.521-4 | 5.2.3.1.9_1 | 4Rx FDD FR1 HST-SFN performance - 2x4 MIMO with baseline receiver for both SA and NSA | To verify PDSCH performance under 4 receive antenna conditions in the HST-SFN scenario defined in B.3.2 when highSpeedDemodFlag-r16 IE is configured. (R4-2017542) | CMCC | RAN5#94 (Feb-22) | R5-218345, R5-220634, R5-221856, R5-220664, R5-220678, R5-222233 | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.3.1.10 | 4Rx FDD FR1 HST DPS performance | [5 empty] | TBD
23 |  | 38.521-4 | 5.2.3.1.10.0 | Minimum conformance requirements |  | CMCC | RAN5#93 (Nov-21) | R5-218346, R5-220664 | CMCC Luting Kong <kongluting@chinamobile.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
24 | Y | 38.521-4 | 5.2.3.1.10_1 | 4Rx FDD FR1 HST DPS performance - 2x4 MIMO with baseline receiver for both SA and NSA | To verify UE performance in the HST-DPS scenario defined in B.3.3 of TS 38.521-4 (R4-2017540) | CMCC | RAN5#94 (Feb-22) | R5-218346, R5-220635, R5-221857, R5-220664, R5-220678, R5-222234 | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.3.2.1 | 4Rx TDD FR1 PDSCH mapping Type A performance | [5 empty] | TBD
25 |  | 38.521-4 | 5.2.3.2.1.0 | Minimum conformance requirements |  | Ericsson | RAN5#93 (Nov-21) |  | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
26 |  | 38.521-4 | 5.2.3.2.1_1 | 4Rx TDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA | Update to verify the PDSCH mapping Type A normal performance under4 receive antenna conditions and with different channel models, MCSs and number of MIMO layers (R4-2017545) | Ericsson | RAN5#93 (Nov-21) | R5-218466 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
|  | 38.521-4 | 5.2.3.2.9 | 4Rx TDD FR1 HST-SFN performance | [5 empty] | TBD
27 |  | 38.521-4 | 5.2.3.2.9.0 | Minimum conformance requirements |  | Ericsson | RAN5#93 (Nov-21) |  | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
28 | Y | 38.521-4 | 5.2.3.2.9_1 | 4Rx TDD FR1 HST-SFN performance - 2x4 MIMO with baseline receiver for both SA and NSA | To verify PDSCH performance under 4 receive antenna conditions in the HST-SFN scenario defined in B.3.2 when highSpeedDemodFlag-r16 is configured (R4-2017541) | Ericsson | RAN5#95 (May-22) | R5-218349, R5-218350, R5-223723 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 1 | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% | 100%
|  | 38.521-4 | 5.2.3.2.10 | 4Rx TDD FR1 HST DPS performance | [5 empty] | TBD
29 |  | 38.521-4 | 5.2.3.2.10.0 | Minimum conformance requirements |  | Ericsson | RAN5#95 (May-22) | R5-221854 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
30 | Y | 38.521-4 | 5.2.3.2.10_1 | 4Rx TDD FR1 HST DPS performance - 2x4 MIMO with baseline receiver for both SA and NSA | To verify UE performance in the HST-DPS scenario defined in B.3.3 of TS 38.521-4 (R4-2017540) | Ericsson | RAN5#95 (May-22) | R5-221854, R5-223724 | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
31 |  | 38.521-4 | A.3.2 | Reference measurement channels for PDSCH performance requirements | To introducte Rel-16 HST TDD FRC without Special slot data. To add HST single Tap MCS17 FRC and HST-DPS FRC (R4-2017546) | CMCC | RAN5#93 (Nov-21) | R5-211824 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
32 |  | 38.521-4 | B.2.2 | Combinations of channel model parameters | To add HST multi-path fading propagation conditions (R4-2017539) | CMCC | RAN5#93 (Nov-21) | R5-211823 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
33 |  | 38.521-4 | B.3.1 | Single Tap Channel Profile | To add HST single tap propagation conditions (R4-2017539) | CMCC | RAN5#93 (Nov-21) | R5-211825 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
34 |  | 38.521-4 | B.3.2 | HST-SFN Channel Profile | To add HST-SFN propagation conditions (R4-2017539) | CMCC | RAN5#93 (Nov-21) | R5-211822 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
35 |  | 38.521-4 | B.3.3 | HST-DPS Channel Profile | To add HST-DPS propagation conditions (R4-2017539) | CMCC | RAN5#93 (Nov-21) | R5-211821 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% | 100% |  | 100% | 100%
48 |  | 38.521-4 | G.1.5 | Minimum Test time | To update "Table G.1.5-1: Minimum Test time for PDSCH demodulation", "Table G.1.5-1a: Minimum Test time for PDSCH demodulation with 1% BLER" and "Table G.1.5-2: Minimum Test time for PDCCH demodulation" for different HST doppler speed | Qualcomm | RAN5#95 (May-22) | R5-221855，R5-221662 (discussion paper) | Qualcomm Vijay Balasubramanian (QCT)<vijayb@qti.qualcomm.com> | 0.2 | 100% | 100% | 100% |  | 100% | 100%
49 |  | 38.521-4 | G.3.4 | Number of samples for throughput ratios | To update "Table G.3.4-1: Test time for testing throughput ratios" for different HST doppler speed | Ericsson | RAN5#95 (May-22) |  | Ericsson Petter Karlsson <petter.karlsson@ericsson.com> | 0
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
36 |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.101-4 and 38.533. |  | RAN5#95 (May-22) | R5-211917, R5-211918, R5-215245，R5-216539, R5-216540, R5-216911, R5-217568, R5-220166, R5-221858, R5-220663, R5-220673, R5-221371, R5-223725, R5-222992 |  | 0.5 | 100% | 100% | 100% (+100%) |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
37 | Y | 38.533 | 4.6.1.7 | EN-DC FR1 event-triggered reporting without gap in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct reporting of an event for UE configured with highSpeedMeasFlag-r16. This test will partly verify the intra-frequency cell search requirements in clause 9.2.5.1 and 9.2.5.2 of 38.133. (R4-2017252) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215948, R5-216912, R5-216915, R5-220939, R5-220941 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 1 | 100% |  | 100% |  |  | 100%
38 | Y | 38.533 | 4.6.4.5 | EN-DC FR1 SSB-based L1-RSRP measurement in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct reporting of L1-RSRP measurement when UE is configured with highSpeedMeasFlag-r16. This test will partly verify the L1-RSRP measurement requirements for UE configured with highSpeedMeasFlag-r16 in clause 9.5.4.1, with the testing configurations for NR cells in Table A.4.6.4.5.1-1 of 38.133. (R4-2017252) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-212910, R5-212911, R5-216913, R5-216915, R5-221859, R5-220941 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> Minimum conformance requirements for SSB-based L1-RSRP measurement for beam reporting also has been changed accordingly in 4.6.4.0 (R5-212910) | 1 | 100% |  | 100% |  |  | 100%
39 | Y | 38.533 | 6.1.1.7 | NR SA FR1 cell re-selection for UE configured with highSpeedMeasFlag-r16 | To verify the requirement for the intra frequency NR cell reselection requirements for UE configured with highSpeedMeasFlag-r16 in clause 4.2.2.3 of 38.133. (R4-2017252) | CMCC | RAN5#95 (May-22) | R5-211827, R5-210279, R5-211829, R5-220931, R5-221655, R5-222490 | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 100% | 100% |  |  | 100%
40 | Y | 38.533 | 6.1.2.5 | NR SA FR1 – E-UTRA cell re-selection to lower priority E-UTRA for UE configured with highSpeedMeasFlag-r16 | To verify the requirement for the NR to E-UTRAN inter-RAT cell reselection requirements specified in clause 4.2.2.5 of 38.133 when the E-UTRAN cell is of lower priority. (R4-2017252) | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-215949, R5-216914, R5-216915, R5-220928, R5-222491 | Huawei, HiSilicon Xuesong Wang <cedar.wang@hisilicon.com> | 1 | 100% | 100% |  |  | 100%
41 | Y | 38.533 | 6.6.1.7 | NR SA FR1 event-triggered reporting without gap in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct reporting of an event for UE configured with highSpeedMeasFlag-r16. This test will partly verify the intra-frequency cell search requirements in clauses 9.2.5.1 and 9.2.5.2 of 38.133. (R4-2017252) | CMCC | RAN5#95 (May-22) | R5-211828, R5-210281, R5-211829, R5-216915, R5-220938, R5-220167, R5-222507 | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 100% | 100% |  |  | 100%
42 | Y | 38.533 | 6.6.3.3 | NR SA FR1 – E-UTRAN event-triggered reporting in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct event-triggered reporting of inter-RAT E-UTRAN measurements for UE configured with highSpeedMeasFlag-r16 in standalone (SA) operation with PCell in FR1 when DRX is used. This test shall partly verify the cell search and measurement requirements in Clauses 9.4.2 and 9.4.3 of 38.133. (R4-2017252) | Ericsson | RAN5#93 (Nov-21) | R5-211219, R5-211220, R5-215413, R5-217570, R5-218352, R5-222492, R5-222508 | Ericsson Jakub Kolodziej<jakub.kolodziej@ericsson.com> | 1 | 100% | 100% |  |  | 100%
43 | Y | 38.533 | 6.6.4.5 | NR SA FR1 SSB-based L1-RSRP measurement in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct reporting of L1-RSRP measurement when UE is configured with highSpeedMeasFlag-r16. This test will partly verify the L1-RSRP measurement requirements for UE configured with highSpeedMeasFlag-r16 in clause 9.5.4.1 of 38.133, with the testing configurations for NR cells in Table A.6.6.4.5.1-1 of 38.133. (R4-2017252) | CMCC | RAN5#95 (May-22) | R5-212612, R5-212613，R5-215243，R5-215244, R5-216915, R5-221859, R5-220168 | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 100% | 100% |  |  | 100%
44 | Y | 38.533 | 8.2.1.2 | E-UTRA – NR FR1 cell re-selection to lower priority NR target cell for UE configured with highSpeedMeasFlag-r16 | To verify the requirement for the E-UTRAN to NR inter-RAT cell reselection requirements specified in clause 4.2.2.5.6 of 36.133. (R4-2017252) | Ericsson | RAN5#93 (Nov-21) | R5-211830, R5-211831, R5-215414, R5-218351, R5-218352, R5-220928, R5-220940, R5-222493 | Ericsson Jakub Kolodziej<jakub.kolodziej@ericsson.com> | 1 | 100% | 100% |  |  | 100%
45 | Y | 38.533 | 8.4.2.9 | E-UTRA – NR FR1 event-triggered reporting with SSB time index detection in DRX for UE configured with highSpeedMeasFlag-r16 | To verify that the UE makes correct reporting of an event. This test will partly verify the NR inter-RAT cell search requirements in clause 8.1.2.4.21of TS 36.133 for E-UTRAN FDD-NR measurements and clause 8.1.2.4.22 of TS 36.133 for E-UTRAN TDD-NR measurements when UE is configured with highSpeedInterRAT-NR-r16. (R4-2017252) | Ericsson | RAN5#93 (Nov-21) | R5-211832, R5-211833, R5-215415, R5-217572, R5-218352, R5-220920, R5-222509 | Ericsson Jakub Kolodziej<jakub.kolodziej@ericsson.com> | 1 | 100% | 100% |  |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
47 |  | 38.903 | <Clause> | <Title> | Add TT analyses for the new test cases introduced for 38.533 |  | RAN5#95 (May-22) | R5-218397 R5-218398 R5-218353 R5-218354, R5-218355, R5-218356, R5-221656, R5-221286 | TT analysis of following HST RRM TCs are finished: - 4.6.1.7, 4.6.4.5, 6.1.2.5, 6.6.1.7, 6.6.4.5 - 6.6.3.3, 8.2.1.2, 8.4.2.9 - 6.1.1.7 | 1 | 100% | 100% | 100% |  | 100% | 100%
46 |  | 38.903 | <Clause> | <Title> | Add TT analyses for the new test cases introduced for 38.521-4. |  | RAN5#95 (May-22) |  | TT analyses for 38.521-4 have been captured in Column "Comments" for 38.521-4 test cases. | 1 | 100% | 100% | 100% (+100%) |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.