## Slide 1
Title: Timeline for Rel-18
Agenda item: 9
Source: Samsung
Document for: Decision
3GPP TSG RAN Meeting #96
Budapest, Hungary, June 6 – 9, 2022
RP-221407

## Slide 2: Endorsed meeting plan from RAN#95-e (in RP-220857)
On top of the meeting plan in RP-220857, it was decided in May that all WG meetings in 2022.Q3 will be electronic except RAN1
TSG
WG
WG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
E-meeting
April
2022
May
2022
11-15
18-22
25-29
02-06
09-13
16-20
June
2022
23-27
30-3
6-10
20-24
13-17
04-08
RAN1-E
RAN4-E
RAN3-E
(5+4)
RAN2-E
RAN5-E
I
N
A
C
T
I
V
E
P
E
R
I
O
D
Friday to Monday,
inclusive
Ad-Hoc
July
2022
August
2022
Sept.
2022
Oct.
2022
Nov.
2022
Dec.
2022
27-1
4-8
11-15
18-22
25-29
1-5
8-12
15-19
22-26
29-2
5-9
12-16
19-23
26-30
3-7
10-14
17-21
24-28
31-4
7-11
14-18
21-25
28-2
5-9
12-16
19-23
26-30
F2F
* For RAN2 Ad-hoc in April, please refer to RP-213608 for more details
TSG
TSG
WG
WG
WG
RAN1-E
RAN2-E
RAN3-E
(5+4)
RAN4-E
RAN5-E
Planned F2F (TBC)
T
S
G
#
9
7
E
T
S
G
#
9
8
E
RAN1-E
(5+3)
RAN2-E
(5+3)
RAN4-E
(5+3)
RAN1-E
(2+5)
RAN2-E
(2+5)
RAN3-E
(2+5)
RAN4-E
(2+5)
RAN5-E
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
Planned F2F (TBC)
Planned E-meeting (TBC)
Back-up Plan
F2F meeting schedules
E-meeting schedules
RAN3-E
(5+2)
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D

## Slide 3: WG meetings in 2022.Q4
Current plan (to be confirmed) is to have two WG meetings in Q4
  Electronic meetings for October
  Face to face meetings for November
In RAN#95-e, there were proposals to have only a single WG meeting in Q4
  According to the proposals, there will only be face to face meetings for November
  The proposals were motivated by companies to alleviate the meeting burden on WG delegates
From Samsung perspective, we acknowledge that the current mode of WG operations is not sustainable
  However, not having the October meetings but still assuming the WGs to deliver Rel-18 specifications according to the current schedule is not reasonable and not feasible

## Slide 4: Moving forward
Note that current Rel-18 schedule was decided in Dec, 2021 under the assumption that 3GPP will return to full face to face meetings
  For May, RAN1 started Rel-18 with electronic meeting
  For August, all WGs will have electronic meetings except RAN1 (F2F with remote participation)
  For October, all WGs will have electronic meetings if there is meeting at all
If October WG meetings are cancelled, RAN would need to
  Shift Rel-18 completion target date by at least a quarter
  Adjust the completion/starting dates for Rel-18 work/study items
    For example, completion dates for work/study items already started in RAN1 should be shifted by a quarter and the starting dates for work/study items in the middle of Rel-18 time span should also be adjusted