## Cover sheet
3GPP TSG-RAN Meeting #96 | [10 empty] | R5-223262
Budapest, Hungary, 6th June 2022 - 9th June 2022
Agenda Item: | 13.4.21
Source: | Nokia, Nokia Shanghai Bell
Title: | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements
Work item code: | LTE_NR_DC_CA_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The technical objective of this work item is to provide conformance test specifications for the Release 16 DCCA enhancements requirements. More specifically, the WI covers the following conformance areas: Develop RRM test cases for DCCA enhancement requirements defined in RAN4; Develop MAC and RRC signaling test cases for DCCA enhancement requirements defined in RAN2;
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 40% (+20%) | 22 (+19) | 84 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 46.4% (+35.1%) | 22 (+21) | 64 (+14)
FR1 |  | 55.4% (+42.7%) | 22 (+21) | 52 (+13)
FR2 |  | 32.8% (+19.6%) | 0 (-1) | 19 (-14)
FR1 + FR2 |  | 20.6% (+14.6%) | 0 | 7 (-15)
NSA Option 3 (EN-DC) |  | 6.3% (+1.3%) | 0 | 16 (-24)
FR1 |  | 5.7% (+0.7%) | 0 | 12 (-19)
FR2 |  | 6.2% (+1.2%) | 0 | 7 (-19)
FR1 + FR2 |  | 10% (+5%) | 0 | 1 (-18)
NSA Option 4 (NE-DC) |  | 65.8% (-13.9%) | 0 (-2) | 4
FR1 |  | 67.3% (-12.4%) | 0 (-2) | 4
FR2 |  | 67.3% (-12.4%) | 0 (-2) | 4
FR1 + FR2 |  | 20.8% (+20.8%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | NSA Option 4 (NE-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 46.7% (+46.7%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%)
UE specific test functions | 38.509 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
NR RF/RRM
RF test cases | 38.521-1 | 75.9% (+75.5%) | 22 (+22) | 29 (-4) | 75.9% (+74.2%) | 22 (+22) | 29 (+23)
RRM test cases | 38.533 | 0.8% (+0.4%) | 0 | 26 (-7) | 1.7% | 0 | 6 | 0% | 0 | 7 | 0% | 0 | 5 | 0% | 0 | 4 (-3) | 0% | 0 | 3 (-3) | 0% | 0 | 1 (-2)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 3.2% (+1.6%) |  |  | 6.7% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 35.6% (+20.1%) | 0 (-3) | 29 | 33.8% (+15.6%) | 0 (-1) | 17 | 46.7% (+17.2%) | 0 (-1) | 12 (+2) | 50% (+45%) | 0 | 2 (+1) | 0% | 0 | 8 | 0% | 0 | 4 |  |  |  | 70% (-10%) | 0 (-2) | 4 | 70% (-10%) | 0 (-2) | 4
Applicability Protocol test cases | 38.523-2 | 56.2% (+21.6%) |  |  | 62.5% (+22.5%) |  |  | 65% (+22.5%) |  |  | 100% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 50% |  |  | 50%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0%
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status
WI code |  | LTE_NR_DC_CA_enh-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Matti Kangas |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | NSA Option 4 (NE-DC)
TS Resp: |  | - |  |  | -
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | NSA Option 4 (NE-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[14 empty] | Overall |  | 55.4% (+42.7%) | 32.8% (+19.6%) | 20.6% (+14.6%) | 5.7% (+0.7%) | 6.2% (+1.2%) | 10% (+5%) | 67.3% (-12.4%) | 67.3% (-12.4%) | 20.8% (+20.8%)
[14 empty] | Number of WP items |  | 62 (+12) | 28 (-15) | 16 (-16) | 21 (-20) | 16 (-20) | 10 (-19) | 9 (+3) | 9 (+3) | 3 (+3)
[14 empty] | Sum weight of WP items |  | 53 (+12) | 19.9 (-15) | 7.9 (-16) | 12.9 (-20) | 7.9 (-20) | 1.9 (-19) | 4.5 (+0.3) | 4.5 (+0.3) | 0.3 (+0.3)
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
52 |  | 38.508-1 | 4.3.1.1.7 | Definition of common test environment for DCCA testing | Introduce NR-DC configurations clause 4.3.1.1.7, add DC_n48A-n70A. Update A.3.1.1 to cover NR-DC. Addition of SIB11 to common environment for early measurements. Modification of SIB1 in common environment for idle/inactive measurements. | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-222308, R5-223755, R5-223400, R5-223399 |  | 0.1 | 33.3% (+33.3%) | 50% (+50%) | 50% (+50%) | 0% |  | 50% | 50% | 50% | 50% | 50% | 50% | 0% | 0% | 0%
TS 38.508-2: Common ICS
53 |  | 38.508-2 | A.4.3.6, A.4.3.5 | Definition of test capabilities for DCCA testing | Addition of Measurement Capabilities for Idle/Inactive measurements testcase Addition of direct SCG SCell activation capability | Nokia, Nokia Shanghai Bell, TDIA, CATT, Lenovo | RAN5#97 (Nov-22) | R5-223401 |  | 0.1 | 50% (+50%) | 50% (+50%) | 50% (+50%) | 50% (+50%) |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
TS 38.509: UE specific testing functions
54 |  | 38.509 | TBD | TBD | Update UE specific testing functions as per need. | TBD | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NR RF/RRM
TS 38.521-1: RF test cases
77 | Y | 38.521-1 | 5.5B | Configurations for NR-DC | Add configuration DC_n48A-n70A. Add clarifying note to Configurations for inter-band CA (two bands) in clause 5.5A.3.1. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223769 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
78 | Y | 38.521-1 | 6.2B | Transmitter power for NR-DC | New clause for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
79 | Y | 38.521-1 | 6.2B.0 | General | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
80 | Y | 38.521-1 | 6.2B.1 | UE maximum output power for NR-DC | Add requirement for DC_n48A-n70A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
81 | Y | 38.521-1 | 6.2B.2 | UE maximum output power reduction for NR-DC | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222311 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
82 | Y | 38.521-1 | 6.2B.3 | UE additional maximum output power reduction for NR-DC | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222312 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
83 | Y | 38.521-1 | 6.2B.4 | Configured output power for NR-DC | Add requirements to Configured transmitted power level for NR-DC and ΔTIB,c for NR-DC configuration DC_n48-n70 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222313 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
96 | Y | 38.521-1 | 6.3B.1 | Minimum output power for NR-DC | Add NR-DC Minimum output power in clause 6.3B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223756 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
97 | Y | 38.521-1 | 6.3B.2 | Transmit OFF power for NR-DC | Add NR-DC clause 6.3B.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223757 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
98 | Y | 38.521-1 | 6.3B.3 | Transmit ON/OFF time mask for NR-DC | Add NR-DC clause 6.3B.3 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223758 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
84 | Y | 38.521-1 | 6.3B | Output power dynamics for NR-DC | Add reference to requirements clause 6.3A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223756 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
99 | Y | 38.521-1 | 6.4B.1 | Frequency error for NR-DC | Add NR-DC Frequency error in clause 6.4B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223759 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
100 | Y | 38.521-1 | 6.4B.2 6.4B.2.1 | Transmit modulation quality for NR-DC | Add NR-DC clause 6.4B.2. Add NR-DC Error Vector Magnitude in clause 6.4B.2.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223760 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
101 | Y | 38.521-1 | 6.4B.2.2 | Carrier leakage for NR-DC | Add NR-DC clause 6.4B.2.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223761 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
102 | Y | 38.521-1 | 6.4B.2.3 | In-band emissions for NR-DC | Add NR-DC clause 6.4B.2.3 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223762 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
85 | Y | 38.521-1 | 6.4B | Transmit signal quality for NR-DC | Add refernce to requirements clause 6.4A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223759 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
103 | Y | 38.521-1 | 6.5B.1 | Output RF spectrum emissions for NR-DC | Add NR-DC Occupied bandwidth in clause 6.5B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223763 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
104 | Y | 38.521-1 | 6.5B.2 6.5B.2.2 | Out of band emission for NR-DC | Add NR-DC clause 6.5B.2. Add NR-DC Spectrum emission mask in clause 6.5B.2.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223764 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
105 | Y | 38.521-1 | 6.5B.2.4.1.0.3 6.5B.2.4.1.1 6.5B.2.4.2 | NR ACLR for Inter-band NR-DC NR ACLR for NR-DC UTRA ACLR | Add NR-DC clause 6.5B.2.4. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223765 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
106 | Y | 38.521-1 | 6.5B.3 | Spurious emission for NR-DC | Add NR-DC for clause 6.5B.3. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223766 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
107 | Y | 38.521-1 | 6.5B.4 | Transmit intermodulation for NR-DC | Add NR-DC for clause 6.5B.4. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223767 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
86 | Y | 38.521-1 | 6.5B | Output RF spectrum emissions for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223763 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100%
87 | Y | 38.521-1 | 7.3B | Reference sensitivity for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
88 | Y | 38.521-1 | 7.4B | Maximum input level for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
89 | Y | 38.521-1 | 7.5B | Adjacent channel selectivity for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
90 | Y | 38.521-1 | 7.6B | Blocking characteristics for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
91 | Y | 38.521-1 | 7.7B | Spurious response for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
92 | Y | 38.521-1 | 7.8B | Intermodulation characteristics for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
93 | Y | 38.521-1 | 7.9B | Spurious emissions for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements. | Nokia, Nokia Shanghai Bell, Ericsson | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
108 |  | 38.522 | 4.1.1 | RF conformance test cases | Add testcase applicability statements for the new test cases introduced for 38.521-1 | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
2 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | Nokia, Nokia Shanghai Bell, Ericsson | RAN5#97 (Nov-22) | R5-221296 |  | 0.1 | 3.3% | 6.7% | 0% |  |  | 20% | 0% | 0% | 0% | 0% | 0%
TS 38.533: RRM test cases
|  | 38.533 | 8.2.2 | E-UTRA – NR Inter-RAT Early Measurement Reporting | New sub-clause header
94 | Y | 38.533 | 8.2.2.1 | E-UTRA – NR Early Measurement Reporting for NR in FR1 | Test Purpose(s): Early measurements of E-UTRA serving cell and NR carrier at FR1, RSRP and RSRQ measurement accuracy. TS: 38.133 A.8.2.2.1, TS: 36.133 4.9.2.4, 9.11.1A, 9.11.2A, 9.1.2B and 9.1.5B | Ericsson | RAN5#96 (Aug-22) |  |  | 1 | 0% | [7 empty] | 0%
95 | Y | 38.533 | 8.2.2.2 | E-UTRA – NR Early Measurement Reporting for NR in FR2 | Test Purpose(s): Early measurements of E-UTRA serving cell and NR carrier at FR2, RSRP and RSRQ measurement accuracy. TS: 38.133 A.8.2.2.2, TS: 36.133 4.9.2.4, 9.11.1A, 9.11.2A, 9.1.2B and 9.1.5B | Ericsson | RAN5#96 (Aug-22) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
|  | 38.533 | 6.6.9 | Idle Mode CA/DC Measurements | New sub-clause header
75 | Y | 38.533 | 6.6.9.1 | NR SA FR1 SA Idle mode CA/DC measurement for FR1 | Test Purpose(s): Early measurements of NR serving cell and NR inter frequency carrier both at FR1, RSRP and RSRQ measurement accuracy. TS:38.133 4.4, 10.1.4B, 10.1.9B, A.6.6.9 | Ericsson | RAN5#96 (Aug-22) | R5-221301 |  | 1 | 5% | 5% |  |  |  | 5%
|  | 38.533 | 6.6.15 | Idle Mode inter-RAT CA/DC Measurements | New sub-clause header
76 | Y | 38.533 | 6.6.15.1 | NR SA FR1 Idle Mode measurements of inter-RAT CA candidate cells for early reporting | Test Purpose(s): Early measurement of NR serving cell at FR1 and inter RAT carrier, RSRP and RSRQ measurement accuracy. TS:38.133 4.4, 10.1.2B, 10.1.7B, 10.2.4, 10.2.5, A.6.6.15 | Ericsson | RAN5#96 (Aug-22) | R5-221302 |  | 1 | 5% | 5% |  |  |  | 5%
17 | Y | 38.533 | 7.7.1.X | NR SA FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRP absolute accuracy, intra frequency NR carriers at FR2 TS:38.133 4.4, 10.1.3B | Ericsson | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
18 | Y | 38.533 | 7.7.1.Y | NR SA FR2-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRP absolute accuracy, inter frequency NR carriers at FR2 TS:38.133 4.4, 10.1.5B | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
19 | Y | 38.533 | 7.7.1.3.X | NR SA FR1-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRP absolute accuracy, NR carriers at FR1 and FR2 TS:38.133 4.4, 10.1.5B | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
20 | Y | 38.533 | 7.7.2.X | NR SA FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRQ absolute accuracy, intra frequency NR carriers at FR2 TS:38.133 4.4, 10.1.8B | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
21 | Y | 38.533 | 7.7.2.Y | NR SA FR2-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRQ absolute accuracy, inter frequency NR carriers at FR2 TS:38.133 4.4, 10.1.10B | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
22 | Y | 38.533 | 7.7.2.Z | NR SA FR1-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRQ absolute accuracy, NR carriers at FR1 and FR2 IS THIS TEST NEEDED! | TBD | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
23 | Y | 38.533 | 4.5.3.X | EN-DC FR1 Direct SCell activation at SCell addition of known SCell | Test Purpose(s): MR-DC Direct SCell activation and interruption delay at SCell addition, NR carrier at FR1 TS: 38.133 8.2.1.2.8, 8.3.4 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
24 | Y | 38.533 | 5.5.3.X | EN-DC FR2 Direct SCell activation at SCell addition of known SCell | Test Purpose(s): MR-DC Direct SCell activation and interruption delay at SCell addition, NR carrier at FR2 TS: 38.133 8.2.1.2.8, 8.3.4 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
25 | Y | 38.533 | 6.5.3.X | NR SA FR1 Direct SCell activation at SCell addition of known SCell | Test Purpose(s): NR-NR Direct SCell activation and interruption delay at SCell addition, NR carriers at FR1 TS: 38.133 8.2.2.2.11, 8.3.4 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
68 | Y | 38.533 | 6.5.3.Y | NR SA FR1 Direct SCell activation at handover with known SCell | Test purpose(s): NR-NR Direct SCell activation and interruption delay at handover with known SCell, NR carriers at FR1 TS: 38.133 8.2.2.2.11, 8.3.5 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
26 | Y | 38.533 | 7.5.3.X | NR SA FR2 - FR2 Direct SCell activation at SCell addition of known SCell | Test Purpose(s): NR-NR Direct SCell activation and interruption delay at SCell addition, NR carriers at FR2 TS: 38.133 8.2.2.2.11, 8.3.4 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
69 | Y | 38.533 | 7.5.3.Y | NR SA FR2 - FR2 Direct SCell activation at handover with known SCell | Test Purpose(s): NR-NR Direct SCell activation and interruption delay at handover with known SCell, NR carriers at FR2 TS: 38.133 8.2.2.2.11, 8.3.4 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
27 | Y | 38.533 | 7.5.3.Z | NR SA FR1 - FR2 Direct SCell activation at SCell addition of known Scell | Test Purpose(s): NR-NR Direct SCell activation and interruption delay at Scell addition, NR carriers at FR1 and FR2 TS: 38.133 8.2.4.2.10, 8.3.9 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
70 | Y | 38.533 | 7.5.3.K | NR SA FR1 - FR2 Direct SCell activation at handover with known Scell | Test Purpose(s): NR-NR Direct SCell activation and interruption delay at handover with known SCell, NR carriers at FR1 and FR2. TS: 38.133 8.2.4.2.10, 8.3.9 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
28 | Y | 38.533 | 4.5.6.X | EN-DC FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): MR-DC SCell dormancy outside active time switching delay, NR carrier at FR1 TS: 38.133 8.6, 8.2.1.2.15 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
29 | Y | 38.533 | 4.5.6.Y | EN-DC FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR1 TS: 38.133 8.6.2, 8.2.1.2.15 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
30 | Y | 38.533 | 5.5.6.X | EN-DC FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR2 TS: 38.133 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
31 | Y | 38.533 | 5.5.6.Y | EN-DC FR1 PSCell SCell dormancy switch of two FR2 SCells inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR1 and FR2 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [7 empty] | 0%
32 | Y | 38.533 | 6.5.6.X | NR SA FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): NR-NR SCell dormancy outside active time switching delay, NR carriers at FR1 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
33 | Y | 38.533 | 6.5.6.Y | NR SA FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR1 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
34 | Y | 38.533 | 7.5.6.X | NR SA FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR2 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
35 | Y | 38.533 | 7.5.6.Y | NR SA FR1 PSCell SCell dormancy switch of two FR2 SCells outside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR1 and FR2 | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
55 |  | 38.903 | TBD | TBD | Define TT and MU for the RRM testcases | TBD | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Layer 2
36 | Y | 38.523-1 | 7.1.1.8.2 | Dormant Bandwidth Part (BWP) operation UL/DL | Test Purpose(s): SCell having dormant BWP, BWP switching | TBD | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.5.11 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0
37 | Y | 38.523-1 | 8.1.5.11.1 | Idle/Inactive Measurements / Idle mode / SIB11 configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through SIB11, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217952, R5-223407 |  | 1 | 60% | 60% |  |  |  | 60% | 60%
38 | Y | 38.523-1 | 8.1.5.11.2 | Idle/Inactive Measurements / Idle mode / RRCRelease configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through RRCRelease message, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217776, R5-223403 |  | 1 | 60% | 60% |  |  |  | 60% | 60%
39 | Y | 38.523-1 | 8.1.5.11.3 | Idle/Inactive Measurements / Inactive mode / SIB11 configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through SIB11, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222003, R5-223405 |  | 1 | 80% (-20%) | 80% (-20%) |  |  |  | 80% | 80%
40 | Y | 38.523-1 | 8.1.5.11.4 | Idle/Inactive Measurements / Inactive mode / RRCRelease configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through RRCRelease message, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222005, R5-223406 |  | 1 | 60% | 60% |  |  |  | 60% | 60%
|  | 38.523-1 | 8.2.6.3 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0
41 | Y | 38.523-1 | 8.2.6.3.1 | Idle/Inactive Measurements / Idle mode / EN-DC / SIB2 & SIB24 configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through LTE SIB2 and LTE SIB24. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#95 (May-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
42 | Y | 38.523-1 | 8.2.6.3.2 | Idle/Inactive Measurements / Idle mode / EN-DC / RRCConnectionRelease configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through RRCConnectionRelease. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#95 (May-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
73 | Y | 38.523-1 | 8.2.6.3.3 | Idle/Inactive Measurements / Inactive mode / NE-DC / SIB11 configuration | Test Purpose(s): NR-LTE Early measurement reporting, Inactive mode, Measurement configuration through SIB11, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222004 |  | 1 | 80% (-20%) |  |  | 80% (-20%) | [7 empty] | 80% | 80%
74 | Y | 38.523-1 | 8.2.6.3.4 | Idle/Inactive Measurements / Inactive mode / NE-DC / RRCRelease configuration | Test Purpose(s): NR-LTE Early measurement reporting, Inactive mode, Measurement configuration through RRCRelease message, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222006 |  | 1 | 80% (-20%) |  |  | 80% (-20%) | [7 empty] | 80% | 80%
71 | Y | 38.523-1 | 8.2.6.3.5 | Idle/Inactive measurements / Idle mode / NE-DC / SIB11 configuration | Test Purpose(s): NR-LTE Early measurement reporting, Idle mode, Measurement configuration through SIB11, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217775, R5-223402 |  | 1 | 60% |  |  | 60% | [7 empty] | 60% | 60%
72 | Y | 38.523-1 | 8.2.6.3.6 | Idle/Inactive measurements / Idle mode / NE-DC / RRCRelease configuration | Test Purpose(s): NR-LTE Early measurement reporting, Idle mode, Measurement configuration through RRCRelease message, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217777, R5-223404 |  | 1 | 60% |  |  | 60% | [7 empty] | 60% | 60%
43 | Y | 38.523-1 | 8.1.1.4.4 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214390 |  | 1 | 5% | 5% |  |  |  | 5% | 5%
64 | Y | 38.523-1 | 8.1.1.4.5 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band non-contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214391 |  | 1 | 5% | 5% |  |  |  | 5% | 5%
65 | Y | 38.523-1 | 8.1.1.4.6 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Inter-band carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214392 |  | 1 | 5% | 5% |  |  |  | 5% | 5% | 5%
44 | Y | 38.523-1 | 8.1.1.4.7 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214433 |  | 1 | 5% | 5% |  |  |  | 5%
66 | Y | 38.523-1 | 8.1.1.4.8 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214434 |  | 1 | 5% | 5% |  |  |  | 5%
67 | Y | 38.523-1 | 8.1.1.4.9 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214435 |  | 1 | 5% | 5% |  |  |  | 5%
|  | 38.523-1 | 8.2.7 | RRC resume | New sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0
|  | 38.523-1 | 8.2.7.1 | RRC resume / EN-DC | New sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0
45 | Y | 38.523-1 | 8.2.7.1.1 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Intra-band contiguous carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
56 | Y | 38.523-1 | 8.2.7.1.2 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Intra-band non-contiguous carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
57 | Y | 38.523-1 | 8.2.7.1.3 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Inter-band carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
46 | Y | 38.523-1 | 8.1.2.1.5.4 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
58 | Y | 38.523-1 | 8.1.2.1.5.5 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
59 | Y | 38.523-1 | 8.1.2.1.5.6 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
47 | Y | 38.523-1 | 8.2.4.1.2.1 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223497 |  | 1 | 95% (+95%) | 95% (+95%) |  |  |  | 95% | 95%
60 | Y | 38.523-1 | 8.2.4.1.2.2 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Intra-band non-contiguous CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223497 |  | 1 | 95% (+95%) | 95% (+95%) |  |  |  | 95% | 95%
61 | Y | 38.523-1 | 8.2.4.1.2.3 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#95 (May-22) | R5-223497 |  | 1 | 95% (+95%) | 95% (+95%) |  |  |  | 95% | 95% | 95%
48 | Y | 38.523-1 | 8.2.4.1.1.4 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
62 | Y | 38.523-1 | 8.2.4.1.1.5 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band non-contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
63 | Y | 38.523-1 | 8.2.4.1.1.6 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Inter-band carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
49 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-216333, R5-216334, R5-217953, R5-222002, R5-223408, R5-223409 |  | 0.1 | 37.5% (+4.4%) | 66.7% (+11.7%) | 0% | 50% |  | 50% | 50% | 100% | 0% | 0% | 0% | 50% | 50%
50 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-216333, R5-216334, R5-217953, R5-222002, R5-223408, R5-223409 |  | 0.1 | 44.4% (+6.9%) | 85% (+18.3%) | 0% | 50% |  | 75% | 80% | 100% | 0% | 0% | 0% | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
51 |  | 38.523-3 | TBD | TBD | Update test environment if necessary. | TBD | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.