## Cover sheet
3GPP TSG-RAN WG5 Meeting #95-e | [10 empty] | R5-222841
Electronic Meeting, 9th May- 20th May 2022
Agenda Item: | 6.3.24
Source: | Huawei, Hisilicon, CMCC
Title: | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Work item code: | NR_MBS_5MBS_5MBUSA-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
3GPP Rel-17 has specified the feature support of multicast and broadcast services (MBS) over 5GS. The objective of UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects work item is to provide conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. This work item will cover Protocol conformance test specifications with NR-MBS operation. At the RAN#95e meeting in March 2022 the Rel-17 RAN5 work item for UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+0%) | 0 | 7
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+0%) | 0 | 7
FR1 |  | 5.1% | 0 | 7
FR2 |  | 5% | 0 | 7
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 5% (+1.7%) |  |  | 10% |  |  | 0%
UE specific test functions | 38.509 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 7 | 0% | 0 | 7 | 0% | 0 | 7
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220423 | New WID on UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MBS_5MBS_5MBUSA-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-17, including CT aspects of NR MBS, Security Aspects of NR MBS, and RAN aspects of NR MBS. | [12 empty] | vs Area
WP Resp: |  | Zhao Ya(Huawei) |  |  | zhaoya@hisilicon.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 5.1% | 5%
[14 empty] | 24 | 24 | 0 (-24)
[14 empty] | 14 | 14 | 0 (-14)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3.6.1 | Downlink physical layer parameters for MBS test | To add Default configuration for DCI scheduling MBS, i.e. DCI format 4_0/4_1/4_2 | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
2 |  | 38.508-1 | 4.4.3.1.2 | SI combination for MBS test | To add SI combination for MBS test | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
3 |  | 38.508-1 | 4.4.3.1.2 | Scheduling of SIB20 and SIB21 for MBS test | To add Scheduling of SIB20 and SIB21 for MBS test | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
4 |  | 38.508-1 | 4.6.2 | System information blocks | To update SIBs related to MBS test, i.e. SIB20 and SIB21[Ref: 38.331 cl. 6.3.1] | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
5 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | To update RRC IEs related to MBS [Ref: 38.331 cl. 6.3.2] | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
6 |  | 38.508-1 | 4.6.X | MBS information elements | To add MBS ralated IEs used in RRC messages [Ref: 38.331 cl. 6.3.6] | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
7 |  | 38.508-1 | 4.7.2 | Contents of 5GSM messages | To Update MBS related parameters into 5GSM message | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
8 |  | 38.508-1 | 4.8.4 | DNN/APN configurations | To add DNN/APN configurations for the MBS | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
9 |  | 38.508-1 | 4.9 | Test procedures | To add test procedures for MBS test | Huawei,Hisilicon | RAN5#96 (Aug-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
10 |  | 38.508-2 | <Clause> | PICs for MBS testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in protocol test cases. | Huawei,Hisilicon | RAN5#96 (Aug-22) | R5-223105 |  | 0.1 | 5% (+1.7%) | 5% (+1.7%) |  | 10% | 0%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
11 |  | 38.509 | 5.2 | Test mode for MBS | To add test mode C related description | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
12 |  | 38.509 | 5.3 | Loop back function for MBS | To add Loop back mode C related description | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
13 |  | 38.509 | 5.9 | Test protocal procedure for MBS | To add paclet counter reporting procedure for MBS | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
14 |  | 38.509 | 6.9 | TMC message for MBS | To add TMC message used in MBS packet counter reporting procedure | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
15 |  | 38.509 | 7.1 | State variables for MBS | To add State variables for Loop back mode C and MBS packet counter | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 38.523-1 | 15 | MBS | New sub-clause header |  |  |  |  | 0
17 |  | 38.523-1 | 15.1 | MBS Broadcast | New sub-clause header |  |  |  |  | 0
18 |  | 38.523-1 | 15.1.1 | MBS Broadcast/ MCCH Information Acquisition | New sub-clause header |  |  |  |  | 0
19 | Y | 38.523-1 | 15.1.1.1 | MBS Broadcast/ MCCH Information Acquisition/ entering the cell providing SIB20 | TP1:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in switched off state and interested to receive MBS broadcast services. WHEN: UE is switched on and camped on a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception TP2:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_IDLE state and interested to receive MBS broadcast services. WHEN: UE reselects to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. TP3:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_INACTIVE state and interested to receive MBS broadcast services. WHEN: UE reselects to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. TP4:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_CONNECTED state and interested to receive MBS broadcast services. WHEN: UE handovers to a cell providing SIB20. THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
20 | Y | 38.523-1 | 15.1.1.2 | MBS Broadcast/ MCCH Information Acquisition/ becoming interested to receive MBS broadcast services | TP1:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_IDLE state and camped on a cell providing SIB20 WHEN: UE does not interest to receive MBS broadcast services THEN: UE does not acquire the MBSBroadcastConfiguration message TP2:[TS 38.331: 5.9.1.1,5.9.1.2, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC_IDLE state and camped on a cell providing SIB20 and did not interest to receive MBS broadcast services WHEN: UE is becomging interested to receive MBS broadcast services THEN: UE acquires the MBSBroadcastConfiguration message at the next repetition period and starts MBS reception. |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
21 | Y | 38.523-1 | 15.1.1.3 | MBS Broadcast/ MCCH Information Acquisition/ MCCH Information change notification | TP1:[TS 38.331: 5.9.1.1, 5.9.1.2, 5.9.1.3, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC IDLE state and camped on a cell providing SIB20 and interested to receive MBS broadcast services WHEN: UE is receiving a notification that the MCCH information has changed due to the start of new MBS service(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH from the slot in which the change notification was received TP2:[TS 38.331: 5.9.1.1, 5.9.1.2, 5.9.1.3, 5.9.2.2, 5.9.2.3,TS 38.300: 16.10.6.2] WITH: UE in NR RRC CONNECTED state and is receiving data via broadcast MRB WHEN:UE is receiving a notification that the MCCH information has changed due to MCCH information modification other than the change caused by the start of new MBS session(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH from the slot in which the change notification was received |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
22 |  | 38.523-1 | 15.1.2 | MBS Broadcast/ Service Continuity | New sub-clause header |  |  |  |  | 0
23 | Y | 38.523-1 | 15.1.2.1 | MBS Broadcast/ Service Continuity/ Cell reselection/ frequency prioritization | TP1:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC IDLE state and is receiving MBS data via broadcast MRB and camped on a cell providing SIB20 and SIB21 WHEN: SIB21 of the serving cell indicates a MBS FSAI in mbs-FSAI-IntraFreq-r17 and does not indicate any MBS FSAI in mbs-FSAI-InterFreq-r17 and the same MBS FSAI is also indicated for this MBS broadcast service in MBS User Service Description (USD) THEN: UE performs cell reselection to the intra-frequency cell even if the inter-frequency cell is better and continues MBS reception TP2:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC IDLE state and is receiving data via broadcast MRB and camped on a cell providing SIB20 and SIB21 WHEN: SIB21 of the serving cell does not indicate MBS FSAI in mbs-FSAI-IntraFreq-r17 and the frequency of an intra-frequency neighbour cell is indicated for this MBS broadcast service in MBS User Service Description (USD) THEN: UE performs cell reselection to the intra-frequency cell even if the inter-frequency cell is better and continues MBS reception TP3:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC IDLE state and is receiving data via broadcast MRB and camped on a cell providing SIB20 and not providing SIB21 WHEN: the frequency of inter-frequency neighbour cell x is indicated for this MBS broadcast service in MBS User Service Description (USD) and the frequency of inter-frequency neighbour cell y is not indicated for this MBS broadcast service in MBS User Service Description (USD) THEN: UE performs cell reselection to the inter-frequency neighbour cell x even if the inter-frequency cell y is better and continues MBS reception TP4:[TS 38.331: 5.2.2,TS 38.300: 16.10.6.5, TS 38.304: 5.2.4.1,TS 23.247 6.5.4] WITH: UE in NR RRC INACTIVE state and is receiving MBS data via broadcast MRB and camped on a cell providing SIB20 and SIB21 WHEN: SIB21 of the serving cell indicates a MBS FSAI in mbs-FSAI-IntraFreq-r17 and does not indicate any MBS FSAI in mbs-FSAI-InterFreq-r17 and the same MBS FSAI is also indicated for this MBS broadcast service in MBS User Service Description (USD) THEN: UE performs cell reselection to the intra-frequency cell even if the inter-frequency cell is better and continues MBS reception | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
24 | Y | 38.523-1 | 15.1.2.2 | MBS Broadcast/ Service Continuity/ Handover/ MBS Interest Indication | TP1:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC CONNECTED state and is receiving MBS data via broadcast MRB and has not transmitted a MBSInterestIndication message WHEN: SIB21 provided in the serving cell indicates that the MBS service is available on a frequency of an inter-frequency neighbour cell and this frequency is also indicated in the USD for this session THEN: UE transmits a MBSInterestIndication message indicating interest in MBS reception on the frequency TP2:[TS 38.331: 5.9.4,TS 38.300: 16.10.6.5.2] WITH: UE in NR RRC CONNECTED state and is receiving MBS data via broadcast MRB and has transmitted a MBSInterestIndication message WHEN: UE performs handover to a inter-frequency neighbour cell not broadcasting SIB21 followed by a handover back to the cell broadcasting SIB21 THEN: UE transmits a MBSInterestIndication message indicating interest in MBS reception on the frequency |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
25 |  | 38.523-1 | 15.1.3 | MBS Broadcast/ MAC | New sub-clause header |  |  |  |  | 0
26 | Y | 38.523-1 | 15.1.3.1 | MBS Broadcast/ MAC/ Correct HARQ process handling | TP1:[TS 38.321: 5.3.2.2] WITH: UE in NR RRC_IDLE state WHEN:UE receives data addressed to G-RNTI on broadcast MRB THEN: UE does not transmit the HARQ feedback for the MBS broadcast HARQ process TP2:[TS 38.321: 5.3.2.2] WITH: UE in NR RRC_IDLE state and is receiving data via broadcast MRB WHEN:UE receives a notification that the MCCH information has changed due to MCCH information modification other than the change caused by the start of new MBS session(s) THEN: UE starts acquiring the MBSBroadcastConfiguration message on MCCH and UE does not transimit the HARQ feedback for the MBS broadcast HARQ process |  | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
27 | Y | 38.523-1 | 15.1.3.2 | MBS Broadcast/ MAC/ DRX operation | TP1:[TS 38.321: 5.7a] WITH: UE in NR RRC_IDLE state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI TP2:[TS 38.321: 5.7a] WITH: UE in NR RRC_INACTIVE state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI TP3:[TS 38.321: 5.7a] WITH: UE in NR RRC_CONNECTED state and is receiving data via broadcast MRB. WHEN:Long DRX cycle for MBS Broadcast is configured for a G-RNTI and [(SFN × 10) + subframe number] modulo (drx-LongCycle-PTM) = drx-StartOffset-PTM THEN: UE starts the OnDurationTimerPTM and monitors the PDCCH for this G-RNTI | Huawei,Hisilicon | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
28 |  | 38.523-1 | 15.2 | MBS Multicast | FFS |  |  |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
29 |  | 38.523-2 | 4.1 | Applicability for MBS test cases | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#98 (Feb-27) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
30 |  | 38.523-2 | 4.2 | ICS for MBS test cases | Add test case applicability expressions for the new test cases introduced in 38.523-1 |  | RAN5#98 (Feb-27) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
31 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.