## Band combination table
Are there any change marks? (More explanation can be found in coversheet) | Band combination configuration | UpLink configuration | Power Class | Subclass | Contact Name | Contact Company | Contact Email | Other supporting companies (min.3) | RAN Plenary in which the combination was requested | Related WI (acronym) | Supported next level fallback modes including initial status when requesting (in DL and UL) | Status (New,Ongoing,Completed,Stopped) | TR# | TPs provided as input for TR | CRs provided to RAN: RAN4 Tdoc (list all specs input) | Core. part Done? (Including all fallback combos ) yes/no | Perf. part Done? yes/no | Open issues/Comments | Note
Unchange | DC_2A-13A-66A_n77A | DC_2A_n77A, DC_13A_n77A, DC_66A_n77A | PC2 | FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-66A_n77A_UL_2A_n77A, (Ongoing) DL_2A-13A_n77A_UL_2A_n77A, (Ongoing) DL_13A-66A_n77A_UL_13A_n77A, (Ongoing) DL_2A-13A_n77A_UL_13A_n77A, (Ongoing) DL_2A-66A_n77A_UL_66A_n77A, (Ongoing) DL_13A-66A_n77A_UL_66A_n77A | Ongoing
Unchange | DC_48D-66A_n77A | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (New) DL_48C-66A_n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A-66A_n5A-n77A | DC_66A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-66A_n77A_UL_66A_n77A (new) DL_66A_n5A-n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A_n5A-n77A | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (Completed) DL_2A-2A_n77A_UL_2A_n77A (new) DL_2A_n5A-n77A_UL_2A_n77A | Ongoing
Unchange | DC_13A-66A-66A_n2A-n77A | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_13A-66A-66A_n77A_UL_13A_n77A (new) DL_13A-66A-66A_n77A_UL_66A_n77A (New) DL_13A-66A_n2A-n77A_UL_13A_n77A (New) DL_13A-66A_n2A-n77A_UL_66A_n77A (New) DL_66A-66A_n2A-n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A-66A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-66A-66A_n77A_UL_2A_n77A (new) DL_2A-66A-66A_n77A_UL_66A_n77A (new) DL_2A-66A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_66A_n77A (new) DL_66A-66A_n5A-n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-2A-66A_n77A_UL_2A_n77A (new) DL_2A-2A-66A_n77A_UL_66A_n77A (New) DL_2A-2A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_2A_n77A | Ongoing
Unchange | DC_5A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_5A_n77A | Ongoing
Unchange | DC_13A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_13A_n77A | Ongoing
Unchange | DC_66A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_66A_n77A | Ongoing
Unchange | DC_13A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A-66A_n77A_UL_13A_n77A (Complete) DL_13A-66A_n77A_UL_66A_n77A (New) DL_13A_n77C_UL_13A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-66A_n77A_UL_2A_n77A (Complete) DL_2A-66A_n77A_UL_66A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-13A_n77A_UL_2A_n77A (Complete) DL_2A-13A_n77A_UL_13A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing
Unchange | DC_66A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A_n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-5A_n77A_UL_2A_n77A (Complete) DL_2A-5A_n77A_UL_5A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing
Unchange | DC_2A-48A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48A_n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing
Unchange | DC_48A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48A-66A_n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing
Unchange | DC_2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-13A-66A_n77A_UL_2A_n77A (Complete) DL_2A-13A-66A_n77A_UL_13A_n77A (Complete) DL_2A-13A-66A_n77A_UL_66A_n77A (New) DL_2A-13A_n77C_UL_2A-n77A (New) DL_2A-13A_n77C_UL_13A-n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_13A-66A_n77C_UL_13A-n77A (New) DL_13A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_13A-66A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_13A-66A-66A_n77A_UL_13A_n77A (Ongoing) DL_13A-66A-66A_n77A_UL_66A_n77A (New) DL_13A-66A_n77C_UL_13A-n77A (New) DL_13A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-5A-66A_n77A_UL_2A_n77A (Complete) DL_2A-5A-66A_n77A_UL_5A_n77A (Complete) DL_2A-5A-66A_n77A_UL_66A_n77A (New) DL_2A-5A_n77C_UL_2A-n77A (New) DL_2A-5A_n77C_UL_5A-n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_5A-66A_n77C_UL_5A-n77A (New) DL_5A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_5A-66A-66A_n77C | DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A-66A-66A_n77A_UL_5A_n77A (Ongoing) DL_5A-66A-66A_n77A_UL_66A_n77A (New) DL_5A-66A_n77C_UL_5A-n77A (New) DL_5A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_2A-2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-13A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-13A_n77A_UL_13A_n77A (New) DL_2A-13A_n77C_UL_2A-n77A (New) DL_2A-13A_n77C_UL_13A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing
Unchange | DC_2A-2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-66A_n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing
Unchange | DC_2A-2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-5A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-5A_n77A_UL_5A_n77A (New) DL_2A-5A_n77C_UL_2A-n77A (New) DL_2A-5A_n77C_UL_5A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing
Unchange | DC_66A-66A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A-66A_n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_2A-48C_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48C_n77A_UL_2A-n77A (New) DL_2A-48A_n77C_UL_2A-n77A | Ongoing
Unchange | DC_48C-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48C-66A_n77A_UL_66A-n77A (New) DL_48A-66A_n77C_UL_66A-n77A | Ongoing
Unchange | DC_2A-13A-66A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-13A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-13A-66A-66A_n77A_UL_13A_n77A (Ongoing) DL_2A-13A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-13A-66A_n77C_UL_2A_n77A (New) DL_2A-13A-66A_n77C_UL_13A_n77A (New) DL_2A-13A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A (New) DL_13A-66A-66A_n77C_UL_13A_n77A (New) DL_13A-66A-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-5A-66A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-5A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-5A-66A-66A_n77A_UL_5A_n77A (Ongoing) DL_2A-5A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-5A-66A_n77C_UL_2A_n77A (New) DL_2A-5A-66A_n77C_UL_5A_n77A (New) DL_2A-5A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A (New) DL_5A-66A-66A_n77C_UL_5A_n77A (New) DL_5A-66A-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-13A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-13A-66A_n77A_UL_13A_n77A (Ongoing) DL_2A-2A-13A-66A_n77A_UL_66A_n77A (New) DL_2A-13A-66A_n77C_UL_2A_n77A (New) DL_2A-13A-66A_n77C_UL_13A_n77A (New) DL_2A-13A-66A_n77C_UL_66A_n77A (New) DL_2A-2A-13A_n77C_UL_2A_n77A (New) DL_2A-2A-13A_n77C_UL_13A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-5A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-5A-66A_n77A_UL_5A_n77A (Ongoing) DL_2A-2A-5A-66A_n77A_UL_66A_n77A (New) DL_2A-5A-66A_n77C_UL_2A_n77A (New) DL_2A-5A-66A_n77C_UL_5A_n77A (New) DL_2A-5A-66A_n77C_UL_66A_n77A (New) DL_2A-2A-5A_n77C_UL_2A_n77A (New) DL_2A-2A-5A_n77C_UL_5A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-48D_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48D_n77A_UL_2A_n77A (New) DL_2A-48C_n77C_UL_2A_n77A | Ongoing
Unchange | DC_48D-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48D-66A_n77A_UL_66A_n77A (New) DL_48C-66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_13A_n2A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n2A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing
Unchange | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n66A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing
Unchange | DC_2A_n2A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A_n2A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing
Unchange | DC_5A_n2A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n2A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing
Unchange | DC_66A_n2A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A_n2A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A_n5A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A_n5A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing
Unchange | DC_5A_n5A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n5A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing
Unchange | DC_13A_n5A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_13A_n5A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing
Unchange | DC_66A_n5A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A_n5A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A_n66A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A_n66A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing
Unchange | DC_5A_n66A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n66A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing
Unchange | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n66A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing
Unchange | DC_66A_n66A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A_n66A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing
Unchange | DC_13A-66A_n2A-n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A-66A_n2A-n77A_UL_13A_n77A (Complete) DL_13A-66A_n2A-n77A_UL_66A_n77A (New) DL_13A-66A_n77C_UL_13A_n77A (New) DL_13A-66A_n77C_UL_66A_n77A (New) DL_13A_n2A-n77C_UL_13A_n77A (New) DL_66A_n2A-n77C_UL_66A_n77A | Ongoing
Unchange | DC_66A-66A_n2A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A_n2A-n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A_n77A (New) DL_66A_n2A-n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-66A_n5A-n77C | DC_66A_n77A DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-66A_n5A-n77A_UL_2A_n77A (Complete) DL_2A-66A_n5A-n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A_n77A (New) DL_2A-66A_n77C_UL_66A_n77A (New) DL_2A_n5A-n77C_UL_2A_n77A (New) DL_66A_n5A-n77C_UL_66A_n77A | Ongoing
Unchange | DC_66A-66A_n5A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A-66A_n5A-n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A_n77A (New) DL_66A_n5A-n77C_UL_66A_n77A | Ongoing
Unchange | DC_2A-2A_n5A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n5A-n77A_UL_2A_n77A (New) DL_2A-2A_n77C_UL_2A_n77A (New) DL_2A_n5A-n77C_UL_2A_n77A | Ongoing
Unchange | DC_2A-2A_n66A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n66A-n77A_UL_2A_n77A (New) DL_2A-2A_n77C_UL_2A_n77A (New) DL_2A_n66A-n77C_UL_2A_n77A | Ongoing
Unchange | DC_n78A-n258A/B/C/D/E/F/G/H/I/J/K/L/M | DC_n78A-n258A/G/H/I | PC2 | FR1+FR2 | Jeremy Chu | Telstra | jeremy.chu@team.telstra.com | LGE, Ericsson, Mediatek | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_n78A-n258A_UL_n78A-n258A_PC3 | Ongoing
Unchange | DC_2A-13A-48A_n77A | DC_2A_n77A DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (complete)DL_2A-13A_n77A_UL_2A_n77A, (new)DL_2A-48A_n77A_UL_2A_n77A, (complete)DL_2A-13A_n77A_UL_13A_n77A, (new)DL_13A-48A_n77A_UL_13A_n77A, | Ongoing
Unchange | DC_2A-48A-66A_n77A | DC_2A_n77A, DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (new)DL_2A-48A_n77A_UL_2A_n77A, (complete)DL_2A-66A_n77A_UL_2A_n77A, (complete)DL_2A-66A_n77A_UL_66A_n77A, (new)DL_48A-66A_n77A_UL_66A_n77A, | Ongoing
Unchange | DC_5A-66A-66A_n77A | DC_5A_n77A, DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (completed) DL_5A-66A_n77A_UL_5A_n77A, (completed) DL_5A-66A_n77A_UL_66A_n77A, (completed) DL_66A-66A_n77A_UL_66A_n77A | Ongoing
Unchange | DC_13A-48A_n77A | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (Completed) DL_13A_n77A_UL_13A_n77A | Ongoing
Unchange | DC_13A-48A-66A_n77A | DC_13A_n77A, DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (new)DL_13A-48A_n77A_UL_13A_n77A, (complete)DL_13A-66A_n77A_UL_13A_n77A, (complete)DL_13A-66A_n77A_UL_66A_n77A, (new)DL_48A-66A_n77A_UL_66A_n77A | Ongoing
Unchange | DC_2A-48A_n77A | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_2A_n77A_UL_2A_n77A | Ongoing
Unchange | DC_48A-66A_n77A | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_66A_n77A_UL_66A_n77A | Ongoing
New | DC_2A-5A_n77(2A) | DC_2A_n77A DC_5A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A-12A_n77(2A) | DC_2A_n77A DC_12A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A-14A_n77(2A) | DC_2A_n77A DC_14A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A-30A_n77(2A) | DC_2A_n77A DC_30A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A-66A_n77(2A) | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_5A-30A_n77(2A) | DC_5A_n77A DC_30A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_5A-66A_n77(2A) | DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_12A-30A_n77(2A) | DC_12A_n77A DC_30A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_12A-66A_n77(2A) | DC_12A_n77A DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_14A-30A_n77(2A) | DC_14A_n77A DC_30A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_14A-66A_n77(2A) | DC_14A_n77A DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_30A-66A_n77(2A) | DC_30A_n77A DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A_n77(2A) | DC_2A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_2A-2A_n77(2A) | DC_2A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_5A_n77(2A) | DC_5A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_12A_n77(2A) | DC_12A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_14A_n77(2A) | DC_14A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_30A_n77(2A) | DC_30A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_66A_n77(2A) | DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New
New | DC_66A-66A_n77(2A) | DC_66A_n77A | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Nokia, Qualcomm | RAN#96 | DC_R18_xBLTE_yBNR_zDLnUL | complete for PC3, new for PC2 | New