## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [10 empty] | R5-224603
Electronic Meeting, 15 - 26 Aug 2022
Agenda Item: | 7.4.2
Source: | Rapporteurs (China Mobile, CATT)
Title: | WP - UE Conformance - Enhancement of Network Slicing Phase 2
Work item code: | eNS_Ph2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
This work item covers the protocol conformance testing for Rel-17 enhancement of network slicing Phase 2.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 50% (+40%) | 6 (+6) | 13
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 50.1% (+40%) | 6 (+6) | 13
FR1 |  | 50.1% (+40%) | 6 (+6) | 13
FR2 |  | 50.1% (+40%) | 6 (+6) | 13
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 46.2% (+46.2%) | 6 (+6) | 13 | 46.2% (+46.2%) | 6 (+6) | 13 | 46.2% (+46.2%) | 6 (+6) | 13
Applicability Protocol test cases | 38.523-2 | 22.5% (+22.5%) |  |  | 22.5% (+22.5%) |  |  | 22.5% (+22.5%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-220621 | New WID - UE Conformance - Enhancement of Network Slicing Phase 2
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Enhancement of Network Slicing Phase 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eNS_Ph2-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-17 Enhancement of Network Slicing Phase 2 (UID-950065) | [12 empty] | vs Area
WP Resp: |  | Luting Kong, CMCC |  |  | kongluting@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 50.1% (+40%) | 50.1% (+40%)
[14 empty] | 17 | 17
[14 empty] | 14.8 | 14.8
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.7 | General and Signaling Test Environment for Rel-17 eNS phase2 testing | Add changes to default messages | CMCC | RAN5#96e (Aug-22) | R5-222460, R5-222461, R5-222462, R5-222463 | kongluting@chinamobile.com | 0.5 | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-17 eNS phase2 |  | CMCC | RAN5#96e (Aug-22) | R5-222459 | kongluting@chinamobile.com | 0.3 | 100% | 100% |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
3 |  | 38.523-1 | 9.1.12 | NSAC / Mobility management aspects | New sub-clause |  |  |  |  | 0
4 | Y | 38.523-1 | 9.1.12.1 | NSAC / Initial registration / Back-off timer | ****TP1: [TS 24,501: 5.5.1.2.2]**** WITH : UE in 5GMM-DEREGISTERED state WHEN: UE is switched on THEN: UE transmits REGISTRATION REQUEST message with ER-NSSAI bit set to "Extended rejected NSSAI supported" in the 5GMM capability IE ****TP2: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives the rejected NSSAI in the REGISTRATION ACCEPT message with the rejection cause of "S-NSSAI not available due to maximum number of UEs reached" and the back-off timer value received along with the S-NSSAI is not zero THEN: UE shall stores the rejected NSSAI and start the timer T3526 ****TP3: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED state and UE stores one or more S-NSSAIs in the rejected NSSAI with the rejection cause "S-NSSAI not available due to maximum number of UEs reached" WHEN: The timer T3526 associated with the S-NSSAI expires THEN: UE remove the S-NSSAI from the rejected NSSAI for the maximum number of UEs reached ****TP4: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED state and UE stores one or more S-NSSAIs in the rejected NSSAI with the rejection cause "S-NSSAI not available due to maximum number of UEs reached" WHEN: UE is switched off THEN: UE remove the S-NSSAI from the rejected NSSAI for the maximum number of UEs reached | CMCC | RAN5#97 (Nov-22) | R5-225338 | kongluting@chinamobile.com | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
5 | Y | 38.523-1 | 9.1.12.2 | NSAC / Initial registration / Back-off timer is not provided or zero | ****TP1: [TS 24,501: 5.5.1.2.4, 10,2]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives the rejected NSSAI in the REGISTRATION ACCEPT message with the rejection cause of "S-NSSAI not available due to maximum number of UEs reached" and the back-off timer value is not provided THEN: UE shall start the timer T3526 with an implementation specific value with minimum 12 minuts ****TP2: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives the rejected NSSAI in the REGISTRATION ACCEPT message with the rejection cause of "S-NSSAI not available due to maximum number of UEs reached" and the back-off timer value received along with the S-NSSAI is zero THEN: UE does not consider the S-NSSAI as the rejected S-NSSAI | CMCC | RAN5#97 (Nov-22) | R5-225339 | kongluting@chinamobile.com | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
6 | Y | 38.523-1 | 9.1.12.3 | NSAC / Initial registration / Rejected / equivalent PLMNs | ****TP1: [TS 24,501: 5.5.1.2.5]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives the rejected NSSAI in the REGISTRATION REJECT message with rejection cause of “S-NSSAI not available due to maximum number of UEs reached” THEN: UE shall stores the rejected NSSAI and start the timer T3526 ****TP2: [TS 24,501: 4.6.1, 5.5.1.2.5]**** WITH: UE receives rejected NSSAI with rejection cause of “S-NSSAI not available due to maximum number of UEs reached” WHEN: UE selectes to the equivalent PLMN in the same registration area THEN: UE shall treat the received rejected NSSAI for the maximum number of UEs reached as applicable to equivalent PLMNs | Lenovo/Motorola Mobility | RAN5#97 (Nov-22) | R5-225340 | rasheed@motorola.com | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
7 | Y | 38.523-1 | 9.1.12.4 | NSAC / Generic UE configuration update / Rejected NSSAI | ****TP1: [TS 24,501: 5.4.4.3]**** WITH: UE in 5GMM-REGISTERED state and stores one or more S-NSSAIs in the allowed NSSAI WHEN: UE receives the rejected NSSAI containing S-NSSAI(s) which are in UE allowed NSSAI list in the CONFIGURATION UPDATE COMMAND message with the rejection cause of "S-NSSAI not available due to maximum number of UEs reached" and the back-off timer value received along with the S-NSSAI is not zero THEN: UE shall add the rejected S-NSSAI(s) in the rejected NSSAI and start the timer T3526 ****TP2: [TS 24,501: 5.4.4.3]**** WITH: UE in 5GMM-REGISTERED state and UE stores one or more S-NSSAIs in the rejected NSSAI with the rejection cause "S-NSSAI not available due to maximum number of UEs reached" WHEN: The timer T3526 associated with the S-NSSAI expires THEN: UE remove the S-NSSAI from the rejected NSSAI for the maximum number of UEs reached | Lenovo/Motorola Mobility | RAN5#97 (Nov-22) |  | rasheed@motorola.com | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 9.1.12.5 | NSAC / De-registration / 5GMM cause value #62 and rejected NSSAI | ****TP1: [TS 24,501: 5.5.2.3.1, 5.5.2.3.2]**** WITH: UE in 5GMM-REGISTERED state and stores one or more S-NSSAIs in the allowed NSSAI WHEN: UE receives a DEREGISTRATION REQUEST message including 5GMM cause value #62 and rejected NSSAI with rejection cause "S-NSSAI not available due to maximum number of UEs reached" THEN: UE shall stores the rejected NSSAI and start the timer T3526 ****TP2: [TS 24,501: 5.5.2.3.1, 5.5.2.3.2]**** WITH: UE in 5GMM-DEREGISTERED state WHEN: UE has neither allowed NSSAI nor configured NSSAI and has rejected NSSAI for the reached maximum number of UEs THEN: UE stays in the current serving cell and attempt to use the rejected S-NSSAI(s) for the maximum number of UEs reached in the current serving cell after the rejected S-NSSAI(s) are removed | Lenovo/Motorola Mobility | RAN5#97 (Nov-22) |  | rasheed@motorola.com | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 9.3.1.4 | NSAC / interworking with EPC | ****TP1: [TS 24,501: 4.6.1]**** WITH: UE stores one or more rejected S-NSSAIs for the maximum number of UEs reached and T3526 is running WHEN: UE selects an E-UTRA cell connected to EPC. THEN:UE shall not stop the timer T3526 ****TP2: [TS 24,501: 4.6.2.2]**** WITH: UE stores one or more rejected S-NSSAIs for the maximum number of UEs reached and T3526 is running WHEN: UE receive ACTIVATE DEFAULT EPS BEARER CONTEXT REQUEST message provided with S-NSSAI and the PLMN ID in E-UTRA cell connected to EPC THEN: UE removes the S-NSSAI from the rejected NSSAI for the maximum number of UEs reached and stop the timer T3526 associated with the S-NSSAI | ZTE | RAN5#97 (Nov-22) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
10 |  | 38.523-1 | 9.1.13 | NSSRG | New sub-clause |  |  |  |  | 0
11 | Y | 38.523-1 | 9.1.13.1 | NSSRG / Initial registration | ****TP1: [TS 24,501: 5.5.1.2.2]**** WITH : UE in 5GMM-DEREGISTERED state WHEN: UE is switched on THEN: UE transmits REGISTRATION REQUEST message with NSSRG bit set to "NSSRG supported" in the 5GMM capability IE ****TP2: [TS 24,501: 5.5.1.2.2]**** WITH : UE has received configured NSSAI and the NSSRG information WHEN: UE needs to initiate registration procedure THEN: UE sends REGISTRATION REQUEST message with requested NSSAI which are associated with common NSSRG value | CMCC | RAN5#97 (Nov-22) |  | kongluting@chinamobile.com | 1 | 0% | 0% |  | 0% | 0%
12 | Y | 38.523-1 | 9.1.13.2 | NSSRG / Generic UE configuration update | ****TP1: [TS 24,501: 5.5.1.2.2]**** WITH : UE has received configured NSSAI WHEN: UE receives new configured NSSAI in the CONFIGURATION UPDATE COMMAND message with NSSRG information THEN: UE stores the new configured NSSAI and the NSSRG information | ZTE | RAN5#97 (Nov-22) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
13 |  | 38.523-1 | 10.1.8 | NSAC / Session management aspects | New sub-clause |  |  |  |  | 0
14 | Y | 38.523-1 | 10.1.8.1 | NASC / PDU session establishment reject / Maximum number of PDU sessions reached / Back-off timer is neither zero nor deactivated | ****TP1: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is neither zero nor deactivated THEN:UE shall start timer T3585 and shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI ****TP2: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: The timer T3585 associated with a S-NSSAI is running WHEN: UE is switched off and switched on THEN: UE shall restart the timer T3585 if the time remainning for T3585 timeout at switch off is greater than the time elapsed betweeen switch off and switch on ****TP3: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE in 5GMM-REGISTERED state WHEN: The timer T3585 associated with the S-NSSAI expires THEN: UE could initiate PDU session establishenment request with the S-NSSAI ****TP3: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with no S-NSSAI provided WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is neither zero nor deactivated THEN:UE shall start timer T3585 and shall not send another PDU SESSION ESTABLISHMENT REQUEST message without an S-NSSAI | CATT | RAN5#97 (Nov-22) | R5-225335 | chenxiaozhong@catt.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
15 | Y | 38.523-1 | 10.1.8.2 | NASC / PDU session establishment reject / Maximum number of PDU sessions reached / Back-off timer is deactivated | ****TP1: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is deactivated THEN:UE shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI until UE is switched off ****TP2: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is deactivated THEN:UE shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI until UE receives a PDU SESSION MODIFICATION COMMAND message for the same S-NSSAI ****TP3: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is deactivated THEN:UE shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI until UE receives a PDU SESSION AUTHENTICATION COMMAND message for the same S-NSSAI ****TP4: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is deactivated THEN:UE shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI until UE receives a PDU SESSION RELEASE COMMAND message without the Back-off timer value IE for the same S-NSSAI ****TP5: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with no S-NSSAI provided WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value which is deactivated THEN:UE shall not send another PDU SESSION ESTABLISHMENT REQUEST message without an S-NSSAI until the USIM is removed | CATT | RAN5#97 (Nov-22) | R5-225336 | chenxiaozhong@catt.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
16 | Y | 38.523-1 | 10.1.8.3 | NASC / PDU session establishment reject / Maximum number of PDU sessions reached / Back-off timer is zero or not included | ****TP1: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value set to zero THEN:UE could send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI ****TP2: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with no S-NSSAI provided WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value set to zero THEN:UE could send another PDU SESSION ESTABLISHMENT REQUEST message without an S-NSSAI ****TP3: [TS 24,501: 4.6.3.1, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value IE is not included THEN:UE could send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI | CATT | RAN5#97 (Nov-22) | R5-225337 | chenxiaozhong@catt.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
17 | Y | 38.523-1 | 10.1.8.4 | NASC / 5GSM message not forwarded / Back-off timer | ****TP1: [TS 24,501: 5.5.5.3.2, 6.4.1.4.2]**** WITH: UE is establishing UE-requested PDU session by sending PDU Session establishment Request message with S-NSSAI WHEN: UE receives DL NAS TRANSPORT with Payload container type set to "N1 SM information", Payload container set to the 5GSM message which was not forwarded, 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value THEN:UE shall start timer T3585 and shall not send another PDU SESSION ESTABLISHMENT REQUEST message for the same S-NSSAI until T3585 expires | ZTE | RAN5#97 (Nov-22) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
18 | Y | 38.523-1 | 10.1.8.5 | NASC / Maximum number of PDU sessions reached / Emergency service | ****TP1: [TS 24,501: 6.4.1.4.2]**** WITH: UE has received PDU SESSION ESTABLISHMENT REJECT with 5GSM cause value #69 "insufficient resources for specific slice" and Back-off timer value WHEN: The timer T3585 is running and the UE needs to initial PDU session establishment for emergency services THEN:UE starts emergency PDU session establishment procedure | ZTE | RAN5#97 (Nov-22) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | CMCC | RAN5#97 (Nov-22) | R5-225341, R5-224590 | kongluting@chinamobile.com | 0.5 | 45% (+45%) | 45% (+45%) |  | 45% | 45%
20 |  | 38.523-2 | 4.2 | <Title> | Add Applicability Condition for new eNS phase2 test cases | CMCC | RAN5#96e (Aug-22) |  | kongluting@chinamobile.com | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.