## Cover sheet
3GPP TSG-RAN WG5 Meeting #98 | [10 empty] | R5-230371
Athens, Greece, Feb 27th - Mar 3rd, 2023
Agenda Item: | 7.4.2
Source: | CMCC
Title: | UE Conformance - Enhancement of data collection for SON/MDT in NR standalone and MR-DC
Work item code: | NR_ENDC_SON_MDT_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
This work item covers the protocol conformance testing for Rel-17 enhancement of data collection for SON/MDT in NR SA (standalone) and MR-DC (EN-DC, NE-DC, NR-DC)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 31% (+15%) | 2 (+1) | 11
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
Option 2 (SA NR) |  | 31.2% (+15.3%) | 2 (+1) | 11
FR1 |  | 31.2% (+15.3%) | 2 (+1) | 11
FR2 |  | 31.2% (+15.3%) | 2 (+1) | 11
FR1 + FR2
Option 3 (EN-DC)
FR1
FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | Option 2 (SA NR) | [8 empty] | Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 70% |  |  | 70% |  |  | 70%
Common ICS | 38.508-2
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 25.5% (+16.4%) | 2 (+1) | 11 | 25.5% (+16.4%) | 2 (+1) | 11 | 25.5% (+16.4%) | 2 (+1) | 11
Applicability Protocol test cases | 38.523-2 | 40% (+40%) |  |  | 40% (+40%) |  |  | 40% (+40%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221365 | UE Conformance - Enhancement of data collection for SON and MDT in NR SA and MR-DC
[2] RP-223069 | Revised WID on UE Conformance - Enhancement of data collection for SON and MDT in NR SA and MR-DC
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Enhancement of data collection for SON/MDT in NR standalone and MR-DC | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_ENDC_SON_MDT_enh-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-17 enhancement of data collection for SON/MDT in NR SA and MR-DC (UID-950064) | [13 empty] | vs Area
WP Resp: |  | Danni Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | Option 2 (SA NR) |  |  | Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | Option 2 (SA NR) | Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2
[15 empty] | 31.2% (+15.3%) | 31.2% (+15.3%)
[15 empty] | 15 | 15 | 0 | 0 | 0
[15 empty] | 11.7 | 11.7 | 0 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6 | RRC default messages | Add Rel-17 MDT/SON changes to default messages if needed | CMCC | RAN5#99 (May-23) | R5-225333, R5-227544 | hanaitong@chinamobile.com | 0.5 | 70% | 70% |  |  | 70% | 70%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | <Clause> | Additional information | Add ICS as needed for the test case applicability statements for the new test cases introduced in protocol test cases. | CMCC | RAN5#99 (May-23) | R5-231441, R5-231558 | hanaitong@chinamobile.com | TBD | 40% (+40%) | 40% (+40%) |  |  | 40% | 40%
RAN and CN protocol
TS 38.523-1: Protocol test cases
RRC
3 |  | 38.523-1 | 8.1.6.1.2 | Logged MDT | [5 empty] | 0
4 | Y | 38.523-1 | 8.1.6.1.2.14 | Logged MDT / RRC_IDLE / Logging and reporting / IDC mechanism | NR MDT support IDC mechanism, including: - upon detection of IDC, the UE suppress logging and tag MDT report with InDeviceCoexDetected flag. - UE resumes the measurement logging when the IDC problem is resolved | CMCC | RAN5#99 (May-23) | R5-227543 | hanaitong@chinamobile.com； How to generate/stop IDC problems in the UE is FFS | 1 | 80% (-20%) | 80% (-20%) |  |  | 80% | 80%
5 | Y | 38.523-1 | 8.1.6.1.2.15 | Logged MDT / RRC_IDLE / early measurements | When earlyMeasIndication-r17 is configured in loggedMeasurementConfiguration, UE is allowed to log measurements on early measurement frequencies in logged MDT; − When earlyMeasIndication-r17 is not configured in loggedMeasurementConfiguration, UE shall not log measurements on early measurement frequencies in logged MDT. | CMCC | RAN5#99 (May-23) | R5-230377 | hanaitong@chinamobile.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
6 | Y | 38.523-1 | 8.1.6.1.2.16 | Logged MDT / RRC_IDLE / sig-based logged MDT | If the UE has logged measurements available for NR and if the RPLMN is included in plmn-IdentityList stored in VarLogMeasReport: if the sigLoggedMeasType in VarLogMeasReport is included: UE include the sigLogMeasConfigAvailable in the RRCSetupComplete message; | CMCC | RAN5#99 (May-23) |  | hanaitong@chinamobile.com | 1 | 0% | 0% |  |  | 0% | 0%
7 |  | 38.523-1 | 8.1.6.1.3 | Radio Link Failure report | [5 empty] | 0
8 | Y | 38.523-1 | 8.1.6.1.3.8 | Radio Link Failure / Logging and reporting / Event A3 / CHO | For each neighbour cell, if any, included in measResultListNR in measResultNeighCells:if the neighbour cell is one of the candidate cells for which the reconfigurationWithSync is included in the masterCellGroup in VarConditionalReconfig at the moment of the detected failure: UE set choConfig in MeasResult2NR to the execution condition for each measId within condTriggerConfig associated to the neighbour cell within VarConditionalReconfig; if at least one execution condition included in choConfig in MeasResult2NR was fulfilled at the moment of conditional reconfiguration execution, or radio link failure: if the first entry of choConfig corresponds to a fullfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set condFirstEventFullfilled to true; if the second entry of choConfig, if available, corresponds to a fullfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set condSecondEventFullfilled to true; if the first entry of choConfig corresponds to a fulfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure; and if the second entry of choConfig, if available, corresponds to a fulfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set firstTriggeredEvent to the execution condition condFirstEvent corresponding to the first entry of choConfig or to the execution condition condSecondEvent corresponding to the second entry of choConfig, whichever execution condition was fulfilled first in time; UE set timeBetweenEvents to the elapsed time between the point in time of fullfilling the condition in choConfig that was fulfilled first in time, and the point in time of fullfilling the condition in choConfig that was fulfilled second in time; | ZTE | RAN5#99 (May-23) |  | Ma Wei <ma.wei4@zte.com.cn> | 1 | 0% | 0% |  |  | 0% | 0%
9 | Y | 38.523-1 | 8.1.6.1.3.9 | Radio Link Failure / Logging and reporting / Event A5 / CHO | For each neighbour cell, if any, included in measResultListNR in measResultNeighCells: if the neighbour cell is one of the candidate cells for which the reconfigurationWithSync is included in the masterCellGroup in VarConditionalReconfig at the moment of the detected failure: UE set choConfig in MeasResult2NR to the execution condition for each measId within condTriggerConfig associated to the neighbour cell within VarConditionalReconfig; if at least one execution condition included in choConfig in MeasResult2NR was fulfilled at the moment of conditional reconfiguration execution, or radio link failure: if the first entry of choConfig corresponds to a fullfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set condFirstEventFullfilled to true; if the second entry of choConfig, if available, corresponds to a fullfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set condSecondEventFullfilled to true; if the first entry of choConfig corresponds to a fulfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure; and if the second entry of choConfig, if available, corresponds to a fulfilled execution condition at the moment of conditional reconfiguration execution, or radio link failure: UE set firstTriggeredEvent to the execution condition condFirstEvent corresponding to the first entry of choConfig or to the execution condition condSecondEvent corresponding to the second entry of choConfig, whichever execution condition was fulfilled first in time; UE set timeBetweenEvents to the elapsed time between the point in time of fullfilling the condition in choConfig that was fulfilled first in time, and the point in time of fullfilling the condition in choConfig that was fulfilled second in time; | ZTE | RAN5#99 (May-23) |  | Ma Wei <ma.wei4@zte.com.cn> | 1 | 0% | 0% |  |  | 0% | 0%
10 | Y | 38.523-1 | 8.1.6.1.3.10 | Radio Link Failure / Logging and reporting / DAPS HO | If the failure is detected due to reconfiguration with sync failure as described in 5.3.5.8.3, set the fields in VarRLF-report as follows: UE set the connectionFailureType to hof; if any DAPS bearer was configured while T304 was running: UE set dapsHOF to true: if radio link failure was detected in the source PCell, according to subclause 5.3.10.3: UE set rlfInSource-DAPS to true; UE set timeConnSourceDAPSFailure to the time between the initiation of the DAPS handover execution and the radio link failure detected in the source PCell while T304 was running; UE set the rlf-Cause to the trigger for detecting the source radio link failure in accordance with clause 5.3.10.4; | ZTE | RAN5#99 (May-23) |  | Ma Wei <ma.wei4@zte.com.cn> | 1 | 0% | 0% |  |  | 0% | 0%
11 | Y | 38.523-1 | 8.1.6.1.3.11 | Radio Link Failure / Logging and reporting / Successful Handovers Reports | If the UE has successful handover information available in VarSuccessHO-Report: UE include successHO-InfoAvailable in the RRCReestablishmentComplete message; | ZTE | RAN5#99 (May-23) |  | Ma Wei <ma.wei4@zte.com.cn> | 1 | 0% | 0% |  |  | 0% | 0%
12 |  | 38.523-1 | 8.1.6.1.4 | Connection Establishment Failure | [5 empty] | 0
13 | Y | 38.523-1 | 8.1.6.1.4.9 | Connection Establishment Failure / Logging and reporting / T300 expiry / Multiple CEF reports | If timer T300 expires: if the UE supports multiple CEF report, append the VarConnEstFailReport as a new entry in the VarConnEstFailReportList; | Qualcomm | RAN5#99 (May-23) | R5-231442 | Yogesh Tugnawat<yogesht@qti.qualcomm.com> | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
14 |  | 38.523-1 | 8.1.6.4 | SON / RACH Optimisation | [5 empty] | 0
15 | Y | 38.523-1 | 8.1.6.4.2 | SON / RACH logging and reporting / logging of on-demand SI | If the purpose of the random access procedure is to request on-demand system information (i.e., if the raPurpose is set to requestForOtherSI or msg3RequestForOtherSI), UE set the intendedSIBs to indicate the SIB(s) the UE wanted to receive as a result of the SI request; UE set the ssbsForSI-Acquisition to indicate the SSB(s) used to receive the SI message; | Lenovo/Motorola Mobility | RAN5#99 (May-23) |  | Abdul Rasheed M D<rasheed@motorola.com> | 1 | 0% | 0% |  |  | 0% | 0%
16 | Y | 38.523-1 | 8.1.6.4.3 | SON / RACH logging and reporting / 2-step RACH report | If contention based random-access resources are used in the random-access procedure: set the msgA-RO-FrequencyStart and msgA-RO-FDM associated to the 2 step random-access resources if used in the random-access procedure; if msgA-SubcarrierSpacing associated to the 2 step random-access resources used in the random-access procedure is available: set the msgA-SubcarrierSpacing associated to the 2 step random-access resources used in the random-access procedure; | Lenovo/Motorola Mobility | RAN5#99 (May-23) |  | Abdul Rasheed M D<rasheed@motorola.com> | 1 | 0% | 0% |  |  | 0% | 0%
17 | Y | 38.523-1 | 8.1.6.4.4 | SON / RACH logging and reporting / fallback to 4-step RA | If the random-access attempt is performed on the contention based random-access resource, the fallback from 2 step RA to 4 step RA was performed by the UE, the an indication fallbackToFourStepRA included in RA report. | Lenovo/Motorola Mobility | RAN5#99 (May-23) |  | Abdul Rasheed M D<rasheed@motorola.com> | 1 | 0% | 0% |  |  | 0% | 0%
MR-DC
18 | Y | 38.523-1 | FFS | FFS | Placeholder for SON/MDT in MR-DC tets case(s) |  | RAN5#99 (May-23) |  |  | 0
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | CMCC | RAN5#99 (May-23) | R5-231443, R5-231559 | hanaitong@chinamobile.com | 0.1 | 40% (+40%) | 40% (+40%) |  |  | 40% | 40%
20 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add Applicability Condition for new test cases | CMCC | RAN5#99 (May-23) | R5-231443, R5-231559 | hanaitong@chinamobile.com | 0.1 | 40% (+40%) | 40% (+40%) |  |  | 40% | 40%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.