3GPP TSG RAN meeting #99									               RP-230422

Rotterdam, NL, 20th – 23rd March 2023

## Status Report to TSG

Agenda item:	9.4.3.4

| WI / SI Name | Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_CADC_R18_yBDL_xBUL |  |  |  |  |
| Unique ID | 961008 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-223438 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: N/A | Core part: 12/2023 | Performance part: 12/2023 | Testing part: N/A |  |
| Overall Completion level | Study Item: | Core part: 51% | Performance Part: 51% | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN WG4 |
| --- | --- | --- |
| Rapporteur | Name | Reihaneh Malekafzaliardakani |
|  | Company | Ericsson |
|  | Email | reihaneh.malekafzaliardakani@ericsson.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

## 2.4	RAN4

See attached excel document and documents in clause 4.

.

## 4.	References

RAN#99:

RP-230421	Revised WID on Rel-18 NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

RP-230422	SR for WI on NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

RAN4#106:

R4-2301498	Revised WID on Rel-18 NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

R4-2301499	Big CR 38.101-1 to introduce new combinations NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

R4-2301500	Big CR 38.101-3 to introduce new combinations NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

RAN#98e:

RP-223438	Revised Rel-18 WID on NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson

RP-222911	SR for WI on NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2), Ericsson