3GPP TSG-RAN WG2 Meeting #107bis	R2-1912811

Chongqing, China, 14-18 October 2019

Agenda Item:	6.5.1

Source: 	MediaTek Inc., CATT

Title:  	Work plan for RACS-RAN work item

Document for:	Discussion

# Introduction

This document presents a work plan for the RACS-RAN work item described in [1].

# Discussion

| Meeting | TUs | Activity | Meeting status |
| --- | --- | --- | --- |
| RAN2#105bis | 0.5 | - Decide approach to UE capability ID in RRC signalling - Initial discussion on filtering - Initial discussion on segmentation approach | - Responded to SA2 (R2-1905466) indicating a preference for the NAS solution, and explaining some aspects of filtering from RAN2 perspective - Reached initial agreements on segmentation approach |
| RAN3#103bis | 0 |  | - Responded to SA2 (R3-192183) indicating the NAS approach could likely be implemented with limited effort. |
| RAN2#106 | 0.5 | - Decide handling of capability ID in RRC signalling - Resolve any issues on filtering - Further details of segmentation | - Reached initial agreements on manufacturer-specific ID and its relation to filtering - Email discussion on further aspects of filtering - Agreed to segment only the UECapabilityInformation message - Agreed to the fields for each message segment, and to have a new uplink message type for the segment |
| RAN3#104 | 0 |  | - No discussion |
| RAN2#107 | 0.5 | - Start drafting work on stage 2 CRs for EPS and 5GS - Decide support of delta signalling - Agree final aspects of filtering based on the email discussion | - Established RAN2 understanding of a single capability ID in NAS signalling and maintained in the network - Determined not to capture the NAS signalling flow for capability ID provisioning at stage 2 level - Confirmed that the UE does not associate capability ID with the filter used during capability enquiry - Determined that capability ID will not be added to the UE capability enquiry procedure in RRC signalling - Established RAN2 understanding that the UE may have more than one manufacturer-assigned ID for different internal UE configurations - Confirmed working assumption from RAN2#106 that there is no interleaving of different RRC messages between segments - Determined that segmentation is also adopted for LTE on the same principles as NR - LS sent to SA2 to inform them of RAN2 decisions and clarify UE behaviour with multiple PLMN-assigned IDs - Draft CR on segmentation endorsed as running CR |
| RAN3#105 | 0 |  | - Rely on company coordination to monitor the work in RAN2 - Rapporteur can coordinate offline discussion - Work is on a “best effort” basis until RAN3#107 |
| RAN2#107bis | 0.5 | - Conclude stage 2 CRs - Start drafting work on stage 3 CRs - Take a final decision on support of delta signalling |  |
| RAN2#108 | 0.5 | - Develop stage 3 CRs to a mature state - Resolve leftover issues from previous meetings - Finalise delta signalling if applicable |  |
| RAN2#109 | 0.5 | - Resolve any last-minute leftover issues - Final approval of stage 2 and 3 CRs |  |
| RAN3#107 | 1 | - Discuss the RAN3 impact for UE radio capability signalling - Discuss and final approval of stage 2 and 3 CRs |  |

# References

[1]	RP-191088, “Updated WID: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects”, MediaTek Inc./CATT, RAN#84