3GPP TSG-RAN WG2 Meeting #107bis	R2-1912841

Chongqing,  China, 14 – 18 October 2019	R2-1909112

Agenda item:	6.18.1

Source:	Nokia, China Telecom (Rapporteurs)

Title:	NPN Work Plan

WID/SID:	NG_RAN_PRN - Release 15

Document for:	Discussion and Decision

# 1	Introduction

A new work item on Non-Public Networks (NPN) was approved for Rel-16 at RAN#84 [RP-191563]. This contribution summarises the agreed objectives, time budget and suggests a plan to carry out the work in RAN2. It is an update from the last meeting to reflect the latest progress.

# 2	Work Item

The agreed work item lists the following objectives for RAN2:

-	CAG/SNPN relevant parameter broadcast from SIB;

-	CAG/SNPN cell selection/reselection;

-	CAG/SNPN cell access control;

-	For CAG, in the case of Intra-RAT intra-system and inter-RAT intra-system, the connected mode mobility support;

-	The connected mode mobility support within SNPN.

It should be noted that:

-	The work is a continuation of what SA2 has already done [23.734] [23.501];

-	RAN3 is the primary group responsible for the work;

-	Focus in RAN2 should first be laid on NR and if time allows LTE (connected to 5GC) can also be addressed.

The agreed time budget for the work item gives RAN2 four meetings to complete the work i.e. until March 2020, with an allocation of 0.5 TU per meeting [RP-191609].

# 3	Work Plan

Table 3.1 below describes a possible plan to carry out the work in RAN2. Given the limited TU allocation, it is suggested to focus the online discussions on only a few aspects.

Table 2.1: NPN Time Budget

| Meeting | Date | TU | Meeting Tasks | Post-meeting email discussions |
| --- | --- | --- | --- | --- |
| RAN2#107 | 2019.08.26 | 0.5 | Endorse Stage 2 Skeleton CR Agree generic mobility principles Focus meeting time on IDLE and INACTIVE mode (cell selection, reselection and broadcast of new information in SI) Continue discussing IDLE and INACTIVE via email with the aim to conclude at the following meeting Update of Stage 2 CR via email discussion | 38.300 CR update IDLE and INACTIVE mode mechanisms |
| RAN3#105 | 2019.08.26 |  | Not collocated with RAN2 |  |
| RAN2#107bis | 2019.10.14 | 0.5 | Endorse Stage 2 Skeleton CR Endorse email discussion outcomes Conclude IDLE and INACTIVE mode Start discussing CONNECTED mode Continue discussing CONNECTED mode via email with the aim to conclude at the following meeting | 38.300 CR 38.304 CR 38.331 CR (for the SIB and IDLE/INACTIVE) CONNECTED mode mechanisms |
| RAN3#105bis | 2019.10.14 |  | Collocated with RAN2 |  |
| SA2#135 | 2019.10.14 |  | Not collocated with RAN2 |  |
| RAN2#108 | 2019.11.18 | 0.5 | Conclude CONNECTED | Stage 2 CR 304 CR 331 CR (for all aspects) |
| RAN3#106 | 2019.11.18 |  | Collocated with RAN2 |  |
| SA2#136 | 2019.11.18 |  | Collocated with RAN2 |  |
| RAN2#109 | 2020.02.24 | 0.5 | Resolve remaining issues for NR Approve Stage 2 and Stage 3 CRs | If needed |
| RAN3#107 | 2020.02.24 |  | Collocated with RAN2 |  |
| SA2#137 | 2020.02.24 |  | TBD |  |