3GPP TSG-RAN WG2 Meeting #109e-bis	R2-2002727

Electronic meeting, April 20 - 30, 2020                     	 (revision of R2-2000480)

Agenda item: 		6.1.1

Source: 		Qualcomm Incorporated (Rapporteur)

Title: 	IAB workplan update

Document for:	Information

# 1	Introduction

At RAN#82, a Work Item on Integrated Access and Backhaul for NR was approved [1]. As rapporteur, in this contribution, we recommend a work plan for RAN1, RAN2, RAN3 and RAN4. The workplan captures interdependences among tasks and timeline for RAN1/2/3/4.

This workplan is a revision of a prior version submitted to RAN2 #109-e [2].

The WID [1] introduced the following objectives in the core part:

- Specification of an IAB-node following architecture 1a including [RAN2-led, RAN3]: - Routing function on IAB-node to support forwarding across the multi-hop topology based on routing identifier. (Additional function in IAB-node apart from DU and MT) - Hop-by-hop propagation of signalling to support low latency scheduling (e.g. TR 38.874 clause 8.6), BH RLF handling (e.g. TR 38.874 clause 9.7.14-15) and resource coordination across the multi-hop topology (e.g. TR 38.874 clause 7.3.3). - UE-bearer to BH RLC-channel mapping and mapping between ingress and egress BH RLC channels functions for support of one-to-one and many-to-one bearer mapping. - Enhancements to gNB functionality to serve as an IAB-donor following architecture 1a [RAN3, RAN2] - Functions on gNB CU-CP for topology, route and resource management [RAN3-led]. - Support for IP routability to IAB-node (e.g. from CU, OAM) [RAN3-led]. - Bearer mapping function on gNB DU to map downlink traffic of one or many UE-bearers to a BH RLC-channel [RAN2-led]. - Specification of possible enhancements to E1, F1 and X2/Xn interfaces [RAN3-led, RAN2]: - On F1: - security protection over the wireless backhaul links. - setting up and reconfiguring IAB-nodes and IAB-donor DUs - On X2 and Xn, necessary functions to enable DC operation with IAB. - On E1, configuration of necessary IAB-specific transport and/or security protection of F1-U. - Specification of procedures for IAB-node integration and topology adaptation, including [RAN3-led, RAN2]: - Procedures for IAB-node integration for SA and NSA modes, including enhancements needed to E-UTRAN for NSA mode. - Specification of IAB-node migration underneath the same IAB-donor (with or without a change of IAB-donor DU),. Migration of IAB-node could be network-controlled or could be due to BH RLF. Support for route redundancy and route selection based on multi-connectivity (e.g. TR 38.874 clause 9.7), leveraging existing NR solutions as well as NR-NR DC, without additional RAN1 work. (see NOTE1). - Specification of enhancements to L2 wireless transport [RAN2-led, RAN3]: - Specification of an adaptation layer above RLC layer. The adaptation layer supports routing across the wireless backhaul and IP as next protocol layer. - Extension of LCID space and potentially LCG space to support one-to-one mapping of UE bearers to BH RLC channels. The extension of LCID space and LCG space is applicable only to IAB-nodes. - Specification of a flow control mechanism (for DL and, if necessary, for UL) to handle congestion. - Specification of mechanisms to enable lossless delivery in hop-by-hop ARQ. - Specification of signalling for L2 transport and resource management [RAN2-led, RAN3, RAN1]: - Specification of RRC and F1-AP procedures and messages for: the setup and release of IAB-nodes; configuration of adaptation layer at the IAB-nodes and IAB-donor DU; configuration of BH RLC channels, QoS information, routing tables, bearer-mappings; configuration of means for network synchronization; and configuration for sharing of time-domain resources among backhaul and access links (see physical layer specification). - Specification of an IP address allocation mechanism for the IAB-nodes [RAN3]. - Specification of enhancements to bearer context setup/release procedures to support flow QoS across multiple hops. - Specification of enhancement for uplink resource request procedure and related signalling to enable low latency uplink data scheduling. - Specification of BH RLF handling (e.g. downstream BH RLF notification). - Physical layer specification [RAN1-led, RAN2, RAN3, RAN4]: - Specification of SSB/RMSI periodicity for NR initial access assumed by an IAB-node. - Specification of extensions to Rel. 15 to support the use of SSBs orthogonal to SSBs used for UEs (via TDM and/or FDM), for inter-IAB-node discovery and measurements, including additional SMTC periodicities and time-domain mapping of SSB locations (e.g. enable muting patterns to deal with half-duplex constraint). - Specification of extension of RACH occasions and periodicities for backhaul RACH resources. w.r.t. access RACH resources, and associated network coordination mechanisms for selection of such parameters (in order to orthogonalize access and BH due to the half-duplex constraints) - Specification of mechanisms for resource multiplexing among backhaul and access links. This includes: - Specification of semi-static configuration for IAB-node/IAB-donor DU resources in case of TDM operation subject to half-duplex constraint. This shall be forward compatible to allow the support of half-duplex scenarios with FDM and SDM resource sharing among backhaul and access links. - Specification of time resource types for the DU’s child links: DL hard, DL soft, UL hard, UL soft, Flexible hard, Flexible soft, Not Available - Specification of dynamic indication (L1 signalling) of the availability of soft resources for a child IAB-node DU - Specification of required transmission/reception rules for IAB-nodes and associated behaviours regarding time resource utilization as discussed in TR 38.874 clause 7.3.3. - Specification of mechanism to support the “case-1” OTA timing alignment. - Specification of RF and RRM requirements [RAN4-led]: - Define RF requirements for both backhaul and access links of an IAB-node including requirements for co-existence (e.g. ACLR, ACS). This may include defining a new power class for MT. - Define RRM core requirements for both backhaul and access links of IAB node. - Define latency requirements for switching between communication over parent backhaul link (i.e. MT) and child backhaul/access links (i.e. DU). - Define timing requirements for IAB specific network synchronization. This may include (a) requirement for “case 1” timing (e.g. accuracy of DL transmission timing alignment between an IAB-node and its parent node), and (b) cell phase synchronization accuracy for multi-hop IAB network. NOTE 1: IAB relies heavily on existing Rel-15 functionality. It may leverage additional features/enhancements defined as part of other Rel-16 WIs, but it should not depend on the timely completion of these features. The scope of this section is limited to the aspects envisioned to be treated as part of the IAB WI.

The WID [1] introduced the following objectives in the performance part:

- Define RRM performance requirements. - Define demodulation performance requirements for both backhaul and access links of an IAB-node, if needed. [RAN4]

# 2	Workplan

## 2.1	Prioritization of efforts

This section captures the interdependences among the various tasks defined in the IAB WID [1] together with criticality to IAB functionality and performance, and size of specification effort.

RAN1-led efforts:

The WID defines five objectives related to physical layer enhancements, which are led by RAN1. These physical layer enhancements are critical to IAB functionality and should therefore start early. The RAN2/3-related efforts are explicitly captured under the RAN2/3-led objectives.

The physical layer enhancements include:

1) SSB/RMSI periodicity for NR initial access.

2) Extensions of SSBs for inter-IAB-node discovery and measurements.

3) Extension of RACH occasions and periodicities for backhaul RACH resources.

4) Mechanisms for resource multiplexing among backhaul and access links.

5) Mechanism to support the “case-1” OTA timing alignment.

RAN2-led efforts:

The WID defines four RAN-2-led objectives as well as three RAN3-led efforts which involve RAN2 contribution.

The WID makes extensive reference to TR 38.874 for these objectives. RAN-2 should therefore start with the baseline stage-2 specifications that can be derived from TR 38.874. These baseline specifications mainly affect TS 38.300.

Also, stage-2 specification for the adaptation layer should start early since it represents a new radio protocol sublayer, which has implications on other efforts.

Further features are dependent on these prior efforts and can follow over time.

The following efforts and their interdependences can be identified:

1) 	Architecture baseline (38.300):

-	Relaying architecture and Interfaces

-	User- and control-plane aspects incl. protocol stacks and bearer-to-RLC-channel mapping

-	Enhancements to L2 structures

-	Enhancements to radio protocol sublayer (adaptation layer)

-	Radio-aware scheduling

2) 	Adaptation layer – stage 2 (38.3xx)

-	Services, functions, procedures

- 	Includes routing and bearer-to-RLC-channel mapping

3) 	Enhancements to bearer context setup/release procedures to support flow QoS across multiple hops: Depends on specification of 38.300 baseline spec and adaptation layer spec.

4) 	L2 signaling for BH RLF handling: Depends on specification of BH RLF procedures by RAN3

5) 	L2 signaling for release of soft resources: Depends on specification of resource management by RAN1

6) 	Flow control mechanism to handle congestion: Depends on evaluation of F1-based mechanisms by RAN3

7) 	Hop-by-hop low latency scheduling: Optimization, not critical for functionality

8) 	Mechanisms for lossless delivery in hop-by-hop ARQ: Not critical for functionality. Implies that RAN3 work on topology adaptation has sufficiently evolved.

9) 	New RRC configurations: Depend on specification of new procedures

10) Extension of LCID space and potentially LCG space: Mostly configuration.

11) Stage 3, ASN.1: Depends on stage-2 specification.

RAN3-led efforts:

The WID defines three RAN-3-led objectives as well as RAN2-led efforts, which involve RAN3 contribution.

RAN-3 should also start with baseline stage-2 specifications that can be derived from TR 38.874. These baseline specifications mainly affect TS 38.401.

Also, enhancement to E-UTRAN for IAB-node operation in NSA should be addressed early and in context with baseline 38.401 specification. These E-UTRAN enhancements mainly affect TS 37.340.

Other tasks can follow as soon as architectural issues and procedures have been resolved.

The following efforts and their interdependences can be identified:

1) Architecture baseline (38.401):

-	5G RAN architecture,

-	Procedures for

-	IAB-node integration incl. OAM-support,

-	Topology adaptation incl. topological redundancy nodes and BH RLF recovery

-	IP address allocation

-	Network synchronization

2) Enhancements to E-UTRAN for IAB-node in NSA (37.340)

3) 	Flow control mechanism to handle congestion: RAN3 should mainly focus on extensions of NR UP protocol (38.425). This work should start early since it might imply radio-layer-based flow-control mechanisms to be defined by RAN2.

4) 	Enhancements to F1* security: This work can start early as it mostly affects SA3 at initial stage.

5) 	Enhancements to E1, F1: Depends on establishment of architecture baseline

6) 	Enhancements to NG and S1-MME: Interaction with SA2. Depends on establishment of architecture baseline

7)  	Enhancements for bearer-to-RLC-channel mapping on IAB-donor-DU for DL traffic: Depends on adaptation layer spec by RAN2.

8) New F1-AP configurations: Depends on specification of new procedures

9) Stage 3, ASN.1: Depends on stage-2 specification.

RAN4-led efforts (core part):

The WID defines the following objective in the core part to be led by RAN4. The RAN-4 effort depends on prior RAN1 work, and it is therefore started at a later point in time.

1) RF and RRM requirements [RAN4-led]:

- 	RF requirements for both backhaul and access links of an IAB-node including requirements for co-existence (e.g. ACLR, ACS).

-	 RRM core requirements for both backhaul and access links of IAB node.

-	Latency requirements for switching between communication over parent backhaul link (i.e. MT) and child

-

RAN4-led efforts (performance part):

The WID [1] defines the following objectives in the performance part to be led by RAN4. The RAN-4 effort depends on prior RAN1 work as well as RAN-4 work in the core part, and it is therefore started at a later point in time.

1) RRM performance requirements.

2) Demodulation performance requirements for both backhaul and access links of an IAB-node.

## 2.2	Timeline

Table 1 summarizes a timeline for RAN1/2/3/4, which has been derived from the interdependences among tasks, their criticality on IAB functionality and performance, and size.

Table 1: Timeline for RAN1, 2, 3, 4 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN1 | #96 | Feb 25-March 1, 2019 | 1 | - Start discussion of stage-2 aspects of all five RAN-1-led tasks: 1) SSB/RMSI periodicity for NR initial access. 2) Extensions of SSBs for inter-IAB-node discovery and measurements. 3) Extension of RACH occasions and periodicities for backhaul RACH resources. 4) Mechanisms for resource multiplexing among backhaul and access links. 5) Mechanism to support the “case-1” OTA timing alignment. |
| RAN2 | #105 | Feb 25-March 1, 2019 | 2 | - Started discussion of stage-2 aspects: 1) RAN2 aspects of architecture - Baseline running CR to TS 38.300 - Protocol stacks 2) Adaptation layer spec - Adapt functionality - Routing and bearer mapping 3) L2 configuration - Backhaul RLC channels and Adapt layer 4) BH RLF handling - BH RLF-related signalling |
| RAN3 | #103 | Feb 25-March 1, 2019 | 1 | - Started discussion of: 1) RAN3 aspects of architecture - Baseline running CR to TS 38.401 2) IAB-node integration - Procedures - IAB-node authorization - OAM-support - Included stage-3 aspects: - Enhancements to E1 and F1 - Enhancements to NG, S1-MME, X2, Xn |
| RAN1 | #96bis | April 8-12, 2019 | 1 | - Continue discussion of stage-2 aspects of all five RAN-1-led tasks. |
| RAN2 | #105bis | April 8-12, 2019 | 2 | - Continued discussion of stage-2 aspects: 1) RAN2 aspects of architecture - Captured easy agreements from TR in running CR to 38.300 - Captured baseline protocol stacks in running CR to 38.300 2) Adaptation layer spec - Agreed that Adapt layer will be named Backhaul Adaptation Protocol (BAP) - Discussed BAP routing and bearer mapping - Started discussion of stage-2 aspects: 5) Flow control mechanism to handle congestion - Agreed on baseline for congestion mitigation 6) Low latency scheduling - Agreed on baseline feature support |
| RAN3 | #103bis | April 8-12, 2019 | 2 | - Continued discussion of stage-2 aspects: 1) RAN3 aspects of architecture - Baseline running CR to TS 38.401 2) IAB-node integration - Procedures - IAB-node authorization - DU IP-address allocation - OAM-support - Enhancements to E-UTRAN for IAB-node in NSA (37.340) - Started discussion of: 3) Intra-donor transport - Enhancements to support bearer-to-RLC-channel mapping - Included stage-3 aspects: - Enhancements to F1 - Enhancements to NG, S1-MME, X2, Xn |
| RAN4RF | #90bis | May 13-17, 2019 | 1 | Start with efforts on core part. |
| RAN1 | #97 | May 13-17, 2019 | 1 | - Continue discussion of stage-2 aspects of all five RAN-1-led tasks. |
| RAN2 | #106 | May 13-17, 2019 | 3 | - Handle LS from RAN3 on use of IPv6 Flow Label (R3-182085) - Discussion of stage-2 aspects: 1) RAN2 aspects of architecture - Updated CR to 38.300 2) BAP layer spec - BAP functionality - BAP routing and bearer mapping 4) Parent node change, multi-connectivity, BH RLF handling - Clarifications on multi-connectivity for IAB-node 9) Misc aspects - Security considerations |
| RAN3 | #104 | May 13-17, 2019 | 1.5 | - Continued discussion of stage-2 aspects: 1) RAN3 aspects of architecture - Updated baseline running CR to TS 38.401 2) IAB-node integration (high priority) - Continued discussion on remaining procedures - Down-selected parent-node selection - Continued discussion on IAB-node indication to core network - Finalized OAM-support - Started topology discovery - Enhancements to E-UTRAN for IAB-node in NSA (37.340) 3) Intra-donor transport (high priority) - Continued discussion on mapping from IP layer to BAP layer 4) L2 configuration - Started discussion on configuration of BAP layer on DU - Included stage-3 aspects: - Enhancements to F1 - Enhancements to NG, S1-MME, X2, Xn |
| RAN4RF | #91 | May 13-17, 2019 | 2 | Continue with efforts on core part. |
| RAN4RD | #91 | May 13-17, 2019 | 0.5 | Start with efforts on core and performance part. |
| RAN1 | #98 | August 26-30, 2019 | 1 | - Finalize discussion of stage-2 aspects and start discussion of stage-3 aspects of all five RAN-1-led tasks. |
| RAN2 | #107 | August 26-30, 2019 | 3 | - Continue discussion of stage-2 aspects with high priority: 1) RAN2 aspects of architecture - Update CR to 38.300 2) BAP layer spec - BAP functionality and modelling (email discussion #48) - BAP bearer mapping (email discussion #47) 3) L2 configuration - Backhaul RLC channels and BAP layer - Configuration protocols - Continued discussion of stage-2 aspects, time permitting: 4) Parent node change, multi-connectivity, BH RLF handling - Discussion of F1-AP transport over LTE RRC for IAB-nodes using EN-DC 5) Flow control mechanism to handle congestion (email discussion #44) - E2E flow control for upstream traffic - HbH flow control for downstream traffic 6) Low latency scheduling (email discussion #46) - Detailed proposals 9) Misc aspects - MT-specific transport aspects - Lossless multi-hop RLC (email discussion #45) |
| RAN3 | #105 | August 26-30, 2019 | 1 | - Continue discussion of stage-2 aspects 1) RAN3 aspects of architecture - Update baseline running CR to TS 38.401 2) IAB-node integration (high priority) - Finalize working assumption for parent-node selection - Finalize discussion on IAB-node indication to core network - Finalized OAM aspects 3) Intra-donor transport (high priority) - Made progress onmapping from IP layer to BAP layer 4) U-plane (high priority) - Agreed on mapping granularity from upper layers to BH RLC channels for UL. - Continue discussion of stage-3 aspects including ASN.1 |
| RAN4RF | #92 | August 26-30, 2019 | 2 | Continue with efforts on core part. |
| RAN4RD | #92 | August 26-30, 2019 | 1 | Continue with efforts on core and performance part. |
| RAN1 | #98bis | Oct 14-18, 2019 | 1 | Finalize discussion of all stage-2 and stage-3 aspects. |
| RAN2 | #107bis | Oct 14-18, 2019 | 3 | - Continue discussion of the following topics with high priority, consider stage-2 and stage-3 aspects 1) RAN2 aspects of architecture - Update on CR to TS 38.300, TS 38.340, TS 38.331. 2) BAP layer spec - Update on CR to 38.340 including open issues based on email discussion summary [107#8] - Discuss stage-3 issues of BAP layer. - Discuss remaining aspects related to routing based on email discussion [107#53] 3) L2 configuration - Discuss remaining issues - Discuss L2 structures for IAB 4) Multi-connectivity, BH RLF handling - BH RLF-related signalling, expected IAB-node behaviour based on email discussion [106#43] - F1-AP transport over LTE RRC for IAB-nodes using EN-DC based on email discussion [107#51] 6) Low latency scheduling (email discussion [106#46]) - Discuss stage 3 issues, in particular, if a new MAC CE format is necessary for pre-emptive BSR 8) Extension of LCID space and potentially LCG space - Discuss stage-3 9) Misc aspects - LS from RAN3 on IAB indication and parent indication - Running CR 38.331 (email discussion [107#52]) - Start running CR on 38.321. - Others |
| RAN3 | #105bis | Oct 14-18, 2019 | 2 | - Continue discussion of stage-2 aspects 1) RAN3 aspects of architecture - Update baseline running CR to TS 38.401, TS 38.413, TS TS 38.423, TS 36.413, TS 36.423. 2) IAB-node integration (high priority) - Finalize topology discovery - Finalize IP address allocation 3) Intra-donor transport (high priority) - Remaining issues on mapping from IP layer to BAP layer 4) U-plane (high priority) - Agree on mapping granularity from upper layers to BH RLC channels for DL and UL. - Discuss LS from RAN2 on F1-C granularity for RLC channel mapping. Start discussion of stage-2 aspects: 5) Topology adaptation - Procedures for parent-node change - Continue discussion of stage-3 aspects |
| RAN4RF | #92bis | Oct 14-18, 2019 | 2 | Continue with efforts on core part. |
| RAN4RD | #92bis | Oct 14-18, 2019 | 1.5 | Continue with efforts on core and performance part. |
| RAN1 | #99 | Nov 18-22, 2019 | 1 | Finalize CRs and ASN.1 of all RAN-1-led tasks. |
| RAN2 | #108 | Nov 18-22, 2019 | 3 | Organizational: - Email discussion: Draft running CR 38.321 [107bis#39] - Email discussion [107bis#40]: SI Broadast, barring, Initial access, Connection setup - Capture IAB-related issues in 37.340 - Reference to NR DC, EN DC as applicable - SCG/MCG failure handling for IAB-node - Reply LS to RAN3 to respond to IAB indication in MSG 5 and OTA indication of parent node. BAP functionality - Upstream BAP header - Decide on BAP routing ID - BAP-layer signaling (e.g. RLF notification) - Clarify receiving entity of BAP-layer signaling - Configuration of RLC channel of BAP layer signaling - Selection of BAP address used for BAP layer signaling - BAP routing and bearer-mapping configuration - Decide and agree if configuration of upstream routing, bearer mapping and mapping from F1 to L2 parameters is done by RRC or F1-AP. - At access IAB-node, configuration of upstream mapping from F1-U/C to donor’DU’s BAP address and BAP path ID (note: RAN3 has so far decided on the upstream bearer mapping). - Configuration of mapping from CG identifier to next-hop BAP address in UL direction (missing in 38.331). - Configuration of MT with BH RLC CH ID via RRC (presently FFS in running CR to 38.331). - Stage-3 details of routing and bearer-mapping tables - “BAP functional view” figure for 38.340 (could also be done in email discussion) Scheduling and QoS - Fairness - The intermediate IAB-node should be configurable with the number of DRBs carried in an N:1 mapped BH RLC channel. RLF handling - Message format of RLF notification LS from RAN1 on signalling for PHY layer support |
| RAN3 | #106 | Nov 18-22, 2019 | 2 | Stage 2 - Protocol stacks with split-donor for running CR to 38.401 IAB-node integration - Stage 2 integration for EN DC IP address allocation - IAB-node IP address: - Allocation of IPv6 address prefix to IAB-node. Request for prefix size. - Allocation of different address(es) for UP domain than for CP domain. Indication on which address(es) to be used for either domain. - CU IP address: - Determination of CU-CP’s IP address by IAb-node. - Determination if IAB-node should use IPsec tunnel mode or transport mode, i.e. if there is an external SeGW. - Determination of SeGW’s IP address (outer tunnel address) vs the CU’s IP address (inner tunnel address) for IPsec tunnel mode. This issue may apply separately to UP and to CP since they may reside in different IP domains. Note: In case of OAM-based configuration, inter-CU topology adaptation cannot be supported in this release. QoS - Prioritization of CP over UP traffic - BH RLC channel needs to allow indicating higher priority for F1-C traffic. - Configuration of number of DRBs mapped to BH RLC channel - The MAC scheduler on inter-mediate IAB-node needs to know how many DRBs are mapped onto BH RLC channel. - LS from RAN2 on prioritization of SRB0 over SRB1 BAP layer - L2 configuration - Configuration of mapping from gNB-DU/gNB-CU UE F1AP ID of IAB-MT to next-hop BAP address. This is based on RAN2 agreements to use BAP address as the BH-link identifier for BAP routing. U-plane - UL mapping of F1-C traffic to L2 parameters Topology adaptation - Stage-2 TP for topological redundancy - Stage-2 TP for BH RLF recovery - IAB-node migration - Update stage-2 with recent agreements on IP address allocation and further stage-3 work as necessary. - Inter-donor migration |
| RAN4RF | #93 | Nov 18-22, 2019 | 2 | Finalize efforts on core part. |
| RAN4RD | #93 | Nov 18-22, 2019 | 1.5 | Continue with efforts on core and performance part. |
| RAN | 86 | Dec 9-12, 2019 |  | Rel-16 completion for RAN1 |
| RAN2 | #109-e | Feb. 24-28, 2020 | 0.5 | Organizational: LSs, CRs, Email discussions - LS on IP assignment in IAB network by RAN3 (R2-1914331, contact: Samsung) While RAN3 is expected to do more work on this, RAN2 should follow up on action defined in this LS. - LS on updated Rel-16 LTE and NR parameter lists (R1-1913675, contact: Qualcomm) The configuration of RRC-related PHY parameters has already been captured in running CR to 38300 (email discussion [108#31][IAB]). Two MAC CEs need to be specified for guard symbols desired/provided. - Report from email discussion [108#31][IAB] Running CR 38.331 36.331 (Ericsson) Discussion of open issues including length of BH RLC Channel. - Report from email discussion [108#46][IAB] Feature List (Ericsson) Discussion of proposals and open issues from report. - Report from email discussion [108#51][IAB] Running CR 38.340 (Huawei) Endorsement of running CR 38340, discussion of report on open issues, and discussion of report on BAP functional view. MAC CEs - Lower priority: Pre-emptive BSR - RAN2 to decide on the reuse of short/long/short truncated/long truncated formats for expected data and corresponding LCID values. Implication of pre-emptive BSR on regular BSR to avoid double reporting. Remaining FFS in agreements from R2@108. - Guard symbols - RAN2 to define MAC CEs for guard symbols desired/provided based on RAN1 LS. Cell barring RAN2 to discuss if IAB-MT ignores CellBarred in MIB and has a separate barring indication in SIB1. The goal is to generally bar ENDC UEs from access to NR cell, while SA IAB-MTs can access some of the NR cells but are barred from others. Finalize CRs and ASN.1 on all RAN2-led tasks. |
| RAN3 | #107-e | Feb. 24-28, 2020 | 1 | 13.1 General Incoming LS - LS on F1AP over LTE leg signalling for IAB from RAN2 (contact: Nokia) - LS on configuration of PHY layer parameters from RAN1 (contact: Qualcomm) 13.2 IAB-support in network interfaces F1AP mapping configurations - DL mapping from IP to L2 at donor DU Use of non-UE-associated or UE-associated F1AP signalling. - UL mapping from F1 and non-F1 to L2 at IAB-node Use of UE-associated or non-UE-associated F1AP signalling for bearer mapping of F1-C and non-F1 traffic (RAN2 already agreed on a RRC- based bootstrapping procedure). Use of UE-associated or non-UE-associated F1AP signalling for the mapping to BAP routing ID for F1-U, F1-C and non-F1 (RRC-based bootstrapping is also already available). - “Intermediate” IAB-node Use of UE-associated or non-UE-associated F1AP signalling for mapping from ingress to egress RLC channel. - Packet routing of SCT/split bearer for ENDC case X2-U can be routed via (a) CU-UP/donor-DU or (b) directly via donor DU. (a) is currently not supported and (b) would need IP-flow-label/DSCP markings by MeNB. - IP address management: - Request by CU to IAB-donor DU for IP address and IAB-donor DU’s reply. - Allocation of multiple IP addresses and IP address prefix. 13.3 Routing functionality and topology adaptaiton IAB-node migration and support of topological redundancy - Functional specification of IAB-node migration after BH RLF failure: - Handling of remaining FFS of stage 2. Finalize CRs and ASN.1 on all RAN3-led tasks. |
| RAN4RD | #94 | Feb 24-28, 2020 | 1.5 | Continue with efforts on core part. |
| RAN | 87 | March 16-19, 2020 |  | Rel-16 completion for RAN2, 3 |
| RAN2 | #109bis-e | April 20-30, 2020 | N/A | Organizational: LSs, CRs, Email discussions - Notation alignment of IAB-specific terms with RAN3. - Report from email discussion [109e#26][IAB] IP address allocation (Samsung) Discussion and agreement on remaining issues on IP address allocation - Report from email discussion [109#35][IAB] RRC open issues (Ericsson) Discussion and agreement on open issues from report. - Report from email discussion [109e#36][IAB] IAB RLF handling open issues (Qualcomm) Discussion and agreement on open issues from report. IAB-MT features - Optionality of mandatory Rel-15 UE features for IAB-MT Discussion and agreement on in compliance with RP#87e agreements on this topic. Finalization of CRs and ASN.1 on all RAN2-led tasks. |
| RAN3 | #107bis-e | April 20-30, 2020 | N/A | Organizational issues: - Notation alignment of IAB-specific terms with RAN2. Technical issues: - Configuration of “bearer mapping” at intermediate IAB nodes Discuss and agree on use of NUA vs. UA signalling and stage 3. - Configuration of DL mapping on IAB-donor Discuss and agree on DL mapping for IPv6 prefix and multiple IPv4 addresses. Discuss and agree on use of NUA vs. UA signalling and stage 3. - Topology discovery to support - IAB-node uses IPsec tunnel mode - IAB-node uses OAM-assigned IP address Discuss and agree on a solution and capture in stage 3. - Remaining IP address topics Discuss and agree at what stage IP address is requested by IAB-node using ENDC. - F1C over LTE/X2 - Discuss and agree if this path configured before or after the direct path, and if it can be used as a complete replacement of the direct path? - Discuss and agree on allocation of IP addresses for this path. - Discuss and agree on the use of E2E IPsec on this path. - Discuss and agree on how to include this path establishment in the IAB-node integration procedure. - Revision of BH RLC Channel ID space We agreed to limit max no of BH RLC Channels to 16k while RAN2 has allocated 64k eLCID on MAC layer. - Topology redundancy procedure in 38.401 Verify if updates and removal of Editor Notes for topological redundancy. |
| RAN4RD | #94bis-e | April 20-30, 2020 | 1.5 | Continue with efforts on core part. |
| RAN2 | #110-e | June 1-12, 2020 | N/A | Finalization of CRs and ASN.1 on all RAN2-led tasks. |
| RAN3 | #110-e | June 1-12, 2020 | N/A | Finalization of CRs and ASN.1 on all RAN3-led tasks. |
| RAN4RD | #95 | May 25-29, 2020 | 1.5 | Finalize efforts on core part. |
| RAN | 88 | Jun 3-6, 2020 |  | Rel-16 ASN.1 freeze Rel-16 completion for RAN 4 (core part) |
| RAN4RD | #96 | August, 24-28, 2020 |  | Start efforts on performance part. |
| RAN | 89 | September 14-17, 2020 |  |  |
| RAN4RD | #96-Bis | October 12-16, 2020 |  | Continue efforts on performance part |
| RAN4RD | #97 | November 16-20, 2020 |  | Finalize efforts on performance part |
| RAN | 90 | December 7-10, 2020 |  | Rel-16 completion for RAN 4 (performance part) |

# References

- RP-200084: Revised WID for NR_IAB; TSG RAN Meeting #87e, Electronic Meeting, March 16-20, 2020

- R2-2000480: Workplan for IAB WI, Qualcomm Inc. (Rapporteur), RAN WG2 #109-e, Electronic Meeting, Feb 24-March 6, 2020